## Chits
Design Review/QA Audit [Cog Engr/RLM/Chair] | Rvw Date | # | Chit/Audit Finding [Originator] | Review Board Recommendation | Project Disposition | Responsibility | Status | Due Date
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 3 | Provide schedule for demonstrating measurement capability required for TRC winding. TRC not even measured yet. [Reiersen] |  |  | Chrzanowski, Jim | During the real time measuring of a layer [that will be performed (3) times during winding], it adds an additional 3-4 hours to the winding time per measurement series. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 5 | Need to figure out how to dissect coil w/o losing registration of winding to tee. Consideration should be given to more exotic, non-destructive options. [Reiersen] |  | The clamps will keep the winding packs registered to the tee during dissection. The Romer arm will be used to provide a record of how the winding packs were registered to the tee prior to cutting. | Chrzanowski, Jim | The winding clamps will remain on the coil/casting during the cutting operations. This should help to restrain the bundle to tee registration during dissection. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 6 | Consider winding a complete coil to establish shimming requirements. Then rewind the coil using differences in clamping pressure to control boundary. [Reiersen] |  | This has been adopted for the TRC. The project still needs to develop a plan for measuring the trial winding and figuring out how that data will be used for the actual winding. (Nelson) | Chrzanowski, Jim | Agree. The TRC trial winding was completed. Evaluation of results will determine whether or not trial windings will be performed for types A, B and C. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 7 | Resolve whether the relief gets filled with RTV or Roving. (Roving would mechanically lock the winding which may not be good). [Reiersen] |  | The relief was filled with RTV (or equivalent) prior to winding to avoid mechanically locking the winding to the tee. | Chrzanowski, Jim | The TRC grooves were sealed with "Then seal" caulking. This caulking will prevent the epoxy from locking the winding. The groove has been eliminated on Type A,B,C castings. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 8 | Lead blocks - it was mentioned during the presentation that this would be made of G10 or G11. For production coil, since G10 tends to become neutron-activated cause "hot spots" (Doe commend use of G11, not G10. Similarly for any other proposed uses of G. [Levine] |  | G11CR (cryogenic grade) will be used which provides more consistent properties than G10 (Williamson) | Chrzanowski, Jim | All of the lead fillers for the production coils will be fabricated using G-11. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 9 | Need to qualify the sil-foil carbon tong Braze procedure or write an exception. [Dudek] |  | Braze procedure will be qualified and documented. Technicians will be qualified to perfomr this procedures. (Chrzanowski) | Chrzanowski, Jim | Process has been qualified and is now a part of the PPPL welding/brazing procedure. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 10 | Measure signal in diagnostic flux loops while coil is energized. Check conformity of flux loops after coil fabrication is complete. Verify that center conductors of loop cables will not shorted to ground or other coil structures. [Stratton] |  | Diagnostic flux loops will be taped in place and measured. They will be checked for shorts. Signal measurements while coil is energized will depend on the availability of diagnostic channels. | Chrzanowski, Jim | Flux loop leads are provided. Diagnostic group must provide/coordinate instrumentation required to perform such measurements. Diagnostic group should coordinate with Geoff Gettelfinger for possible incorporation in the test plans. | TBD
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 11 | The diagnostic flux loops need to be accurate, located (~1/16") at the outer "corners" of the winding pads! A groove should be put it into the surface on which the loop should be used to accurately, measure the path of each loop as-built . [Stratton] |  | (See response to Chit #10) | Chrzanowski, Jim | Investigating the possibility of using simple inexpensive gauge pads to position the flux loops. Further work is required. | By 1/30/2005
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 12 | Provide epoxy strainer on fluid line to coil distribution manifold. [Gettelfinger] |  | Epoxy strainer will be added (Chrzanowski) | Chrzanowski, Jim | Epoxy filters have been added to epoxy delivery system. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 13 | Additional potential issue: 1) cladding and chill plates too time consuming. [ Dudek] |  | The TRC will be used to determine how much time will be required to apply the cladding and chill plates. Improvements will be made as required. (Chrzanowski) | Chrzanowski, Jim | The installation of the cladding appears workable, however additional hands-on work along with redesign efforts is required prior to determining the actual installation and fabrication cost & schedule. | By 1/30/2005
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 14 | Add to the assembly procedure the electrical tests required to assure that no shorts are present in the copper coolant system. [Brown] |  | Electrical tests will be added to the assembly procedure (Chrzanowski) | Chrzanowski, Jim | Test has been added. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 15 | Use a conductivity meter or some other device to monitor the resistance to ground (MCWF) during chadding installation. [Nelson] |  | Use of an in-process "whisker" sensor will be investigated (Chrzanowski) | Chrzanowski, Jim | Agreed. This test is incorporated in the procedure during installation of cladding. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 16 | Take lots of pictures. [Dudek] |  | Extensive digital phots will be taken (Chrzanowski) | Chrzanowski, Jim | Concur. New camera has been procured for the field. This camera will be used by all field crews during fabrication. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 17 | Consider using fiber optic strain gages. [Nelson] |  | Fiber optic strain gages will be installed on the TRC. We will figure out if and how to pay for signal conditioning later. (Chrzanowski) | Chrzanowski, Jim | Agreed. These will be incorporated in the TRC per FDR recommendations. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 18 | Consider renting another Romer arm for 3rd winding station. [Nelson] |  | Will be considered during winding the 1st production coil (Chrzanowski) | Chrzanowski, Jim | Agree. The need for the 3rd. Romer will be evaluated once two winding lines are operational. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 19 | Develop an insulation schematic to show what is connected. [Nelson] |  |  | Chrzanowski, Jim |  | TBD
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 20 | Use a grounded paddle to check for whiskers. [Nelson] |  |  | Chrzanowski, Jim | Device has been fabricated and will be tested on the TRC. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 21 | Electrical insulation looks marginal. [Nelson] |  | Shim material will be distributed to provide improved turn-to-turn voltage standoff capability. Thinner glass tape will be procured and available as shim material for the production coils (Chrzanowski) | Chrzanowski, Jim | The turn to turn insulation plan has been reviewed and has deemed appropriate | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 22 | Assure resistive brazing qualification (procedure and individual) are completed before brazing on TRC. [Malsbury] |  |  | Chrzanowski, Jim | See chit #9 | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 23 | Use of FM Laser Radar is at the conceptual planning level. This is not "In the Bag! [Gettelfinger] |  | Feasibility of this approach and alternatives for measuring displacement will be investigated (Nelson/Gettelfinger) | Chrzanowski, Jim | This is not being planned. NO ACTION REQUIRED | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 24 | Consider vacuum only impregnation. [Cole] |  | Vacuum only impregnation is considered ill-advised. | Chrzanowski, Jim | Disagree: The VPI procedures are based on R&D activities and will include a combination of both vacuum and pressure. These decisions will be made during the VPI operation at the discretion of the VPI Director. | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 25 | Provide an in-line electrical test at the insulated cable to check for copper "whiskers". [Heitzenroeder] |  |  | Chrzanowski, Jim | See chit #19 | COMPLETED Approved by Larry Dudek
Twisted Racetrack -Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 26 | Define all in process, pre-VPI, and post VPI electrical tests and Peer Review to beginning of work. [Heitzenroeder] |  | All tests will be conducted in accordance with reviewed and apporved procedures (Chrzanowski) | Chrzanowski, Jim | Agreed. This has been added in the manufacturing procedures. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 1 | A joint Management/ACC final walk down of the facility be conducted. [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 2 | The ACC believes it would be prudent to assure that the issues affecting each stage are addressed prior to commencing that stage. [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 3 | NCSX procedures are not necessarily in accordance with PPPL established methodologies. Specifically: (1) Change control is not addressed (2) No ATI is specifically identified (3) Existing PPPL Procedures currently exist do not address the TRC, but are g [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 4 | The Work Planning Form, identified on the JHA’s (#1138) does not address the TRC operation. Is there a WPF specifically for the TRC [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 5 | The JHA’s are in draft and should be reviewed and signed off prior to operations. This includes signing by all people who will perform the work, per ESH-004. [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 6 | Non-conformances should be addressed. Are there currently any outstanding NCR’s? The chain-of-command/disposition of NCR’s has not been established and documented. [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 7 | Metrology requirements are not clarified in documentation, e.g., calibration requirements/traceability to NIST, Roamer arm capabilities, critical measurements, etc. [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 9 | Training Matrix is incomplete, e.g., The matrix is not approved and HR/Training Department is not on approval review/sign-off. Other training requirements to consider for inclusion are: Metrology, Procedures, Fire watch, etc. [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 10 | None of the four technicians slated to perform this work have all of the listed required training. [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 11 | One of the training requirements is for a course that has not yet been developed (Coil Lead Brazing). [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 12 | The requirement for Field Supervision during TRC manufacturing is identified but does it provide adequate coverage? For “initial” operations, more uncertainty exists, making it prudent to assure the strongest level of field supervision is available. Field [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 13 | Fire Protection needs final review/approval of Jeanes. Determination of requirements for Fire Extinguishers to be established and Fire Extinguishers to be located as required. [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 14 | Flame permits are not yet issued for the TRC. [Barnes] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 15 | The standing platforms at the winding station should be reviewed by IH for tripping hazard and remediate as appropriate. [Malsbury] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 16 | The “clean room” for TRC operations is not complete. Is it complete enough for safe initial operations? [Malsbury] |  |  | Chrzanowski, Jim |  | COMPLETED Approved by Larry Dudek
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 1 | Need to demonstrate that adequate clearance among and between all the components exists during final assembly. [Perry] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 2 | Need to document the assembly tooling requirements and demonstrate that they are reasonable and achievable and that budget exists to pay for them. [Perry] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 3 | Document locations for all tooling balls. Document need for in-process sensors (motion, proximity, etc.) [Perry] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 4 | Document assembly requirements for the base support structure. [Perry] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 5 | Document assembly plan in a signed-off final assembly document. [Perry] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 6 | Cryostat base needs to be on the field period before they are put together. [Brown] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 7 | Explain risk management approach for the almost inevitable insulation pinches. Is this a minor issue? [Gettelfinger |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 8 | Need to develop a method to localize a vacuum leak in the field joint so that it can be repaired. [Dudek] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 9 | Per Peer Review, current weight of filed period is 78,000 lbs. Significantly greater than current crane capability. Upgrade to crane is not in scope at this time. [Simmons] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 10 | Establish a "weight coordinator" to watch that field period lift weight stays within crane limits. [Heitzenroeder] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 11 | Develop an electrical and coolant coil test plan integrated with machine assembly. [Heitzenroeder] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 12 | Verify lift-over clearance for solenoid is adequate. [ Heitzenroeder] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 13 | WBS 7 should be reviewed to assure that sufficient resources and schedule exist for the multiple levels (PFA joining, port extensions, NB duct, etc) of leak checking called out in plan. [Perry] |  |  | Cole, Mike |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cole/Nelson/Perry | 2004-04-15 | 14 | Tom Brown's presentation on spool piece to clamp minimum clearance indicated that the spool piece would need to be supported by a cantilevered arm to rotate it into position. Will the stress on the spool piece weld be acceptable? [Perry] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 1 | Need to have Viola and Chrzanowski review schedule in detail for timing of fixture deliveries with mockups and training. [Dudek] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 2 | Where are the TF Coils sub-assemblies going to be assembled? The west side of the Test Cell is available, but the overhead crane won't reach. [Chrzanowski] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 3 | Identify weights of each assembly component and completed assembly. [Viola] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 4 | Schedule for Jobs 1808/1810 -Where is the mag. Sensor installation in the schedule? -Where is fit-check of mod-coil subassemblies in the schedule. [Neilson] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 5 | Should perform a tolerance analysis (vs. tolerance budget) to determine if the tolerances required are achievable with the manufacturing and assembly processes selected. Would also serve as a map to troubleshoot the assembly process if it is determined [Dudek] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 6 | 1) Identify lay down and storage area for all components and completed sub-assemblies 2) If schedule changes such that parts accumulate, is a problem? [Neilson] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 7 | At some point, the field period assembly trajectory needs to be under configuration control. [Neilson] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 8 | What is the flammability of Microtherm concern is sparks from welding. [Viola] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 9 | The platform needs to address the safety access to the 20' difference in elevation needed for access for insulation and welding. [Viola] |  |  | Cole, Mike |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cole/Dudek/Nelson | 3/302004 | 10 | Need to look at deflection of parts/as fixture during assembly. [Dudek] |  |  | Cole, Mike |  | Resolve prior to PDR
VV Structural Analysis Peer Review | 2004-04-22 | 3 | Build local model of port extension to get a better picture of the stresses where the port extensions attach to the shell. [Reiersen] |  |  | Dahlgren, Fred |  | Resolve by PDR
ACC Review of Manufacturing Facility - Station 2 | 2004-10-21 | 8 | Many of the chits generated at the FRD related to operational procedures and would need to be resolved before operational procedures could be finalized. [Barnes] |  |  |  | Operational procedures will require the concurrence of the RLM that relevant chits have been addressed to the degree required for that stage of operation.
Coil Test Facility Plumbing FDR Gettelfinger/vonHalle/Perry | 2004-11-10 | 1 | Relief valves vent into the room, oxygen deficiency potential must thoroughly evaluated. [Perry] |  |  | Gettelfinger, Geoff | Reliefs will vent to a hermetic dump line to exhaust system | 2005-03-15
Coil Test Facility Plumbing FDR Gettelfinger/vonHalle/Perry | 2004-11-10 | 2 | IH needs at least 1 week notice before the foaming operation begins to complete preparations to support this activity. Note that the results of the surveys will take 1-2 weeks to complete. [Levine] |  |  | Gettelfinger, Geoff | Complete. | Complete.
Coil Test Facility Plumbing FDR Gettelfinger/vonHalle/Perry | 2004-11-10 | 3 | Comments on the CTF Hazards Analysis must be resolved, and the document must be approved by the Safety Review Committee (SRC) prior to commencing CTF operations. [Levine] |  |  | Gettelfinger, Geoff | Agreed. | 2005-03-15
Coil Test Facility Plumbing FDR Gettelfinger/vonHalle/Perry | 2004-11-10 | 4 | For upper pressure control use a pressure regulator/control valve (offers finer control and smaller control band than RV) [Kalish] |  |  | Gettelfinger, Geoff | Agreed. | 2005-03-15
Coil Test Facility Plumbing FDR Gettelfinger/vonHalle/Perry | 2004-11-10 | 5 | Make adjustable relief valve visible/audible to tell when it is venting [Nelson] |  |  | Gettelfinger, Geoff | Reliefs will vent to a hermetic dump line to exhaust system | 2005-03-15
VV Structural Analysis Peer Review Dahlgren/Nelson/Reiersen | 2004-04-22 | 1 | How do we document what model was analyzed? Need to associate the model version with an identifier. |  |  | Goranson, Paul |  | Resolve by PDR
VV Structural Analysis Peer Review Dahlgren/Nelson/Reiersen | 2004-04-22 | 2 | Add a doublers or criss-cross rib to reduce the max deflection on the shell such that the deflections at the ends of the parts are ok (part 2 and 9) |  |  | Goranson, Paul |  | Resolve by PDR
VV Structural Analysis Peer Review Dahlgren/Nelson/Reiersen | 2004-04-22 | 4 | Consider thickening the thickness of the turret and port extensions to being peak stresses below allowable (375ºc) of 25ksi esp. around ports 15 and 18. |  |  | Goranson, Paul |  | Resolve by PDR
VV Structural Analysis Peer Review Dahlgren/Nelson/Reiersen | 2004-04-22 | 5 | Do our clearance calculations accommodate the max. deflections at the end of the port extensions? What allowance was made? |  |  | Goranson, Paul |  | Resolve by PDR
VV Structural Analysis Peer Review Dahlgren/Nelson/Reiersen | 2004-04-22 | 6 | Weld efficiency. Determine allowables based on non-radiographed welds. |  |  | Goranson, Paul |  | Resolve by PDR
VV Structural Analysis Peer Review Dahlgren/Nelson/Reiersen | 2004-04-22 | 7 | Unbalances pressure loads also need to be considered. |  |  | Goranson, Paul |  | Resolve by PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 1 | Consider making an intermediate port connection on all circular ports, with the joint just outboard of the modular coil. Consider making the extension tubes out of stainless. Consider an assembly strategy which would permit removal and replacement of ex [Johnson] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 2 | Present run of RF parts does not enter the vessel near enough to the ends at the antenna to allow a connection. RF parts need to be revisited. [Majeski] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 3 | Needs to reposition the PF 5 leads (or rotate coil) to eliminate lead interference with Port 16. [Brown] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 4 | Reposition port #13, its too close to the TF winding. [Brown] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 5 | Consider unifying ports 9 and 13 to avoid interference during bake, to reduce costs. [Zarnstorff] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 6 | Near port 9, does the TF support structure have to be this large and come this close to the port? Can the edge of the support structure be pulled back? [Zarnstorff] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 7 | Consider stepping the diameter of port 3 to a larger diameter tube outside the modular coils. This would allow a larger angle of view of the oblate cross-section (a region that has limited access). [Zarnstorff] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 8 | In the regions of very close proximity between vessel and coils, what instrumentation should be built into the structure to allow monitoring so that bake out does not endanger the coils.[Zarnstorff] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 9 | On the NB Port: the internally bolted joints must be (somehow) designed so that each bolt does not become a virtual leak. [Zarnstorff] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 10 | Include (consider) the port tolerances in the minimum clearance study [Heitzenroeder] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 11 | Port 16 vs. # small bolts issue (interference?)[Gettelfinger] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 12 | Resolve bake out clearances at Port 4. Can diag stand a lesser port size? [Gettelfinger] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 13 | Work out the assembly sequence of the NB transition duct internal seal. (Can a man make it up from the inside) [Dudek] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 14 | Further consider port NB joint detail. Bolted joint with seal weld? [Gettelfinger] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 15 | Consider beam geometry with port NB, all OK? [Gettelfinger] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 16 | Have all system interfaces been reviewed? Are services other than diagnostic e.q., (RF, NB) been consulted? [Viola] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 17 | This design represents # port additions of about 30% to the previous design. Besides the obvious installation of the ports there is additional insulating cooling tubes, assembly alignment etc. Is this cost budgeted? [Viola] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 18 | Consider joining adjacent circular ports into one oval shape if there is any advantage [Viola] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 19 | Be wary of conflate seal leaks due to thermal gradients across the copper. Sandia and PPPL have had failures. [Gettelfinger] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 20 | Check clearances between welds of adjacent tubes. You will get a significant amount of distortion. [Viola] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 21 | The additional ports virtually "use up" any spare locations where diamond wire cutting could occur. An alternative method of cutting the vessel is needed [Viola] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 22 | What is the project's position on Inconel vs. SS port extrusions? Pick one and document the decision. [Gettelfinger] |  |  | Goranson, Paul |  | Resolve prior to PDR
VV Ports Peer Review Cole/Heitzenroeder/Dudek | 2004-01-29 | 23 | Re-orient rather than re-locate or re-sizing to address tight clearances. (This is ok with diagnostics) [Heitzenroeder] |  |  | Goranson, Paul |  | Resolve prior to PDR
Coil Tolerence, Trim Coil Peer Review Brooks/Nelson/Reiersen | 2004-04-21 | 1 | Dynamic deflections - especially for modular coils - have to be taken into account in criteria. [Heitzenroeder] |  |  | Kalish, Mike | On Hold for Trim Coil Re-Design | Must be resolved prior to trim coil PDR
Coil Tolerence, Trim Coil Peer Review Brooks/Nelson/Reiersen | 2004-04-21 | 2 | Tolerances of + 3.0mm for PF5, PF 6 and TF (and maybe trim coils) may require an "extra" effort. Will be helpful to define exceptions to the rule so that we meet tolerances as required but are allowed relief in less critical areas. [Kalish] |  |  | Kalish, Mike | On Hold for Trim Coil Re-Design | Must be resolved prior to trim coil PDR
Coil Tolerence, Trim Coil Peer Review Brooks/Nelson/Reiersen | 2004-04-21 | 3 | Provide requirements for brining out trim coil leads. How many individual circuits penetrate the cryostat on day one? [Kalish] |  |  | Kalish, Mike | On Hold for Trim Coil Re-Design | Must be resolved prior to trim coil PDR
Coil Tolerence, Trim Coil Peer Review Brooks/Nelson/Reiersen | 2004-04-21 | 4 | Re: Building Steel: need to characterize residual error fields and island when (a) use PF coils to compensate steel fields, as best you can ; (b) same as (a) but allow upper/lower PF coil currents to differ; (c) same as (b) but include trim coils. [Zarnstorff] |  |  | Kalish, Mike | On Hold for Trim Coil Re-Design | Must be resolved prior to trim coil PDR
Coil Tolerence, Trim Coil Peer Review Brooks/Nelson/Reiersen | 2004-04-21 | 5 | Document current patterns in trim coils required to correct each mode and each phase. [Reiersen] |  |  | Kalish, Mike | On Hold for Trim Coil Re-Design | Must be resolved prior to trim coil PDR
Coil Tolerence, Trim Coil Peer Review Brooks/Nelson/Reiersen | 2004-04-21 | 6 | Consider a 2-step tolerance requirement for the modular coils based on separation from the plasma boundary. [Reiersen] |  |  | Kalish, Mike | On Hold for Trim Coil Re-Design | Must be resolved prior to trim coil PDR
Coil Tolerence, Trim Coil Peer Review Brooks/Nelson/Reiersen | 2004-04-21 | 7 | Tolerance requirements on trim coils need to be justified. [Reiersen] |  |  | Kalish, Mike | On Hold for Trim Coil Re-Design | Must be resolved prior to trim coil PDR
TF Coil Peer Review Kalish/Reiersen/Nelson | 2004-09-15 | 1 | Thermo-hydraulic analyses need to be documented. |  |  | Kalish, Mike | Complete, Thermo- Hydraulic Analysis is complete | Resolve prior to PDR
TF Coil Peer Review Kalish/Reiersen/Nelson | 2004-09-15 | 2 | What is the risk during cool down due to different expansion coefficients |  |  | Kalish, Mike | Complete, Cool down and thermal contraction accounted for in analysis. | Resolve prior to PDR
TF Coil Peer Review Kalish/Reiersen/Nelson | 2004-09-15 | 3 | Does this add additional weight? What is the new total weight of 120 º field period. |  |  | Kalish, Mike | Complete, Wedge casting weight is more than offset by reduction in weight in reduced copper cross-section | Resolve prior to PDR
TF Coil Peer Review Kalish/Reiersen/Nelson | 2004-09-15 | 4 | Check the impact of out-of -plane defamations on resonant field errors. |  |  | Kalish, Mike | Complete, Analysis requires +/- 3mm Tolerance | Resolve prior to PDR
TF Coil Peer Review Kalish/Reiersen/Nelson | 2004-09-15 | 5 | The insulate -after-shaving and after ground-wrapping must be demonstrated by development program due to high risk. |  |  | Kalish, Mike | Resolved N/A, The insulate after shaving ground wrap scheme has been abandoned for a conventional winding pack approach | Resolve prior to PDR
TF Coil Peer Review Kalish/Reiersen/Nelson | 2004-09-15 | 6 | Consider ways of soliciting vendor input on how to fabricate the coil assembly and on the vendor scope. |  |  | Kalish, Mike | Resolved, Vendor meetings are planned to solicit vendor input . | Resolve prior to PDR
TF Coil Peer Review Kalish/Reiersen/Nelson | 2004-09-15 | 7 | Check structural calculations modeling of wedge region is not accurate and up-down asymmetries are suspicious. |  |  | Kalish, Mike | Complete, Caluculations have been revised. Up-Down asymmetries were result of fixed vertical restraints on bottom of coil | Resolve prior to PDR
Conventional Coil TF Stress Analysis Kalish,Myatt/Reiersen/Chrzanowski | 2004-04-01 | 1 | Quantify material properties for our specific epoxy- insulation systems. [Reiersen] |  |  | Kalish, Mike | Complete, Material properties with their pedigree are presented in calculation memos | Resolve prior to PDR
Conventional Coil TF Stress Analysis Kalish,Myatt/Reiersen/Chrzanowski | 2004-04-01 | 2 | Review design criteria especially with respect to very local regions of high stress. [Reiersen] |  |  | Kalish, Mike | Complete, Calculation memos referance and follow design crieteria. All calculations will be checked including stress allowable criteria prior to FDR | Resolve prior to PDR
Conventional Coil TF Stress Analysis Kalish,Myatt/Reiersen/Chrzanowski | 2004-04-01 | 3 | Investigate the use of 3D glass to lower thermal cool down stresses. [Reiersen] |  |  | Kalish, Mike | Resolved / NA 3D Glass option investigated but decision to apply Kapton directly to the conductor negates any advantage of 3D glass | Resolve prior to PDR
Conventional Coil TF Stress Analysis Kalish,Myatt/Reiersen/Chrzanowski | 2004-04-01 | 4 | Add leads to analysis plan. [Reiersen] |  |  | Kalish, Mike | Resolved, Stress analysis added to stress evaluation plan with results prior to FDR | Resolve prior to PDR
Conventional Coil TF Stress Analysis Kalish,Myatt/Reiersen/Chrzanowski | 2004-04-01 | 5 | Are there any issues with leads and coolant feeds? Historically these are a common failure site. [Neilson] |  |  | Kalish, Mike | Resloved, Leads are brought out directly eliminating potential braze joint failures at leads. Simple resilient design used. Analysis to follow | Resolve prior to PDR
Conventional Coil TF Stress Analysis Kalish,Myatt/Reiersen/Chrzanowski | 2004-04-01 | 6 | Look at test Data and determine if a lower modulus can be used as well as if there is an indication of a soft plastic region in the .02% strain range. [Kalish] |  |  | Kalish, Mike | Resolved, NA Insulation thermal stress cracking not an issue due to new Kapton on copper insulation scheme | Resolve prior to PDR
Conventional Coil TF Stress Analysis Kalish,Myatt/Reiersen/Chrzanowski | 2004-04-01 | 7 | Consider testing for thermal cycling with coil samples. [Kalish] |  |  | Kalish, Mike | Resloved, Test Bars are in fabrication and testing both mechanical and thermal is planned | Resolve prior to PDR
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.7 | Concern with timely statusing and closure of Chits. [Malsbury] |  |  | Malsbury, Judy | See response to finding 1.6. J. Malsbury to verify that corrective action is being accomplished. | By 5/31/2005
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.8 | Concern with timely statusing and closure of Chits. [Malsbury] |  |  | Malsbury, Judy | See response to finding 1.6. J. Malsbury to verify that corrective action is being accomplished. | By 5/31/2005
Shield Wall Reconfiguration PDR Parsells/Perry/Dudek | 2004-03-09 | 1 | New Scope? An interface control document must be generated for: (1) N2 emergency exhaust duct; and (2) tons of pipe and creeping add-ons. I can do #1. |  |  | Perry, Erik |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Parsells/Perry/Dudek | 2004-03-09 | 2 | If there is a plan at some future date to add another layer of shield block, wouldn't it not be prudent to make the larger base shield block large enough to support the future blocks? |  |  | Perry, Erik |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Parsells/Perry/Dudek | 2004-03-09 | 3 | Forklift handling has been mentioned for the blocks. If forklift is used then 4' clearance is needed from face of the block. Slots under block would be needed. Rigging from forklift must be avoided consider standard block handling design Richmond anchor |  |  | Perry, Erik |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Parsells/Perry/Dudek | 2004-03-09 | 4 | An ALARA Cost/Benefit Analysis should be performed for the shielding design. Consult with George Ascione. |  |  | Perry, Erik |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Parsells/Perry/Dudek | 2004-03-09 | 5 | Consider raising the shield wall to highest "Practical" Height. Avoid relying on later reconfigurations. |  |  | Perry, Erik |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Parsells/Perry/Dudek | 2004-03-09 | 6 | GRD requirement for seismic references DOE-STD-1020 which calls out JBC-2000. Static site specific criteria lead to the required horizontal shear of: V=.15W for "detailed plain masonry shear wall" V=.20 for "ordinary plain masonry shear wall" verify desi |  |  | Perry, Erik |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Parsells/Perry/Dudek | 2004-03-09 | 7 | Shielding design and extent must be verified by analysis to meet the NCSX radiation exposure requirements for occupants outside the NCSX Test Cell (e.g., control room operator, office occupants, etc.) include sky shine. |  |  | Perry, Erik |  | Must be resolved prior to reconfiguration
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 1 | 1)The distance between top of one tray to the top of another tray shall be 18". This leave a clearance of 12" between trays for trapping etc. 2) Distance between one horizontal tray to another. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 2 | Verify whether the FCPC side wall can carry the load of 600#/ft. of the tray system. Also, determine the maximum side lad that can be imposed to see as to what factor of safety is provided. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 3 | What is the cost impact if the number of support structures are reduced by increasing the span. Can we adopt a design with a span of minimum 50' so that the number of supports are reduced. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 4 | Where is the detailed drawing for the structure bridging between towers of types 1 and 2? [Zarnstorff] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 5 | On drawings S1/1 Bridge Elevation, the diagonal bracing shown for the bridges does not correspond with that shown on drawings S3 and S4 (the angles are clearly different) [Zarnstorff] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 6 | On drawings S2/6 "Typical Bracing Detail", where does this detail apply? This does not correspond to the bracing for the Tray support towers shown on drawings S2. [Zarnstorff] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 7 | On drawings S3 and S4, no dimensions are specified for a) the vertical columns. b) the height of the concrete caissons above grade . c) the horizontal separation between the caissons . Drawings S4/2 "Bridge Section" does not show the horizon [Zarnstorff] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 8 | On drawings S6/1 "Building Section", it is not clear what is new and what is existing. Also, the method for attaching the new structure to the building is not specified or detailed. Also: How will the building penetration be sealed (needed to prevent) [Zarnstorff] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 9 | Why must the large bridge (drawing S4) be so much broader (˜ 8 feet between pillars) that the small bridge ( ˜4 feet between pillars, drawings S3 ? [Zarnstorff] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 10 | The present design uses 4 different types of cable support platforms (with different widths etc. ) and four different tower types (ignoring Support type 3) in the straight part of the run. Why such a complicated design? Why not do it all with 60' to 70' [Zarnstorff] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 11 | Presently, the trays are supported on a raised beam, mounted above the bridging structures, as shown on drawings S4/2 and S3/2. Why not make these cross-pieces part of the bracing structure, set between the side beams, and lay the bottom trays directly . [Zarnstorff] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 12 | Contractor to document underground discrepancies and feed back information to client [Jones] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 13 | Note: that the existing bridge has a clearance of 19'3". Should new bridge equal this clearance? [Jones] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 14 | Tube steel ex. 4x2x 1/4 for tray support is unorthodox. Revise design to incorporate a material compatible with tray manufactures mounting clamps. [Jones] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 15 | Tray support spacing appears to exceed NEMA 20C capacity Review/Revise as appropriate to comply snow/ice load in calculations. [Jones] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 16 | Tray support size is short. Ex. Provide 40" minimum for a 36' tray and support clamps. Note: that tray flange is out on "Cope" ladder tray. Provide addition support length for RUN variation. [Jones] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 17 | Support system has no provision for fittings and vertical riser support - see tray manufactures specification for fitting requirements.[Jones] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 18 | 4/0 bare at column bridge must be tied to building grid when in the proximity of building or fence (existing requirement) [Jones] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 19 | 1-1/c 1000 mcm cables should have overall jacket to aid cable pull, provide added protection and maintain twist spacing. [Jones] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 20 | Please see attached requirements for fiber and copper cables required for WBS5. Three points: 1. Prevent droops and resolve bending -see attached. 2. Allow space for growth. 3. Follow all pull spec for fiber. [Oliaro] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 21 | C-site underground infrastructure is old and not well documented, so location of tower is critical to be documented in details, long time before final drawings. [Ilic] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 22 | Several calculations and analysis have been mentions. All should be complied and documented. [Malinowski] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 23 | Before contract is awarded, determine funding source for the extra tray being added to support control cables WBS 4 or 5? Neilson] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 24 | *Ensure that Safety Management plans are documented in the contract SOW. * Ensure that adequate day-to-day oversight is provided by PPPL. [Neilson] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 25 | High strength bolts are specified. Suspect bolts controls are required & cost increase & controls must be budgeted. [Potensky] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 26 | Do the support braces have the proper clearances from the road etc. example S-3 Bridge Section [Potensky] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 27 | Any digging greater than 12" requires PPPL digging permit/hole. The digging permit will govern how the hole will be dug. Manholes will have to be hand dug & GPR required, etc. [Potensky] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 28 | Need to incorporate site seismic and wind loads into the design of the structure. Also snow and ice loads should be considers. Levine] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 29 | Burns should provide calculations of the loadings of this new structure on existing buildings (FCPC and Power Building). In general, all load calculations should be review by PPPL. [Levine] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 30 | Trays mounted on square tubing is unconventional for standard hold-down clamps. How are trays going to be held down. Will this be acceptable for expansion hold down clamps also? [Van Kirk] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 31 | 1.Trays shall be supported per manufacturer's specs. This does not appear to be the case. Radius tray @ 1/20. 2. Manufacturer recommended support at 2; both sides of thermal contractions of expansion joints. Where do these take place? Show on drawing [Van Kirk] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 32 | Width of all supports need to be increased to accommodate hold-down clamps. [Van Kirk] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 33 | Distance between tray elevation needs to increase to 18" from bottom of one tray to bottom of another tray. [Van Kirk] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 34 | Liner support dimensions for tray inadequate - spacing too long. Manufactures' recommended spacing for said load plus snow and ice load should be followed. NEMA 20C = 20' spacing at 100#/ft. We are more near? Lbs../ft. see chit #15 [Van Kirk] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 35 | Electrical notes and details are inadequate for tray installation. [Jones] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 36 | Maintenance access after bridge construction. Can all existing systems be accessed for repair/replacement? Especially neutral beam transformers at C-site and pump house? [Lacenere] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 37 | Final design structure shall support (13) duplexed 1000 mcm cables total weight of cable per circuit is approximately 9#/ft. Therefore cable weight is 13*9 = 117#/ft. My concern is the structure for supporting the cable tray & cables alone FCPC Building [Lacenere] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 38 | Too many elevation changes of cable tray between FCPC building and C-site. The NEC allows for 360 degrees of total bends between pull points. PPPL allows for maximum of 270 degrees between pull points. Also the maximum bending radius for duplex 1000 m [Lacenere] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 39 | Clearance of north side of C-site pump house double doors for equipment removal with structure passing right above loading dock. [Wise] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 40 | Caisson in MOAT will need to be increased 6' deeper because gravel in moat is 5' deep. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 41 | Caisson TS4 will have to be moved west so that it does not interfere with existing transformer footing and support base. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 42 | Caisson TS3 and TS6 are blocking access to Sub-18 (for vehicle etc.) [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 43 | Drawing S1 does not show location of 13.8 kV duct bank [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 44 | Drawing S1 does not show location of 5kV system that goes to C-site pump house. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 45 | Drawing S1 does not show 2, 400 V street lighting system at D-site and clearance. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 46 | Drawing S1 does not show 480 V and phone cable system above ground and it's clearance. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 47 | The spacing between trays needs to be increased to a minimum of 12" from top of rail of lower tray to bottom of upper tray. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 48 | Reduce the number of drops in the tray system to reduce cable side wall forces. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 49 | There is a possible code violation where tray system passes through Sub-18 since it has nothing to do with Sub-18. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 50 | Burns Group to insure that cable pulling (six duplexed cable 2-1/c-1000mcm) in each of the trays can be performed per Tray & Cable manufacture's recommendations and per standard industry practice. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Ramakrishnan/vonHalle/Perry | 2004-04-21 | 51 | Provide 1-C-500mcm bare copper cable in each tray. This cable shall be grounded at both ends. Each tray section shall also be attached to the ground cable. [Ramakrishnan] |  |  | Ramakrishnan, Raki |  | Must be resolved prior to machine installation in test cell
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 1 | Section 3.3.2: A) requirement for ground-loop detections out of scope, should be deleted. B) 3rd line: isn't this redundant with req't for single PT ground? [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 2 | Appendix A. Is there instrumentation that will show success for each demonstration: If not, then tests are needed per the definition in 4.2 [Malinowski] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 3 | 4.2 examination excludes use of instruments. We need an inspection approach that allows for special equipment. [Malinowski] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 4 | Appendix A, general terms such as "minimize" "fast" and "C fall rating" need more specific definitions. [Malinowski] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 5 | Section 3.3.2: I question whether the NCSX Project could disassembly/reassembly the machine, if a modular coil need replacement. A more realistic schedule or plan should be generated. [Chrzanowski] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 6 | 3.2.3 1st paragraph: "e…. consistent with the facility achieving a high level….." [Neilson] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 7 | All requirements should be verified by some combination of the methods presented No "N/A's" [Neilson] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 8 | Are the ref's scenario waveforms under configure control? What about the 3-coil assembly trajectory over the VV? |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 9 | Electrical design criteria should be added here (and perhaps in the GRD) [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 10 | Section 3.2.3, the 75% availability is for the whole device, not the coils alone. The requirement here should come form the RAM plan. [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 11 | Section 3.2.3, should include a requirement for design features to ensure that the coils can be accurately positioned and actual position measured during assembly and operation [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 12 | Make the TDS an appendix to the SRD so it is a stand-alone dor. [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 13 | References GRD requirements to show traceability [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 14 | QCM needs to correspond to requirements in this documents. [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 15 | Section 3.2.2, should include to co-wound sense coils. [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 16 | Section 3.2.2, we should check with Raki on whether he wants two feeds per MC circuit. Note: This is required for the C-site power option. [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 17 | In section 3.2.1.2, 4th sentence: should state what vessel back out temperature this holds for (350ºC). [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 18 | In section 3.2.1.2, the 1st sentence: should state that the coils should be held at 80ºK for the full range of vacuum vessel operating temperatures (˜20º - 250ºC). [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 19 | Section 2.3 should include the NCSX GRD [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 20 | Remove autoclave (all tooling) requirements from SRD. [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 21 | 3.2.2 In revolving facility autoclave requirement modify statement - should read. Heat assemblies from RT to 50º C in 4 hrs, 50º C to 110º C in 5 hrs. [Chrzanowski] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 22 | Consideration should be given to organizing the requirements around machine states i.e. (the functional flaw diagram) in Section 3. [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
MC SRD Specification Review Williamson/Cole/Reiersen | 2004-03-31 | 23 | Applicable documents (Section 2) should identify all and only those documents referenced in this SRD. [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 1 | Location of the inconel-to-stainless transition joint and requirements for diagnostic flexibility need to be captured somewhere. Is it an interface or flowed down from the GRD? [Neilson] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 2 | What sets the VV insulation thickness? Is there a reference in the interface section or do you state that the insulation is 1" thick. [Brown] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 3 | Section 3.2.1.2.1.2 or section 3.2.1.3.2 needs to recognize the GRD requirement to operate with the 250ºC liner (for lithium OP), presumably by operating with the vessel at 250ºC [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 4 | Need a metrology requirement requiring that design features be incorporated to enable accurate measurement of the vessel position during assembly and in the assembled state during operation. [Zarnstorff] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 5 | Need to look at consequences of loss of site power, loss of heating/cooling , etc., see any requirements derived from this? [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 6 | Resolve issue of "what is possible" i.e. horizontal and vertical design loads. [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 7 | Organize 3.13 as a stand-alone section, not along WBS lines. [Reiersen] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 8 | Section 3.3.1.4: NCSX structural & cryogenic design criteria is a draft & almost 2 yrs. old. Valid reference? [Malsbury] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 9 | Section 3.3.1.2 b) standards for degreases & cleaning. [Malsbury] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 10 | ( paragraph 2) add all docs ref'd in body of spec. [Malsbury] |  |  | Reiersen, Wayne |  | By 1/31/2005
VV SRD Specification Review Goranson/Cole/Reiersen | 2004-04-01 | 11 | Revise GRD to clarify pre-pulse temp. 20-60 ºC following pulse. Uniformities of temp required on VV? [Simmons] |  |  | Reiersen, Wayne |  | By 1/31/2005
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.1 | Documents are in draft form that should have been finalized. |  |  | Reiersen, Wayne | SEMP, SRDs are being finalized and will be signed by mid-January. Criteria docs already signed and posted. | By 1/31/2005 (Revised from 12/17/2004)
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.11 | Design basis calculations for the MCWF were not all finalized and approved. |  |  | Reiersen, Wayne | All will be formally documented and checked in analysis reports by the Comprehensive Modular Coil FDR. | By 3/5/2005
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.12 | Recommendation made that plans and procedures be streamlined. |  |  | Reiersen, Wayne | All plans and procedures for design control will be reviewed and modified as appropriate (not finalized). | By 1/28/2005
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.2 | The Configuration Management Plan and supporting guides and procedures will be reviewed and revised to incorporate 3D models |  |  | Simmons, Bob | The ProE/INTRALINK system has a very disciplined process of handling revisions to drawings and models and this is being followed EXACTLY since ProE/INTRALINK will not permit otherwise. What has not been adequately done is to fully document this in NCSX d | By 1/15/2005 (Revised from 12/17/2004)
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.3 | NCSX-PROC-004 will be revised to eliminate configuration item identification. |  |  | Simmons, Bob | The Project response made it very clear that “the formal practice of configuration identification has never been done and should not be required.” PROC-004 is in the process of being revise to clarify what is a Configuration Item and should be finalized | By 1/31/2005 (Revised from 12/17/2004)
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.4 | Concerns were expressed about the relationship between the Ops Center and the NCSX Records Mgmt System |  |  | Simmons, Bob | Both the DMP and the SEMP have been revised to clarify the relationship between the Ops Center and the NCSX Records Management System. Both documents are in final review and will be posted for signature next week. | By 1/31/2005 (Revised from 12/17/2004)
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.9 | Concerns with NCSX Design Review processing of chits |  |  | Simmons, Bob | Systems Engineering Support Manager will obtain Head Engineering and Technical Infrastructure concurrence on NCSX-PROC-004 | By 1/31/2005 (Revised from 12/17/2004)
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.13 | Recommendation made that plans and procedures be streamlined. |  |  | Simmons, Bob | A peer review of these plans and procedures will be held. | By 2/25/2005
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.14 | Recommendation made that plans and procedures be streamlined. |  |  | Simmons, Bob | The plans and procedures for design control will be finalized using the output of the peer review. | By 3/25/2005
QA Audit #0406 NCSX Design Control | 2004-11-17 | 2.1 | Training on the NCSX systems for design control has not been defined or provided. |  |  | Simmons, Bob | COMPLETED. REV 1 ISSUED IN EARLY DECEMBER. | COMPLETED
QA Audit #0406 NCSX Design Control | 2004-11-17 | 2.2 | Training on the NCSX systems for design control has not been defined or provided. |  |  | Simmons, Bob | Training will be provided to all project personnel involved in design control activities. | By 5/19/2005
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.5 | The status of all chits from the design reviews for the MCWF and VVSA FDR will be reviewed. |  |  | Tyrrell, Marianne | A consolidated tracking log for all CHITs has been developed and is in the process of being statused. A revised disposition status and copy of this CHIT Tracking Log will be available next week (e.g.,, completed, planned for next design review , expected | By 1/31/2005 (Revised from 12/17/2004)
QA Audit #0406 NCSX Design Control | 2004-11-17 | 1.6 | All open chits will have milestones associated with them by which the chit should be closed. NCSX plans and procedures will be appropriately modified to reflect this practice. |  |  | Tyrrell, Marianne | NCSX Procedure 004 ready for signature. NCSX Engineering Administrator will use newly developed CHIT/Audit Finding Tracking Log to follow-up with WBS Managers and responsible engineers. | By 1/31/2005 (Revised from 12/17/2004)
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 1 | Add TC Instrumentation to the back side of the Spool Piece test to monitor the temperature during the weld. |  |  | Dudek, Larry | This will be added to the Spool piece at the time of the test. | By 5/19/2005
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 2 | Perform a visual inspection of the root pass of the welds |  |  | Dudek, Larry | This was done on the first test pieces. The parts passed. | Completed
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 3 | Insulate the backside of the weld with microtherm to determine if there are any burning issues with the insulation during the test |  |  | Dudek, Larry | This was done on the test piece. It was determined that there was no effect | Completed
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 4 | Is there a flux that can be used to make Inconel weld flow better |  |  | Dudek, Larry | Still investigating | By 1/31/2005
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 5 | Anneal pieces before welding to ensure it's in a similar condition to the |  |  | Dudek, Larry | This was done on the test pieces. | Completed
Twisted Racetrack Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 1 | No details presented on how "real time" determination of surface error (+/-) provided. Readiness of metrology effort for TRC Winding needs to be established |  |  | Williamson, Dave | Measurements will be taken during a trial winding of several turn layers on the TRC. A procedure for determining the shimming requirements for the winding packs will be developed. STATUS: Measurements taken 12/6/04, analysis in progress. Open | By 1/15/2005
Twisted Racetrack Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 2 | The metrology measurement system needs to be demonstrated before the winding of the coil. |  |  | Williamson, Dave | Measurements will be taken during a trial winding on the TRC. STATUS: Measurements taken 12/6/04, analysis in progress. Open | By 1/15/2005
Twisted Racetrack Coil FDR Williamson/Reiersen/Dudek | 2004-10-15 | 4 | The specification for electrical isolation needs to be clarified. Properties of adhesive tape needs to be determined. Electrical tests need to be in the procedures. |  |  | Williamson, Dave | The TRC product specification and flow-down procedures shall define the method for applying the turns, leads, and ground insulation. The procedures will identify all electrical tests. STATUS: Spec, procedures have been signed off. CLOSED | By 1/15/2005
MC Winding Pack Peer Review Williamson/Nelson/Reiersen | 2004-03-19 | 1 | There is significant uncertainty in the achievable copper cross-section, due to : Keystoning, twist deformation, waviness of the chill plates, squishiness of the insulation Recommendation: go ahead with twisted racetrack based on current design. Do not |  |  | Williamson, Dave | Winding will proceed with reference design, except when changes can be accommodated without significant delay. Goal remains that TRC will accurately reflect final configuration. STATUS: Cladding installed, winding to commence 1/10/05. Open | Resolve by PDR
MC Winding Pack Peer Review Williamson/Nelson/Reiersen | 2004-03-19 | 2 | Show the location of the magnetic loops in winding pack |  |  | Williamson, Dave | Magnetic loops location be identified in TRC product spec and flow-down procedures. STATUS: Spec - procedures have been signed off. CLOSED | Resolve by PDR
MC Winding Pack Peer Review Williamson/Nelson/Reiersen | 2004-03-19 | 3 | Why are the 14 mil. (lateral and 32 mil. (radial) shims adequate? The 14 mil. shim looks small just based on conductor tolerances. Consider re-optimizing conductor aspect ratio and shim thickness or even re-size the conductor. |  |  | Williamson, Dave | Winding procedure has been modified to accommodate practical measurement technique: after winding 4-5 turn layers, measurements will be taken to determine optimum single layer shim thickness (up to 0.3 in.) for radial adjustment. Lateral shims TBD. STATUS: Analysis of TRC trial winding measurements in progress. Open | Resolve by PDR
MC Winding Pack Peer Review Williamson/Nelson/Reiersen | 2004-03-19 | 4 | Mold release the tee before applying the chill plates. Move the kapton from the tee onto the back of the chill plate to isolate the chill plate from the tee. |  |  | Williamson, Dave | Winding procedure incorporates mold release on tee except for masked areas. Kapton Layer, 0.035 -in. thick, to be applied to back of claddings. STATUS: CLOSED | Resolve by PDR
MC Winding Pack Peer Review Williamson/Nelson/Reiersen | 2004-03-19 | 5 | Fill in radius at the base of the tee prior to applying mold release to avoid locking the winding to the tee. |  |  | Williamson, Dave | Tee Relief groove to be filled with RTV. STATUS: CLOSED | Resolve by PDR
MC Winding Pack Peer Review Williamson/Nelson/Reiersen | 2004-03-19 | 6 | Consider removing French toast after potting so the coil behaves as modeled (or show it is inconsequential) |  |  | Williamson, Dave | Plan to check feasibility of removing French Toast from TRC. STATUS: Open | Resolve by PDR
MC Winding Pack Peer Review Williamson/Nelson/Reiersen | 2004-03-19 | 7 | Verify that cu cooling tubes are electrically isolated from each other and ground (e.g. the tee) |  |  | Williamson, Dave | Cooling tubes to be redesigned, however isolation will be preserved by use of electrical break at poloidal break. STATUS: Open | Resolve by PDR
MC Winding Pack Peer Review Williamson/Nelson/Reiersen | 2004-03-19 | 8 | Will not be able to maintain a 0.100 inch gap between chill plates unless they are custom wedge-shaped or tapered. If we have to do this custom shaping in the field it will be very time consuming. |  |  | Williamson, Dave | Gap between chill plates is not critical, however tests have indicated that a larger gap is necessary for ease of assembly: gap will increased to 1/8 in. STATUS: Open pending final modifications to chill plate. | Resolve by PDR
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski Chit Author [Reiersen] | 2003-06-12 | 1 | Verify that existing NEPA and WP cover the handling of cryogens and powering of test coils. |  |  | Williamson, Dave | Racetrack coil has been built and tests. STATUS: CLOSED
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski Chit Author [Reiersen] | 2003-06-12 | 2 | Add enough instrumentation to verify our thermal and stress analysis-- looks tight now. |  |  | Williamson, Dave | Racetrack coil has been built and tests. STATUS: CLOSED
Racetrack Coil FDR Chrzanowski/Reiersen/Dudek | 2003-06-12 | 3 | Determine forces on clamp bolts and verify factor of safety with respect to pull out strength |  |  | Williamson, Dave | Racetrack coil has been built and tests. STATUS: CLOSED
Racetrack Coil FDR Chrzanowski/Reiersen/Dudek | 2003-06-12 | 4 | Need to finalize design of clamps -- not clear that we have a design that works. |  |  | Williamson, Dave | Racetrack coil has been built and tests. STATUS: CLOSED
Racetrack Coil FDR Chrzanowski/Reiersen/Dudek | 2003-06-12 | 5 | Consider going back to the half-lapped insulation if that is likely to be the reference design. |  |  | Williamson, Dave | Racetrack coil has been built and tests. STATUS: CLOSED
Racetrack Coil FDR Chrzanowski/Reiersen/Dudek | 2003-06-12 | 6 | Try winding inside / outside turn rather than layer by layer |  |  | Williamson, Dave | Racetrack coil has been built and tests. STATUS: CLOSED
Racetrack Coil FDR Chrzanowski/Reiersen/Dudek | 2003-06-12 | 7 | Suggest investigating < half-lapped insulation for R&D program to verify "armadillo- effect". |  |  | Williamson, Dave | Racetrack coil has been built and tests. STATUS: CLOSED
Racetrack Coil FDR Chrzanowski/Reiersen/Dudek | 2003-06-12 | 8 | Consider thermocouple buried in the base of the tee. This would measure any heat going into the casting. |  |  | Williamson, Dave | Racetrack coil has been built and tests. STATUS: CLOSED
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 1 | Consider changing clamp design to permit subassembly of clamp to permit subassembly of clamp threaded fasteners (see Attachment 3). This should reduce overall coil assembly time. [Dudek] | Concur | Alternate clamp designs that facilitate handling fewer parts will be pursued. Fabrication drawings for the TRC coils will be provided by late February and may not have these features. | Williamson, Dave | Will be developed prior to FDR for clamp design | 2005-02-28
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 2 | Modify clamp seat assembly design so most parts can be assembled to clamp before mounting on coil. [Zarnstorff] | Same as Chit #1 | Will be tracked unde Chit#1. No separate action required. | Williamson, Dave | CLOSED
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 3 | Extend figures so they extend all the way around the tube. [Nelson] | Concur | Modify design accordingly. | Williamson, Dave | High priority | 2005-02-04
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 4 | Build TRC clamps in accordance with production coil clamp design. Need to provide fabrication drawings. [Reiersen] | Concur | Fabrication drawings for the production coil clamps will be provided for fabricating the TRC clamps. | Williamson, Dave | High priority | 2005-02-28
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 5 | Change chill plate thickness from .060" to 040" all around. Repeat reference thermal calculation with revised cladding insulation overlap, and crimp joint resistance. [Reiersen] | Concur | Fabrication drawings will show .040" chill plate thickness. Reference thermal analyses will be updated appropriately and documented in an analysis report for the comprehensive type C FDR | Williamson, Dave | Chill plates drawings are needed ASAP. Thermal analyses will be updated for the comprehensive Type C FDR. | 2005-02-04
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 6 | Consider using other materials than stainless for the clamp bars to reduce fabrication costs, e.g. aluminum bronze. Ask the vendor for input on potential cost savings via choice of materials. [M. Zarnstorff] | Concur | The clamps for the TRC will be fabricated using stainless steel. Alternative materials will be investigated with potential vendors prior to the comprehensive type C FDR to see if significantly lower cost alternatives exist. | Williamson, Dave |  | 2005-02-28
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 7 | 2" offset in lead block may not work for production coils, especially Coil Type A . The concern is interference with the TF coils during field period assembly. [B. Nelson] | Concur | Interference checks during FPA and in the installed position will be provided for the comprehensive type C FDR | Williamson, Dave |  | 2005-02-28
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 8 | Need to document the detailed structural analysis of the clamps. Bending and shear and tensile loads on the bolt are a concern. Assembly procedure must ensure that Belleville washers do not bottom out. Maximum unbalanced loads need to be estimated. [Reiersen] | Concur | Structural analysis of the clamps will be provided for the comprehensive type C FDR. | Williamson, Dave |  | 2005-02-28
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 9 | Chrzanowski needs to specify the overlap min/max overlap for the reference design and show how the TRC is being built (2 sketches). [Reiersen] | Concur | Chrzanowski to provide a sketch showing the "as built" overlap on the TRC and the min/max overlap for the production coils. | Chrzanowski, Jim |  | 2005-02-11
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 10 | Impact of lead extension on field errors need to be look at for the production coils. [Reiersen] | Concur | Impact of extending leads an additional 2" on field errors will be assessed and addressed at the comprehensive Type C FDR. | Brooks, Art |  | 2005-02-28
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 11 | Need a different material for the lug. The copper softens after brazing and it is difficult to thread and torque a bolt. [Reiersen] | Concur | Alternate materials (e.g. Glidcop or Cu Cr Zr alloys) will be investigated for the production coils prior to the comprehensive Type C FDR. | Williamson, Dave |  | 2005-02-28
TRC - Chill Plate and Clamp Modification [Willliamson/Nelson/Neilson] | 2005-01-27 | 12 | Need to document thermal hydraulic calculations for the comprehnsive Type C FDR. [Reiersen] | Concur | Thermal hydraulic calculations will be documented in analysis reports for the comprehensive type C FDR. | Williamson, Dave |  | 2005-02-28
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 1 | Are we sure that the leads at the midplane miss the NBI transition ducts and allow space for routing the coaxial bus? [Nelson] | (Need to finalize TF Coil lead configuration and bus connection and re-check clearances at each coil.) | Yes. The clearaces have been checked in the pro engineer model
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 2 | Could the top and bottom supports be made the same way, so the "fixed" support could be made either at the top or bottom to preserve stellarator symmetry. This would also allow easier adjustment of the vertical location during assembly, since replacing shims looks more difficult than turning adjustment screws. [Nelson] | Concur (Should be considered.)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 3 | Put scribe marks/targets on the coil that are visible during assembly to aid in adjustment of the coil position. These could be on the inboard side at the midplane, the outboard side at the midplane, and at the top and bottom either outboard or inboard of the support. The inboard marks should be visible from the bore of the machine when the solenoid is not yet in position. [Nelson] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 4 | Investigate whether the lead block geometry could be slightly modified to close up the field error loop and reduce the lateral footprint of the lead/coax connection. [Nelson] | Concur | Lead block geometry has been modified so that the kickless cable fits in a gap between the two terminals reducing the lateral footprint and field errors
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 5 | Look at the assembly with the TF Coils retracted to make sure there is still clearance everywhere. [Nelson] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 6 | Thermal cycling may cause undesirable slipping at the wedged surfaces, which are presently located only by a friction joint. Consider adding simple G11 rings at the top and bottom that would be physically bolted to the coil wedge castings. This would ensure proper alignment at assembly and would tend to return the assembly to the desired position during thermal cycling. The pin joints may do the same thing, but the rings seem simpler. [Nelson] | Concur (Consider as alternatives to pins.)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 7 | Keep braze joints in the conductor out of the higher stress areas. [Nelson] | Concur | The Coil Specification will provide detailed guidance as to the allowable locations for the braze joints
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 8 | Document the "honeycomb" issue, where cool-down of the copper turns tries to shear the turn to turn insulation within the thick ground wall tube. This is an artifact of the apparent difference between the small glass epoxy shrinkage and larger copper shrinkage. It is not known whether this is a real problem or not. [Nelson] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 9 | Put the magnetic sensor loops on at PPPL, not at Vendor. [Nelson] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 10 | Check interference between TF Coils and MC leads. [Cole] | Concur | Mike Cole to check. | Cole
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 11 | Verify RT Clearance between TF structure and modular coil leads, terminal, coax. Revise leads design to accommodate (Williamson) | Concur [Same as chit #10]
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 12 | Verify RT clearance between TF structure and modular coil winding forms. Implement change to type-B MCWF. [Williamson] | Concur | Williamson to modify MC winding forms appropriately. Interference checks to be re-run with stocked models.
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 13 | On slide 45, does our project design criteria use the just principal stress or the Tresca (2x max shear) stress intensity? The just principal stress is only for pure tension. The same comment applies to slides 46 and 57. *Note: that using Tresca stress intensity, the alternating stress is almost double (110 Mpa v 66 Mpa). [Dahlgren] | Concur. Analysis results should address design criteria.
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 14 | On slide 44, the bonded assumption at the lower coil interface may affect the global stiffness of the model and the results at the upper interface. [Dahlgren] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 15 | On slide 42, Coeficient of Friction needs to be measured and the assumption verified on actual casting surface. [Dahlgren] | Concur. Needs to be checked at temperature and with appropriate surface finish.
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 16 | On slide, 41, wedge castings in the model does not appear to have a fully tapered wedging surface. [Dahlgren] | Disagree (At the very end of the casting where the view is taken, there is not a fully tapered wedging surface)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 17 | Failure modes are to be identified and addressed. [Ramakrishnan] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 18 | Material properties need to be checked as part of analysis checking. [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 19 | What happen with selecting u 2 coeficient of friction when operating at cryo temperature. [Brown] | Concur (See chit #15)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 20 | Re-check TF/MC interface with respect to MC stocked model. [Brown] | Concur (See chit #12)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 21 | Provide calculations values of resistance and inductance of the coil and establish the voltage to be impressed on the TF coil connection. [Ramakrishnan] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 22 | Instrumentation and control issues need to be addressed at FDR. It is a requirement that the TF System is responsible for generating. [Reiersen]
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 23 | Extrapolations of dielectric strength of sandwiched materials based on individual volts/mil in thin layers is unrealistic. Suggest the R&D should be performed to determine intrinsic dielectric strength based on adequate sample group. Perhaps at cryo temperature unless research shows that RT tests results are applicable of 80K or can be scaled. [Neumeyer] | Concur (Voltage withstand capacity at cryo temperature should be established for actual insulation scheme.)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 24 | Thick 3/8" ground wall seems excessive. Not necessary for voltage stand-off or mechanical robustness. May be difficult to avoid delamination/stress cracks due to temperature gradiant and/or differential thermal expansion during cure and/or operations. [Neumeyer] | Concur (Justify 3/8" groundwall thickness.)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 25 | Basis for current and voltage ratings not presented. Not clear whether scenarios/coils/power supply are coordinated. Inductance and resistance calculations not presented. Conductor heating calculation not presented. Is there a chance for higher than normal voltage on TF due to induction from modular, e.g. , If TF is open circuited during test shot on modular-only? [Neumeyer] | Concur (Needs formal documentation and checking.)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 26 | Keep flux loop outside ground wrap. [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 27 | Consider purchasing an extra coil. If one of 18 proved to be a "weak sister" or out of spec, the schedule impact could be significant. [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 28 | Has procurement schedule been reviewed with PPPL Procurement division and is there agreement on lead times and process? [Neilson] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 19 | Need to confirm assumed Sm values for cast 304SS [Heitzenroeder] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 30 | Consider upper and lower epoxy/glass built-up "Blocks" or Stirrups" applied over the ground wrap on each coil side, both above and below each wedge half. Low $$$ insurance if coil bond to wedge fails. [Gettelfinger] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 31 | Stagger the conductor braze - joints so they are up-down symmetric -or- make them the same on each coil and be careful to mount the coils in a stellarator -symmetric pattern. [Zarnstorff] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 32 | In order to satisfy lot a flexibility requirement, need to analyze ability of TF to achieve +/- .5 Tesla in context of other coils being excited.. To credible levels (e.g. the list high B scenario) specifically will these coils be able to satisfy GRD 3.2.1.5.3.4.2.? [Zarnstorff] | Concur (Resolve issue of "requirement" versus "assess capability")
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 33 | Shim coil mounting so TF Midplane is aligned with machine midplane @80K. This is the best way to ensure stellarator symmetry in the face of the finite deformation, etc. (esp. at higher TF with combined fields) [Zarnstorff] | Concur (Consider along with stellarator symmetric supports (previous chit). Marking the coils may be critical.)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 34 | Make the vertical support structures symmetric (top and bottom). [Zarnstorff] | Concur ( Same as previous chit)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 35 | Provide drawings of nose casting and coil to Tech Shop to determine 1) ability to machine 2) estimate of tolerance limit 3) estimate of cast. [Dudek] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 36 | Evaluation criteria for prospective vendors need to include past performance and the implementation of their QA program (not the QA manual). [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 37 | Deformation (DMX = approx. 0.013) is more than 10 times of shell structure. It is possible that most of the TF loads may go to shell structure through bolt joints. The load path shall be evaluated. [H.M. Fan] | Other ( Consider as part of structures design)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 38 | Need to determine if thermal stresses from Cu shrinking in honeycomb is a problem. (May answer 2D axisymmetric model.) [Brooks] | Concur (See previous chit)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 39 | Need to assess impact of upper vertical spring support on TF stresses T deflections. [Brooks] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 40 | Need same analysis of lead/transition regime stress. [Brooks] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 41 | Optimize design of lead tabs with consideration of the coax lead stem to which they will attach. Consider the following: 1) minimize space 2) minimize stray field 3) minimize Jx8 forces 3) optimize current flow pattern to minimize current bunching and hot spots 4) provide support structure and fasteners such that required conductivity will be maintained throughout pulse. Provide at least 2" creepage path from exposed conductors to grounds. [Neumeyer] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 42 | Stresses in leads and transition region need to be addressed. [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 43 | Product spec needs to identify stay out zones and "no overlap" requirements for braze joints. [Reiersen] | Concur (see chit #7 | The Coil Specification will provide detailed guidance as to the allowable locations for the braze joints
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 44 | The analysis is inconsistent with the design. The design says the wedges and winding are bonded. The analysis assumed they slip. Ditto for the thickness of the ground wrap [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 45 | The design shows that the TF Coil current is to be limited based on other coil currents. This dictates the use of a coil protection calculator, if the machine is to be properly protected. [Ramakrishnan] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 46 | Design criteria should be established for friction joints. [Reiersen] | Concur | Design criteria all provided in the NCSX structural and cryogenic design criteria and will be applied in the analyses.
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 47 | Analyses do not show interaction with structures. The interface loads need to be addressed in the design of the TF coils and structures. [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 48 | Need to define mechanism for cooling the coils down from RT. [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 49 | Need to define minimum clearance requirements (after taking into account tolerances on all components) and adjust TF and MC designs to achieve this. [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 50 | The upper bracket, barrel strap and other components were stated not be part of the TF coil. Are they all included in the scope and estimate of some other work package? [Neilson] | Concur | These components to be added to the scope and cost for work package WBS15
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 51 | The TF Coil and structures form a assembly with many DOF for adjustment. Need to define the sequence in how pieces are put together and how adjustments made. [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 52 | Consider substituting G11 for G10. Previous experience with G10 indicates that the bromine in this material becomes activated by D-D neutrons and creates radioactive "hot spots". [Levine] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 53 | Orientation of the leads from the TF bundle needs to be analyzed and documented. [Ramakrishnan] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 54 | Document the criteria used for selecting the number of turns and coils current [Ramakrishnan] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 55 | A. What are the limits of the following? What should be the protection 1) over current 2) I^2T B. Are there any stress limits that have to be detected or corrected? C. What is the factor of safety in the design for the above? [Ramakrishnan] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 56 | Minimize use of shims stock in pulsed operation shims move. [Viola] | Concur (Consider non-shim options)
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 57 | Need to develop the TF-to -Lead (kickless cable) connection concept. (Bolted electrical joint, field errors, and space issues). [Reiersen] | Concur
TF Coil System PDR Kalish/Nelson/Reiersen | 2005-02-07 | 58 | Consider thickening the ground-wrap thickness in the nose region to increase stress margin between wedge castings. Decrease conductor size slightly if necessary. [Zarnstorff] | Concur | Thicker Ground Wrap in the nose section does not reduce stress. Stresses already low inside the wedge casting case. Further Coil profile has been optimized to maximize copper cross section in the nose region. Thinning the copper cross section to add groundwrap would actually increase copper stresses above and below the wedge casting in peak stress areas.
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 1 | Consider providing table of coordinates for 3 seats at flange ends at each trajectory step. [Nelson] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 2 | Include a requirement in spec that assembly cannot tip over during operation, including seismic accelerator of .11g -Also apply to gantry. [Nelson] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 3 | Assemble tolerance information into one place to verify uses and approach of modular coil to vacuum vessel and confirm tolerance req. for fixture. [Nelson] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 4 | Need to articulate a concept for a control system. [Reiersen] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 5 | Look at left and right sides for required fixture motion. [Nelson] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 6 | Ask vendor to perform and test (prior to delivery) to prove that the system can go to a pre-determined location and back and forth with the required accuracy and precision. [Raftopoulos] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 7 | Consider making the spherical seats adjustable in place so that you don’t have to take coils apart to make adjustments. [Raftopoulos] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 8 | Need to specify that minimum motion per 'bump' (or infinitely variable speed on motors) [Dudek] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 9 | Verify range of motion specified for each D.O.F includes assembly of both half period (i.e. from left to right) for example, fixture must move up to assembly one half, but down to assemble other. [Brooks] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 10 | Need to specify fails safe brakes on all motions. (i.e., loss of power will lock mechanism) [Dudek] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 11 | Clearance analysis needs to include tolerances and components installed on vacuum vessel surface (insulation, mag. Diagnostics etc.) [Neilson] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 12 | Investigate schedule impact of fitting A-A and C-C coils before assembly of half periods and field periods. [Reiersen] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 13 | Consider adding vacuum vessel stand as part of the MCAF procurement. [Reiersen] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 14 | With 6 DOF, show by error analysis that the 0.20" control is achievable. The vendor needs to demonstrate this as part of the acceptance test. [Reiersen] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 15 | Show lifting points for 0/H crane. All there features on the MCWF to accommodate this lift? [Reiersen] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 16 | Perform seismic analysis to see if the present design is ok. Investigate sudden accelerations and decelerations as well. [Reiersen] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 17 | Generate a 3-pt table so the vendors can design their own mechanisms. [Reiersen] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 18 | Consider building vacuum vessel stand with the same contrast as the manipulator. [Dudek] | Concur
Modular Coil Assembly Fixture Brown/Nelson/Dudek | 2005-02-16 | 19 | Ensure that you have a safe margin for movement of fixture in all direction/rotations. etc. Don't limit fixture to minimum motions. [Chrzanowski] | Concur