## Assembly Steps
| Field Period Assembly Steps | Expected Days | nb men | man hrs | 1 FTE Crane | Measurement | Contingency | Comments
Stage 1 (VV Prep - max loops) - FPA that includes 135 diagnostic sensors |  | 152.5833 |  | 1022.6667 |  |  |  | See note 1
1 | Receive VV and Inspect | 4
2 | Mount VV on VV Prep fixture (+60° position), see comment | 1 | 3 | 24 | X
3 | Establish metrology setting and monuments with respect to assembly | 4 | 3 | 96 | X | 2
4 | Mark surface for 135 loop placement and verification check | 23.5 | 1 |  |  | 1 |  | 4 marks for each of 135 loops (540 marks): Note 2
5 | Mark surface for coolant line stud placement (on half period) | 4 | [5 empty] | 600 studs per period at ~ 8" spacing. Metrology will be used to locate marks based on CAD defined locations. Fine accuracy is NOT important.
6 | Attach studs (hardware) on for mounting coolant lines. | 5 | 3 | 120 | X |  |  | 300 studs at ~ 8" spacing. [300 studs / 10 studs per hr / 6 hrs per day] Per Mike Viola, assume 10 studs per hr
7 | Install diagnostic loops | 22.5 | 3 | 540 | X | 2 |  | [135 diagnostic loops / 1 per hr / 6 hrs per day]
8 | Run diagnostic loop leads | 5.625 | [5 empty] | Assumes 4 loops / hr, per Geroge Labic
9 | Loop termination and verification check | 45 | [5 empty] | Assumes 1 hr/wire and 2 wires per loop, per Geroge Labic
10 | Install cooling lines to vacuum vessel | 10.6667 | 2 | 170.6667 |  |  |  | Assumes 3 tubes per day, per Gorenson. There are 64 tubes per period.
11 | Rotate VV to - 60° position and establish metrology settings | 2
12 | Mark surface for 7 loop placement and verification check | 2.1667
13 | Mark surface for coolant line stud placement (on half period) | 4
14 | Attach studs (hardware) on for mounting coolant lines. | 1.6667
15 | Install diagnostic loops | 1.1667
16 | Run diagnostic loop leads | 0.29167
17 | Loop termination and verification check | 2.3333
18 | Install cooling lines to vacuum vessel | 10.6667
11 | Prepare and transfer completed VV to holding area | 3 | 3 | 72 | X
Stage 1 (VV Prep - min loops) - FPA that includes 13 diagnostic sensors |  | 63.25 |  | 426.6667 |  |  |  | See note 1
1 | Receive VV and Inspect | 4
2 | Mount VV on VV Prep fixture (+60° position) | 1 | 3 | 24 | X
3 | Establish metrology setting and monuments with respect to assembly | 4 | 3 | 96 | X | 2
4 | Mark surface for 6 loop placement and verification check | 2 | 1 |  |  | 1 |  | 4 marks for each of 6 loops (540 marks): Note 2
5 | Mark surface for coolant line stud placement (on half period) | 4 | [5 empty] | 300 studs at ~ 8" spacing.
6 | Attach studs (hardware) on for mounting coolant lines. | 1.6667 | 3 | 40 | X |  |  | 300 studs at ~ 8" spacing. [300 studs / 30 studs per hr / 6 hrs per day] See note 3.
7 | Install diagnostic loops | 1 | 3 | 24 | X | 2 |  | [6 diagnostic loops / 1 per hr / 6 hrs per day]
8 | Run diagnostic loop leads | 5.625 | [5 empty] | Assumes 4 loops / hr
9 | Loop termination and verification check | 2 | [5 empty] | Assumes 1 hr/wire and 2 wires per loop
10 | Install cooling lines to vacuum vessel | 10.6667 | 2 | 170.6667 |  |  |  | Assumes 3 tubes per day. There are 64 tubes per period.
11 | Rotate VV to - 60° position and establish metrology settings | 2
12 | Mark surface for 7 loop placement and verification check | 2.1667
13 | Mark surface for coolant line stud placement (on half period) | 4
14 | Attach studs (hardware) on for mounting coolant lines. | 1.6667
15 | Install diagnostic loops | 1.1667
16 | Run diagnostic loop leads | 0.29167
17 | Loop termination and verification check | 2.3333
18 | Install cooling lines to vacuum vessel | 10.6667
11 | Prepare and transfer completed VV to holding area | 3 | 3 | 72 | X
Stage 1B (Installation of magnetic loops on each Spool Piece) |  | 11.3333 |  | 136
1 | Receive Spool and Inspect | 2
2 | Mount Spool on mounting table | 1 | 3 | 24 | X
3 | Establish metrology setting and monuments with respect to assembly | 2 | 3 | 48 | X | 2
4 | Mark surface for 15 loop placement and verification check | 3.6667 |  |  |  | 1 |  | 4 marks for each of 16 loops (60 marks)
5 | Install diagnostic loops | 2.6667 | 3 | 64 | X | 2 |  | [16 diagnostic loops / 1 per hr / 6 hrs per day]
6 | Run diagnostic loop leads | 0.66667 | [5 empty] | Assumes 4 loops / hr, per Geroge Labic
7 | Loop termination and verification check | 5.3333 | [5 empty] | Assumes 1 hr/wire and 2 wires per loop, per Geroge Labic
8 | Prepare and transfer completed VV to holding area | 1 | 3 | 24 | X
Stage 2 (MC Half Period Assembly) - two operations required |  | 27 |  | 808 |  |  |  | See note 4. Assume first MCHP assembly will take 30% longer.
1 | Mount Type A in fixture and set spherical seats | 2 | 3 | 48 | X | 2
2 | Mount the Type B in fixture, locating it on the Type A spherical seats; check A-to-B alignment. | 2 | 3 | 48 | X | 2 |  | Note: A Rogowski coil will be mounted at the side of Type-A on one MC half period.
3 | Add shims between A and B and ream 24 holes | 5 | 5 | 200 | X
4 | Bolt together Type A and B; check alignment | 2 | 3 | 48 |  | 2 |  | 1
4 | Set Type B spherical seats; adjust fixture to accept Type C | 2 | 3 | 48 | X | 2
5 | Mount the Type C in fixture, locating it on the Type B spherical seats; check alignment. | 2 | 3 | 48 | X | 2
6 | Add shims between B and C and ream 24 holes | 5 | 5 | 200 | X
7 | Bolt together Type B and C; check alignment | 2 | 3 | 48 | X | 2
8 | Set Type C spherical seats; make final alignment check | 2 | 3 | 48 | X | 2
9 | Mount all turning fixture interfacing hardware | 2 | 3 | 48 | X
10 | Prepare and transfer completed MC half period assembly to holding area | 1 | 3 | 24 | X
Stage 3 (MC installation) |  | 33 |  | 816
1 | Mount VV to base support fixture; perform metrology check | 2 | 3 | 48 | X | 2 | 2 | Extra days needed if VV needs adjusting
2 | Attach local protective strips to VV surface and add locating sensors to VV or MC | 2
3 | Support MC from crane; set orientation and perform metrology checks | 2 | 3 | 48 | X | 2 | 3 | Extra days needed the first time through
4 | Rotate right MC to stand-off position and check position | 3 | 3 | 72 | X | 2
5 | Transfer MC to external support system and recheck position | 2 | 3 | 48 | X | 2
6 | Support second MC from crane; set orientation and perform metrology checks | 2 | 3 | 48 | X | 2
7 | Rotate left MC to stand-off position and check position | 3 | 3 | 72 | X | 2
8 | Move left and right MC to final position and take gap measurements to validate shim dimensions | 2 | 3 | 48 | X | 2
9 | Install shims (back off left and right MC’s as reqd); ream 24 holes | 7 | 5 | 280 | X |  |  | There may well be less than 24 ream holes because of space limitaionsl
10 | Bolt together at flange interface. | 2 | 3 | 48
11 | Perform final metrology position check of completed full period assembly as well as check spherical seat position of the Type-C MC that interfaces with the next FP Assembly. | 2 | 2 | 32 | X | 2
12 | Attach VV to MC using final hardware links; secure VV at each end to MC's using temporary supports. | 2 | 3 | 48 | X
13 | Remove temporary interference strips and locating sensors | 1
14 | Prepare and transfer completed assembly to Stage 4 area | 1 | 3 | 24 | X
Stage 4 (Final FP Assembly) |  | 81 |  | 3232
1 | Mount MC/VV assembly to support frame at final assembly station; perform metrology checks | 3 | 3 | 72 | X | 2
2 | Position and weld all ports to VV except for the two large horizontal diagnostic ports | 20 | 6 | 960 | X | 2 |  | 22 ports at this time. Need an alignment method to support two teams
3 | Inspect Welds | 5 | 2 | 80
4 | Assemble left TF Coil Assembly and check position | 3 | 4 | 96 | X | 2
5 | Change platforms | 2 | 3 | 48 | X
6 | Assemble right TF Coil Assembly (requires support readjustment) and perform measurement checks | 3 | 4 | 96 | X | 2 |  | Currently assumes readjustment of stage 4 supports to accommodate rotating right side TF
7 | Attach TF coils to MC's | 5 | 3 | 120 | X
8 | Change platforms | 2 | 4 | 64 | X
9 | Position and weld two large horizontal diagnostic ports to VV | 8 | 3 | 192 | X | 2
10 | Inspect Welds | 1 | 2 | 16
12 | Assemble external trim coils, I&C, leads and coolant lines | 10 | 6 | 480 | X | 2 |  | It is assumed that this effort is carried out during steps 7 thru 10, a parallel effort. The 10 days is not counted in the total elapsed time.
11 | Close up VV (added blank-off flanges and weld on end plates), bakeout VV to 350 deg C and leak check | 20 | 4 | 640 |  |  |  | It is assumed that this occurs continuously (for a 7 day work week). This saves 5 days in the schedule.
13 | Perform final metrology measurements of interfacing surfaces and adjust final support base interfaces | 10 | 3 | 240 | X | 2
14 | Prepare Field Period for shipment | 2 | 3 | 48 | X
15 | Transfer completed assembly to C-site test cell | 2 | 5 | 80 | X
Stage 5 (TF Half Period Assembly)
1 | Assemble half period TF coil base structure | 3 | 3 | 72 | X |  |  | Crane assist needed. 66 structural bolted interfaces, insulation interface between each three outer TF castings.
2 | Install lower TF support hardware, backed-off to accecpt TF winding | 2 | 2 | 32
3
4
Notes:
1 | Man-hour estimates assumes working a 6 hr day.
2 | This assumes a one turn loop design with placement of 4 marks per hour. An additional day has been added for repositioning the Romer arm as the VV is rotated.
3 | All modular coils are delivered to begin Stage 2 assembly with blatters installed at wings, temperature sensors installed and bushings (with pilot holes) at bolted interface holes.