## Sequence
Step | Stage 2 Half Period Assembly |  | $ M&S | # men | days | man-days | Comments
1 | Inventory pre-fabricated shims (insulated on top & bottom) | insul top and bottom or in middle? | 5000 |  |  | 0
|  | Each shim 4-5 bolts long |  |  |  | 0 | One shim per bot?
|  | G-11 / steel / G-11 layup |  |  |  | 0
|  | Steel thickness can be pre-determined for a particular coil (based on meas. Data) |  |  |  | 0
2 | Mount MCWF A on assembly stand. |  |  | 4 | 1 | 4
3 | Install corner aligment plates. |  |  | 2 | 1 | 2
4 | Check fiducials on A - re-set to re-establish default coordinate system due to added weight deflecting things. |  |  | 2 | 1 | 2
5 | Install a few of PJ bushings using his technique. | cost in LD's budget |  | 2 | 1 | 2 | Is this the same?
6 | Lower B onto A to pre bolt tightened position using corner guide system. | [5 empty] | This was missing
7 | Check fiducials on A & B - hopefully positions will be right on; if not, determine correction required, adjust 3 points, and re-shim. |  |  | 1 | 1 | 1
8 | Back office to review data & approve or set corrective action. |  |  | 1 | 1 | 1
2 | Check each shim location - verify that shim thicknesses are correct. If off by more than 0.005? Grind shim as req'd. or use peelable shims |  |  | 2 | 5 | 10
2a |  | Most likely grind the steel shim portion which will be ~3/8" thick |  |  |  | 0
3 | Separate A and B |  |  |  |  | 0
5b |  | shims set Z location |  |  |  | 0
|  | hydroset with few bushings set X-Y |  |  |  | 0
6 | Check for correct position of A and B |  |  | 2 | 1 | 2
| Install wing bladders |  | 1000 | 2 | 1 | 2
| Install the PJ bushings using his technique. | cost in LD's budget |  | 2 | 3 | 6
| Install studs / bolts; tighten in sequence. |  |  | 2 | 0.5 | 1
| Check MCWF positions again. |  |  | 2 | 1 | 2
| Allow 48 hrs. for Stycast to cure. | Is this now for the bladders? |  | 0 | 0 | 0
| Repeat the process for B-C |  | 6000 | 24 | 17.5 | 35
All tapped holes in B-C connection.
|  |  | Total Labor = |  |  | 428400
[5 empty] | M&S | 108000
[5 empty] | Grand total | 536400