## Assembly Steps
| Field Period Assembly Steps | Expected Days | nb men | man hrs | 1 FTE Crane | Measurement | Contingency | Comments
Stage 1 (VV Prep) - for one FPA that includes diagnostic sensors |  | 79.5 |  | 2356
1 | Receive VV and inspect | 4 | 3 | 96 | X | 2 |  | see note 2
2 | Mount VV on VV Prep fixture (top side up) | 0.5 | 3 | 12 | X
3 | Establish metrology setting and monuments with respect to assembly; align VV base to reference coordinate system | 3 | 3 | 72 | X | 2
4 | Install local platforms | 0 |  |  | X |  |  | These are local "steps" used as needed to reach top areas
5 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
6 | Attach studs (hardware) on top side for mounting diagnostics, coolant lines and insulation. [1200 studs / 25 studs per hr / 6 hrs per day] See note 1. | 8 | 3 | 192 | X |  |  | Install 50 diagnostic coils (x 4 studs) first period + 350 tube studs + 6" grid of studs (650) for insulation. 1200 total studs on top.
7 | Wind magnetic diagnostic sensors to top surface and take metrology measurements [50 diagnostic loops / 1 per hr / 6 hrs per day] | 8 | 3 | 192 | X | 2
8 | Install cooling/heating lines to vacuum vessel top surface | 8 | 4 | 256 |  |  |  | 32 tube preformed on top
9 | Install insulation to vacuum vessel to top surface | 10 | 5 | 400
10 | Flip VV to expose lower surface | 1 | 3 | 24 | X
11 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
12 | Attach studs (hardware) on top side for mounting diagnostics, coolant lines and insulation | 8 | 3 | 192 | X |  |  | Install 50 diagnostic coils (x 4 studs) first period + 350 tube studs + 6" grid of studs (650) for insulation. 1200 total studs on bottom.
13 | Wind magnetic diagnostic sensors to top surface and take metrology measurements [50 diagnostic loops / 1 per hr / 6 hrs per day = 8.3 days] | 8 | 3 | 192 | X | 2
14 | Install cooling/heating lines to vacuum vessel bottom surface | 8 | 4 | 256
15 | Install insulation to vacuum vessel to bottom surface | 10 | 5 | 400
16 | Prepare and transfer completed VV to holding area | 3 | 3 | 72 | X
Stage 1 (VV Prep) - for FPA that has no diagnostic sensors |  | 61.5 |  | 1796
1 | Receive VV inspect | 4 | 3 | 96 | X | 2
2 | Mount VV on VV Prep fixture (top side up) | 0.5 | 3 | 12 | X
3 | Establish metrology setting and monuments with respect to assembly; align VV base to reference coordinate system | 3 | 3 | 72 | X | 2
4 | Install local platforms | 0 |  |  | X |  |  | These are local "steps" used as needed to reach top areas
5 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
6 | Attach studs (hardware) on top side for coolant lines and insulation. [1000 studs / 25 studs per hr / 6 hrs per day = 6.7days] See note 1. | 7 | 3 | 168 | X |  |  | 350 tube studs + 6" grid of studs (650) for insulation. 1000 total studs on top.
7 | Install cooling/heating lines to vacuum vessel top surface | 8 | 3 | 192
8 | Install insulation to vacuum vessel to top surface | 10 | 5 | 400
9 | Flip VV to expose lower surface | 1 | 3 | 24 | X
10 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
11 | Attach studs (hardware) on top side for coolant lines and insulation. [1000 studs / 25 studs per hr / 6 hrs per day = 6.7days] See note 1. | 7 | 3 | 168 | X |  |  | 350 tube studs + 6" grid of studs (650) for insulation. 1000 total studs on bottom.
12 | Install cooling/heating lines to vacuum vessel bottom surface | 8 | 3 | 192
13 | Install insulation to vacuum vessel to bottom surface | 10 | 5 | 400
14 | Prepare and transfer completed VV to holding area | 3 | 3 | 72 | X
Stage 2 (MC Half Period Assembly) - two operations required |  | 27 |  | 808 |  |  |  | Requires two operations for a complete Field Period
1 | Mount Type A in fixture and set spherical seats | 2 | 3 | 48 | X | 2
2 | Mount the Type B in fixture, locating it on the Type A spherical seats; check A-to-B alignment. | 2 | 3 | 48 | X | 2
3 | Add shims between A and B and ream 24 holes | 5 | 5 | 200 | X
4 | Bolt together Type A and B; check alignment | 2 | 3 | 48 |  | 2
4 | Set Type B spherical seats; adjust fixture to accept Type C | 2 | 3 | 48 | X | 2
5 | Mount the Type C in fixture, locating it on the Type B spherical seats; check alignment. | 2 | 3 | 48 | X | 2
6 | Add shims between B and C and ream 24 holes | 5 | 5 | 200 | X
7 | Bolt together Type B and C; check alignment | 2 | 3 | 48 | X | 2
8 | Set Type C spherical seats; make final alignment check | 2 | 3 | 48 | X | 2
9 | Mount all turning fixture interfacing hardware | 2 | 3 | 48 | X
10 | Prepare and transfer completed MC half period assembly to holding area | 1 | 3 | 24 | X
Stage 3 (MC installation) |  | 30 |  | 816
1 | Mount VV to MC turning fixture base and gantry frame; perform metrology check | 2 | 3 | 48 | X | 2 | 2 | Extra days needed if VV needs adjusting
2 | Mount MC on turning fixture; set orientation and perform metrology checks | 2 | 3 | 48 | X | 2 | 3 | Extra days needed the first time through
3 | Rotate right MC to stand-off position and check position | 3 | 3 | 72 | X | 2
4 | Transfer load to gantry crane and recheck position | 2 | 3 | 48 | X | 2
5 | Move MC turning fixture to left side and mount MC on turning fixture; set orientation and perform metrology checks | 2 | 3 | 48 | X | 2
6 | Rotate left MC to stand-off position and check position | 3 | 3 | 72 | X | 2
7 | Move left and right MC to final position and take gap measurements to validate shim dimensions | 2 | 3 | 48 | X | 2
8 | Install shims (back off left and right MC’s as reqd); ream 24 holes | 7 | 5 | 280 | X
9 | Bolt together at flange interface. | 2 | 3 | 48
10 | Perform final metrology position check of completed full period assembly as well as check spherical seat position of the Type-C MC that interfaces with the next FP Assembly. | 2 | 2 | 32 | X | 2
11 | Attach VV to MC using final hardware links; secure VV at each end to MC's using temporary supports. | 2 | 3 | 48 | X
12 | Prepare and transfer completed assembly to Stage 4 area | 1 | 3 | 24 | X
Stage 4 (Final FP Assembly) |  | 70 |  | 2968
1 | Mount MC/VV assembly to support frame at final assembly station; perform metrology checks | 2 | 3 | 48 | X | 2
2 | Position and weld all ports to VV except for the two large horizontal diagnostic ports | 20 | 6 | 960 | X | 2 |  | 22 ports at this time. Need an alignment method to support two teams
3 | Inspect Welds | 5 | 2 | 80
4 | Assemble left TF Coil Assembly and check position | 3 | 4 | 96 | X | 2
5 | Change platforms | 2 | 3 | 48 | X
6 | Assemble right TF Coil Assembly (requires support readjustment) and perform measurement checks | 3 | 4 | 96 | X | 2 |  | Currently assumes readjustment of stage 4 supports to accommodate rotating right side TF
7 | Attach TF coils to MC's | 3 | 3 | 72 | X
8 | Change platforms | 2 | 4 | 64 | X
9 | Position and weld two large horizontal diagnostic ports to VV | 8 | 3 | 192 | X | 2
10 | Inspect Welds | 1 | 2 | 16
12 | Assemble external trim coils, I&C, leads and coolant lines | 10 | 6 | 480 | X | 2 |  | It is assumed that this effort is carried out during steps 7 thru 10, a parallel effort. The 10 days is not counted in the total elapsed time. Note: number men increased over Rev 5 (was 3).
11 | Close up VV (added blank-off flanges and weld on end plates), bakeout VV to 350 deg C and leak check | 20 | 4 | 640 |  |  |  | It is assumed that this occurs continuously (for a 7 day work week). This saves 5 days in the schedule.
13 | Using metrology measurements adjust final support base interfaces | 2 | 3 | 48 | X | 2
14 | Prepare Field Period for shipment | 2 | 3 | 48 | X
15 | Transfer completed assembly to C-site test cell | 2 | 5 | 80 | X
| Total VV Prep assembly days | 220.5 | [5 empty] | Assumes 2 diagnostic periods and 1 non-diagnostic period.
| Total MC Half Period assembly days | 162
| Total MC installation days | 90
| Total Final FP Assembly days | 210
Notes:
1 | Background data used for estimating.
If you have the stud locations identified in advance, they are in close proximity, and you are shooting the same studs, you can shoot 30-40 studs an hour.
If you are changing sizes or have to change locations, then 20-30 an hour is reasonable. (Steve Kemp input)
2 | The measurement manpower estimate implies that this activity is accomplished by an engineer and technician working together (both metrology trained).