## Schedule
| Updated 4/6/06 |  |  |  | FY 2006 | [34 empty] | FY 2007 | [8 empty] | FY 2008
|  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUG |  |  |  | SEPT |  |  | OCT |  |  |  |  | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A
ITEM | TASK | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30
Target - Finish Last Field Period Assembly
VV period Arrival dates
1 | VV PREP STATION (Build to Print)
1.01 | Concept definition and requirements | Complete
1.02 | VV Support Fixture plus dwgs | Complete
1.03 | Metrology layout | Complete
1.04 | Structural Analysis | Complete
1.05 | Fab Activities - VV Support Stand
2.06 | VV Assembly Operations | [8 empty] | 1st VV
2nd VV
3rd VV
[37 empty] | A1 | [6 empty] | B4 |  | B6 |  | A5 |  | C6
2 | HALF PERIOD ASMBLY (Build to Print)
[10 empty] | C1 |  | C2 | [5 empty] | C3 |  |  | C4 | [6 empty] | C5 | [8 empty] | N: A2; J: A3; FY 2007 F: B1; FY 2007 M: A4; FY 2007 A: B2; FY 2007 M: B3; FY 2007 J: B5; FY 2008 N: A6
| Stage 2 review & left side weldment details | [29 empty] | PDR | [5 empty] | N: FDR
Mag alignment & match plate component
2.01 | Concept definition and requirements
2.02 | Left side HP Support Stand Weldment | Complete
2.03 | Right side HP support stand | [35 empty] | J: A1 / B1 / C1
2.04 | Magnetic alignment instrument | [35 empty] | FY 2007 M: A2 / B2 / C2 MA; FY 2008 M: A6 / B6 / C6
2.05 | Machine hole match plate and support | [35 empty] | FY 2007 S: A5 / B5 / C5
2.06 | Structural Analysis
2.07 | Fab Activities - Left side HP support fixture | [35 empty] | FY 2007 S: A4 / B4 / C4 MA
| - Fab remaining components | [35 empty] | FY 2007 A: A3 / B3 / C3
3 | MC INSTALLATION (Build to Print) | [21 empty] | PDR | [5 empty] | FDR
3.01 | Concept definition and requirements | Complete
3.02 | MC Crane Load Support System | Model Complete
3.03 | Laser Screen Guides modifications | Model Complete
3.04 | VV support stand and Misc fixtures | Model Complete
3.05 | Mechanical screw drive system
3.06 | Metrology layout
3.07 | Structural Analysis
3.08 | Fab Activities
3.09 | Assembly Activities
- Trial Runs - no VV
- MC Installation (1 Station)
4 | TF HP ASSEMBLY (Build to Print)
[27 empty] | PDR |  |  |  |  | FDR
4.01 | Concept definition and requirements | Complete
4.02 | TF support and rotation Fixture
4.03 | Metrology layout
4.04 | Structural Analysis
4.05 | Fab Activities -
4.06 | TF HP Assembly Operations
5 | FINAL FP ASSEMBLY (Build to Print) | [29 empty] | PDR | [5 empty] | D: FDR
5.01 | Concept definition and requirements
5.02 | MC Support Stand
5.03 | FP Assembly platforms
5.04 | Metrology layout
5.05 | Structural Analysis
5.06 | Fabrication - follow-up activities
| - FP Assembly | [35 empty] | FY 2007 J: FPA-1; FY 2008 F: FPA-3
FPA-2
Models
All Dwgs
Models / Dwgs
Models / Dwgs
Models

## Timeline
ESTIMATE START AND END DATES
ITEM | TASK | START | END | COMMENTS
1 | VV PREP STATION (Build to Print)
1.01 | Concept definition and requirements |  |  | Complete
1.02 | VV Support Fixture plus dwgs |  |  | Complete
1.03 | Metrology layout |  |  | Complete
1.04 | Structural Analysis |  |  | Complete
1.05 | PDR / FDR |  |  | Complete
1.06 | Fab Activities - VV Support Stand (1 Reqd) |  |  | Sent to Procurement 10/10/05
2 | HALF PERIOD ASSEMBLY (Build to Print)
2.01 | Concept definition and requirements |  |  | Complete
2.02 | Left side HP Support Stand Weldment |  |  | Complete
2.03 | Right side HP support stand | 2006-04-24 | 2006-05-05 | 50% complete (models done)
2.04 | Magnetic alignment instrument | 2006-05-08 | 2006-05-27 | started early - 25% complete
2.05 | Machine hole match plate and support | 2006-04-24 | 2006-05-27
2.06 | Structural Analysis | 2006-04-10 | 2006-06-01 | 25% overall with 75% complete for item 2.02 analysis
2.07 | PDR / FDR | 2006-06-05 | 2006-06-26
2.08 | Fab Activities - Left side HP support fixture |  |  | In-house vs outside fab is TBD
- Fab remaining components
3 | MC INSTALLATION (Outside design & Fab)
3.01 | Concept definition and requirements |  |  | Complete
3.02 | MC Crane Load Support System | 2006-05-22 | 2006-06-02
3.03 | Laser Screen Guide Modifications | 2006-06-13 | 2006-06-26
3.04 | VV support stand and Misc fixtures | 2006-06-27 | 2006-06-11
3.05 | Mechanical screw drive system | 2006-06-12 | 2006-08-01
3.06 | Metrology layout | 2006-08-02 | 2006-08-08
3.07 | Structural Analysis | 2006-08-09 | 2006-09-19
3.08 | PDR / FDR | 2006-08-09 | 2006-09-06
3.09 | Fab Activities (1 Reqd) |  |  | See schedule
4 | TF HP ASSEMBLY (Build to Print)
4.01 | Concept definition and requirements |  |  | Complete
4.02 | TF Rotation Fixture plus dwgs | 2006-07-31 | 2006-08-25
4.03 | Metrology layout | 2006-08-28 | 2006-09-01
4.04 | Structural Analysis | 2006-08-28 | 2006-09-15
4.05 | PDR / FDR | 2006-09-05 | 10/206
4.06 | Fab Activities (1 Reqd)
5 | FINAL FP ASSEMBLY (Build to Print)
5.01 | Concept definition and requirements |  |  | Complete
5.02 | MC Support Stand | 2006-07-24 | 2006-08-25
5.03 | FP Assembly platform | 2006-08-25 | 2006-09-22
5.04 | Metrology layout / support stand dwgs | 2006-09-25 | 2006-10-20
5.05 | Structural Analysis | 2006-09-04 | 2006-10-20
5.06 | PDR / FDR | 2006-11-01 | 2006-12-06
5.07 | Fabrication (2 Reqd) |  |  | See schedule

## Cost Summary
| Field Period Hardware Cost Estimates | [5 empty] | PPPL Shop Rate ($/hr) = | 81
Unit
|  | Weight | $ per | Unit |  | Total |  | Equiv |  |  |  | Man-
| Description | (lbs) | Lb | Cost ($) | Qnty | Cost ($) | Comments | hrs |  |  | Hware | power
Stage 1 - VV Support Stand Cost
| Support Stand Weldment | 290 | 7 | 2030 | 2 | 4060 |  | 50.1235
| Support Axle Weldment | 47 | 15 | 705 | 2 | 1410 |  | 17.4074
| Axle locking clamp | 19 | 15 | 285 | 2 | 570 |  | 7.037
| Port 12 blank-off cover | 115 | 7 | 805 | 2 | 1610 |  | 19.8765
| Lateral support Weldment | 46 | 15 | 690 | 1 | 690 |  | 8.5185
| Worm Gear mounting bracket | 20 | 30 | 600 | 1 | 600 |  | 7.4074
| Machine hoist ring |  |  | 210.48 | 2 | 420.96 | McMaster-Carr
| Worm Gear |  |  | 294 | 1 | 294 | Boston Gear G1104
| Worm |  |  | 322 | 1 | 322 | Boston Gear H1104
| Hand Wheel |  |  | 153.72 | 1 | 153.72 | McMaster-Carr
| Base-Mount Ball Bearings |  |  | 39.65 | 1 | 39.65 | McMaster-Carr
| Misc Hardware |  |  |  |  | 500
| Assembly Cost |  |  |  |  | 2720 |  | 33.5802
| Contingency, % | 20 |  |  |  | 2678.066 |  | 33.0625
[6 empty] | 16068.396 |  | 177.0132 | 4.4253 | wks
Stage 2 - MCHP Assembly Cost
| Left side HP Support Stand Weldment | 5000 | 3 | 15000 | 1 | 15000 |  | 185.1852
| Right side HP support stand | 3000 | 3 | 9000 | 1 | 9000 |  | 111.1111
| Machine hoist ring |  |  | 210.48 | 1 | 210.48 | McMaster-Carr
| Magnetic alignment instrument |  |  |  |  | 16000 | See Mag Measurement Cost tab | 197.5309
| Machine hole match plate |  |  |  |  | 2000 | Estimate for match plate for drilling and reaming holes
| Misc Hardware |  |  |  |  | 500
| Assembly Cost |  |  |  |  | 3400 |  | 41.9753
| Contingency, % | 20 |  |  |  | 9222.096
[6 empty] | 55332.576 |  | 535.8025 | 13.3951 | wks
Stage 3 - MC Assembly Cost
| Laser Screen Modification parts | 300 | 4 | 1200 | 2 | 2400 |  | 29.6296
| Reworked Laser Screen Weldment |  |  |  | 2 | 1800 |  | 22.2222
| Test cell hook adaptor plate | 300 | 7 | 2100 | 1 | 2100 |  | 25.9259
| Nook screw system |  |  | 1500 | 3 | 4500 | Based on earlier Nook quotes of similar items
| Reducer |  |  | 500 | 3 | 1500
| Motor |  |  | 500 | 3 | 1500 | Based on 1/2 hp DC motor price from Baldor ($491)
| In-line encoder |  |  | 300 | 3 | 900
| Limit switches |  |  | 200 | 3 | 600 |  |  |  |  | 9000 | 13800
| MC temporary support system | 2100 | 4 | 8400 | 1 | 8400 | weldment plus some machined structure | 103.7037
| VV support system | 1600 | 4 | 6400 | 1 | 6400 | weldment plus some machined structure | 79.0123
| Hilman roller - 8-0T plus R & U guides |  | 950 |  | 8 | 7600 | Based on Hilman phone quote
| Flange bolt access platform |  |  |  |  | 0 | Use cherry picker | 0
| Hardware & Misc items |  |  |  |  | 1500
| Assembly Cost |  |  |  |  | 3400 |  | 41.9753
| Contingency, % | 20 |  |  |  | 8520 |  | 105.1852
[6 empty] | 48720 |  | 407.6543 | 10.1914 | wks
Stage 4 - TF 3-Coil Assembly Cost
| TF support base | 750 | 7 | 5250 | 1 | 5250 |  | 64.8148
| Outboard casting I-beam support | 218 | 7 | 1526 | 3 | 4578 |  | 56.5185
| Inboard casting support | 152 | 7 | 1064 | 2 | 2128 |  | 26.2716
| Temporary TF center support | 271 | 7 | 1897 | 2 | 3794 |  | 46.8395
| Hardware |  |  |  |  | 500
| Assembly Cost |  |  |  |  | 3400 |  | 41.9753
| Contingency, % | 30 |  |  |  | 5895 |  | 72.7778
[6 empty] | 25545 |  | 309.1975 | 7.7299 | wks
Stage 5 - FP Assembly Cost
| MC support stand | 3159 | 4 | 12636 | 1 | 12636 |  | 156
| TF HP assembly structure | 5041 | 4 | 20164 | 1 | 20164 | A redesign may reduce the cost | 248.9383 |  |  | 5000
| TF casters |  |  | 117.85 | 3 | 353.55 | McMaster-Carr (23515T11)
| MCHP tilt support fittings | 20 | 15 | 300 | 2 | 600 |  | 7.4074
| TF support roller bearings |  |  | 400 | 2 | 800
| VV port instl platform |  |  |  |  | 20000 |  | 40
| Hardware |  |  |  |  | 500
| Assembly Cost |  |  |  |  | 3400 |  | 41.9753
| Contingency, % | 30 |  |  |  | 17536.065 |  | 216.4946
[6 empty] | 75989.615 |  | 710.8156 | 17.7704 | wks
[5 empty] | TOTAL FIELD PERIOD ASSEMBLY FIXTURE HARDWARE COST | 221655.587
Rate
| Manpower Cost Estimate | Month | % time | Hours | ($/hr)
| Drafting | 8 | 1 | 1150.6667 | 115 | 132326.6667
| Electrical drafting |  |  | 0 | 102 | 0 | was 120 hrs
| Engineering | 8 | 0.5 | 575.3333 | 172 | 98957.3333
| Stress Analysis |  |  | 480 | 172 | 82560
313844
[5 empty] | TOTAL FPA COST | 535499.587 | Includes contingencies
TOTAL COST TO COMPLETE
[5 empty] | FPA Hardware Cost | 205587.191 | Includes Stage 2 through Stage 5
[5 empty] | FPA Hardware Cost less Contingency | 164414.03
[5 empty] | Manpower Cost Estimate | 313844
[5 empty] | Total Cost less contingency | 478258.03 | This assumes one unit of each built
[5 empty] | Scaled down FPA Cost | 450458.03 | This assumes one unit of each built |  |  |  | 27800 | savings
[6 empty] | 46110.48 | Added cost for second Stage 2 (Hardware only)
[6 empty] | 43289.55 | Added cost for second Stage 5 (Hardware only)
[5 empty] | TOTAL COST | 539858.06 | Assumed scaled down FPA cost

## Mag Measurement Cost
MAGNETIC MEASUREMENT COST ESTIMATE
LABOR COSTS
| Hr per | nb of | Total
| Template | Template | Man-hours | Fabrication Activity
|  |  | 16 | Program set up and cut loops
| 1 | 20 | 20 | Locate template
| 1 | 20 | 20 | Wind loop wire
| 1 | 20 | 20 | Terminate wires
|  |  | 8 | Add junction box
|  |  | 8 | Misc activities
|  |  | 92 | Loop assembly
|  |  | 40 | Machine tube, cut vertical panel and assemble
|  | Total labor costs | 10692 | Labor cost at hourly of: | 81
MATERIAL COSTS
Total
| Qnty | Unit Cost | Cost
| 2 | 143.62 | 287.24 | .043" x 36" x 48" sheet per McMaster-Carr
| 1 |  | 2417 | 24" OD x 6' acrylic tube per GE Cast Acrylic Tube | (see note 1)
|  |  | 2500 | Vertical panel
|  |  | 250 | hardware
5454.24
|  |  | 16146.24 | Magnetic Measurement Cost Estimate
note 1: spoke with Keith at GE Polimer Shapes
phone no: 866-437-7427