## Schedule
| Updated 9/2/05 |  |  | FY 2005 | [8 empty] | FY 2006 | [53 empty] | FY 2007 | [8 empty] | FY 2008
|  |  |  | AUG |  |  |  | SEPT |  |  |  | OCT | [5 empty] | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUG |  |  |  | SEPT |  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A
ITEM | TASK | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25
Target - Finish Last Field Period Assembly
VV period Arrival dates
1 | VV PREP STATION (Build to Print) |  |  | PR |  |  |  |  | FDR
1.01 | Concept definition and requirements | Complete | [6 empty] | 9/16
1.02 | VV Support Fixture plus dwgs | Complete
1.03 | Metrology layout | Complete
1.04 | Structural Analysis | Complete
1.05 | Fab Activities - VV Support Stand
[25 empty] | 1st VV | [33 empty] | 2nd VV |  |  |  | FY 2007 F: 3rd VV
2.06 | VV Assembly Operations
[34 empty] | Complete MC test |  | C1 |  |  | C2 | [6 empty] | C3 |  |  |  | C4 |  |  |  |  | C5 |  |  |  |  | A1 |  |  | O: A2; N: A3; D: B1; FY 2007 F: A4; FY 2007 M: A5; FY 2007 M: B3; FY 2007 J: B4; FY 2007 J: B5; FY 2007 A: C6; FY 2007 S: A6; FY 2007 O: B6 Complete
2 | HALF PERIOD ASMBLY (Build to Print) | bar: FY 2007 A
2.01 | Concept definition and requirements | Complete | [16 empty] | PDR | [6 empty] | FDR
2.02 | MC Holding Fixture | Complete
2.03 | Structural Analysis
2.04 | Fab Activities - Support fixture | [61 empty] | D: A1 / B1 / C1
[68 empty] | A2 / B2 / C2 | [9 empty] | A6 / B6 / C6
A5 / B5 / C5
A3 / B3 / C3
A4 / B4 / C4
3 | MC INSTALLATION (Build to Print) | [26 empty] | PDR | [5 empty] | FDR
3.01 | Concept definition and requirements
3.02 | MC Crane Load Support System
3.03 | Laser Screen Guides modifications
3.04 | VV support stand and Misc fixtures
3.05 | Platform for flange bolting
3.06 | Metrology layout
3.07 | Structural Analysis
3.08 | Fab Activities
- Crane support system
- Laser Screen Mod (In house)
3.09 | Assembly Activities
- Trial Runs - no VV
- MC Installation (1 Station)
4 | TF HP ASSEMBLY (Build to Print)
[31 empty] | PDR | [5 empty] | FDR
4.01 | Concept definition and requirements
4.02 | TF Rotation Fixture
4.03 | Metrology layout
4.04 | Structural Analysis
4.05 | Fab Activities -
4.06 | TF HP Assembly Operations
5 | FINAL FP ASSEMBLY (Build to Print) | [42 empty] | PDR | [5 empty] | FDR
5.01 | Concept definition and requirements | Finished
5.02 | MC Support Stand
5.03 | FP Assembly platforms
5.04 | Metrology layout
5.05 | Structural Analysis
5.06 | Fabrication - follow-up activities | [61 empty] | FY 2008 M: FPA-3
- FP Assembly
FPA-1
FPA-2
6 | INTERFACE / TEST ACTIVITIES
6.01 | TFTR test cell FPA arngmt dwg
6.02 | Generate As-Built spherical seat dwg
6.03 | Spherical seat metrology measurements
Models
All Dwgs
Models / Dwgs
Models / Dwgs
Models
Part Dwgs 75% done
Models
Finish prts dwg and assemblies
Procmt
Procmt
Procmt
Procmt
Procmt

## Schedule time line
ESTIMATE START AND END DATES
ITEM | TASK | START | END | COMMENTS
1 | VV PREP STATION (Build to Print)
1.01 | Concept definition and requirements |  |  | Complete
1.02 | VV Support Fixture plus dwgs |  |  | Complete
1.03 | Metrology layout |  |  | Complete
1.04 | Structural Analysis |  |  | Complete
1.05 | PDR / FDR |  |  | Complete
1.06 | Fab Activities - VV Support Stand (1 Reqd) | 2005-09-26 |  | Sent to Procurement 10/10/05
2 | HALF PERIOD ASSEMBLY (Build to Print)
2.01 | Concept definition and requirements |  |  | Complete
2.02 | MC Holding Fixture |  |  | Complete
2.03 | Metrology layout |  |  | Complete
2.04 | Structural Analysis | 2005-10-17 | 2005-11-21
2.05 | PDR / FDR | 2005-12-07 | 2006-01-04
2.06 | Procurement (build to print) 2 Reqd |  |  | In-house vs outside fab is TBD
3 | MC INSTALLATION (Outside design & Fab)
3.01 | Concept definition and requirements |  |  | Complete
3.02 | MC Crane Load Support System | 2005-10-10 | 2005-11-11
3.03 | Laser Screen Guide Modifications | 2005-11-14 | 2005-11-23
3.04 | VV support stand and Misc fixtures | 2005-11-28 | 2005-12-09
3.05 | Platform for flange bolting | 2005-12-12 | 2006-01-06
3.06 | Metrology layout | 2006-01-09 | 2006-01-21
3.07 | Structural Analysis | 2006-01-02 | 2006-02-11
3.08 | PDR / FDR | 2006-02-01 | 2006-03-08
3.09 | Fab Activities (1 Reqd) |  |  | See schedule
- Crane support system
- Laser Screens
4 | TF HP ASSEMBLY (Build to Print)
4.01 | Concept definition and requirements |  |  | Complete
4.02 | TF Rotation Fixture plus dwgs | 2006-01-23 | 2006-02-11
4.03 | Metrology layout | 2006-02-13 | 2006-02-24
4.04 | Structural Analysis | 2006-02-13 | 2006-03-25
4.05 | PDR / FDR | 2006-02-28 | 2006-04-11
4.06 | Fab Activities (1 Reqd) |  |  | In-house vs outside fab is TBD
5 | FINAL FP ASSEMBLY (Build to Print)
5.01 | Concept definition and requirements |  |  | Complete
5.02 | MC Support Stand | 2006-03-06 | 2006-04-07
5.03 | FP Assembly platform | 2006-04-10 | 2006-05-05
5.04 | Metrology layout / support stand dwgs | 2006-04-17 | 2006-05-13
5.05 | Structural Analysis | 2006-04-17 | 2006-05-26
5.06 | PDR / FDR | 2006-05-30 | 2006-07-11
5.07 | Fabrication (2 Reqd) |  |  | See schedule
- TF HP support
- FP Assembly platform
6 | INTERFACE / TEST ACTIVITIES
6.01 | TFTR test cell FPA arngmt dwg | 2006-06-05 | 2006-06-23
6.02 | Generate As-Built spherical seat dwg | 2005-10-10 | 2005-10-15
6.03 | Run test / metrology measurements | 2005-10-19 | 2005-11-08

## Costing
| Hardware Cost Estimates | [5 empty] | PPPL Shop Rate ($/hr) = | 85
Unit
|  | Weight | $ per | Unit |  | Total |  | Equiv
| Description | (lbs) | Lb | Cost ($) | Qnty | Cost ($) | Comments | hrs
Stage 1 - VV Support Stand Cost
| Support Stand Weldment | 290 | 7 | 2030 | 2 | 4060 |  | 47.7647
| Support Axle Weldment | 47 | 15 | 705 | 2 | 1410 |  | 16.5882
| Axle locking clamp | 19 | 15 | 285 | 2 | 570 |  | 6.7059
| Port 12 blank-off cover | 115 | 7 | 805 | 2 | 1610 |  | 18.9412
| Lateral support Weldment | 46 | 15 | 690 | 1 | 690 |  | 8.1176
| Worm Gear mounting bracker | 20 | 30 | 600 | 1 | 600 |  | 7.0588
| Machine hoist ring |  |  | 210.48 | 2 | 420.96 | McMaster-Carr
| Worm Gear |  |  | 294 | 1 | 294 | Boston Gear G1104
| Worm |  |  | 322 | 1 | 322 | Boston Gear H1104
| Hand Wheel |  |  | 153.72 | 1 | 153.72 | McMaster-Carr
| Base-Mount Ball Bearings |  |  | 39.65 | 1 | 39.65 | McMaster-Carr
| Misc Hardware |  |  |  |  | 500
| Assembly Cost |  |  |  |  | 2720 |  | 32
| Contingency, % | 20 |  |  |  | 2678.066 |  | 31.5067
[6 empty] | 16068.396 |  | 168.6831 | 4.2171 | wks
Stage 2 - MC Support Stand Cost
| Support Stand Weldment | 2833 | 7 | 19831 | 1 | 19831 |  | 233.3059
| Machine hoist ring |  |  | 210.48 | 1 | 210.48 | McMaster-Carr
| Hardware |  |  |  |  | 500
| Assembly Cost |  |  |  |  | 2720 |  | 32
| Contingency, % | 20 |  |  |  | 4652.296 |  | 54.7329
[6 empty] | 27913.776 |  | 320.0388 | 8.001 | wks
Stage 3 - MC Assembly Cost
| Laser Screen Modification parts | 300 | 4 | 1200 | 2 | 2400 |  | 28.2353
| Reworked Laser Screen Weldment |  |  |  | 2 | 1800 |  | 21.1765
| Test cell hook adaptor plate | 300 | 7 | 2100 | 1 | 2100 |  | 24.7059
| Nook screw system |  |  | 1500 | 3 | 4500 | Based on earlier Nook quotes of similar items
| Reducer |  |  | 500 | 3 | 1500
| Motor |  |  | 500 | 3 | 1500 | Based on 1/2 hp DC motor price from Baldor ($491)
| In-line encoder |  |  | 300 | 3 | 900
| Limit switches |  |  | 200 | 3 | 600
| MC temporary support | 750 | 4 | 3000 | 1 | 3000 |  | 35.2941
| Flange bolt access platform | 1000 | 4 | 4000 | 1 | 4000 |  | 47.0588
| VV support system | 750 | 4 | 3000 | 1 | 3000 |  | 35.2941
| Hardware & Misc itens |  |  |  |  | 1500
| Assembly Cost |  |  |  |  | 3400 |  | 40
| Contingency, % | 30 |  |  |  | 9060 |  | 106.5882
[6 empty] | 36860 |  | 338.3529 | 8.4588 | wks
Stage 4 - TF 3-Coil Assembly Cost
| TF support base | 750 | 7 | 5250 | 1 | 5250 |  | 61.7647
| Outboard casting I-beam support | 218 | 7 | 1526 | 3 | 4578 |  | 53.8588
| Inboard casting support | 152 | 7 | 1064 | 2 | 2128 |  | 25.0353
| Tempory TF center support | 271 | 7 | 1897 | 2 | 3794 |  | 44.6353
| Hardware |  |  |  |  | 500
| Assembly Cost |  |  |  |  | 3400 |  | 40
| Contingency, % | 30 |  |  |  | 5895 |  | 69.3529
[6 empty] | 25545 |  | 294.6471 | 7.3662 | wks
Stage 5 - FP Assembly Cost
| MC support stand | 3159 | 4 | 12636 | 1 | 12636 |  | 148.6588
| TF HP assembly structure | 5041 | 4 | 20164 | 1 | 20164 | A redesign may reduce cost | 237.2235
| TF casters |  |  | 117.85 | 3 | 353.55 | McMaster-Carr (23515T11)
| MCHP tilt support fittings | 20 | 15 | 300 | 2 | 600 |  | 7.0588
| TF support roller bearings |  |  | 400 | 2 | 800
| VV port instl platform |  |  |  |  | 20000 |  | 40
| Hardware |  |  |  |  | 500
| Assembly Cost |  |  |  |  | 3400 |  | 40
| Contingency, % | 30 |  |  |  | 17536.065 |  | 206.3066
[6 empty] | 75989.615 |  | 679.2478 | 16.9812 | wks
[5 empty] | TOTAL FIELD PERIOD ASSEMBLY FIXTURE COST | 182376.787