## Estimate Detail
Sum of Budget Remaining | [6 empty] | Name
Job | WBS4 | ACT | TITLE | ES | EF | OD | COLE | DUDEK | EA//EM | EA//SM | EE//EM | EE//SM | EM//EM | EM//TB | FAN | FOM TECHS SM | FOM TECHS TB | FREUDENBERG | GORANSON | HEITZENROED | LOVETT | M&S | MCGINNIS | MYATT | NELSON | ORNLEM | ORNLEM | R///RM2 | TRAVEL | WILLIAMSON | Total
| 12FD | 1203-902 | **dummy task ECP45 ETC update hours | 2006-04-01 | 2006-08-14 | 94 | [20 empty] | 25.44 |  |  |  | 25.44
1203 | 12FD | 1203-241 | Check FMECA Analyses | 2005-09-01 | 2006-08-14 | 238 |  |  | 1 | [17 empty] | 2 |  |  |  | 3
|  | 1203-271 | Develop Assy Rqmnts spec & process | 2006-05-01 | 2006-08-14 | 74 | [12 empty] | 10 | [11 empty] | 10
|  | 1203-801 | Issue VV FP final assy dwg | 2005-11-01 | 2006-08-16 | 197 | [20 empty] | 2 |  |  |  | 2
|  | 1203-802 | Issue spacer field machining dwgs | 2006-01-01 | 2007-09-28 | 171 | [20 empty] | 8 |  |  |  | 8
|  | 1203-803 | Issue VV final assy dwg | 2006-05-01 | 2007-01-31 | 83 | [20 empty] | 16 |  |  |  | 16
|  | 1203-804 | Issue VV assy specification | 2006-12-01 | 2006-12-19 | 13 | [20 empty] | 40 |  |  |  | 40
|  | 1203-820 | BOM for all VV parts | 2005-10-03 | 2006-08-18 | 220 | [20 empty] | 1.5 |  |  |  | 1.5
1204 |  | 122-031 | Title III engr WBS 12 non vvsa | 2006-02-01 | 2008-09-30 | 669 |  | 17.82 | [10 empty] | 100.44 | [6 empty] | 97.2 |  |  |  |  | 215.46
| 122 | 122-037 | Deliver Pourable Insulation | 2008-02-11 | 2008-06-13 | 89 | [15 empty] | 45 | [8 empty] | 45
|  | 122-051 | Deliver Port Thermal Insulation | 2007-08-31 | 2008-01-16 | 89 | [15 empty] | 25 | [8 empty] | 25
|  | 122-065 | Deliver Blanket Thermal Insulation | 2006-11-20 | 2007-02-28 | 65 | [15 empty] | 3 | [8 empty] | 3
|  | 123-050 | Fabricate& Deliver Insul Boots WBS 122 | 2007-10-02 | 2008-04-11 | 130 | [15 empty] | 55 | [8 empty] | 55
| 123 | 123-037 | Fabricate and Deliver H/C Tubing WBS 123 | 2006-10-02 | 2006-10-27 | 20 | [15 empty] | 45 | [8 empty] | 45
| 124 | 124-037 | PPPL Fab VV Vert. Supports (log # M1091) | 2005-12-01 | 2007-10-31 | 207 | [7 empty] | 384 | [16 empty] | 384
| 124L | 124-037L | VV Lateral Supports Fab by PPPL WBS 124 | 2007-06-01 | 2007-08-24 | 60 | [7 empty] | 400 | [16 empty] | 400
| 124P | 124-130 | VV NB port cover Fabrication (for 3 inconnel | 2007-08-03 | 2007-11-02 | 65 | [15 empty] | 59.67 | [8 empty] | 59.67
| 125 | 125-037 | Procurement Local I&C WBS 125 | 2006-10-02 | 2007-01-03 | 60 | [15 empty] | 2.4 | [8 empty] | 2.4
1250 |  | 121-034.1 | VVSA Title III engr | 2005-10-01 | 2006-09-29 | 249 | [12 empty] | 86.5 | [9 empty] | 1.384 |  | 87.884
|  | 121-038 | assist MTM testing of VVSA | 2006-01-17 | 2006-08-07 | 143 | [7 empty] | 5.6 | [16 empty] | 5.6
| VVS8 | VVSA-551 | Final Machine | 2006-08-11 | 2006-08-17 | 5 | [15 empty] | 50 | [8 empty] | 50
|  | VVSA-561 | Vacuum Test | 2006-07-24 | 2006-08-07 | 11 | [15 empty] | 30 | [8 empty] | 30
|  | VVSA-571 | Cut Off Ports | 2006-08-08 | 2006-08-10 | 3 | [15 empty] | 50 | [8 empty] | 50
|  | VVSA-581 | Inspect & Pack for Shipping LI#4 | 2006-09-06 | 2006-09-08 | 3 | [15 empty] | 23 | [8 empty] | 23
|  | VVSA-591 | Receive at PPPL | 2006-09-11 | 2006-09-12 | 2 | [15 empty] | 22 | [8 empty] | 22
| VVS9 | VVSA-611 | PPPL Receive Tooling | 2006-07-03 | 2006-09-14 | 54 | [15 empty] | 97.2 | [8 empty] | 97.2
1403 | TCCO | 1403-206C | Finish Cooling, Electr Schematic Dwgs - Type C | 2005-03-01 | 2006-08-31 | 381 | [23 empty] | 4 | 4
|  | 1403-223C | Finish Top level coil assembly-Type C | 2005-03-01 | 2006-08-31 | 381 | [20 empty] | 32.3 |  |  |  | 32.3
|  | 1403-224C | Finish VPI mold assembly-Type C | 2005-03-01 | 2006-08-31 | 381 | [20 empty] | 12 |  |  |  | 12
|  | 1403-40.2Z | Update nonlinear winding pack analysis | 2004-08-02 | 2007-01-02 | 560 | [11 empty] | 52.7 | [5 empty] | 0.5 | 0.4 |  |  |  |  | 4 | 57.6
|  | 1403-42H | calculate EM loads at leads | 2005-09-01 | 2007-01-02 | 288 | [23 empty] | 18 | 18
|  | 1403-47A | Update,review & approve FMECA | 2005-09-26 | 2007-01-02 | 271 | [23 empty] | 36 | 36
|  | 1403-47C | Perform cool-down/warmup analysis | 2006-10-02 | 2006-12-01 | 43 | [8 empty] | 40 | [15 empty] | 40
|  | 1403-50A | Check inductance calculation | 2006-10-02 | 2006-12-01 | 43 | [20 empty] | 40 |  |  |  | 40
|  | 1403-58C | Check and promote clamp, I&C assy dwgs -Type C | 2005-06-01 | 2006-08-31 | 316 | 10 | [23 empty] | 10
|  | 1403-60C | Finish Update design basis document | 2005-05-02 | 2007-01-02 | 374 | [23 empty] | 32 | 32
|  | 1403-73 | Prep struct analysis report | 2005-05-01 | 2007-01-02 | 374 | [11 empty] | 16 | [12 empty] | 16
|  | 1403-76 | Structural analysis of leads | 2004-10-01 | 2007-01-02 | 517 | [11 empty] | 16 | [12 empty] | 16
|  | 1403-90 | Compile Material properties database | 2004-10-01 | 2007-01-02 | 517 | [8 empty] | 12 | [15 empty] | 12
1411 | 14T | 172-031.1 | Title III engr | 2005-10-01 | 2007-03-01 | 350 | [13 empty] | 263.04 | [8 empty] | 10.686 | 43.977 | 317.703
1416 | DWTA | 1416A-105 | Top level models and drawings | 2006-03-03 | 2006-08-30 | 127 | [14 empty] | 8 | [9 empty] | 8
|  | 1416A-109 | -Check and Promote Top Level Drawings | 2006-08-31 | 2006-09-07 | 5 | 20 | [23 empty] | 20
|  | 1416A-153 | Lead Terminals-Splice Plates | 2006-05-01 | 2006-08-30 | 86 | [14 empty] | 10 | [9 empty] | 10
|  | 1416A-157 | Lead Terminals-Check and Promote | 2006-05-01 | 2006-08-30 | 86 | 14 | [23 empty] | 14
|  | 1416A-201 | Coil Post VPI mods-Studs Removed | 2005-12-03 | 2006-08-18 | 177 | [14 empty] | 4 | [9 empty] | 4
|  | 1416A-205 | Coil Post VPI mods-Clamp Arrangement | 2005-12-03 | 2006-08-18 | 177 | [14 empty] | 8 | [9 empty] | 8
|  | 1416A-209 | Coil Post VPI mods-Check and Promote | 2006-08-21 | 2006-08-25 | 5 | 4 | [23 empty] | 4
|  | 1416A-221 | I&C-Strain Gages and T/C | 2006-03-03 | 2006-09-29 | 148 | [14 empty] | 10 | [9 empty] | 10
|  | 1416A-225 | I&C-Rogowski Coils | 2006-03-03 | 2006-09-28 | 147 | [14 empty] | 28 | [9 empty] | 28
|  | 1416A-229 | I&C-Check and Promote | 2006-08-01 | 2006-09-29 | 43 | 20 | [23 empty] | 20
|  | 1416A-233 | Coil-to-Coil -Current Feed Insul, Covers | 2006-09-15 | 2006-09-21 | 5 | [14 empty] | 20 | [9 empty] | 20
|  | 1416A-237 | Coil-to-Coil -Windings Insul Blanket | 2006-07-03 | 2006-09-29 | 63 | [14 empty] | 10 | [9 empty] | 10
|  | 1416A-241 | Coil-to-Coil -Bushing Installation | 2006-09-15 | 2006-09-21 | 5 | [14 empty] | 20 | [9 empty] | 20
|  | 1416A-245 | Coil-to-Coil -Check and Promote | 2006-10-02 | 2006-10-06 | 5 | 20 | [23 empty] | 20
|  | 1416A-249 | -Type-A Coil Asm Specification | 2006-05-01 | 2006-08-30 | 86 | [23 empty] | 8 | 8
|  | 1416A-253 | -Review and Approve Type-A Spec | 2006-08-31 | 2006-09-07 | 5 | [23 empty] | 20 | 20
|  | 1416A-257 | -Update Coil Fab Procedures | 2006-08-31 | 2006-09-07 | 5 | [23 empty] | 20 | 20
|  | 1416A-261 | -Prepare for FDR | 2006-08-31 | 2006-09-07 | 5 | [23 empty] | 40 | 40
| DWTB | 1416B-105 | Top level models and drawings | 2006-03-11 | 2006-08-25 | 118 | [14 empty] | 20 | [9 empty] | 20
|  | 1416B-109 | -Check and Promote Top Level Drawings | 2006-08-28 | 2006-09-01 | 5 | 19.99 | [23 empty] | 19.99
|  | 1416B-149 | Lead Block Assy-Check and Promote | 2006-03-01 | (blank) | 107 | 3.998 | [23 empty] | 3.998
|  | 1416B-153 | Lead Terminals-Splice Plates | 2006-08-01 | 2006-08-07 | 5 | [14 empty] | 19.99 | [9 empty] | 19.99
|  | 1416B-157 | Lead Terminals-Check and Promote | 2006-08-08 | 2006-08-14 | 5 | 19.99 | [23 empty] | 19.99
|  | 1416B-201 | Coil Post VPI mods-Studs Removed | 2006-03-03 | 2006-09-29 | 148 | [14 empty] | 9.995 | [9 empty] | 9.995
|  | 1416B-205 | Coil Post VPI mods-Clamp Arrangement | 2006-03-03 | 2006-09-29 | 148 | [14 empty] | 20 | [9 empty] | 20
|  | 1416B-205A | Coil Post VPIU mods cooling/electrical | 2006-08-01 | 2006-08-11 | 9 | [20 empty] | 40 |  |  |  | 40
|  | 1416B-209 | Coil Post VPI mods-Check and Promote | 2006-08-01 | 2006-08-25 | 19 | 20 | [23 empty] | 20
|  | 1416B-221 | I&C-Strain Gages and T/C | 2006-08-28 | 2006-09-01 | 5 | [14 empty] | 19.99 | [9 empty] | 19.99
|  | 1416B-225 | I&C-Rogowski Coils | 2006-09-05 | 2006-09-11 | 5 | [14 empty] | 40 | [9 empty] | 40
|  | 1416B-229 | I&C-Check and Promote | 2006-08-01 | 2006-08-25 | 19 | 20 | [23 empty] | 20
|  | 1416B-233 | Coil-to-Coil -Current Feed Insul, Covers | 2006-08-04 | 2006-08-10 | 5 | [14 empty] | 19.99 | [9 empty] | 19.99
|  | 1416B-237 | Coil-to-Coil -Windings Insul Blanket | 2006-08-11 | 2006-08-17 | 5 | [14 empty] | 19.99 | [9 empty] | 19.99
|  | 1416B-241 | Coil-to-Coil -Bushing Installation | 2006-08-18 | 2006-08-24 | 5 | [14 empty] | 19.99 | [9 empty] | 19.99
|  | 1416B-245 | Coil-to-Coil -Check and Promote | 2006-08-25 | 2006-08-31 | 5 | 19.99 | [23 empty] | 19.99
|  | 1416B-249 | -Type-B Coil Asm Specification | 2006-09-01 | 2006-09-08 | 5 | [23 empty] | 40 | 40
|  | 1416B-253 | -Review and Approve Type-B Spec | 2006-09-11 | 2006-09-15 | 5 | [23 empty] | 19.99 | 19.99
|  | 1416B-257 | -Update Coil Fab Procedures | 2006-09-18 | 2006-09-22 | 5 | [23 empty] | 19.99 | 19.99
|  | 1416B-261 | -Prepare and Conduct FDR | 2006-09-25 | 2006-09-29 | 5 | [23 empty] | 40 | 40
|  | 1416B-265 | -Resolve FDR Comments | 2007-01-03 | 2007-01-16 | 10 | [23 empty] | 70 | 70
1421 | IH1 | IH1-005 | review requirements, as-built casting features | 2006-08-28 | 2006-09-18 | 15 | [12 empty] | 40 | [10 empty] | 0 | 40
|  | IH1-010 | obtain results from mockup test | (blank) | 2006-09-18 | 0 | [23 empty] | 0 | 0
|  | IH1-015 | Review for approval to proceed | (blank) | 2006-09-18 | 0 | [23 empty] | 0 | 0
|  | IH1-020 | Prepare dwgs and release | 2006-09-19 | 2006-11-06 | 35 | [12 empty] | 16 |  |  |  | 120 | [6 empty] | 0 | 136
|  | IH1-025 | Issue dwgs for Fabrication | (blank) | 2006-11-06 | 0 | [23 empty] | 0 | 0
| IH2 | IH2-005 | review and finalize structural requirements | 2006-08-28 | 2006-10-02 | 25 | [11 empty] | 40 | [11 empty] | 0 | 40
|  | IH2-010 | select and test concept(s) | (blank) | 2006-10-02 | 0 | [12 empty] | 0 | [10 empty] | 0 | 0
|  | IH2-015 | Finalize / select design (config and materials | 2006-08-21 | 2006-10-30 | 50 | [12 empty] | 120 | [10 empty] | 40 | 160
|  | IH2-020 | Review for approval to proceed | (blank) | 2006-10-30 | 0 | [23 empty] | 0 | 0
|  | IH2-025 | Prepare dwgs and release | 2006-10-31 | 2006-12-20 | 35 | [16 empty] | 200 | [6 empty] | 0 | 200
|  | IH2-030 | Issue dwgs for Fabrication | (blank) | 2006-12-20 | 0 | [23 empty] | 0 | 0
| IH3 | IH3-005 | review and finalize structural requirements | 2006-08-28 | 2006-09-18 | 15 | [11 empty] | 40 | [11 empty] | 0 | 40
|  | IH3-010 | Finalize concept | 2006-09-05 | 2006-09-18 | 10 | 20 | [11 empty] | 40 | [10 empty] | 0 | 60
|  | IH3-015 | Review for approval to proceed | (blank) | 2006-09-18 | 0 | [23 empty] | 0 | 0
|  | IH3-020 | Prepare tooling specs, drawings | 2006-09-19 | 2006-10-30 | 30 | 80 | [11 empty] | 20 | [10 empty] | 0 | 100
|  | IH3-025 | Issue dwgs for Procuremenet/ Fabrication | (blank) | 2006-10-30 | 0 | [23 empty] | 0 | 0
| IH4 | IH4-005 | Complete testing | 2006-08-28 | 2006-09-25 | 20 | [11 empty] | 80 | [11 empty] | 0 | 80
|  | IH4-010 | Finalize design, select material | 2006-09-05 | 2006-09-18 | 10 | [11 empty] | 20 | [11 empty] | 40 | 60
|  | IH4-015 | Review for approval to prceed | (blank) | 2006-09-25 | 0 | [23 empty] | 0 | 0
|  | IH4-020 | Prepare dwgs and release | 2006-09-12 | 2006-10-23 | 30 | [14 empty] | 240 | [8 empty] | 0 | 240
|  | IH4-025 | Issue dwgs for Fabrication | (blank) | 2006-10-23 | 0 | [23 empty] | 0 | 0
| IH5 | IH5-005 | Identify all stud, bushing, sperical washer, i | 2006-10-09 | 2006-11-03 | 20 | 16 | [22 empty] | 0 | 16
|  | IH5-010 | Prepare advanced procurement dwgs calling out | 2006-10-16 | 2006-11-10 | 20 | 40 | [22 empty] | 0 | 40
|  | IH5-015 | Issue specs/dwgs for procurement (studs, bushi | (blank) | 2006-11-10 | 0 | [23 empty] | 0 | 0
|  | IH5-020 | Finish 3-coil, 6 coil, and 18 coil top assembl | 2006-11-20 | 2006-12-19 | 20 | [14 empty] | 160 |  | 160 | [6 empty] | 0 | 320
|  | IH5-025 | Develop as-built model and drawing format | 2006-12-06 | 2007-01-10 | 20 | 40 | [22 empty] | 0 | 40
|  | IH5-030 | Complete assembly spec | 2006-12-13 | 2007-01-10 | 15 | [23 empty] | 0 | 0
| IH6 | IH6-005 | Finalize requirements | 2006-09-11 | 2006-10-06 | 20 | [23 empty] | 16 | 16
|  | IH6-010 | finalize design | 2006-09-18 | 2006-10-06 | 15 | [23 empty] | 16 | 16
|  | IH6-015 | Review for approval to proceed | (blank) | 2006-10-06 | 0 | [23 empty] | 0 | 0
|  | IH6-020 | Prepare dwgs and release | 2006-10-09 | 2006-11-10 | 25 | [14 empty] | 80 | [8 empty] | 0 | 80
|  | IH6-025 | Issue dwgs for Fabrication | (blank) | 2006-11-10 | 0 | [23 empty] | 0 | 0
1431 | IH1 | IH1-030 | Bid, Award, Procure or Fabricate | 2006-11-07 | 2007-02-08 | 60 | [23 empty] | 0 | 0
|  | IH1-035 | Receive and inspect 3 point positioning hardwa | (blank) | 2007-02-08 | 0 | [23 empty] | 0 | 0
| IH2 | 1421-410 | Bid, Award, Procure or Fab Bladders | 2006-12-21 | 2007-02-15 | 35 | [15 empty] | 60 | [8 empty] | 60
|  | IH2-040 | Receive and inspect Bladders | (blank) | 2007-02-15 | 0 | [23 empty] | 0 | 0
| IH3 | IH3-030 | Bid, Award, Procure or Fab Bolt Reaming | 2006-10-31 | 2007-02-01 | 60 | [23 empty] | 0 | 0
|  | IH3-035 | Receive and inspect Bolt Reaming | (blank) | 2007-02-01 | 0 | [23 empty] | 0 | 0
| IH4 | 1421-210 | Bid, Award, Procure Shear plate and shims | 2006-10-24 | 2007-01-25 | 60 | [15 empty] | 138 | [8 empty] | 138
|  | 1421-411 | Deliverhardware for inboard joint friciton | 2006-10-24 | 2007-01-25 | 60 | [15 empty] | 52 | [8 empty] | 52
|  | IH4-035 | Receive and inspect Shear plate and shims | (blank) | 2007-01-25 | 0 | [23 empty] | 0 | 0
| IH5 | 1421-110 | Bid, Award, Procure stud, bushing, sperical wa | 2006-11-13 | 2007-01-31 | 50 | [15 empty] | 449 | [8 empty] | 449
|  | IH5-040 | Receive and inspect stud, bushing, sperical wa | (blank) | 2007-01-31 | 0 | [23 empty] | 0 | 0
| IH6 | IH6-030 | Bid, Award, Procure or Fab Other insulation | 2006-11-13 | 2007-01-31 | 50 | [23 empty] | 0 | 0
|  | IH6-035 | Receive and inspect Other insulation over wing | (blank) | 2007-01-31 | 0 | [23 empty] | 0 | 0
1451 | LABR | TITLE3W | Titel III Design ORNL- Component Fab & WINDING | 2005-10-10 | 2007-11-26 | 534 | [22 empty] | 24.96 | 566.9664 | 591.9264
1460 |  | WINDFIX | 3rd winding fixture | 2006-10-02 | 2007-01-10 | 65 |  |  |  | 160 |  |  |  | 316 | [7 empty] | 13 | [8 empty] | 489
1465 |  | COILTEST | Additional coil testing-TESTING | 2006-11-01 | 2006-12-01 | 21 |  |  |  |  | 149 | 99 | 149 | 297 | [7 empty] | 25 | [8 empty] | 719
|  | COILTESTA | Coil testing-Qualify optical strain gages | 2006-12-04 | 2007-01-09 | 21 | [20 empty] | 437 |  |  |  | 437
|  | COILTESTB | Document Report | 2007-01-10 | 2007-02-07 | 21 | [20 empty] | 175 |  |  |  | 175
1601 | 161 | 191-001 | Title I design WBS 161 LN2 manifolds&piping | 2007-07-02 | 2007-10-02 | 65 |  |  | 80 | [20 empty] | 251 | 331
|  | 191-011 | Title II design WBS 161 LN2 manifolds&piping | 2007-10-03 | 2008-01-07 | 60 |  |  | 160 | [20 empty] | 503 | 663
|  | 191-031 | Title III engr WBS 161 | 2008-01-08 | 2009-02-18 | 280 |  |  | 8 | [20 empty] | 86 | 94
|  | 191-037 | Procurement WBS 161 | 2008-01-08 | 2008-07-09 | 130 | [15 empty] | 52.95 | [8 empty] | 52.95
|  | 191-038 | PDR#17 | 2008-07-10 | 2008-10-09 | 65 | [15 empty] | 44.36 | [8 empty] | 44.36
|  | 191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 | 2008-07-10 | 2008-10-09 | 65 | [9 empty] | 71 | 284 | [13 empty] | 355
|  | 191-042 | PDR #17,25,3 | 2008-07-10 | 2008-10-09 | 65 | [9 empty] | 23 | 90 | [13 empty] | 113
| 162 | 132-000 | PDR #17 & 25 | 2007-07-02 | 2008-10-16 | 325 | [19 empty] | 200 |  |  |  | 20 | 220
|  | 132-001 | Title I design WBS 162 Coil leads | 2007-07-02 | 2008-01-14 | 130 | [19 empty] | 20 |  |  |  | 869 | 889
|  | 132-011 | Title II design WBS 162 Coil leads | 2008-01-15 | 2008-07-16 | 130 | [19 empty] | 20 |  |  |  | 869 | 889
|  | 132-015 | Title III design WBS 162 Coil leads | 2008-07-17 | 2008-10-09 | 60 | [9 empty] | 8 | [13 empty] | 98 | 106
|  | 132-037 | Coil Leads Procurement WBS 162 | 2008-07-17 | 2008-10-09 | 60 | [15 empty] | 223.62 | [8 empty] | 223.62
| 163 | 163.001 | Title I design WBS 163 Coil protection | 2007-10-01 | 2008-01-10 | 65 | [19 empty] | 80 |  | 80 |  | 82 | 242
|  | 163.011 | Title II design WBS 163 Coil protection | 2008-01-11 | 2008-03-06 | 40 | [19 empty] | 80 |  | 80 |  | 82 | 242
1901 | 191 | 0191-6 | LOE-FY06 WBS 191 | 2005-10-03 | 2006-09-29 | 249 | [18 empty] | 190.3 |  |  |  | 2.076 |  | 192.376
|  | 0191-6X | LOE-FY07 WBS 191 | 2006-10-03 | 2007-09-27 | 247 | [18 empty] | 1100 |  |  |  | 12 |  | 1112
|  | 0191-7 | LOE-FY08 WBS 191 | 2007-10-03 | 2008-09-29 | 247 | [18 empty] | 488 |  |  |  | 12 |  | 500
|  | 191-8 | LOE-FY089 WBS 191 | 2008-10-03 | 2009-04-15 | 130 | [18 empty] | 244 |  |  |  | 6 |  | 250
| 192 | 0192-6 | LOE-FY06 WBS 192 | 2005-10-03 | 2006-09-29 | 249 | 276.8 | [14 empty] | 5.1641 | [6 empty] | 2.076 |  | 284.0401
|  | 0192-6X | LOE-FY07 WBS 192 | 2006-10-03 | 2007-09-20 | 242 | 667 | [14 empty] | 29.95 | [6 empty] | 12 |  | 708.95
|  | 0192-7 | LOE-FY08 WBS 192 | 2007-10-03 | 2008-09-22 | 242 | 600 | [14 empty] | 29.95 | [6 empty] | 12 |  | 641.95
|  | 0192-99 | LOE-FY09 | 2008-10-01 | 2009-04-13 | 130 | 400 | [14 empty] | 20 | [6 empty] | 6 |  | 426
Total | [6 empty] | 2331.768 | 17.82 | 249 | 160 | 149 | 99 | 149 | 1402.6 | 52 | 102 | 374 | 264.7 | 432.94 | 263.04 | 787.945 | 1650.264 | 480 | 0.5 | 2022.7 | 497.2 | 831.24 | 160 | 101.182 | 3954.9234 | 16532.8224

## database
ACT | TITLE | OD | ES |  | EF | WBS2 | Job | WBS4 | Order | Resource Code | Name | EVQ | BQ | Budget Remaining
125-037 | Procurement Local I&C WBS 125 | 60 | 2006-10-02 |  | 2007-01-03 | 12 | 1204 | 125 | 91 | 41 | M&S | 0 | 2.4 | 2.4
122-065 | Deliver Blanket Thermal Insulation | 65 | 2006-11-20 |  | 2007-02-28 | 12 | 1204 | 122 | 13 | 41 | M&S | 0 | 3 | 3
123-050 | Fabricate& Deliver Insul Boots WBS 122 | 130 | 2007-10-02 |  | 2008-04-11 | 12 | 1204 | 122 | 24 | 41 | M&S | 0 | 55 | 55
122-051 | Deliver Port Thermal Insulation | 89 | 2007-08-31 |  | 2008-01-16 | 12 | 1204 | 122 | 34 | 41 | M&S | 0 | 25 | 25
122-037 | Deliver Pourable Insulation | 89 | 2008-02-11 |  | 2008-06-13 | 12 | 1204 | 122 | 44 | 41 | M&S | 0 | 45 | 45
WINDFIX | 3rd winding fixture | 65 | 2006-10-02 |  | 2007-01-10 | 14 | 1460 |  | 00 | 41 | M&S | 0 | 13 | 13
COILTEST | Additional coil testing-TESTING | 21 | 2006-11-01 |  | 2006-12-01 | 14 | 1465 |  | 00 | 41 | M&S | 0 | 25 | 25
191-037 | Procurement WBS 161 | 130 | 2008-01-08 |  | 2008-07-09 | 16 | 1601 | 161 |  | 41 | M&S | 0 | 52.95 | 52.95
191-038 | PDR#17 | 65 | 2008-07-10 |  | 2008-10-09 | 16 | 1601 | 161 |  | 41 | M&S | 0 | 44.36 | 44.36
132-037 | Coil Leads Procurement WBS 162 | 60 | 2008-07-17 |  | 2008-10-09 | 16 | 1601 | 162 | 01 | 41 | M&S | 0 | 223.62 | 223.62
VVSA-561 | Vacuum Test | 11 | 2006-07-24 | A | 2006-08-07 | 12 | 1250 | VVS8 | 14 | 48 | M&S | 30 | 60 | 30
VVSA-571 | Cut Off Ports | 3 | 2006-08-08 |  | 2006-08-10 | 12 | 1250 | VVS8 | 15 | 48 | M&S | 0 | 50 | 50
VVSA-551 | Final Machine | 5 | 2006-08-11 |  | 2006-08-17 | 12 | 1250 | VVS8 | 16 | 48 | M&S | 0 | 50 | 50
VVSA-581 | Inspect & Pack for Shipping LI#4 | 3 | 2006-09-06 |  | 2006-09-08 | 12 | 1250 | VVS8 | 17 | 48 | M&S | 0 | 23 | 23
VVSA-591 | Receive at PPPL | 2 | 2006-09-11 |  | 2006-09-12 | 12 | 1250 | VVS8 | 18 | 48 | M&S | 0 | 22 | 22
VVSA-611 | PPPL Receive Tooling | 54 | 2006-07-03 | A | 2006-09-14 | 12 | 1250 | VVS9 | 11 | 48 | M&S | 388.8 | 486 | 97.2
124-030L | SPEA VV Lateral Supports WBS 124 | 43 | 2007-04-02 |  | 2007-05-31 | 12 | 1204 | 124L | 20 |  |  | 0 | 0 | 0
124-036.9L | Award VV Lateral Supports WBS 124 | 0 |  |  | 2007-05-31 | 12 | 1204 | 124L | 21 |  |  | 0 | 0 | 0
124-110 | SPEA VV NB port cover | 43 | 2007-06-04 |  | 2007-08-02 | 12 | 1204 | 124P | 20 |  |  | 0 | 0 | 0
124-120 | Award VV NB port cover | 0 |  |  | 2007-08-02 | 12 | 1204 | 124P | 21 |  |  | 0 | 0 | 0
122-055 | SPEA Blanket Thermal Insulation | 35 | 2006-10-02 |  | 2006-11-17 | 12 | 1204 | 122 | 11 |  |  | 0 | 0 | 0
122-060 | Award Blanket Thermal Insulation | 0 |  |  | 2006-11-17 | 12 | 1204 | 122 | 12 |  |  | 0 | 0 | 0
123-040 | Issue RFQ & Select Vendor insul boots WBS 122 | 43 | 2007-08-01 |  | 2007-10-01 | 12 | 1204 | 122 | 22 |  |  | 0 | 0 | 0
123-045 | Award Insulation Boots WBS 122 | 0 |  |  | 2007-10-01 | 12 | 1204 | 122 | 23 |  |  | 0 | 0 | 0
122-035 | SPEA Port Thermal Insulation | 43 | 2007-07-02 |  | 2007-08-30 | 12 | 1204 | 122 | 32 |  |  | 0 | 0 | 0
122-041 | Award Port Thermal Insulation | 0 |  |  | 2007-08-30 | 12 | 1204 | 122 | 33 |  |  | 0 | 0 | 0
122-030 | SPEA Pourable Insulation | 43 | 2007-12-03 |  | 2008-02-08 | 12 | 1204 | 122 | 42 |  |  | 0 | 0 | 0
122-036.9 | Award Pourable Insulation | 0 |  |  | 2008-02-08 | 12 | 1204 | 122 | 43 |  |  | 0 | 0 | 0
VVSA-021 | Sect 5.1.2 Fiducials | 433 | 2004-11-29 | A |  | 12 | 1250 | VVS1 |  |  |  | 0 | 0 | 0
VVSA-552 | Tack on ports,weld on tube&block | 13 | 2006-08-18 |  | 2006-09-05 | 12 | 1250 | VVS8 | 16 |  |  | 0 | 0 | 0
121-160 | S005243 #13-Receipt/Acceptance of 3rd VVSA | 0 |  |  | 2006-09-12 | 12 | 1250 | VVS8 | 19 |  |  | 0 | 0 | 0
121-038.1 | All Vacuum Vessel Sections (3) Delivered | 0 |  |  | 2006-09-12 | 12 | 1250 | VVS8 | 20 |  |  | 0 | 0 | 0
VVSA-601 | Pack Tooling for PPPL | 1 | 2006-09-11 |  | 2006-09-11 | 12 | 1250 | VVS9 | 10 |  |  | 0 | 0 | 0
121-165 | S005243 #14-Delivery of tooling,dies,fixtures | 0 |  |  | 2006-09-14 | 12 | 1250 | VVS9 | 12 |  |  | 0 | 0 | 0
1403-42A1 | Document analysis of MCWF eddy currents | 43 | 2006-10-02 |  | 2006-12-01 | 14 | 1403 | TCCO | 97 |  |  | 0 | 0 | 0
1403-990 | Analysis of C1 test data*not budgeted* | 43 | 2006-07-03 | A | 2006-08-31 | 14 | 1403 | TCCO | 97 |  |  | 0 | 0 | 0
1416B-262 | TYPE A, B & C closeout FDR | 0 |  |  | 2007-01-02 | 14 | 1416 | DWTB |  |  |  | 0 | 0 | 0
1403-PDR | PDR | 0 |  |  | 2006-10-30 | 14 | 1421 | DW08 | 98 |  |  | 0 | 0 | 0
1403-FDR | FDR | 0 |  |  | 2006-11-27 | 14 | 1421 | DW08 | 99 |  |  | 0 | 0 | 0
1203-241 | Check FMECA Analyses | 238 | 2005-09-01 | A | 2006-08-14 | 12 | 1203 | 12FD | 04 | EA//EM | EA//EM | 19 | 20 | 1
WINDFIX | 3rd winding fixture | 65 | 2006-10-02 |  | 2007-01-10 | 14 | 1460 |  | 00 | EA//SM | EA//SM | 0 | 160 | 160
COILTEST | Additional coil testing-TESTING | 21 | 2006-11-01 |  | 2006-12-01 | 14 | 1465 |  | 00 | EE//EM | EE//EM | 0 | 149 | 149
COILTEST | Additional coil testing-TESTING | 21 | 2006-11-01 |  | 2006-12-01 | 14 | 1465 |  | 00 | EE//SM | EE//SM | 0 | 99 | 99
COILTEST | Additional coil testing-TESTING | 21 | 2006-11-01 |  | 2006-12-01 | 14 | 1465 |  | 00 | EM//EM | EM//EM | 0 | 149 | 149
124-037 | PPPL Fab VV Vert. Supports (log # M1091) | 207 | 2005-12-01 | A | 2007-10-31 | 12 | 1204 | 124 | 14 | EM//TB | EM//TB | 384 | 768 | 384
124-037L | VV Lateral Supports Fab by PPPL WBS 124 | 60 | 2007-06-01 |  | 2007-08-24 | 12 | 1204 | 124L | 22 | EM//TB | EM//TB | 0 | 400 | 400
121-038 | assist MTM testing of VVSA | 143 | 2006-01-17 | A | 2006-08-07 | 12 | 1250 |  | 08 | EM//TB | EM//TB | 154.4 | 160 | 5.6
WINDFIX | 3rd winding fixture | 65 | 2006-10-02 |  | 2007-01-10 | 14 | 1460 |  | 00 | EM//TB | EM//TB | 0 | 316 | 316
COILTEST | Additional coil testing-TESTING | 21 | 2006-11-01 |  | 2006-12-01 | 14 | 1465 |  | 00 | EM//TB | EM//TB | 0 | 297 | 297
121-034.1 | VVSA Title III engr | 249 | 2005-10-01 | A | 2006-09-29 | 12 | 1250 |  | 07 | ORNL35 | TRAVEL | 6.616 | 8 | 1.384
172-031.1 | Title III engr | 350 | 2005-10-01 | A | 2007-03-01 | 14 | 1411 | 14T | 10 | ORNL35 | TRAVEL | 7.068 | 12 | 4.932
0191-6 | LOE-FY06 WBS 191 | 249 | 2005-10-03 | A | 2006-09-29 | 19 | 1901 | 191 | 02 | ORNL35 | TRAVEL | 9.924 | 12 | 2.076
0191-6X | LOE-FY07 WBS 191 | 247 | 2006-10-03 |  | 2007-09-27 | 19 | 1901 | 191 | 02 | ORNL35 | TRAVEL | 0 | 12 | 12
0191-7 | LOE-FY08 WBS 191 | 247 | 2007-10-03 |  | 2008-09-29 | 19 | 1901 | 191 | 02 | ORNL35 | TRAVEL | 0 | 12 | 12
191-8 | LOE-FY089 WBS 191 | 130 | 2008-10-03 |  | 2009-04-15 | 19 | 1901 | 191 | 02 | ORNL35 | TRAVEL | 0 | 6 | 6
0192-6 | LOE-FY06 WBS 192 | 249 | 2005-10-03 | A | 2006-09-29 | 19 | 1901 | 192 | 07 | ORNL35 | TRAVEL | 9.924 | 12 | 2.076
0192-6X | LOE-FY07 WBS 192 | 242 | 2006-10-03 |  | 2007-09-20 | 19 | 1901 | 192 | 07 | ORNL35 | TRAVEL | 0 | 12 | 12
0192-7 | LOE-FY08 WBS 192 | 242 | 2007-10-03 |  | 2008-09-22 | 19 | 1901 | 192 | 07 | ORNL35 | TRAVEL | 0 | 12 | 12
0192-99 | LOE-FY09 | 130 | 2008-10-01 |  | 2009-04-13 | 19 | 1901 | 192 | 07 | ORNL35 | TRAVEL | 0 | 6 | 6
0192-6 | LOE-FY06 WBS 192 | 249 | 2005-10-03 | A | 2006-09-29 | 19 | 1901 | 192 | 07 | ORNL41 | M&S | 24.6859 | 29.85 | 5.1641
0192-6X | LOE-FY07 WBS 192 | 242 | 2006-10-03 |  | 2007-09-20 | 19 | 1901 | 192 | 07 | ORNL41 | M&S | 0 | 29.95 | 29.95
0192-7 | LOE-FY08 WBS 192 | 242 | 2007-10-03 |  | 2008-09-22 | 19 | 1901 | 192 | 07 | ORNL41 | M&S | 0 | 29.95 | 29.95
0192-99 | LOE-FY09 | 130 | 2008-10-01 |  | 2009-04-13 | 19 | 1901 | 192 | 07 | ORNL41 | M&S | 0 | 20 | 20
132-000 | PDR #17 & 25 | 325 | 2007-07-02 |  | 2008-10-16 | 16 | 1601 | 162 | 01 | ORNLEM | ORNLEM | 0 | 200 | 200
132-001 | Title I design WBS 162 Coil leads | 130 | 2007-07-02 |  | 2008-01-14 | 16 | 1601 | 162 | 01 | ORNLEM | ORNLEM | 0 | 20 | 20
132-011 | Title II design WBS 162 Coil leads | 130 | 2008-01-15 |  | 2008-07-16 | 16 | 1601 | 162 | 01 | ORNLEM | ORNLEM | 0 | 20 | 20
163.001 | Title I design WBS 163 Coil protection | 65 | 2007-10-01 |  | 2008-01-10 | 16 | 1601 | 163 |  | ORNLEM | ORNLEM | 0 | 80 | 80
163.011 | Title II design WBS 163 Coil protection | 40 | 2008-01-11 |  | 2008-03-06 | 16 | 1601 | 163 |  | ORNLEM | ORNLEM | 0 | 80 | 80
123-037 | Fabricate and Deliver H/C Tubing WBS 123 | 20 | 2006-10-02 |  | 2006-10-27 | 12 | 1204 | 123 | 35 | 41 | M&S | 0 | 15 | 15
1403-58C | Check and promote clamp, I&C assy dwgs -Type C | 316 | 2005-06-01 | A | 2006-08-31 | 14 | 1403 | TCCO | 96 | ORNLEM | COLE | 90 | 100 | 10
1416A-109 | -Check and Promote Top Level Drawings | 5 | 2006-08-31 |  | 2006-09-07 | 14 | 1416 | DWTA | 01 | ORNLEM | COLE | 0 | 20 | 20
1416A-157 | Lead Terminals-Check and Promote | 86 | 2006-05-01 | A | 2006-08-30 | 14 | 1416 | DWTA | 02 | ORNLEM | COLE | 6 | 20 | 14
1416A-209 | Coil Post VPI mods-Check and Promote | 5 | 2006-08-21 |  | 2006-08-25 | 14 | 1416 | DWTA | 02 | ORNLEM | COLE | 16 | 20 | 4
1416A-229 | I&C-Check and Promote | 43 | 2006-08-01 |  | 2006-09-29 | 14 | 1416 | DWTA | 02 | ORNLEM | COLE | 0 | 20 | 20
1416A-245 | Coil-to-Coil -Check and Promote | 5 | 2006-10-02 |  | 2006-10-06 | 14 | 1416 | DWTA | 02 | ORNLEM | COLE | 0 | 20 | 20
1416B-209 | Coil Post VPI mods-Check and Promote | 19 | 2006-08-01 |  | 2006-08-25 | 14 | 1416 | DWTB |  | ORNLEM | COLE | 0 | 20 | 20
1416B-229 | I&C-Check and Promote | 19 | 2006-08-01 |  | 2006-08-25 | 14 | 1416 | DWTB |  | ORNLEM | COLE | 0 | 20 | 20
1416B-245 | Coil-to-Coil -Check and Promote | 5 | 2006-08-25 |  | 2006-08-31 | 14 | 1416 | DWTB |  | ORNLEM | COLE | 0 | 19.99 | 19.99
1416B-109 | -Check and Promote top level drawings | 5 | 2006-08-28 |  | 2006-09-01 | 14 | 1416 | DWTB | 10 | ORNLEM | COLE | 0 | 19.99 | 19.99
1416B-149 | Lead Block Assy-Check and Promote | 107 | 2006-03-01 | A |  | 14 | 1416 | DWTB | 10 | ORNLEM | COLE | 15.992 | 19.99 | 3.998
1416B-157 | Lead Terminals-Check and Promote | 5 | 2006-08-08 |  | 2006-08-14 | 14 | 1416 | DWTB | 10 | ORNLEM | COLE | 0 | 19.99 | 19.99
IH3-010 | Finalize concept | 10 | 2006-09-05 |  | 2006-09-18 | 14 | 1421 | IH3 |  | ORNLEM | COLE | 0 | 20 | 20
IH3-020 | Prepare tooling specs, drawings | 30 | 2006-09-19 |  | 2006-10-30 | 14 | 1421 | IH3 |  | ORNLEM | COLE | 0 | 80 | 80
IH5-005 | Identify all stud, bushing, sperical washer, i | 20 | 2006-10-09 |  | 2006-11-03 | 14 | 1421 | IH5 |  | ORNLEM | COLE | 0 | 16 | 16
IH5-010 | Prepare advanced procurement dwgs calling out | 20 | 2006-10-16 |  | 2006-11-10 | 14 | 1421 | IH5 |  | ORNLEM | COLE | 0 | 40 | 40
IH5-025 | Develop as-built model and drawing format | 20 | 2006-12-06 |  | 2007-01-10 | 14 | 1421 | IH5 |  | ORNLEM | COLE | 0 | 40 | 40
0192-6 | LOE-FY06 WBS 192 | 249 | 2005-10-03 | A | 2006-09-29 | 19 | 1901 | 192 | 07 | ORNLEM | COLE | 1323.2 | 1600 | 276.8
0192-6X | LOE-FY07 WBS 192 | 242 | 2006-10-03 |  | 2007-09-20 | 19 | 1901 | 192 | 07 | ORNLEM | COLE | 0 | 667 | 667
0192-7 | LOE-FY08 WBS 192 | 242 | 2007-10-03 |  | 2008-09-22 | 19 | 1901 | 192 | 07 | ORNLEM | COLE | 0 | 600 | 600
0192-99 | LOE-FY09 | 130 | 2008-10-01 |  | 2009-04-13 | 19 | 1901 | 192 | 07 | ORNLEM | COLE | 0 | 400 | 400
122-031 | Title III engr WBS 12 non vvsa | 669 | 2006-02-01 | A | 2008-09-30 | 12 | 1204 |  | 99 | EM//EM | DUDEK | 4.18 | 22 | 17.82
191-001 | Title I design WBS 161 LN2 manifolds&piping | 65 | 2007-07-02 |  | 2007-10-02 | 16 | 1601 | 161 |  | EA//EM | EA//EM | 0 | 80 | 80
191-011 | Title II design WBS 161 LN2 manifolds&piping | 60 | 2007-10-03 |  | 2008-01-07 | 16 | 1601 | 161 |  | EA//EM | EA//EM | 0 | 160 | 160
191-031 | Title III engr WBS 161 | 280 | 2008-01-08 |  | 2009-02-18 | 16 | 1601 | 161 |  | EA//EM | EA//EM | 0 | 8 | 8
122-031 | Title III engr WBS 12 non vvsa | 669 | 2006-02-01 | A | 2008-09-30 | 12 | 1204 |  | 99 | ORNLEM | ORNLEM | 22.8 | 120 | 97.2
1403-47C | Perform cool-down/warmup analysis | 43 | 2006-10-02 |  | 2006-12-01 | 14 | 1403 | TCCO | 97 | EA//EM | FAN | 0 | 40 | 40
1403-90 | Compile Material properties database | 517 | 2004-10-01 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | EA//EM | FAN | 108 | 120 | 12
191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 | 65 | 2008-07-10 |  | 2008-10-09 | 16 | 1601 | 161 |  | EM//SM | FOM TECHS SM | 0 | 71 | 71
191-042 | PDR #17,25,3 | 65 | 2008-07-10 |  | 2008-10-09 | 16 | 1601 | 161 |  | EM//SM | FOM TECHS SM | 0 | 23 | 23
132-015 | Title III design WBS 162 Coil leads | 60 | 2008-07-17 |  | 2008-10-09 | 16 | 1601 | 162 | 01 | EM//SM | FOM TECHS SM | 0 | 8 | 8
191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 | 65 | 2008-07-10 |  | 2008-10-09 | 16 | 1601 | 161 |  | EM//TB | FOM TECHS TB | 0 | 284 | 284
191-042 | PDR #17,25,3 | 65 | 2008-07-10 |  | 2008-10-09 | 16 | 1601 | 161 |  | EM//TB | FOM TECHS TB | 0 | 90 | 90
1403-40.2Z | Update nonlinear winding pack analysis | 560 | 2004-08-02 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | ORNLEM | FREUDENBERG | 474.3 | 527 | 52.7
1403-73 | Prep struct analysis report | 374 | 2005-05-01 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | ORNLEM | FREUDENBERG | 64 | 80 | 16
1403-76 | Structural analysis of leads | 517 | 2004-10-01 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | ORNLEM | FREUDENBERG | 64 | 80 | 16
IH2-005 | review and finalize structural requirements | 25 | 2006-08-28 |  | 2006-10-02 | 14 | 1421 | IH2 |  | ORNLEM | FREUDENBERG | 0 | 40 | 40
IH3-005 | review and finalize structural requirements | 15 | 2006-08-28 |  | 2006-09-18 | 14 | 1421 | IH3 |  | ORNLEM | FREUDENBERG | 0 | 40 | 40
IH4-005 | Complete testing | 20 | 2006-08-28 |  | 2006-09-25 | 14 | 1421 | IH4 |  | ORNLEM | FREUDENBERG | 0 | 80 | 80
IH4-010 | Finalize design, select material | 10 | 2006-09-05 |  | 2006-09-18 | 14 | 1421 | IH4 |  | ORNLEM | FREUDENBERG | 0 | 20 | 20
1203-271 | Develop Assy Rqmnts spec & process | 74 | 2006-05-01 | A | 2006-08-14 | 12 | 1203 | 12FD | 05 | ORNLEM | GORANSON | 190 | 200 | 10
122-031 | Title III engr WBS 12 non vvsa | 669 | 2006-02-01 | A | 2008-09-30 | 12 | 1204 |  | 99 | ORNLEM | GORANSON | 23.56 | 124 | 100.44
121-034.1 | VVSA Title III engr | 249 | 2005-10-01 | A | 2006-09-29 | 12 | 1250 |  | 07 | ORNLEM | GORANSON | 413.5 | 500 | 86.5
IH1-005 | review requirements, as-built casting features | 15 | 2006-08-28 |  | 2006-09-18 | 14 | 1421 | IH1 |  | ORNLEM | GORANSON | 0 | 40 | 40
IH1-020 | Prepare dwgs and release | 35 | 2006-09-19 |  | 2006-11-06 | 14 | 1421 | IH1 |  | ORNLEM | GORANSON | 0 | 16 | 16
IH2-010 | select and test concept(s) | 0 |  |  | 2006-10-02 | 14 | 1421 | IH2 |  | ORNLEM | GORANSON | 0 | 0 | 0
IH2-015 | Finalize / select design (config and materials | 50 | 2006-08-21 |  | 2006-10-30 | 14 | 1421 | IH2 |  | ORNLEM | GORANSON | 0 | 120 | 120
IH3-010 | Finalize concept | 10 | 2006-09-05 |  | 2006-09-18 | 14 | 1421 | IH3 |  | ORNLEM | GORANSON | 0 | 40 | 40
IH3-020 | Prepare tooling specs, drawings | 30 | 2006-09-19 |  | 2006-10-30 | 14 | 1421 | IH3 |  | ORNLEM | GORANSON | 0 | 20 | 20
172-031.1 | Title III engr | 350 | 2005-10-01 | A | 2007-03-01 | 14 | 1411 | 14T | 10 | EA//EM | HEITZENROED | 376.96 | 640 | 263.04
1416A-105 | Top level models and drawings | 127 | 2006-03-03 | A | 2006-08-30 | 14 | 1416 | DWTA | 01 | ORNLEM | LOVETT | 32 | 40 | 8
1416A-153 | Lead Terminals-Splice Plates | 86 | 2006-05-01 | A | 2006-08-30 | 14 | 1416 | DWTA | 02 | ORNLEM | LOVETT | 10 | 20 | 10
1416A-201 | Coil Post VPI mods-Studs Removed | 177 | 2005-12-03 | A | 2006-08-18 | 14 | 1416 | DWTA | 02 | ORNLEM | LOVETT | 16 | 20 | 4
1416A-205 | Coil Post VPI mods-Clamp Arrangement | 177 | 2005-12-03 | A | 2006-08-18 | 14 | 1416 | DWTA | 02 | ORNLEM | LOVETT | 32 | 40 | 8
1416A-221 | I&C-Strain Gages and T/C | 148 | 2006-03-03 | A | 2006-09-29 | 14 | 1416 | DWTA | 02 | ORNLEM | LOVETT | 10 | 20 | 10
1416A-225 | I&C-Rogowski Coils | 147 | 2006-03-03 | A | 2006-09-28 | 14 | 1416 | DWTA | 02 | ORNLEM | LOVETT | 12 | 40 | 28
1416A-233 | Coil-to-Coil -Current Feed Insul, Covers | 5 | 2006-09-15 |  | 2006-09-21 | 14 | 1416 | DWTA | 02 | ORNLEM | LOVETT | 0 | 20 | 20
1416A-237 | Coil-to-Coil -Windings Insul Blanket | 63 | 2006-07-03 | A | 2006-09-29 | 14 | 1416 | DWTA | 02 | ORNLEM | LOVETT | 10 | 20 | 10
1416A-241 | Coil-to-Coil -Bushing Installation | 5 | 2006-09-15 |  | 2006-09-21 | 14 | 1416 | DWTA | 02 | ORNLEM | LOVETT | 0 | 20 | 20
1416B-221 | I&C-Strain Gages and T/C | 5 | 2006-08-28 |  | 2006-09-01 | 14 | 1416 | DWTB |  | ORNLEM | LOVETT | 0 | 19.99 | 19.99
1416B-225 | I&C-Rogowski Coils | 5 | 2006-09-05 |  | 2006-09-11 | 14 | 1416 | DWTB |  | ORNLEM | LOVETT | 0 | 40 | 40
1416B-233 | Coil-to-Coil -Current Feed Insul, Covers | 5 | 2006-08-04 |  | 2006-08-10 | 14 | 1416 | DWTB |  | ORNLEM | LOVETT | 0 | 19.99 | 19.99
1416B-237 | Coil-to-Coil -Windings Insul Blanket | 5 | 2006-08-11 |  | 2006-08-17 | 14 | 1416 | DWTB |  | ORNLEM | LOVETT | 0 | 19.99 | 19.99
1416B-241 | Coil-to-Coil -Bushing Installation | 5 | 2006-08-18 |  | 2006-08-24 | 14 | 1416 | DWTB |  | ORNLEM | LOVETT | 0 | 19.99 | 19.99
1416B-201 | Coil Post VPI mods-Studs Removed | 148 | 2006-03-03 | A | 2006-09-29 | 14 | 1416 | DWTB | 00 | ORNLEM | LOVETT | 9.995 | 19.99 | 9.995
1416B-205 | Coil Post VPI mods-Clamp Arrangement | 148 | 2006-03-03 | A | 2006-09-29 | 14 | 1416 | DWTB | 00 | ORNLEM | LOVETT | 20 | 40 | 20
1416B-105 | Top level models and drawings | 118 | 2006-03-11 | A | 2006-08-25 | 14 | 1416 | DWTB | 10 | ORNLEM | LOVETT | 20 | 40 | 20
1416B-153 | Lead Terminals-Splice Plates | 5 | 2006-08-01 |  | 2006-08-07 | 14 | 1416 | DWTB | 10 | ORNLEM | LOVETT | 0 | 19.99 | 19.99
IH4-020 | Prepare dwgs and release | 30 | 2006-09-12 |  | 2006-10-23 | 14 | 1421 | IH4 |  | ORNLEM | LOVETT | 0 | 240 | 240
IH5-020 | Finish 3-coil, 6 coil, and 18 coil top assembl | 20 | 2006-11-20 |  | 2006-12-19 | 14 | 1421 | IH5 |  | ORNLEM | LOVETT | 0 | 160 | 160
IH6-020 | Prepare dwgs and release | 25 | 2006-10-09 |  | 2006-11-10 | 14 | 1421 | IH6 |  | ORNLEM | LOVETT | 0 | 80 | 80
124-130 | VV NB port cover Fabrication (for 3 inconnel | 65 | 2007-08-03 |  | 2007-11-02 | 12 | 1204 | 124P | 22 | 41 | M&S | 0 | 59.67 | 59.67
1421-410 | Bid, Award, Procure or Fab Bladders | 35 | 2006-12-21 |  | 2007-02-15 | 14 | 1431 | IH2 | 25 | 48 | M&S | 0 | 60 | 60
1421-210 | Bid, Award, Procure Shear plate and shims | 60 | 2006-10-24 |  | 2007-01-25 | 14 | 1431 | IH4 | 25 | 48 | M&S | 0 | 138 | 138
1421-411 | Deliverhardware for inboard joint friciton | 60 | 2006-10-24 |  | 2007-01-25 | 14 | 1431 | IH4 | 25 | 48 | M&S | 0 | 52 | 52
1421-110 | Bid, Award, Procure stud, bushing, sperical wa | 50 | 2006-11-13 |  | 2007-01-31 | 14 | 1431 | IH5 | 25 | 48 | M&S | 0 | 449 | 449
IH1-020 | Prepare dwgs and release | 35 | 2006-09-19 |  | 2006-11-06 | 14 | 1421 | IH1 |  | ORNLEM | MCGINNIS | 0 | 120 | 120
IH2-025 | Prepare dwgs and release | 35 | 2006-10-31 |  | 2006-12-20 | 14 | 1421 | IH2 |  | ORNLEM | MCGINNIS | 0 | 200 | 200
IH5-020 | Finish 3-coil, 6 coil, and 18 coil top assembl | 20 | 2006-11-20 |  | 2006-12-19 | 14 | 1421 | IH5 |  | ORNLEM | MCGINNIS | 0 | 160 | 160
1403-40.2Z | Update nonlinear winding pack analysis | 560 | 2004-08-02 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | 41MYATT | MYATT | 4.5 | 5 | 0.5
1403-40.2Z | Update nonlinear winding pack analysis | 560 | 2004-08-02 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | ORNLEM | NELSON | 3.6 | 4 | 0.4
0191-6 | LOE-FY06 WBS 191 | 249 | 2005-10-03 | A | 2006-09-29 | 19 | 1901 | 191 | 02 | ORNLEM | NELSON | 909.7 | 1100 | 190.3
0191-6X | LOE-FY07 WBS 191 | 247 | 2006-10-03 |  | 2007-09-27 | 19 | 1901 | 191 | 02 | ORNLEM | NELSON | 0 | 1100 | 1100
0191-7 | LOE-FY08 WBS 191 | 247 | 2007-10-03 |  | 2008-09-29 | 19 | 1901 | 191 | 02 | ORNLEM | NELSON | 0 | 488 | 488
191-8 | LOE-FY089 WBS 191 | 130 | 2008-10-03 |  | 2009-04-15 | 19 | 1901 | 191 | 02 | ORNLEM | NELSON | 0 | 244 | 244
TITLE3W | Titel III Design ORNL- Component Fab & WINDING | 534 | 2005-10-10 | A | 2007-11-26 | 14 | 1451 | LABR | 51 | ORNL35 | TRAVEL | 15.04 | 40 | 24.96
1203-902 | **dummy task ECP45 ETC update hours | 94 | 2006-04-01 | A | 2006-08-14 | 12 |  | 12FD | 03 | ORNLEM | ORNLEM | 214.56 | 240 | 25.44
1203-241 | Check FMECA Analyses | 238 | 2005-09-01 | A | 2006-08-14 | 12 | 1203 | 12FD | 04 | ORNLEM | ORNLEM | 38 | 40 | 2
1203-801 | Issue VV FP final assy dwg | 197 | 2005-11-01 | A | 2006-08-16 | 12 | 1203 | 12FD | 07 | ORNLEM | ORNLEM | 38 | 40 | 2
1203-820 | BOM for all VV parts | 220 | 2005-10-03 | A | 2006-08-18 | 12 | 1203 | 12FD | 08 | ORNLEM | ORNLEM | 28.5 | 30 | 1.5
1203-803 | Issue VV final assy dwg | 83 | 2006-05-01 | A | 2007-01-31 | 12 | 1203 | 12FD | 10 | ORNLEM | ORNLEM | 24 | 40 | 16
1203-804 | Issue VV assy specification | 13 | 2006-12-01 |  | 2006-12-19 | 12 | 1203 | 12FD | 11 | ORNLEM | ORNLEM | 0 | 40 | 40
1203-802 | Issue spacer field machining dwgs | 171 | 2006-01-01 | A | 2007-09-28 | 12 | 1203 | 12FD | 12 | ORNLEM | ORNLEM | 32 | 40 | 8
1403-223C | Finish Top level coil assembly-Type C | 381 | 2005-03-01 | A | 2006-08-31 | 14 | 1403 | TCCO | 96 | ORNLEM | ORNLEM | 290.7 | 323 | 32.3
1403-224C | Finish VPI mold assembly-Type C | 381 | 2005-03-01 | A | 2006-08-31 | 14 | 1403 | TCCO | 96 | ORNLEM | ORNLEM | 108 | 120 | 12
1403-50A | Check inductance calculation | 43 | 2006-10-02 |  | 2006-12-01 | 14 | 1403 | TCCO | 97 | ORNLEM | ORNLEM | 0 | 40 | 40
1416B-205A | Coil Post VPIU mods cooling/electrical | 9 | 2006-08-01 |  | 2006-08-11 | 14 | 1416 | DWTB |  | ORNLEM | ORNLEM | 0 | 40 | 40
COILTESTA | Coil testing-Qualify optical strain gages | 21 | 2006-12-04 |  | 2007-01-09 | 14 | 1465 |  | 00 | ORNLEM | ORNLEM | 0 | 437 | 437
COILTESTB | Document Report | 21 | 2007-01-10 |  | 2007-02-07 | 14 | 1465 |  | 00 | ORNLEM | ORNLEM | 0 | 175 | 175
163.001 | Title I design WBS 163 Coil protection | 65 | 2007-10-01 |  | 2008-01-10 | 16 | 1601 | 163 |  | R///RM2 | R///RM2 | 0 | 80 | 80
163.011 | Title II design WBS 163 Coil protection | 40 | 2008-01-11 |  | 2008-03-06 | 16 | 1601 | 163 |  | R///RM2 | R///RM2 | 0 | 80 | 80
172-031.1 | Title III engr | 350 | 2005-10-01 | A | 2007-03-01 | 14 | 1411 | 14T | 10 | 35 | TRAVEL | 8.246 | 14 | 5.754
123-037 | Fabricate and Deliver H/C Tubing WBS 123 | 20 | 2006-10-02 |  | 2006-10-27 | 12 | 1204 | 123 | 35 | 41 | M&S | 0 | 30 | 30
1403-206C | Finish Cooling, Electr Schematic Dwgs - Type C | 381 | 2005-03-01 | A | 2006-08-31 | 14 | 1403 | TCCO | 96 | ORNLEM | WILLIAMSON | 36 | 40 | 4
1403-40.2Z | Update nonlinear winding pack analysis | 560 | 2004-08-02 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | ORNLEM | WILLIAMSON | 36 | 40 | 4
1403-42H | calculate EM loads at leads | 288 | 2005-09-01 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | ORNLEM | WILLIAMSON | 42 | 60 | 18
1403-47A | Update,review & approve FMECA | 271 | 2005-09-26 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | ORNLEM | WILLIAMSON | 4 | 40 | 36
1403-60C | Finish Update design basis document | 374 | 2005-05-02 | A | 2007-01-02 | 14 | 1403 | TCCO | 97 | ORNLEM | WILLIAMSON | 48 | 80 | 32
1416A-249 | -Type-A Coil Asm Specification | 86 | 2006-05-01 | A | 2006-08-30 | 14 | 1416 | DWTA | 02 | ORNLEM | WILLIAMSON | 32 | 40 | 8
1416A-253 | -Review and Approve Type-A Spec | 5 | 2006-08-31 |  | 2006-09-07 | 14 | 1416 | DWTA | 02 | ORNLEM | WILLIAMSON | 0 | 20 | 20
1416A-257 | -Update Coil Fab Procedures | 5 | 2006-08-31 |  | 2006-09-07 | 14 | 1416 | DWTA | 02 | ORNLEM | WILLIAMSON | 0 | 20 | 20
1416A-261 | -Prepare for FDR | 5 | 2006-08-31 |  | 2006-09-07 | 14 | 1416 | DWTA | 02 | ORNLEM | WILLIAMSON | 0 | 40 | 40
1416B-249 | -Type-B Coil Asm Specification | 5 | 2006-09-01 |  | 2006-09-08 | 14 | 1416 | DWTB |  | ORNLEM | WILLIAMSON | 0 | 40 | 40
1416B-253 | -Review and Approve Type-B Spec | 5 | 2006-09-11 |  | 2006-09-15 | 14 | 1416 | DWTB |  | ORNLEM | WILLIAMSON | 0 | 19.99 | 19.99
1416B-257 | -Update Coil Fab Procedures | 5 | 2006-09-18 |  | 2006-09-22 | 14 | 1416 | DWTB |  | ORNLEM | WILLIAMSON | 0 | 19.99 | 19.99
1416B-261 | -Prepare and Conduct FDR | 5 | 2006-09-25 |  | 2006-09-29 | 14 | 1416 | DWTB |  | ORNLEM | WILLIAMSON | 0 | 40 | 40
1416B-265 | -Resolve FDR Comments | 10 | 2007-01-03 |  | 2007-01-16 | 14 | 1416 | DWTB |  | ORNLEM | WILLIAMSON | 0 | 70 | 70
172-031.1 | Title III engr | 350 | 2005-10-01 | A | 2007-03-01 | 14 | 1411 | 14T | 10 | ORNLEM | WILLIAMSON | 63.023 | 107 | 43.977
TITLE3W | Titel III Design ORNL- Component Fab & WINDING | 534 | 2005-10-10 | A | 2007-11-26 | 14 | 1451 | LABR | 51 | ORNLEM | WILLIAMSON | 341.6336 | 908.6 | 566.9664
IH1-005 | review requirements, as-built casting features | 15 | 2006-08-28 |  | 2006-09-18 | 14 | 1421 | IH1 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH1-010 | obtain results from mockup test | 0 |  |  | 2006-09-18 | 14 | 1421 | IH1 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH1-015 | Review for approval to proceed | 0 |  |  | 2006-09-18 | 14 | 1421 | IH1 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH1-020 | Prepare dwgs and release | 35 | 2006-09-19 |  | 2006-11-06 | 14 | 1421 | IH1 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH1-025 | Issue dwgs for Fabrication | 0 |  |  | 2006-11-06 | 14 | 1421 | IH1 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH2-005 | review and finalize structural requirements | 25 | 2006-08-28 |  | 2006-10-02 | 14 | 1421 | IH2 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH2-010 | select and test concept(s) | 0 |  |  | 2006-10-02 | 14 | 1421 | IH2 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH2-015 | Finalize / select design (config and materials | 50 | 2006-08-21 |  | 2006-10-30 | 14 | 1421 | IH2 |  | ORNLEM | WILLIAMSON | 0 | 40 | 40
IH2-020 | Review for approval to proceed | 0 |  |  | 2006-10-30 | 14 | 1421 | IH2 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH2-025 | Prepare dwgs and release | 35 | 2006-10-31 |  | 2006-12-20 | 14 | 1421 | IH2 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH2-030 | Issue dwgs for Fabrication | 0 |  |  | 2006-12-20 | 14 | 1421 | IH2 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH3-005 | review and finalize structural requirements | 15 | 2006-08-28 |  | 2006-09-18 | 14 | 1421 | IH3 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH3-010 | Finalize concept | 10 | 2006-09-05 |  | 2006-09-18 | 14 | 1421 | IH3 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH3-015 | Review for approval to proceed | 0 |  |  | 2006-09-18 | 14 | 1421 | IH3 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH3-020 | Prepare tooling specs, drawings | 30 | 2006-09-19 |  | 2006-10-30 | 14 | 1421 | IH3 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH3-025 | Issue dwgs for Procuremenet/ Fabrication | 0 |  |  | 2006-10-30 | 14 | 1421 | IH3 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH4-005 | Complete testing | 20 | 2006-08-28 |  | 2006-09-25 | 14 | 1421 | IH4 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH4-010 | Finalize design, select material | 10 | 2006-09-05 |  | 2006-09-18 | 14 | 1421 | IH4 |  | ORNLEM | WILLIAMSON | 0 | 40 | 40
IH4-015 | Review for approval to prceed | 0 |  |  | 2006-09-25 | 14 | 1421 | IH4 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH4-020 | Prepare dwgs and release | 30 | 2006-09-12 |  | 2006-10-23 | 14 | 1421 | IH4 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH4-025 | Issue dwgs for Fabrication | 0 |  |  | 2006-10-23 | 14 | 1421 | IH4 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH5-005 | Identify all stud, bushing, sperical washer, i | 20 | 2006-10-09 |  | 2006-11-03 | 14 | 1421 | IH5 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH5-010 | Prepare advanced procurement dwgs calling out | 20 | 2006-10-16 |  | 2006-11-10 | 14 | 1421 | IH5 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH5-015 | Issue specs/dwgs for procurement (studs, bushi | 0 |  |  | 2006-11-10 | 14 | 1421 | IH5 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH5-020 | Finish 3-coil, 6 coil, and 18 coil top assembl | 20 | 2006-11-20 |  | 2006-12-19 | 14 | 1421 | IH5 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH5-025 | Develop as-built model and drawing format | 20 | 2006-12-06 |  | 2007-01-10 | 14 | 1421 | IH5 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH5-030 | Complete assembly spec | 15 | 2006-12-13 |  | 2007-01-10 | 14 | 1421 | IH5 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH6-005 | Finalize requirements | 20 | 2006-09-11 |  | 2006-10-06 | 14 | 1421 | IH6 |  | ORNLEM | WILLIAMSON | 0 | 16 | 16
IH6-010 | finalize design | 15 | 2006-09-18 |  | 2006-10-06 | 14 | 1421 | IH6 |  | ORNLEM | WILLIAMSON | 0 | 16 | 16
IH6-015 | Review for approval to proceed | 0 |  |  | 2006-10-06 | 14 | 1421 | IH6 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH6-020 | Prepare dwgs and release | 25 | 2006-10-09 |  | 2006-11-10 | 14 | 1421 | IH6 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH6-025 | Issue dwgs for Fabrication | 0 |  |  | 2006-11-10 | 14 | 1421 | IH6 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH1-030 | Bid, Award, Procure or Fabricate | 60 | 2006-11-07 |  | 2007-02-08 | 14 | 1431 | IH1 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH1-035 | Receive and inspect 3 point positioning hardwa | 0 |  |  | 2007-02-08 | 14 | 1431 | IH1 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH2-040 | Receive and inspect Bladders | 0 |  |  | 2007-02-15 | 14 | 1431 | IH2 | 26 | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH3-030 | Bid, Award, Procure or Fab Bolt Reaming | 60 | 2006-10-31 |  | 2007-02-01 | 14 | 1431 | IH3 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH3-035 | Receive and inspect Bolt Reaming | 0 |  |  | 2007-02-01 | 14 | 1431 | IH3 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH4-035 | Receive and inspect Shear plate and shims | 0 |  |  | 2007-01-25 | 14 | 1431 | IH4 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH5-040 | Receive and inspect stud, bushing, sperical wa | 0 |  |  | 2007-01-31 | 14 | 1431 | IH5 | 26 | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH6-030 | Bid, Award, Procure or Fab Other insulation | 50 | 2006-11-13 |  | 2007-01-31 | 14 | 1431 | IH6 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
IH6-035 | Receive and inspect Other insulation over wing | 0 |  |  | 2007-01-31 | 14 | 1431 | IH6 |  | ORNLEM | WILLIAMSON | 0 | 0 | 0
191-001 | Title I design WBS 161 LN2 manifolds&piping | 65 | 2007-07-02 |  | 2007-10-02 | 16 | 1601 | 161 |  | ORNLEM | WILLIAMSON | 0 | 251 | 251
191-011 | Title II design WBS 161 LN2 manifolds&piping | 60 | 2007-10-03 |  | 2008-01-07 | 16 | 1601 | 161 |  | ORNLEM | WILLIAMSON | 0 | 503 | 503
191-031 | Title III engr WBS 161 | 280 | 2008-01-08 |  | 2009-02-18 | 16 | 1601 | 161 |  | ORNLEM | WILLIAMSON | 0 | 86 | 86
132-000 | PDR #17 & 25 | 325 | 2007-07-02 |  | 2008-10-16 | 16 | 1601 | 162 | 01 | ORNLEM | WILLIAMSON | 0 | 20 | 20
132-001 | Title I design WBS 162 Coil leads | 130 | 2007-07-02 |  | 2008-01-14 | 16 | 1601 | 162 | 01 | ORNLEM | WILLIAMSON | 0 | 869 | 869
132-011 | Title II design WBS 162 Coil leads | 130 | 2008-01-15 |  | 2008-07-16 | 16 | 1601 | 162 | 01 | ORNLEM | WILLIAMSON | 0 | 869 | 869
132-015 | Title III design WBS 162 Coil leads | 60 | 2008-07-17 |  | 2008-10-09 | 16 | 1601 | 162 | 01 | ORNLEM | WILLIAMSON | 0 | 98 | 98
163.001 | Title I design WBS 163 Coil protection | 65 | 2007-10-01 |  | 2008-01-10 | 16 | 1601 | 163 |  | ORNLEM | WILLIAMSON | 0 | 82 | 82
163.011 | Title II design WBS 163 Coil protection | 40 | 2008-01-11 |  | 2008-03-06 | 16 | 1601 | 163 |  | ORNLEM | WILLIAMSON | 0 | 82 | 82

## ornl manpower profile
ACC | ACCOUNT TITLE | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08
| COLE | 1.8 | 1.3 | 1.1 | 0.5 | 0.4 | 0.5 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.2 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2
| FREUDENBERG | 0.2 | 0.9 | 0.2 | 0.2 | 0.1 | 0
| GORANSON | 0.6 | 1.1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LOVETT | 1.2 | 1.5 | 1.1 | 0.5 | 0.7
| MCGINNIS |  | 0.2 | 0.5 | 1.2 | 1.2
| NELSON | 0.6 | 0.6 | 0.6 | 0.6 | 0.4 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5 | 0.3 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2
| WILLIAMSON | 0.5 | 1.9 | 0.6 | 0.4 | 0.4 | 0.7 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 1.6 | 1.8 | 1.5 | 2.5 | 2.2 | 1.5 | 1.4 | 1.2 | 1 | 1 | 0.9 | 0.9 | 0.6 | 0.3 | 0.3
| x unnamed | 0.7 |  | 0.1 | 0.1 | 2.2 | 1.7 | 0.3 | [5 empty] | 0 | 0
Total
| total | 5.6 | 7.5 | 4.7 | 3.5 | 5.4 | 3.5 | 1.5 | 1.2 | 1.2 | 1.2 | 1.2 | 2.6 | 2.8 | 2.2 | 3.1 | 2.7 | 1.9 | 2 | 1.8 | 1.6 | 1.6 | 1.5 | 1.5 | 1.2 | 0.9 | 0.7