## Baseline Reconciliation
NCSX EAC - Reconciliation Detail
| WBS II |  | JOB | COST TO DATE 4/1/03 - 4/30/07 |  | ETC 5/1/07 THROUGH COMPLETION |  |  |  |  | TOTAL |  | ecp31 | deltas
[6 empty] | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | ETC | TOTAL EAC
| 12 - Vacuum Vessel Systems | Phil | 1201 - Vacuum Vessel Prelim Dsn | 424 | [6 empty] | 0 | 424 | 424 | 0 | 0% | 1201
|  | Phil | 1202 - Vacuum Vessel R&D | 1770.9 | [6 empty] | 0 | 1770.9 | 1791 | -20.1 | -1.122% | 1202
|  | Phil | 1203 - Vacuum Vessel Final Dsn | 1217 | [6 empty] | 0 | 1217 | 944 | 273 | 28.92% | 1203
1204-VV Sys Procurements (non VVSA) |  | Larry | 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 535.9 |  | 47 | 162 | 1 | 198 | 0 | 408 | 943.9 | 557 | 386.9 | 69.46% | 1204
|  | Phil | 1206 - VV Field Weld Joint R&D | 15.954 | [6 empty] | 0 | 15.954 | 74 | -58.046 | -78.44% | 1206
|  | Larry | 1250 - Vacuum Vessel Fabrication | 5788.9 |  | -252 | 0 | 0 | 0 | 0 | -252 | 5536.9 | 5741 | -204.1 | -3.555% | 1250
|  |  | Subtotal | 9752.654 |  | -205 | 162 | 1 | 198 | 0 | 156 | 9908.654 | 9531 | 377.654 | 3.962%
[14 empty] | 0 | #DIV/0!
| 13 - Conventional Coils | Phil | 1301 - TF Design | 970.1 | [6 empty] | 0 | 970.1 | 837 | 133.1 | 15.9% | 1301
1302 - PF Design |  | Phil | 1302 - PF Design -KALISH | 19.338 |  | 44 | 213 | 0 | 0 | 0 | 257 | 276.338 | 253 | 23.338 | 9.225% | 1302
|  | Phil | 1303 - Central Solenoid Support Design | 154.9 | [6 empty] | 0 | 154.9 |  | 154.9 | #DIV/0!
|  | Phil | 1350 - TF Coil Fabr Prep | 535.99 | [6 empty] | 0 | 535.99 | 400 | 135.99 | 34% | 1350
|  | Phil | 1351 - TF Coil Fabr Supplies | 482.959 | [6 empty] | 0 | 482.959 | 1318 | -835.041 | -63.36% | 1351
|  | Phil | 1352 - PF Coil Procurement-KALISH |  |  | 0 | 968 | 634 | 28 | 0 | 1630 | 1630 | 1362 | 268 | 19.68% | 1352
|  | Phil | 1353 - CS Structure Procurement-DAHLGREN |  |  | 0 | 0 | 78 | 259 | 0 | 337 | 337 | 270 | 67 | 24.81% | 1353
|  | Phil | 1354 - Trim Coil Design &Procurement-KALISH |  |  | 0 | 0 | 162 | 0 | 0 | 162 | 162 | 258 | -96 | -37.21% | 1354
|  | Phil | 1355 - WBS 13 I&C Proc and Coil Assy-KALISH |  |  | 0 | 32 | 39 | 2 | 0 | 73 | 73 | 92 | -19 | -20.65% | 1355
|  | Phil | 1361 - TF Fabrication-KALISH | 1062.999 | (1) | 228 | 775 | 0 | 0 | 0 | 1003 | 2065.999 |  | 2065.999 | #DIV/0!
|  |  | Subtotal | 3226.286 |  | 272 | 1988 | 913 | 289 | 0 | 3462 | 6688.286 | 4790 | 1898.286 | 39.63%
[14 empty] | 0 | #DIV/0!
| 14 - Modular Coils | Phil | 1401 - Mod Coil Prel.Dsn | 304.5 | [6 empty] | 0 | 304.5 | 303 | 1.5 | 0.495% | 1401
|  | Phil | 1402 - Mod.Coil Analyses | 239.14 | [6 empty] | 0 | 239.14 | 239 | 0.14 | 0.05858% | 1402
|  | Phil | 1403 modular coil winding form design | 3310.9 | [6 empty] | 0 | 3310.9 | 3149 | 161.9 | 5.141% | 1403
|  | Phil | 1404-MCWF R&D & 1st Prod Casting | 2554.9 |  | -36 | 0 | 0 | 0 | 0 | -36 | 2518.9 | 2534 | -15.1 | -0.5959% | 1404
|  | Phil | 1405-Mod Coil Winding R&D Prep | 168 | [6 empty] | 0 | 168 | 168 | 0 | 0% | 1405
|  | Phil | 1406 - Mod. Coil Winding Facility | 2263 | [6 empty] | 0 | 2263 | 2214 | 49 | 2.213% | 1406
|  | Phil | 1407 -Mod Coil Winding Facility | 2569 | [6 empty] | 0 | 2569 | 2523 | 46 | 1.823% | 1407
1408-Mod Coil Winding Supplies |  | Larry | 1408 - MC Winding Supplies-CHRZANOWSKI | 2353 |  | 178 | 172 | 0 | 0 | 0 | 350 | 2703 | 1836 | 867 | 47.22% | 1408
|  | Phil | 1409 - Mod. Coil Test Stand | 832.9 | [6 empty] | 0 | 832.9 | 488 | 344.9 | 70.68% | 1409
|  | Phil | 1410 MC Twisted Racetrack Fabr | 1049.908 | [6 empty] | 0 | 1049.908 | 799 | 250.908 | 31.4% | 1410
1411-MCWF Fabrication S005242 |  | Phil | 1411 - MCWF Fabr. S005242-HEITZENROEDER | 9965 |  | -80 | 0 | 0 | 0 | 0 | -80 | 9885 | 8329 | 1556 | 18.68% | 1411
|  | Phil | 1412 - Complete Winding Facilities | 540.732 | [6 empty] | 0 | 540.732 | 310 | 230.732 | 74.43% | 1412
|  | Phil | 1413 - Mod Coil Fracture Analysis | 27.819 | [6 empty] | 0 | 27.819 | 23 | 4.819 | 20.95% | 1413
|  | Phil | 1414 - Coil Testing | 638.674 | [6 empty] | 0 | 638.674 |  | 638.674 | #DIV/0!
|  | Phil | 1415 - Dimensional Control Testing | 24.038 | [6 empty] | 0 | 24.038 |  | 24.038 | #DIV/0!
Mod Coil Design 1416 Coil Design, Job 1421 Interface design |  | Phil | 1416 &1421 - Mod Coil Interface Design-WILLIAMSON | 1108.49 |  | 1066 | 422 | 0 | 0 | 0 | 1488 | 2596.49 |  | 2596.49 | #DIV/0!
Job 1429 Interface R&D/Test |  | Phil | 1429 - MC Interface R&D-GETTELFINGER | 157.99 |  | 118 | 0 | 0 | 0 | 0 | 118 | 275.99 |  | 275.99 | #DIV/0!
|  | Phil | 1419 - Winding Facility Modification | 48.434 | [6 empty] | 0 | 48.434 |  | 48.434 | #DIV/0!
|  | Phil | 1431 - Mod. Coil Interface Hardware-DUDEK |  |  | 362 | 660 | 0 | 17 | 0 | 1039 | 1039 | 86 | 953 | 1108% | 1431
1451 - Mod Coil Winding (incl 1459 punch list and unplanned work) |  | Larry | 1451 - Mod Coil Winding-CHRZANOWSKI | 5982.2 | (1) | 1054 | 1813 | 0 | 0 | 0 | 2867 | 8849.2 | 5091 | 3758.2 | 73.82% | 1451
|  | Larry | 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  |  | 90 | 411 | 0 | 0 | 0 | 501 | 501 |  | 501 | #DIV/0!
|  | Phil | 1460 - 3rd Winding Fixture | 57.337 | [6 empty] | 0 | 57.337 |  | 57.337 | #DIV/0!
|  |  | Subtotal | 34195.962 |  | 2752 | 3478 | 0 | 17 | 0 | 6247 | 40442.962 | 28092 | 12350.962 | 43.97%
[14 empty] | 0 | #DIV/0!
1501 - Structures Design | 15 - Coil Structures | Phil | 1501 - Coil Structures Design-DAHLGREN | 330.94 | (1) | 164 | 22 | 0 | 0 | 0 | 186 | 516.94 | 221 | 295.94 | 133.9% | 1501
1550 - Structures Procurement |  | Phil | 1550 - Coil Struct. Procurement -DAHLGREN | 4.061 |  | 0 | 403 | 673 | 0 | 0 | 1076 | 1080.061 | 1191 | -110.939 | -9.315% | 1550
|  |  | Subtotal | 335.001 |  | 164 | 425 | 673 | 0 | 0 | 1262 | 1597.001 | 1412 | 185.001 | 13.1%
[14 empty] | 0 | #DIV/0!
1601 - Coil Services | 16 - Coil Services | Phil | 1601 - Coil Services Design-GORANSON | 2.614 |  | 6 | 323 | 372 | 160 | 0 | 861 | 863.614 | 1140 | -276.386 | -24.24% | 1601
[14 empty] | 0 | #DIV/0!
1701-Cryostat design | 17 - Cryostat and Base Support Structure | Phil | 1701 - Cryostat Design-GETTLEFINGER | 431.073 |  | 0 | 0 | 207 | 0 | 0 | 207 | 638.073 | 504 | 134.073 | 26.6% | 1701
|  | Phil | 1702 - Base Support Struct Design-DAHLGREN |  |  | 0 | 163 | 0 | 0 | 0 | 163 | 163 | 541 | -378 | -69.87% | 1751
|  | Phil | 1751 - Cryostat Procurement-GETTLEFINGER |  |  | 0 | 0 | 0 | 325 | 0 | 325 | 325 | 315 | 10 | 3.175% | 1752
|  | Phil | 1752 - Base Support Proc-DAHLGREN |  |  | 0 | 61 | 28 | 0 | 0 | 89 | 89 |  | 89 | #DIV/0!
|  |  | Subtotal | 431.073 |  | 0 | 224 | 235 | 325 | 0 | 784 | 1215.073 | 1360 | -144.927 | -10.66%
[14 empty] | 0 | #DIV/0!
| 18 - Field Period Assembly | Larry | 1801-Field Period Assy | 64.38 | [6 empty] | 0 | 64.38 | 61 | 3.38 | 5.541% | 1801
1802 - FP Assy Oversight Support |  | Larry | 1802 - FP Assy Oversight&Support-VIOLA | 986.703 | (1) | 253 | 790 | 858 | 88 | 0 | 1989 | 2975.703 | 1444 | 1531.703 | 106.1% | 1802
1803- FP Assy Tooling/Constructability |  | Larry | 1803 - FP Asy Tooling/Constrblty-BROWN | 1142.2 |  | 131 | 316 | 75 | 0 | 0 | 522 | 1664.2 | 1220 | 444.2 | 36.41% | 1803
|  | Larry | 1804-FP Assy Measurement | 558.937 | [6 empty] | 0 | 558.937 | 502 | 56.937 | 11.34% | 1804
|  | Larry | 1805 - FP Assy Hardware & Fixt Procurement | 6.876 | [6 empty] | 0 | 6.876 |  | 6.876 | #DIV/0!
1806 - FP Assy Specs and Drawings |  | Larry | 1806 - FP Assembly specs | 26.517 |  | 92 | 382 | 40 | 0 | 0 | 514 | 540.517 |  | 540.517 | #DIV/0!
1810 - Field Period Assembly plus 1859 unplanned work |  | Larry | 1810-Field Period Assy -Station 1 2 3 VIOLA | 693.632 | (1) | 1266 | 2353 | 1961 | 165 | 0 | 5745 | 6438.632 | 2203 | 4235.632 | 192.3% | 1810
|  | Larry | 1815 - Field Period Assy |  |  | 0 | 223 | 1017 | 94 | 0 | 1334 | 1334 |  | 1334 | #DIV/0!
|  |  | Subtotal | 3479.245 |  | 1742 | 4064 | 3951 | 347 | 0 | 10104 | 13583.245 | 5430 | 8153.245 | 150.2%
[14 empty] | 0 | #DIV/0!
1901 - Stellarator Core Mngt & Integr | 19 - Stellarator Core Management and Integration | Phil | 1901 - Stellarator Core Mngtt&Integr-COLE | 2128.2 |  | 162 | 408 | 432 | 448 | 170 | 1620 | 3748.2 | 2752 | 996.2 | 36.2% | 1901
|  |  | SUB TOTAL WBS 1 | 53551.035 |  | 4893 | 11072 | 6577 | 1784 | 170 | 24496 | 78047.035 | 54507 | 23540.035 | 43.19%
[14 empty] | 0 | #DIV/0!
[14 empty] | 0 | #DIV/0!
2001-VPS Gas& Cond Sys Oversight | 21 - Fueling Systems | Larry | 2101 - Fueling Systems-BLAMCHARD | 62.893 |  | 0 | 0 | 13 | 56 | 0 | 69 | 131.893 | 151 | -19.107 | -12.65% | 2101
| 22 - Torus Vacuum Pumping Systems | Larry | 2201 - Vacuum Pumping Systems-BLANCHARD |  |  | 0 | 0 | 70 | 102 | 0 | 172 | 172 | 349 | -177 | -50.72% | 2201
| 25 Neutral Beam Refurbishment | Larry | 2501 - Neutral Beam Refurbishment | 284.946 |  | 0 | 0 | 0 | 0 | 0 | 0 | 284.946 | 284 | 0.946 | 0.3331% | 2501
|  |  | SUB TOTAL WBS 2 | 347.839 |  | 0 | 0 | 83 | 158 | 0 | 241 | 588.839 | 784 | -195.161 | -24.89%
[14 empty] | 0 | #DIV/0!
3101 Magnetic Diagnostics | 31 - Magnetic Diagnostics | Larry | 3101 - Magnetic Diagnostics-STRATTON | 611.4 | (1) | 184 | 107 | 0 | 0 | 0 | 291 | 902.4 | 426 | 476.4 | 111.8% | 3101
| 36 - Edge and Divertor Diagnostics | Larry | 3601 - Edge Divertor Diagnostics-STRATTON |  |  | 0 | 0 | 0 | 31 | 0 | 31 | 31 | 46 | -15 | -32.61% | 3601
| 38 - Electron Beam (EB) Mapping | Larry | 3801 - Electron Beam Mapping-STRATTON |  |  | 0 | 0 | 101 | 162 | 0 | 263 | 263 | 310 | -47 | -15.16% | 3801
3901 - Diagnostics sys Integration | 39 - Diagnostics Integration | Larry | 3901 - Diagnostics sys Integration-STRATTON | 342.506 |  | 11 | 29 | 30 | 62 | 0 | 132 | 474.506 | 361 | 113.506 | 31.44% | 3901
|  |  | SUB TOTAL WBS 3 | 953.906 |  | 195 | 136 | 131 | 255 | 0 | 717 | 1670.906 | 1143 | 527.906 | 46.19%
[14 empty] | 0 | #DIV/0!
4101 - AC Power | 41 - AC Power | Al | 4101 - AC Power-RAMAKRISHNAN | 107.351 |  | -104 | 0 | 57 | 102 | 0 | 55 | 162.351 | 430 | -267.649 | -62.24% | 4101
4301 - DC Systems | 43 - DC Systems | Al | 4301 - DC Systems-RAMAKRISHNAN | 369.4 |  | 0 | 11 | 274 | 318 | 0 | 603 | 972.4 | 454 | 518.4 | 114.2% | 4301
4401 - Control & Protection | 44 - Control and protection Systems | Al | 4401 - Control & Protection-RAMAKRISHNAN | 80.521 |  | 0 | 0 | 314 | 770 | 0 | 1084 | 1164.521 | 1309 | -144.479 | -11.04% | 4401
4501 - Power Sys Dsn & Integr | 45 - Power System Design and Integration | Al | 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 161.056 |  | 0 | 0 | 356 | 274 | 53 | 683 | 844.056 | 1107 | -262.944 | -23.75% | 4501
| 46 FCPC Bldg Mods | Al | 4601 - FCPC Bldg Mods | 1.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1 | 0.3 | 30% | 4601
|  |  | SUB TOTAL WBS 4 | 719.628 |  | -104 | 11 | 1001 | 1464 | 53 | 2425 | 3144.628 | 3301 | -156.372 | -4.737%
[14 empty] | 0 | #DIV/0!
| 51 - Network and Fiber Infrastructure | Al | 5101 - Network and Fiber |  |  | 0 | 0 | 7 | 143 | 0 | 150 | 150 |  | 150 | #DIV/0!
| 52 - Central Instrumentation & Control | Al | 5201 - I&C Systems-SICHTA |  |  | 0 | 0 | 81 | 115 | 0 | 196 | 196 | 611 | -415 | -67.92% | 5201
| 53 - Data Acquisition & Facility Computing | Al | 5301 - Data Acquisition-SICHTA |  |  | 0 | 0 | 51 | 114 | 0 | 165 | 165 | 351 | -186 | -52.99% | 5301
| 54 - Facility Timing & Synchronization | Al | 5401 - Facility Timing & |  |  | 0 | 0 | 12 | 193 | 0 | 205 | 205 | 221 | -16 | -7.24% | 5401
| 55 - Real Time Plasma & Power Supply Control Sys | Al | 5501 - Real Time Control |  |  | 0 | 0 | 17 | 112 | 0 | 129 | 129 | 162 | -33 | -20.37% | 5501
| 56 - Central Safety and Interlock Systems | Al | 5601 - Central Safety &Interlock Sys-SICHTA |  |  | 0 | 0 | 12 | 210 | 0 | 222 | 222 | 382 | -160 | -41.88% | 5601
5801 -Central I&C Integr | 58 - Central I&C management and Integration | Al | 5801 - Central I&C Integr& Oversight-SICHTA | 33.022 |  | 7 | 24 | 19 | 19 | 0 | 69 | 102.022 | 323 | -220.978 | -68.41% | 5801
|  |  | SUB TOTAL WBS 5 | 33.022 |  | 7 | 24 | 199 | 906 | 0 | 1136 | 1169.022 | 2050 | -880.978 | -42.97%
[14 empty] | 0 | #DIV/0! |  | 2373
| 61 - Water Systems | Larry | 6163 - Facility Systems Support FY04 | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0% | 6163
|  | Larry | 6101 - Water Systems-DUDEK |  |  | 0 | 0 | 46 | 0 | 0 | 46 | 46 | 95 | -49 | -51.58% | 6101
| 62 - Cryogenic Systems | Larry | 6201 - Cryogenic Systems-DUDEK |  |  | 0 | 0 | 271 | 384 | 0 | 655 | 655 | 463 | 192 | 41.47% | 6201
| 63 - Utility Systems | Larry | 6301 - Utility Systems-DUDEK |  |  | 0 | 0 | 105 | 0 | 0 | 105 | 105 | 109 | -4 | -3.67% | 6301
| 64 - PFC/VV Heating & Cooling (Bakeout) | Larry | 6401 - PFC/VV Htng/Cooling(bakeout)- DUDEK |  |  | 0 | 0 | 107 | 466 | 0 | 573 | 573 |  | 573 | #DIV/0!
|  |  | SUB TOTAL WBS 6 | 24 |  | 0 | 0 | 529 | 850 | 0 | 1379 | 1403 | 691 | 712 | 103%
[14 empty] | 0 | #DIV/0!
| 71 Shield Wall | Larry | 7101 - Shield Wall Modif | 32.605 |  | 0 | 0 | 0 | 0 | 0 | 0 | 32.605 | 80 | -47.395 | -59.24% | 7101
7301 - Platform Design & | 73 - Platform Design & Fabrication | Larry | 7301 - Platform Design & | 75.836 |  | 2 | 5 | 197 | 0 | 0 | 204 | 279.836 | 164 | 115.836 | 70.63% | 7301
7401 - TC Prep & Mach Assy Planning | 74 - Machine Assembly Planning and Oversight | Larry | 7401 - TC Prep & Mach Assy Planning-PERRY | 854.9 |  | -308 | 23 | 615 | 857 | 230 | 1417 | 2271.9 | 1565 | 706.9 | 45.17% | 7401
| 75 - Test Cell and Basement Assembly Operations | Larry | 7501 - Construction Support Crew-PERRY |  |  | 0 | 0 | 336 | 806 | 265 | 1407 | 1407 | 1111 | 296 | 26.64% | 7501
| 75 - Test Cell and Basement Assembly Operations | Larry | 7503 - Machine Assembly (station 6)-PERRY |  |  | 0 | 0 | 1668 | 2205 | 638 | 4511 | 4511 | 1254 | 3257 | 259.7% | 7503
| 76 - Tooling Design & Fabrication | Larry | 7601 - Tooling Design & Fabrication-PERRY |  |  | 0 | 0 | 207 | 205 | 0 | 412 | 412 | 238 | 174 | 73.11% | 7601
|  |  | SUB TOTAL WBS 7 | 963.341 |  | -306 | 28 | 3023 | 4073 | 1133 | 7951 | 8914.341 | 4412 | 4502.341 | 102%
[14 empty] | 0 | #DIV/0!
8101 - Project Management & Control | 81 - Project Management and Control | Jim | 8101 - Project Management & Control-NEILSON | 2822.4 | (1) | 278 | 1034 | 1158 | 1074 | 299 | 3843 | 6665.4 | 4197 | 2468.4 | 58.81% | 8101
8102 - NCSX MIE Management ORNL |  | Jim | 8102 - NCSX MIE Management ORNL-LYON | 553.747 |  | 60 | 159 | 159 | 102 | 19 | 499 | 1052.747 | 387 | 665.747 | 172% | 8102
8202 - Engr Mgmt & Sys Eng Support | 82 - Project Engineering | Phil | 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2646.4 | (1) | 476 | 665 | 663 | 660 | 185 | 2649 | 5295.4 | 2835 | 2460.4 | 86.79% | 8202
8203 - Design Integration |  | Phil | 8203 - Design Integration-BROWN | 985.511 | (1) | 160 | 377 | 376 | 374 | 121 | 1408 | 2393.511 | 1116 | 1277.511 | 114.5% | 8203
8204 - Systems Analysis |  | Phil | 8204 - Systems Analysis-BROOKS | 1276.406 | (1) | 181 | 295 | 293 | 292 | 93 | 1154 | 2430.406 | 601 | 1829.406 | 304.4% | 8204
8205 - Dimensional Control Coord. |  | Phil | 8205 - Dimensional Control Coordin-REIERSEN | 301.9 |  | 102 | 266 | 162 | 56 | 12 | 598 | 899.9 | 332 | 567.9 | 171.1% | 8205
8210 - Project Rebaseline Estimating |  | Phil | 8210 - FY07 Rebaseling tasks | 37.646 |  | 19 | 0 | 0 | 0 | 0 | 19 | 56.646 |  | 56.646 | #DIV/0!
|  | Phil | 8215 Plant Design |  |  | 15 | 32 | 32 | 32 | 10 | 121 | 121 |  | 121 | #DIV/0!
|  | Jim | 8998 - Allocations-STRYKOWSKY | 1415.99 | (1) | 144 | 384 | 406 | 431 | 88 | 1453 | 2868.99 | 1577 | 1291.99 | 81.93% | 8998
| 84 Project Physics | Jim | 8401 - Project Physics | 323.9 | [6 empty] | 0 | 323.9 | 324 | -0.1 | -0.03086% | 8401
|  | Jim | 8402 - Project Physics MIE ORNL | 146.467 | [6 empty] | 0 | 146.467 | 146 | 0.467 | 0.3199% | 8402
| 85 - Integrated Systems Testing | Al | 8501 - Integrated Systems Testing-GENTILE |  |  | 0 | 0 | 276 | 70 | 419 | 765 | 765 | 1189 | -424 | -35.66% | 8501
8998 - Allocations |  |  | SUB TOTAL WBS 8 | 10510.367 |  | 1435 | 3212 | 3525 | 3091 | 1246 | 12509 | 23019.367 | 12704 | 10315.367 | 81.2%
|  |  | TOTAL | 67103.138 |  | 6120 | 14483 | 15068 | 12581 | 2602 | 50854 | 117957.138 | 79592 | 38365.138 | 48.2%
|  |  | DCMA | 75 | [7 empty] | 75
| CC - Contingency |  | Contingency-Project |  |  | 144 | 2205 | 3492 | 4450 | 4089 | 14380 | 14380 | 12804
|  |  | TOTAL | 67178.138 |  | 6264 | 16688 | 18560 | 17031 | 6691 | 65234 | 132412.138 | 92401
|  |  | (1) ADJUSTED FOR PLANNED RETROACTIVE G&A rate reduction in FY07 (estimated) | [10 empty] | 30463.293 |  | 79.4%
|  | Jim |  | 5262.504 |  | 482 | 1577 | 1723 | 1607 | 406 | 5795 | 11057.504 | 6631 | 4426.504
|  | Larry |  | 20428.331 |  | 2748 | 6786 | 7718 | 5881 | 1133 | 24266 | 44694.331 | 25685 | 19009.331
|  | Phil |  | 40659.653 |  | 2987 | 6085 | 4151 | 2653 | 591 | 16467 | 57126.653 | 40736 | 16390.653
|  | AL |  | 752.65 |  | -97 | 35 | 1476 | 2440 | 472 | 4326 | 5078.65 | 6540 | -1461.35
|  |  |  | 67103.138 |  | 6120 | 14483 | 15068 | 12581 | 2602 | 50854 | 117957.138 | 79592 | 38365.138

## BCWS by JOB
RLM | JOB |  | BTC | BCWS May 1,2007 - Aug 30,2007 | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12 | JUN fy12 | JUL fy12 | AUG fy12 | SEP fy12
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON |  | 3844 | 228 | 61 | 54 | 54 | 59 | 49 | 95 | 83 | 62 | 91 | 87 | 87 | 91 | 87 | 87 | 91 | 87 | 87 | 107 | 84 | 79 | 98 | 93 | 102 | 102 | 93 | 102 | 102 | 98 | 98 | 95 | 82 | 69 | 87 | 87 | 100 | 95 | 87 | 95 | 91 | 95 | 91 | 80 | 76 | 64 | 80
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON |  | 497 | 50 | 13 | 12 | 12 | 13 | 11 | 14 | 13 | 10 | 14 | 13 | 13 | 14 | 13 | 13 | 14 | 13 | 13 | 14 | 12 | 11 | 13 | 13 | 14 | 14 | 13 | 14 | 14 | 13 | 13 | 9 | 8 | 7 | 8 | 8 | 9 | 9 | 8 | 9 | 9 | 9 | 9 | 5 | 5 | 4 | 5
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY |  | 1453 | 119 | 30 | 29 | 29 | 31 | 26 | 36 | 31 | 23 | 34 | 32 | 32 | 34 | 32 | 32 | 34 | 32 | 31 | 38 | 30 | 28 | 35 | 33 | 36 | 36 | 33 | 36 | 36 | 35 | 31 | 38 | 33 | 28 | 35 | 35 | 40 | 38 | 35 | 38 | 36 | 38 | 36 | 23 | 22 | 19 | 23 | 1
|  |  | 5794 | 397 | 104 | 95 | 95 | 103 | 86 | 145 | 127 | 95 | 139 | 132 | 132 | 139 | 132 | 132 | 139 | 132 | 131 | 159 | 126 | 118 | 146 | 139 | 152 | 152 | 139 | 152 | 152 | 146 | 142 | 142 | 123 | 104 | 130 | 130 | 149 | 142 | 130 | 142 | 136 | 142 | 136 | 108 | 103 | 87 | 108 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK |  | 409 | 46 |  | 17 | 25 | 4 |  | 27 | 29 | 2 |  |  |  | 30 | 27 | 12 | 12 | 12 | 12 | 1 | [11 empty] | 60 | 88 | 34 | 17
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** |  | -252 | -252 | -162 |  |  | -90
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI |  | 348 | 148 | 17 | 24 | 51 | 56 | 29 | 26 | 22 | 28 | 41 | 35 | 11 | 5 | 3
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK |  | 1039 | 336 | 144 | 7 | 103 | 82 | 27 | 452 | 64 | 22 | 25 | 23 | 20 | 11 | 10 | 10 | 10 | 6 | 6 | [12 empty] | 12 | 4 | 1
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI |  | 2769 | 821 | 237 | 171 | 231 | 182 | 136 | 213 | 188 | 133 | 222 | 211 | 183 | 209 | 193 | 156 | 87 | 16 | 1
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  | 501 | 43 |  | 4 | 19 | 20 | 47 | 57 | 43 | 26 | 42 | 43 | 42 | 26 | 24 | 25 | 26 | 33 | 24
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA |  | 1987 | 210 | 64 | 47 | 47 | 52 | 43 | 79 | 58 | 43 | 63 | 60 | 86 | 71 | 67 | 66 | 68 | 64 | 63 | 89 | 65 | 60 | 74 | 81 | 84 | 83 | 74 | 68 | 62 | 59 | 59 | 61 | 27
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK |  | 522 | 107 |  | 11 | 54 | 42 | 23 | 30 | 24 | 35 | 81 | 46 | 43 | 13 | 9 |  |  |  | 36 | 39 | 31 | 5
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA |  | 5742 | 996 | 190 | 196 | 294 | 316 | 269 | 261 | 179 | 177 | 238 | 185 | 204 | 189 | 177 | 162 | 197 | 186 | 198 | 214 | 183 | 110 | 164 | 250 | 245 | 167 | 161 | 136 | 113 | 108 | 108 | 113 | 52
D - Larry Dudek | Job: 1815 - Field Period Assy |  | 1335 | 0 | [14 empty] | 155 | 55 | 13 | 3 | 30 | 40 | 58 | 49 | 92 | 102 | 112 | 110 | 172 | 123 | 126 | 64 | 31
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD |  | 69 | 0 | [28 empty] | 13 | 21 | 3 | 2 | 3 | 2 | 0 | 2 | 12 | 11
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD |  | 170 | 0 | [20 empty] | 22 | 20 | 25 | 3 | [5 empty] | 0 | 7 | 15 | 19 | 19 | 22 | 16 | 2
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON |  | 290 | 145 | 12 | 15 | 22 | 96 | 37 | 57 | 24 | 17 | 9 | 1
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON |  | 31 | 0 | [29 empty] | 9 | 8 | 1 | 2 | 2 | 7 | 2
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON |  | 263 | 0 | [22 empty] | 25 | 24 | 28 | 24 |  |  |  | 23 | 20 | 17 | 26 | 29 | 33 | 14
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON |  | 133 | 8 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 6 | 5 | 4 | 5 | 5 | 6 | 6 | 5 | 6 | 5 | 6 | 5
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK |  | 46 | 0 | [17 empty] | 13 | 1 | 1 | 2 | 2 | 1 | 5 | 11 | 8 | 2
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER |  | 654 | 0 | [17 empty] | 23 | 18 |  | 59 | 35 | 21 | 23 | 17 |  |  | 30 | 44 | 61 | 57 | 49 | 55 | 42 | 32 | 29 | 26 | 30 | 2 | 1
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK |  | 105 | 0 | [17 empty] | 18 | 18 | 11 | 13 | 10 |  |  | 15 | 16 | 4
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH |  | 573 | 0 | [23 empty] | 7 | 8 | 23 | 24 | 21 | 23 | 25 | 57 | 58 | 73 | 68 | 60 | 57 | 45 | 24
D - Larry Dudek | Job: 7301 - Platform Design & |  | 202 | 0 | [16 empty] | 5 | 43 | 74 | 68 | 12
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY |  | 1416 | -308 | -308 |  |  |  |  | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 | 12 | 5 | 71 | 63 | 68 | 66 | 60 | 66 | 66 | 62 | 61 | 64 | 54 | 45 | 56 | 55 | 86 | 85 | 79 | 85 | 83 | 84 | 81 | 79 | 77 | 70 | 4
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY |  | 1406 | 0 | [20 empty] | 10 | 38 | 42 | 42 | 38 | 42 | 42 | 40 | 42 | 42 | 40 | 44 | 40 | 38 | 83 | 87 | 83 | 87 | 87 | 87 | 87 | 83 | 87 | 91 | 4
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY |  | 4511 | 0 | [18 empty] | 59 | 393 | 369 | 129 | 103 | 102 | 108 | 147 | 75 | 74 | 107 | 243 | 98 | 128 | 224 | 105 | 206 | 295 | 206 | 172 | 181 | 197 | 151 | 248 | 211 | 157 | 23
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY |  | 414 | 0 | [20 empty] | 6 | 24 | 26 | 26 | 24 | 26 | 26 | 25 | 25 | 26 | 23 | 19 | 24 | 24 | 27 | 26 | 24 | 13
|  |  | 24683 | 2300 | 196 | 494 | 848 | 762 | 613 | 1207 | 635 | 486 | 726 | 608 | 593 | 559 | 514 | 435 | 560 | 376 | 362 | 460 | 493 | 695 | 863 | 703 | 735 | 653 | 658 | 669 | 589 | 545 | 610 | 830 | 574 | 417 | 544 | 389 | 562 | 619 | 482 | 428 | 358 | 375 | 324 | 410 | 375 | 318 | 31 | 0 | 0 | 0 | 0 | 0 | 0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH |  | 258 | 14 | 5 |  |  | 9 | 30 | 35 | 25 | 30 | 48 | 32 | 33 | 11
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH |  | 1629 | 0 | [10 empty] | 4 | 20 | 40 | 136 | 173 | 325 | 270 | 183 | 101 | 56 | 63 | 65 | 64 | 69 | 32 | [8 empty] | 2 | 12 | 14
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN |  | 339 | 0 | [23 empty] | 4 | 8 | 16 | 2 | 2 | 47 | 52 | 45 | 38 | 47 | 47 | 31
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH |  | 161 | 0 | [17 empty] | 15 | 15 | 19 | 20 | 7 | 6 | 18 | 16 | 18 | 18 | 9
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH |  | 73 | 0 | [9 empty] | 4 | 4 | 4 | 5 | 3 | 7 | 4 |  | 15 | 12 | 3 | 6 | 4 | [12 empty] | 2
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH |  | 1004 | 168 | 8 | 65 | 60 | 35 | 60 | 61 | 59 | 56 | 59 | 58 | 104 | 57 | 57 | 56 | 103 | 54 | 52
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod |  | -36 | -36 | -36
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER |  | -84 | -84 | 5 | 1 |  | -90
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON |  | 280 | 58 | 12 | 23 | 8 | 15 | 12 | 116 | 56 | 19 | 17 | 2
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON |  | 1208 | 894 | 177 | 276 | 250 | 191 | 102 | 118 | 26 | 19 | 25 | 24
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER |  | 118 | 118 | 30 |  | 51 | 37
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN |  | 186 | 128 | 7 | 31 | 32 | 58 | 36 | 22 | 0
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN |  | 1074 | 0 | [13 empty] | 32 | 109 | 131 | 131 | 143 | 93 | 51 | 63 | 60 | 66 | 66 | 60 | 66 | 3
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON |  | 861 | 6 | 6 | [7 empty] | 28 | 27 | 27 | 28 | 27 | 48 | 31 | 47 | 58 | 77 | 61 | 53 | 26 | 20 | 23 | 23 | 20 | 23 | 23 | 21 | 4 | 42 | 42 | 39 | 34 | 3
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER |  | 207 | 0 | [17 empty] | 6 | 4 | 4 | 10 | 22 | 43 | 44 | 21 | 23 | 23 | 7
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN |  | 164 | 0 | [5 empty] | 43 | 36 | 28 | 41 | 15 | 1
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER |  | 325 | 0 | [29 empty] | 74 | 64 | 54 | 52 | 36 | 31 | 14
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN |  | 91 | 0 | [10 empty] | 1 | 1 | 1 | 6 | 18 | 17 | 18 | 20 | 6 | 1 | 1 | 1 | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs |  | 517 | 67 | 9 | 15 | 17 | 26 | 25 | 28 | 19 | 25 | 37 | 35 | 35 | 36 | 32 | 32 | 33 | 34 | 39 | 19 | 7 | 7 | 7
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE |  | 1618 | 133 | 34 | 32 | 32 | 35 | 29 | 38 | 33 | 25 | 36 | 34 | 34 | 36 | 34 | 34 | 36 | 34 | 33 | 40 | 31 | 30 | 37 | 35 | 38 | 38 | 35 | 38 | 38 | 37 | 33 | 40 | 34 | 29 | 36 | 36 | 42 | 40 | 36 | 40 | 38 | 40 | 38 | 45 | 43 | 37 | 45
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN |  | 2519 | 290 | 82 | 76 | 63 | 69 | 53 | 61 | 53 | 40 | 59 | 56 | 56 | 59 | 56 | 56 | 59 | 56 | 56 | 61 | 48 | 45 | 56 | 53 | 59 | 59 | 53 | 59 | 59 | 56 | 56 | 59 | 51 | 43 | 53 | 53 | 61 | 59 | 53 | 59 | 56 | 59 | 56 | 48 | 46 | 39 | 48 | 2
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN |  | 1412 | 132 | 33 | 32 | 32 | 35 | 29 | 35 | 30 | 23 | 33 | 32 | 32 | 33 | 32 | 32 | 33 | 32 | 32 | 35 | 27 | 26 | 32 | 30 | 33 | 33 | 30 | 33 | 33 | 32 | 32 | 33 | 29 | 24 | 30 | 30 | 35 | 33 | 30 | 33 | 32 | 33 | 32 | 32 | 30 | 26 | 32 | 2
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS |  | 1160 | 148 | 37 | 36 | 36 | 39 | 32 | 27 | 24 | 18 | 26 | 25 | 25 | 26 | 25 | 25 | 26 | 25 | 25 | 27 | 21 | 20 | 25 | 24 | 26 | 26 | 24 | 26 | 26 | 25 | 25 | 26 | 22 | 19 | 24 | 24 | 27 | 26 | 24 | 26 | 25 | 26 | 25 | 25 | 24 | 20 | 25
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS |  | 592 | 84 |  | 27 | 27 | 30 | 18 | 21 | 20 | 15 | 22 | 25 | 35 | 37 | 35 | 18 | 12 | 12 | 12 | 13 | 14 | 14 | 18 | 18 | 16 | 16 | 14 | 11 | 9 | 9 | 9 | 9 | 6 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks |  | 19 | 19 | 15 | 4
H - Phil Heitzenroeder | Job: 8215 Plant Design |  | 129 | 8 |  |  |  | 8 | 7 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3
|  |  | 15824 | 2147 | 424 | 618 | 608 | 497 | 433 | 608 | 384 | 300 | 434 | 372 | 394 | 351 | 347 | 481 | 643 | 774 | 729 | 657 | 442 | 331 | 367 | 342 | 377 | 399 | 316 | 316 | 237 | 201 | 209 | 338 | 295 | 251 | 283 | 238 | 248 | 193 | 150 | 165 | 158 | 165 | 158 | 157 | 150 | 127 | 153 | 4 | 0 | 0 | 0 | 0 | 0
[5 empty] | 82 | 76 | 63 | 69 | 53 | 61 | 53 | 40 | 59
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN |  | 52 | -104 | -104 | [16 empty] | 0 | 0 | 0 | 12 | 11 | 14 | 4 | 3 | 1 | 1 | 3 | 6 | 6 | 4 | 3 | 8 | 27 | 29 | 15 | 6 | 3
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN |  | 604 | 0 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 38 | 31 | 41 | 53 | 18 | 1 | 1 | 1 | 1 | 14 | 74 | 1 | 0 | 62 | 52 | 66 | 66 | 72
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN |  | 1084 | 0 | [21 empty] | 11 | 26 | 33 | 32 | 41 | 42 | 60 | 69 | 103 | 73 | 55 | 67 | 75 | 111 | 97 | 91 | 56 | 31 | 10 | 1
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN |  | 682 | 0 | [17 empty] | 21 | 23 | 20 | 18 | 17 | 37 | 34 | 29 | 37 | 43 | 40 | 37 | 39 | 22 | 18 | 19 | 13 |  |  | 3 | 35 | 33 | 35 | 56 | 53
V - Al vonHalle | Job: 5101 - Network and Fiber |  | 151 | 0 | [26 empty] | 3 | 2 | 2 | 2 | 14 | 14 | 18 | 23 | 32 | 31 | 10
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA |  | 197 | 0 | [22 empty] | 5 | 3 | 2 | 2 | 21 | 25 | 24 | 15 | 6 | 5 | 7 | 9 | 5 | 14 | 20 | 22 | 12
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA |  | 165 | 0 | [24 empty] | 4 | 7 | 11 | 21 | 7 | 7 | 12 | 10 | 12 | 9 | 10 | 13 | 17 | 15 | 10
V - Al vonHalle | Job: 5401 - Facility Timing & |  | 204 | 0 | [26 empty] | 5 | 4 | 3 | 16 | 25 | 24 | 15 | 16 | 32 | 24 | 10 | 15 | 12 | 3
V - Al vonHalle | Job: 5501 - Real Time Control |  | 131 | 0 | [26 empty] | 5 | 7 | 6 | 6 | 8 | 7 | 9 | 14 | 21 | 25 | 9 | 13 | 1
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA |  | 221 | 0 | [25 empty] | 2 | 2 | 3 | 4 | 19 | 20 | 17 | 18 | 18 | 34 | 32 | 29 | 7 | 11 | 5
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA |  | 71 | 5 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE |  | 767 | 0 | [18 empty] | 22 | 32 | 29 | 24 | 21 | 27 | 24 | 27 | 24 | 22 | 26 | 27 | 14 | 20 | 9 | [8 empty] | 116 | 110 | 94 | 99
|  |  | 4329 | -99 | -103 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 61 | 77 | 94 | 114 | 82 | 106 | 104 | 96 | 120 | 173 | 263 | 187 | 242 | 261 | 226 | 250 | 272 | 348 | 253 | 197 | 168 | 112 | 55 | 59 | 169 | 110 | 94 | 99 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 50630 | 4745 | 621 | 1208 | 1552 | 1364
4745
[71 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 10400 | add'l cont
[47 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1300 | 1400 | 1450 | 1500 | 1450 | 1300 | 1100 | 1000 | 900 | 800 | 400 | 200 | #REF! | ETC
|  | ACWP | BTC | BCWS May 1,2007 - Augy 30,2007 | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12
11056.504 | Jim Anderson | 5262.504 | 5794 | 397 | 104 | 95 | 95 | 103 | 86 | 145 | 127 | 95 | 139 | 132 | 132 | 139 | 132 | 132 | 139 | 132 | 131 | 159 | 126 | 118 | 146 | 139 | 152 | 152 | 139 | 152 | 152 | 146 | 142 | 142 | 123 | 104 | 130 | 130 | 149 | 142 | 130 | 142 | 136 | 142 | 136 | 108 | 103 | 87 | 108 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45111.331 | Larry Dudek | 20428.331 | 24683 | 2300 | 196 | 494 | 848 | 762 | 613 | 1207 | 635 | 486 | 726 | 608 | 593 | 559 | 514 | 435 | 560 | 376 | 362 | 460 | 493 | 695 | 863 | 703 | 735 | 653 | 658 | 669 | 589 | 545 | 610 | 830 | 574 | 417 | 544 | 389 | 562 | 619 | 482 | 428 | 358 | 375 | 324 | 410 | 375 | 318 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56483.653 | Phil Heitzeroeder | 40659.653 | 15824 | 2147 | 424 | 618 | 608 | 497 | 433 | 608 | 384 | 300 | 434 | 372 | 394 | 351 | 347 | 481 | 643 | 774 | 729 | 657 | 442 | 331 | 367 | 342 | 377 | 399 | 316 | 316 | 237 | 201 | 209 | 338 | 295 | 251 | 283 | 238 | 248 | 193 | 150 | 165 | 158 | 165 | 158 | 157 | 150 | 127 | 153 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5081.65 | Al vonHalle | 752.65 | 4329 | -99 | -103 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 61 | 77 | 94 | 114 | 82 | 106 | 104 | 96 | 120 | 173 | 263 | 187 | 242 | 261 | 226 | 250 | 272 | 348 | 253 | 197 | 168 | 112 | 55 | 59 | 169 | 110 | 94 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 67103.138 | 50630 | 4745 | 621 | 1208 | 1552 | 1364
4745
117733.138
[5 empty] | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11
|  |  | Jim Anderson | BCWS | 104 | 199 | 294 | 397 | 483 | 628 | 755 | 850 | 989 | 1121 | 1253 | 1392 | 1524 | 1656 | 1795 | 1927 | 2058 | 2217 | 2343 | 2461 | 2607 | 2746 | 2898 | 3050 | 3189 | 3341 | 3493 | 3639 | 3781 | 3923 | 4046 | 4150 | 4280 | 4410 | 4559 | 4701 | 4831 | 4973 | 5109 | 5251 | 5387 | 5495 | 5598 | 5685 | 5793 | 5794 | 5794
|  |  |  | BCWP | 102 | 199 | 294 | 396.9789
|  |  |  | ACWP | 111.7184 | 218.6445 | 309.5976 | 416.8916
[5 empty] | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11
|  |  | Larry Dudek | BCWS | 196 | 690 | 1538 | 2300 | 2913 | 4120 | 4755 | 5241 | 5967 | 6575 | 7168 | 7727 | 8241 | 8676 | 9236 | 9612 | 9974 | 10434 | 10927 | 11622 | 12485 | 13188 | 13923 | 14576 | 15234 | 15903 | 16492 | 17037 | 17647 | 18477 | 19051 | 19468 | 20012 | 20401 | 20963 | 21582 | 22064 | 22492 | 22850 | 23225 | 23549 | 23959 | 24334 | 24652 | 24683 | 24683 | 24683
|  |  |  | BCWP | 122 | 778 | 1447 | 2191.7652
|  |  |  | ACWP | 305.793 | 823.5043 | 1302.9008 | 2004.9938
[5 empty] | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11
|  |  | Phil Heitzeroeder | BCWS | 424 | 1042 | 1650 | 2147 | 2580 | 3188 | 3572 | 3872 | 4306 | 4678 | 5072 | 5423 | 5770 | 6251 | 6894 | 7668 | 8397 | 9054 | 9496 | 9827 | 10194 | 10536 | 10913 | 11312 | 11628 | 11944 | 12181 | 12382 | 12591 | 12929 | 13224 | 13475 | 13758 | 13996 | 14244 | 14437 | 14587 | 14752 | 14910 | 15075 | 15233 | 15390 | 15540 | 15667 | 15820 | 15824 | 15824
|  |  |  | BCWP | 300 | 817 | 1546 | 1938.6461
|  |  |  | ACWP | 317.203 | 705.0554 | 1005.8607 | 1659.2607
[5 empty] | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11
|  |  | Al vonHalle | BCWS | -103 | -102 | -101 | -99 | -98 | -95 | -92 | -90 | -87 | -84 | -81 | -78 | -75 | -72 | -69 | -66 | -63 | -2 | 75 | 169 | 283 | 365 | 471 | 575 | 671 | 791 | 964 | 1227 | 1414 | 1656 | 1917 | 2143 | 2393 | 2665 | 3013 | 3266 | 3463 | 3631 | 3743 | 3798 | 3857 | 4026 | 4136 | 4230 | 4329 | 4329 | 4329
|  |  |  | BCWP | -103 | -102 | -101 | -98.3768
|  |  |  | ACWP | -104.2596 | -104.2596 | -104.3015 | -104.3015
|  |  | TOTAL PROJECT | BCWS | 621 | 1829 | 3381 | 4745 | 5878 | 7841 | 8990 | 9873 | 11175 | 12290 | 13412 | 14464 | 15460 | 16511 | 17856 | 19141 | 20366 | 21703 | 22841 | 24079 | 25569 | 26835 | 28205 | 29513 | 30722 | 31979 | 33130 | 34285 | 35433 | 36985 | 38238 | 39236 | 40443 | 41472 | 42779 | 43986 | 44945 | 45848 | 46612 | 47349 | 48026 | 48870 | 49608 | 50234 | 50625 | 50630 | 50630
|  |  |  | BCWP | 421 | 1692 | 3186 | 4429.0134
|  |  |  | ACWP | 630.4547 | 1642.9445 | 2514.0576 | 3976.8446
671.9424
corrected

## ACWP by JOB
RLM | JOB | ACWP May 1,2007 - Aug 30,2007 |  | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12 | JUN fy12 | JUL fy12 | AUG fy12 | SEP fy12
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON | 212.2788 | 8101 | 55.8777 | 58.9419 | 48.7333 | 48.726
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON | 91.512 |  | 30.964 | 22.991 | 13.862 | 23.695
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY | 113.1008 | 8998 | 24.8767 | 24.9933 | 28.3578 | 34.873
|  | 416.8916 |  | 111.7184 | 106.9261 | 90.9531 | 107.294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 39.6239 | 1204 | 16.0209 | 1.3261 | 5.4769 | 16.8
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -254.4373 | 1250 | -161.88 | 0 | -92.5573
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 88.1534 | 1408 | 23.8679 | 11.6976 | 31.1989 | 21.389
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 191.3229 | 1431 | 144.2801 | 0 | 47.0428
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 900.0867 |  | 283.7075 | 218.7955 | 157.2876 | 240.296
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 213.991 | 1459 | 42.2044 | 55.2785 | 51.7021 | 64.806
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA | 284.5957 | 1802 | 84.3784 | 51.4086 | 66.9277 | 81.881
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 128.1259 | 1803 | 34.185 | 34.0075 | 22.4994 | 37.434
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 566.7311 |  | 106.9026 | 120.8905 | 140.889 | 198.049
D - Larry Dudek | Job: 1815 - Field Period Assy | 0
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD | 0
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON | 111.7126 | 3101 | 27.0665 | 15.8846 | 38.1895 | 30.572
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON | 0
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON | 17.6602 | 3901 | 2.6208 | 4.2019 | 6.7205 | 4.117
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK | 0
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER | 0
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK | 0
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 0
D - Larry Dudek | Job: 7301 - Platform Design & | 0
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -282.5723 | 7401 | -297.561 | 4.2205 | 4.0193 | 6.749
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY | 0
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY | 0
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY | 0
|  | 2004.9938 |  | 305.793 | 517.7113 | 479.3966 | 702.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 13.784 |  | 4.26 | 1.5406 | 1.4053 | 6.578
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH | 0
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN | 0
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH | 0
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH | 185.3505 |  | -6.0157 | 40.395 | 54.4283 | 96.543
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod | -35.1034 | 1404 | -35.9384 | 0 | 0 | 0.835
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -83.2136 | 1411 | 7.495 | 2.0635 | -92.7721
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 68.0759 | 1416 | 12.3179 | 9.522 | 18.891 | 27.345
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 552.1157 | 1421 | 81.6509 | 107.2854 | 109.3563 | 253.823
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER | 80.6372 | 1429 | 29.9725 | 17.1863 | 20.5674 | 12.911
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN | 174.6521 | 1501 | 54.1006 | 47.3749 | 37.1207 | 36.056
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON | 0
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER | 4.3022 | 1701 | -0.23265 | 3.0813 | 1.4536
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN | 0
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs | 2.007 |  |  |  | -0.128 | 2.135
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 96.648 |  | 36.462 | 17.472 | 11.047 | 31.667
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 264.2051 | 8202 | 59.5964 | 58.6317 | 58.6029 | 87.374
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN | 22.052 | 8203 | 5.0798 | 5.2382 | 1.641 | 10.093
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS | 193.3133 | 8204 | 42.5836 | 53.1523 | 47.1084 | 50.469
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS | 81.5541 | 8205 | 17.5068 | 20.0831 | 22.4922 | 21.472
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks | 38.8805 | 8210 | 8.3642 | 4.8261 | 9.5912 | 16.099
H - Phil Heitzenroeder | Job: 8215 Plant Design | 0
|  | 1659.2607 |  | 317.203 | 387.8524 | 300.8052 | 653.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | -104.1027 | 4101 | -104.1027 | 0 | 0
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN | 0
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN | 0
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | -0.19881 | 4501 | -0.15696 | 0 | -0.041849
V - Al vonHalle | Job: 5101 - Network and Fiber | 0
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA | 0
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA | 0
V - Al vonHalle | Job: 5401 - Facility Timing & | 0
V - Al vonHalle | Job: 5501 - Real Time Control | 0
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 0
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE | 0
|  | -104.3015 |  | -104.2596 | 0 | -0.041849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3976.8446 |  | 630.4547 | 1012.4898 | 871.113 | 1462.787
corrected

## BCWP by JOB
RLM | JOB |  | BCWP May 1,2007 - Aug 30,2007 |  | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12 | JUN fy12 | JUL fy12 | AUG fy12 | SEP fy12 | [6 empty] | RLMS | JJJJ | Total
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON |  | 229.1165 | 8101 | 59 | 56 | 54 | [68 empty] | A | 8101 | 229.1165 | X
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON |  | 49.6048 |  | 13 | 12 | 12 | [69 empty] | 8102 | 49.6048 | X
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY |  | 118.2576 | 8998 | 30 | 29 | 29 | [69 empty] | 8998 | 118.2576 | X
|  |  | 396.9789 |  | 102 | 97 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | A Total |  | 396.9789
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 1204 | 68.4894 | 1204 |  | 55 | 9 | [68 empty] | D | 1204 | 68.4894
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | 1250 | -251.6947 | 1250 | -162 |  | -90 | [69 empty] | 1250 | -251.6947
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 1408 | 156.4268 | 1408 | 7 | 33 | 23 | [69 empty] | 1408 | 156.4268
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1431 | 256.8971 | 1431 | 81 | 77 | [70 empty] | 1431 | 256.8971
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1451 | 946.222 |  | 236 | 176 | 299 | [69 empty] | 1451 | 946.222
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 1459 | 44.1632 | 1459 |  | 18 | 14 | [69 empty] | 1459 | 44.1632
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1802 | 210.1107 | 1802 | 64 | 47 | 47 | [69 empty] | 1802 | 210.1107
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 1803 | 64.0883 | 1803 |  | 12 | 42 | [69 empty] | 1803 | 64.0883
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 1810 | 854.5431 |  | 190 | 193 | 267 | [69 empty] | 1810 | 854.5431
D - Larry Dudek | Job: 1815 - Field Period Assy | 1815 | 0 | [73 empty] | 1815 | 0
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD | 2101 | 0 | [73 empty] | 2101 | 0
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 2201 | 0 | [73 empty] | 2201 | 0
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON | 3101 | 138.94 | 3101 | 12 | 42 | 54 | [69 empty] | 3101 | 138.94
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 3601 | 0 | [73 empty] | 3601 | 0
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON | 3801 | 0 | [73 empty] | 3801 | 0
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON | 3901 | 9.3261 | 3901 | 2 | 2 | 2 | [69 empty] | 3901 | 9.3261
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK | 6101 | 0 | [73 empty] | 6101 | 0
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER | 6201 | 0 | [73 empty] | 6201 | 0
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK | 6301 | 0 | [73 empty] | 6301 | 0
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 6401 | 0 | [73 empty] | 6401 | 0
D - Larry Dudek | Job: 7301 - Platform Design & | 7301 | 2.5533 |  |  | 1 | 2 | [69 empty] | 7301 | 2.5533
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 7401 | -308.3 | 7401 | -308 | [71 empty] | 7401 | -308.3
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY | 7501 | 0 | [73 empty] | 7501 | 0
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY | 7503 | 0 | [73 empty] | 7503 | 0
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY | 7601 | 0 | [73 empty] | 7601 | 0
|  |  | 2191.7652 |  | 122 | 656 | 669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | D Total |  | 2185.7585
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 1302 | 47.3325 |  | 5 | [70 empty] | H | 1302 | 47.3325
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH | 1352 | 0 | [73 empty] | 1352 | 0
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN | 1353 | 0 | [73 empty] | 1353 | 0
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH | 1354 | 0 | [73 empty] | 1354 | 0
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 1355 | 0 | [73 empty] | 1355 | 0
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH | 1361 | 199.4121 |  | 4 | 45 | 59 | [69 empty] | 1361 | 199.4121
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod | 1404 | -35.94 | 1404 | -36 | [71 empty] | 1404 | -35.94
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | 1411 | -80.3908 | 1411 | 6 | 4 | -90 | [69 empty] | 1411 | -80.3908
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 1416 | 103.1533 | 1416 | 4 | 29 | 55 | [69 empty] | 1416 | 103.1533
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 1421 | 711.1819 | 1421 | 62 | 167 | 406 | [69 empty] | 1421 | 711.1819
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER | 1429 | 83.2365 | 1429 | 30 |  | 44 | [69 empty] | 1429 | 83.2365
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN | 1501 | 81.9424 | 1501 | 2 | 43 | 30 | [69 empty] | 1501 | 81.9424
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 1550 | 0 | [73 empty] | 1550 | 0
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON | 1601 | 6.2288 |  |  | 6 | [70 empty] | 1601 | 6.2288
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER | 1701 | 0 | 1701 | [72 empty] | 1701 | 0
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN | 1702 | 0 | [73 empty] | 1702 | 0
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 1751 | 0 | [73 empty] | 1751 | 0
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN | 1752 | 0 | [73 empty] | 1752 | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs | 1806 | 27.7447 |  |  | 3 | 22 | [69 empty] | 1806 | 27.7447
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 1901 | 132.6417 |  | 34 | 32 | 32 | [69 empty] | 1901 | 132.6417
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 8202 | 289.203 | 8202 | 108 | 100 | 87 | [69 empty] | 8202 | 289.203
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN | 8203 | 130.9084 | 8203 | 31 | 29 | 29 | [69 empty] | 8203 | 130.9084
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS | 8204 | 147.9102 | 8204 | 35 | 34 | 34 | [69 empty] | 8204 | 147.9102
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS | 8205 | 75.2674 | 8205 |  | 21 | 21 | [69 empty] | 8205 | 75.2674
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks | 8210 | 18.8142 | 8210 | 15 | 4 | [70 empty] | 8210 | 18.8142
H - Phil Heitzenroeder | Job: 8215 Plant Design | 8215 | 0 | [73 empty] | 8215 | 0
|  |  | 1938.6461 |  | 300 | 517 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | H Total |  | 1938.6461
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | 4101 | -104.1 | 4101 | -104 | [70 empty] | V | 4101 | -104.1
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN | 4301 | 0 | [73 empty] | 4301 | 0
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN | 4401 | 0 | [73 empty] | 4401 | 0
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 4501 | 0 | 4501 | [72 empty] | 4501 | 0
V - Al vonHalle | Job: 5101 - Network and Fiber | 5101 | 0 | [73 empty] | 5101 | 0
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA | 5201 | 0 | [73 empty] | 5201 | 0
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA | 5301 | 0 | [73 empty] | 5301 | 0
V - Al vonHalle | Job: 5401 - Facility Timing & | 5401 | 0 | [73 empty] | 5401 | 0
V - Al vonHalle | Job: 5501 - Real Time Control | 5501 | 0 | [73 empty] | 5501 | 0
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 5601 | 0 | [73 empty] | 5601 | 0
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 5801 | 5.7232 |  | 1 | 1 | 1 | [69 empty] | 5801 | 5.7232
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE | 8501 | 0 | [73 empty] | 8501 | 0
|  |  | -98.3768 |  | -103 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | V Total |  | -98.3768
|  |  | 4429.0134 | 0 | 421 | 1271 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4423.0067
corrected
corrected

## COST PERFORMANCE BY RLM & JOB
NCSX Cost Performance Report
Period May 1, 2007 through August 31, 2007
(Measured against unofficial proposed baseline)
RLM | JOB | BCWS | BCWP | ACWP | SPI | CPI | schedule variance | cost variance
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON | 228 | 229.1165 | 212.2788 | 1.0049 | 1.0793 | 1.1165 | 16.8377
| Job: 8102 - NCSX MIE Management ORNL-LYON | 50 | 49.6048 | 91.512 | 0.9921 | 0.54206 | -0.39518 | -41.9072
| Job: 8998 - Allocations-STRYKOWSKY | 119 | 118.2576 | 113.1008 | 0.99376 | 1.0456 | -0.74242 | 5.1568
|  | 397 | 396.9789 | 416.8916 | 0.99995 | 0.95224 | -0.021093 | -19.9127
0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 46 | 68.4894 | 39.6239 | 1.4889 | 1.7285 | 22.4894 | 28.8655
| Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -252 | -251.6947 | -254.4373 | 0.99879 | 0.98922 | 0.30528 | 2.7426
| Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 148 | 156.4268 | 88.1534 | 1.0569 | 1.7745 | 8.4268 | 68.2734
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 336 | 256.8971 | 191.3229 | 0.76457 | 1.3427 | -79.1029 | 65.5742
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 821 | 946.222 | 900.0867 | 1.1525 | 1.0513 | 125.222 | 46.1353
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 43 | 44.1632 | 213.991 | 1.0271 | 0.20638 | 1.1632 | -169.8278
| Job: 1802 - FP Assy Oversight&Support-VIOLA | 210 | 210.1107 | 284.5957 | 1.0005 | 0.73828 | 0.11075 | -74.4849
| Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 107 | 64.0883 | 128.1259 | 0.59896 | 0.5002 | -42.9117 | -64.0376
| Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 996 | 854.5431 | 566.7311 | 0.85798 | 1.5078 | -141.4569 | 287.812
| Job: 1815 - Field Period Assy | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 2101 - Fueling Systems-BLANCHARD | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 3101 - Magnetic Diagnostics-STRATTON | 145 | 138.94 | 111.7126 | 0.95821 | 1.2437 | -6.06 | 27.2274
| Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 3801 - Electron Beam Mapping-STRATTON | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 3901 - Diagnostics sys Integration-STRATTON | 8 | 9.3261 | 17.6602 | 1.1658 | 0.52809 | 1.3261 | -8.3341
| Job: 6101 - Water Systems-DUDEK | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 6201 - Cryogenic Syst-GETTELFINGER | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 6301 - Utility Systems-DUDEK | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 7301 - Platform Design & | 0 | 2.5533 | 0 | #DIV/0! | #DIV/0! | 2.5533 | 2.5533
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -308 | -308.3 | -282.5723 | 1.001 | 1.091 | -0.3 | -25.7277
| Job: 7501 - Construction Support Crew-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 7503 - Machine Assembly (station 6)-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 7601 - Tooling Design & Fabrication-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
|  | 2300 | 2191.7652 | 2004.9938 | 0.95294 | 1.0932 | -108.2348 | 186.7713
0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 14 | 47.3325 | 13.784 | 3.3809 | 3.4339 | 33.3325 | 33.5485
| Job: 1352 - PF Coil Procurement-KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 1353 - CS Structure Procurement-DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 1354 - Trim Coil Design &Procurement-KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 1361 - TF Fabrication-KALISH | 168 | 199.4121 | 185.3505 | 1.187 | 1.0759 | 31.4121 | 14.0615
| Job: 1404 - MCWF R&D 1st Prod | -36 | -35.94 | -35.1034 | 0.99833 | 1.0238 | 0.06 | -0.83662
| Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -84 | -80.3908 | -83.2136 | 0.95703 | 0.96608 | 3.6092 | 2.8228
| Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 58 | 103.1533 | 68.0759 | 1.7785 | 1.5153 | 45.1533 | 35.0774
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 894 | 711.1819 | 552.1157 | 0.79551 | 1.2881 | -182.8181 | 159.0661
| Job: 1429 - MC Interface R&D-GETTELFINGER | 118 | 83.2365 | 80.6372 | 0.70539 | 1.0322 | -34.7635 | 2.5993
| Job: 1501 - Coil Structures Design-DAHLGREN | 128 | 81.9424 | 174.6521 | 0.64017 | 0.46917 | -46.0576 | -92.7097
| Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 1601 - Coil Services Design-GORANSON | 6 | 6.2288 | 0 | 1.0381 | #DIV/0! | 0.2288 | 6.2288
| Job: 1701 - Cryostat Design-GETTLEFINGER | 0 | 0 | 4.3022 | #DIV/0! | 0 | 0 | -4.3022
| Job: 1702 - Base Support Struct Design-DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 1752 - Base Support Proc-DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 1806 - FP Assembly specs | 67 | 27.7447 | 2.007 | 0.4141 | 13.824 | -39.2553 | 25.7377
| Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 133 | 132.6417 | 96.648 | 0.99731 | 1.3724 | -0.35832 | 35.9937
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 290 | 289.203 | 264.2051 | 0.99725 | 1.0946 | -0.79701 | 24.9979
| Job: 8203 - Design Integration-BROWN | 132 | 130.9084 | 22.052 | 0.99173 | 5.9363 | -1.0916 | 108.8564
| Job: 8204 - Systems Analysis-BROOKS | 148 | 147.9102 | 193.3133 | 0.99939 | 0.76513 | -0.089752 | -45.4031
| Job: 8205 - Dimensional Control Coordin-ELLIS | 84 | 75.2674 | 81.5541 | 0.89604 | 0.92291 | -8.7326 | -6.2867
| Job: 8210 - FY07 Rebaseling tasks | 19 | 18.8142 | 38.8805 | 0.99022 | 0.4839 | -0.1858 | -20.0663
| Job: 8215 Plant Design | 8 | 0 | 0 | 0 | #DIV/0! | -8 | 0
|  | 2147 | 1938.6461 | 1659.2607 | 0.90296 | 1.1684 | -208.3539 | 279.3854
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | -104 | -104.1 | -104.1027 | 1.001 | 0.99997 | -0.1 | 0.00269
| Job: 4301 - DC Systems-RAMAKRISHNAN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 4401 - Control & Protection-RAMAKRISHNAN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 0 | 0 | -0.19881 | #DIV/0! | 0 | 0 | 0.19881
| Job: 5101 - Network and Fiber | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 5201 - I&C Systems-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 5301 - Data Acquisition-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 5401 - Facility Timing & | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 5501 - Real Time Control | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
| Job: 5801 - Central I&C Integr& Oversight-SICHTA | 5 | 5.7232 | 0 | 1.1446 | #DIV/0! | 0.72324 | 5.7232
| Job: 8501 - Integrated Systems Testing-GENTILE | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
|  | -99 | -98.3768 | -104.3015 | 0.9937 | 0.9432 | 0.62324 | 5.9247
|  | 4745 | 4429.0134 | 3976.8446 | 0.93341 | 1.1137 | -315.9866 | 452.1688
| ornl jobs | 1208 | 1030.5551 | 810.3586 | 0.85311 | 1.2717 |  | 220.1965
| pppl jobs | 3537 | 3398.4583 | 3166.486 | 0.96083 | 1.0733 |  | 231.9723
| highlighted schedule variances = | 2400 | 1914.455 | 1440.3026 | 0.79769 | 1.3292 | -485.545 | 474.1524
| highlighted cost variances = | 686 | 597.8196 | 1086.19 | 0.87146 | 0.55038 | -88.1804 | -488.3703
corrected

## TOTAL PROJECT REPORT
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
TOTAL PROJECT |  |  |  | Jim Anderson |  | 2007-07-30
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level |  | Activity ID | Activity description | Milestones | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish | Variance target 1 early finish | Variance target 1 early finish
METFY07R1 - Dimensional control plans for station 2 | 8205 | BE | 2007-08-31 | 2007-09-21 |  | 3 | - | METFY07R1 | Dimensional control plans for station 2 | 3 | 8205 | BE | 01JUN07* | 2007-08-31 | 01JUN07A | 2007-09-21 | -14 | -14
1803-205 - Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2007-10-03 |  | 3 | - | 1803-205 | Station 2 Assembly Drawings | 3 | 1806 | MC | 11JUN07* | 2007-09-11 | 11JUN07A | 2007-10-03 | -16 | -16
INTRF-045 - FDR prep outboard shims | 1421 | DW | 2007-07-18 | 29JUN07A |  | 3 | - | INTRF-045 | FDR prep outboard shims | 3 | 1421 | DW | 2007-07-05 | 2007-07-18 | 25JUN07A | 29JUN07A | 12 | 12
1803-201 - Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2007-10-12 |  | 3 | - | 1803-201 | Station 2 Assembly Specification | 3 | 1806 | MC | 11JUN07* | 2007-09-11 | 01JUL07A | 2007-10-12 | -23 | -23
1416-506 - Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2007-11-21 |  | 3 | - | 1416-506 | Check and promote top-level models/drawings | 3 | 1416 | DW | 2007-08-01 | 2007-11-21 | 01JUL07A | 2007-11-21 | 0 | 0
1803-3.4 - Stage 3 support FDR | 1803 | TB | 2007-07-13 | 17JUL07A |  | 3 | - | 1803-3.4 | Stage 3 support FDR | 3 | 1803 | TB | 13JUL07* | 2007-07-13 | 02JUL07A | 17JUL07A | -2 | -2
1501-525P - Coils Support Structure - PDR | 1501 | FD | 2007-07-20 | 20JUL07A |  | 3 | - | 1501-525P | Coils Support Structure - PDR | 3 | 1501 | FD | 20JUL07* | 2007-07-20 | 20JUL07A | 20JUL07A | 0 | 0
3101-326 - ROWGOSKI COIL - FDR | 3101 | BS | 2007-09-06 | 09AUG07A |  | 3 | - | 3101-326 | ROWGOSKI COIL - FDR | 3 | 3101 | BS |  | 2007-09-06 |  | 09AUG07A | 19 | 19
S21-5.04X - Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2007-09-24 | 2007-12-30 | 2 | - | S21-5.04X | Shims required for 1st 3 pack MC assy | 2 | 1431 | LD | 2007-09-20 |  | 2007-09-24 |  | -2 | -2
METDCP-3 - Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2007-11-02 |  | 3 | - | METDCP-3 | Dimensional control plans for station 3 | 3 | 8205 | BE | 2007-09-04 | 2007-10-15 | 2007-09-24 | 2007-11-02 | -14 | -14
1416-601 - Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2007-11-06 |  | 3 | - | 1416-601 | Prepare EM and structural analysis of leads | 3 | 1416 | DW | 01OCT07* | 2007-11-06 | 01OCT07* | 2007-11-06 | 0 | 0
INTRF-055 -AB/BC/AA inboard interface-FDR | 1421 | DW | 2007-09-04 | 05OCT07* | 2007-11-30 | 2 | - | INTRF-055 | AB/BC/AA inboard interface - FDR | 2 | 1421 | DW |  | 2007-09-04 |  | 05OCT07* | -23 | -23
1302-225M - PF Coil PDR | 1302 | MK | 2007-12-11 | 2007-10-19 | 2008-03-30 | 2 | - | 1302-225M | PF Coil PDR | 2 | 1302 | MK |  | 2007-12-11 |  | 2007-10-19 | 1900-02-03 | 35
1361C-104M - ** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 | 2007-10-19 | 2007-12-31 | 2 | - | 1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** | 2 | 1361 | MK |  | 2007-09-28 |  | 2007-10-19 | -15 | -15
1803-5.6 - Station 5 FDR | 1803 | TB | 2007-11-21 | 2007-10-29 |  | 3 | - | 1803-5.6 | Station 5 FDR | 3 | 1803 | TB |  | 2007-11-21 |  | 2007-10-29 | 1900-01-16 | 17
METDCP-5 - Dimensional control plans for station 5 | 8205 | BE | 2008-02-15 | 2008-03-06 |  | 3 | - | METDCP-5 | Dimensional control plans for station 5 | 3 | 8205 | BE | 2007-10-16 | 2008-02-15 | 2007-11-05 | 2008-03-06 | -14 | -14
1361C-106 - Fab, Test & Deliver Coil #6 | 1361 | MK | 2007-11-23 | 2007-11-23 |  | 3 | - | 1361C-106 | Fab, Test & Deliver Coil #6 | 3 | 1361 | MK | 23NOV07* | 2007-11-23 | 23NOV07* | 2007-11-23 | 0 | 0
1302-270 - PF Coils - FDR | 1302 | MK | 2008-03-24 | 2007-12-20 |  | 3 | - | 1302-270 | PF Coils - FDR | 3 | 1302 | MK | 2008-03-21 | 2008-03-24 | 2007-12-19 | 2007-12-20 | 1900-02-28 | 60
1416-605 - Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 | 2008-01-25 |  | 3 | - | 1416-605 | Prepare Type-ABC closeout FDR | 3 | 1416 | DW | 2007-12-14 | 2008-01-14 | 2008-01-07 | 2008-01-25 | -9 | -9
1702-515 - Base support - PDR | 1702 | FD | 2007-11-26 | 2008-02-04 |  | 3 | - | 1702-515 | Base support - PDR | 3 | 1702 | FD | 2007-11-26 | 2007-11-26 | 2008-02-04 | 2008-02-04 | -41 | -41
[8 empty] | 1421-3144 | C-C Joint - FDR | 3 | 1421 | DW |  | 2008-01-07 |  | 2008-02-07 | -23 | -23
|  |  | Cost and schedule Performance |  |  |  |  | 1501-541 | Coil Support Structures - FDR | 3 | 1501 | FD | 2007-09-21 | 2007-09-21 | 2008-02-21 | 2008-02-21 | -100 | -100
[5 empty] | From May 1,2007 | Current Month |  | 141-036 | PF Coils Awarded | 2 | 1352 | MK |  | 2008-05-27 |  | 2008-03-03 | 1900-02-28 | 60
|  |  |  | BCWS = | 4745 | 1364 |  | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 3 | 1810 | MV | 2008-02-01 | 2008-02-06 | 2008-03-04 | 2008-03-07 | -22 | -22
|  |  |  | BCWP = | 4429.0134 | 1243.0134 |  | METDCP-6 | Dimensional control plans for station 6 | 3 | 8205 | BE | 2008-02-18 | 2008-06-09 | 2008-03-07 | 2008-06-27 | -14 | -14
|  |  |  | ACWP = | 3976.8446 | 1462.787 |  | 1702-525M | Base Support Structure FDR | 2 | 1702 | FD |  | 2008-02-04 |  | 2008-03-27 | -38 | -38
|  |  |  | CV = | 452.1688
|  |  |  | SV = | -315.9866
|  |  |  | CPI = | 1.1137 | 0.84976
|  |  |  | SPI = | 0.93341 | 0.9113
|  |  |  | BAC = | 117733.138
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact

## Monthly Report-LARRY
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
NCSX Construction |  |  |  | Larry Dudek |  | 2007-08-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Mod Coil Fab Jobs 1408/1451/1459 | JC |  | Fueling & Vacuum WBS 21 & 22 |  | BB
Cryo Systems WBS 62 | GG |  | Diagnostics WBS 3 |  | BS
Assy Tooling design/fab Job 1803 | TB |  | Water/Utilities WBS 61/63 |  | LD
Field Period Assy Jobs 1802/1810/1815 | MV |  | Bakeout Systems WBS 64 |  | MK
Final Machine Assy WBS 75 | EP
Highlights and Progress:
WBS 1803: Completed disposition of all outstanding chits on Station 3 FDR and issued drawings for fabrication (less SISSCO rigging interface and laser mounts). SISSCO rigging interface structure models and preliminary drawings were completed.
Issues (not currently impacting technical, cost, or schedule but being watched):
WBS 1803: FEA analysis of SISSCO rigging interface structure showed the structure to be inadequate. Additional hours have been used to rework the design, resulting in a cost variance for August.
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level
[8 empty] | Activity ID | Activity description | Milestones | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish | Variance target 1 early finish
1803-3.4 - Stage 3 support FDR | 1803 | TB | 2007-07-13 | 17JUL07A |  | 3 | - | 1803-3.4 | Stage 3 support FDR | 3 | 1803 | TB | 13JUL07* | 39276 | 02JUL07A | 17JUL07A | -2
3101-326 - ROWGOSKI COIL - FDR | 3101 | BS | 2007-09-06 | 09AUG07A |  | 3 | - | 3101-326 | ROWGOSKI COIL - FDR | 3 | 3101 | BS |  | 39331 |  | 09AUG07A | 19
S21-5.04X - Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2007-09-24 | 2007-12-30 | 2 | - | S21-5.04X | Shims required for 1st 3 pack MC assy | 2 | 1431 | LD | 2007-09-20 |  | 2007-09-24 |  | -2
1803-5.6 - Station 5 FDR | 1803 | TB | 2007-11-21 | 2007-10-29 |  | 3 | - | 1803-5.6 | Station 5 FDR | 3 | 1803 | TB |  | 39407 |  | 2007-10-29 | 17
R1810-1329 - Final Scan of VVSA #3 Station 1 complete | 1810 | MV | 2008-02-06 | 2008-03-07 |  | 3 | - | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 3 | 1810 | MV | 2008-02-01 | 39484 | 2008-03-04 | 2008-03-07 | -22
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 2300 | 762
|  |  |  | BCWP = | 2191.7652 | 744.7652
|  |  |  | ACWP = | 2004.9938 | 702.093
|  |  |  | CV = | 186.7713
|  |  |  | SV = | -108.2348
|  |  |  | CPI = | 1.0932 | 1.0608
|  |  |  | SPI = | 0.95294 | 0.97738
|  |  |  | BAC = | 45111.331
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact

## Monthly Report-JIM
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Project Management |  |  |  | Jim Anderson |  | 2007-08-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
PPPL Project Management Job 8101 | JA
ORNL Project Management Job 8102 | JL
Allocations Job 8998 | RLS
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 397 | 103
|  |  |  | BCWP = | 396.9789 | 102.9789
|  |  |  | ACWP = | 416.8916 | 107.294
|  |  |  | CV = | -19.9127
|  |  |  | SV = | -0.021093
|  |  |  | CPI = | 0.95224 | 0.95978
|  |  |  | SPI = | 0.99995 | 0.9998
|  |  |  | BAC = | 11056.504
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 | [5 empty] | Stage 3 support FDR |  | * | 2007-07-13 | 3 | 2007-07-13
3101-326 0 0 0 | [5 empty] | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 | [5 empty] | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 | [5 empty] | Station 5 FDR |  |  | 2007-11-21 | 3 | 2008-02-01
P3-171V 11 11 0 | [5 empty] | Final Scan |  |  | 2008-02-06 | 3 | 2008-05-12
PLCT-C6 14 14 0 | [5 empty] | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 | [5 empty] | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 | [5 empty] | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 | [5 empty] | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
[6 empty] | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
[6 empty] | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
[6 empty] | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
[6 empty] | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2
N/A

## Monthly Report-AL
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Electrical, I&C and Startup |  |  |  | Al vonHalle |  | 2007-07-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Electrical Powers Systems WBS 4 | RR
Instrumentation and Controls | PS
Startup | CG
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level
[10 empty] | Activity ID | Activity description | Early start | Early finish | Milestones | Job Number | Job Manager
[10 empty] | 1803-3.4 | Stage 3 support FDR | 13JUL07* | 2007-07-13 | 3 | 1803 | TB
[10 empty] | 3101-326 | FDR - ROWGOSKI COIL |  | 2007-09-06 | 3 | 3101 | BS
[10 empty] | S21-5.04X | Shims required for 1st 3 pack MC assy |  | 2007-09-20 | 2 | 1431 | LD
[10 empty] | 1803-5.6 | Station 5 FDR |  | 2007-11-21 | 3 | 1803 | TB
[10 empty] | R1810-1329 | Final Scan | 2008-02-01 | 2008-02-06 | 3 | 1810 | MV
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | -99 | 1
BCWP =
ACWP =
CV =
SV =
CPI =
SPI =
|  |  |  | BAC = | 5081.65
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 | [5 empty] | Stage 3 support FDR |  | * | 2007-07-13 | 3 |  |  | 2007-07-13
3101-326 0 0 0 | [5 empty] | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 | [5 empty] | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 | [5 empty] | Station 5 FDR |  |  | 2007-11-21 | 3 |  |  | 2008-02-01
P3-171V 11 11 0 | [5 empty] | Final Scan |  |  | 2008-02-06 | 3 |  |  | 2008-05-12
PLCT-C6 14 14 0 | [5 empty] | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 | [5 empty] | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 | [5 empty] | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 | [5 empty] | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
[6 empty] | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
[6 empty] | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
[6 empty] | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
[6 empty] | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2
No Milestones during the period

## Monthly Report- PHIL
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Stellarator CoreDesign and Procurement |  |  |  | Phil Heitzenroeder |  | 2007-08-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Conventional Coils WBS 13 | Mike Kalish |  | Modular Coils Jobs 1416/1421/1429/1431 |  | Dave Williamson
Coil Services WBS 16 | Paul Goranson |  | Coil Structures & Base Support Structure WBS 15 |  | Fred Dahlgren
Cryostat Job 1701/1751 | Geoff Gettelfinger |  | Assembly Specs & Dwgs Job 1806 |  | Mike Cole
Assy tooling & constructability Job 1803 | Tom Brown |  | Systems Analysis Job 8204 |  | Art Brooks
Dimensional Control Job 8205 | Bob Ellis |  | Systems Engineering & Support Job 8202 |  | Wayne Reiersen
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level |  | Activity ID | Activity description | Milestones | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish | Variance target 1 early finish
METFY07R1 - Dimensional control plans for station 2 | 8205 | BE | 2007-08-31 | 2007-09-21 |  | 3 | - | METFY07R1 | Dimensional control plans for station 2 | 3 | 8205 | BE | 01JUN07* | 2007-08-31 | 01JUN07A | 2007-09-21 | -14
1803-205 - Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2007-10-03 |  | 3 | - | 1803-205 | Station 2 Assembly Drawings | 3 | 1806 | MC | 11JUN07* | 2007-09-11 | 11JUN07A | 2007-10-03 | -16
INTRF-045 - FDR prep outboard shims | 1421 | DW | 2007-07-18 | 29JUN07A |  | 3 | - | INTRF-045 | FDR prep outboard shims | 3 | 1421 | DW | 2007-07-05 | 2007-07-18 | 25JUN07A | 29JUN07A | 12
1803-201 - Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2007-10-12 |  | 3 | - | 1803-201 | Station 2 Assembly Specification | 3 | 1806 | MC | 11JUN07* | 2007-09-11 | 01JUL07A | 2007-10-12 | -23
1416-506 - Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2007-11-21 |  | 3 | - | 1416-506 | Check and promote top-level models/drawings | 3 | 1416 | DW | 2007-08-01 | 2007-11-21 | 01JUL07A | 2007-11-21 | 0
1501-525P - Coils Support Structure - PDR | 1501 | FD | 2007-07-20 | 20JUL07A |  | 3 | - | 1501-525P | Coils Support Structure - PDR | 3 | 1501 | FD | 20JUL07* | 2007-07-20 | 20JUL07A | 20JUL07A | 0
METDCP-3 - Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2007-11-02 |  | 3 | - | METDCP-3 | Dimensional control plans for station 3 | 3 | 8205 | BE | 2007-09-04 | 2007-10-15 | 2007-09-24 | 2007-11-02 | -14
1416-601 - Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2007-11-06 |  | 3 | - | 1416-601 | Prepare EM and structural analysis of leads | 3 | 1416 | DW | 01OCT07* | 2007-11-06 | 01OCT07* | 2007-11-06 | 0
INTRF-055 - AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 05OCT07* | 2007-11-30 | 2 | - | INTRF-055 | AB/BC/AA inboard interface - FDR | 2 | 1421 | DW |  | 2007-09-04 |  | 05OCT07* | -23
1302-225M - PF Coil PDR | 1302 | MK | 2007-12-11 | 2007-10-19 | 2008-03-30 | 2 | - | 1302-225M | PF Coil PDR | 2 | 1302 | MK |  | 2007-12-11 |  | 2007-10-19 | 35
1361C-104M - ** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 | 2007-10-19 | 2007-12-31 | 2 | - | 1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** | 2 | 1361 | MK |  | 2007-09-28 |  | 2007-10-19 | -15
METDCP-5 - Dimensional control plans for station 5 | 8205 | BE | 2008-02-15 | 2008-03-06 |  | 3 | - | METDCP-5 | Dimensional control plans for station 5 | 3 | 8205 | BE | 2007-10-16 | 2008-02-15 | 2007-11-05 | 2008-03-06 | -14
1361C-106 - Fab, Test & Deliver Coil #6 | 1361 | MK | 2007-11-23 | 2007-11-23 |  | 3 | - | 1361C-106 | Fab, Test & Deliver Coil #6 | 3 | 1361 | MK | 23NOV07* | 2007-11-23 | 23NOV07* | 2007-11-23 | 0
1302-270 - PF Coils - FDR | 1302 | MK | 2008-03-24 | 2007-12-20 |  | 3 | - | 1302-270 | PF Coils - FDR | 3 | 1302 | MK | 2008-03-21 | 2008-03-24 | 2007-12-19 | 2007-12-20 | 60
1416-605 - Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 | 2008-01-25 |  | 3 | - | 1416-605 | Prepare Type-ABC closeout FDR | 3 | 1416 | DW | 2007-12-14 | 2008-01-14 | 2008-01-07 | 2008-01-25 | -9
1702-515 - Base Support - PDR | 1702 | FD | 2007-11-26 | 2008-02-04 |  | 3 | - | 1702-515 | Base Support - PDR | 3 | 1702 | FD | 2007-11-26 | 2007-11-26 | 2008-02-04 | 2008-02-04 | -41
1421-3144 - C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-02-07 |  | 3 | - | 1421-3144 | C-C Joint - FDR | 3 | 1421 | DW |  | 2008-01-07 |  | 2008-02-07 | -23
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 2147 | 497
|  |  |  | BCWP = | 1938.6461 | 392.6461
|  |  |  | ACWP = | 1659.2607 | 653.4
|  |  |  | CV = | 279.3854
|  |  |  | SV = | -208.3539
|  |  |  | CPI = | 1.1684 | 0.60093
|  |  |  | SPI = | 0.90296 | 0.79003
|  |  |  | BAC = | 57127
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact