## Summary
BCWS Monthly
|  | ACWP | BTC | BCWS May 1,2007 - Sep 30,2007 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12
11056.504 | Jim Anderson | 5262.504 | 5794 | 628 | 104 | 95 | 95 | 103 | 86 | 145 | 127 | 95 | 139 | 132 | 132 | 139 | 132 | 132 | 139 | 132 | 131 | 159 | 126 | 118 | 146 | 139 | 152 | 152 | 139 | 152 | 152 | 146 | 142 | 142 | 123 | 104 | 130 | 130 | 149 | 142 | 130 | 142 | 136 | 142 | 136 | 108 | 103 | 87 | 108 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45120.891 | Larry Dudek | 20428.331 | 24692.56 | 4016.71 | 196.37 | 494.09 | 847.87 | 726.2 | 547.57 | 1204.61 | 641.57 | 490.99 | 733.18 | 615.01 | 599.26 | 565.74 | 520.27 | 441.47 | 567.25 | 382.9 | 368.82 | 467.28 | 499.05 | 700.13 | 870.14 | 709.69 | 742.23 | 653.24 | 657.74 | 669.4 | 589.32 | 545.17 | 610.17 | 830.32 | 573.51 | 417 | 544 | 389 | 562 | 619 | 482 | 428 | 358 | 375 | 324 | 410 | 375 | 318 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58190.353 | Phil Heitzeroeder | 40659.653 | 17530.7 | 3188 | 424 | 618 | 608 | 497 | 433 | 608 | 413.6 | 344.9 | 505.2 | 417.8 | 461.8 | 418.7 | 375.5 | 644.8 | 856.7 | 999.1 | 943.7 | 810.4 | 517 | 369.6 | 442.4 | 422.3 | 412.7 | 404.6 | 301.5 | 362.7 | 283.7 | 192 | 209 | 338 | 295 | 251 | 283 | 238 | 248 | 193 | 150 | 165 | 158 | 165 | 158 | 157 | 150 | 127 | 153 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5081.65 | Al vonHalle | 752.65 | 4329 | -95 | -103 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 61 | 77 | 94 | 114 | 82 | 106 | 104 | 96 | 120 | 173 | 263 | 187 | 242 | 261 | 226 | 250 | 272 | 348 | 253 | 197 | 168 | 112 | 55 | 59 | 169 | 110 | 94 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total BCWS | 67103.138 | 52346.26 | 7737.71 | 621.37 | 1208.09 | 1551.87 | 1328.2 | 1067.57 | 1960.61
|  |  | 119449.398 | 7737.71
|  | Jim Anderson |  | BCWS | 104 | 199 | 294 | 397 | 483 | 628 | 755 | 850 | 989 | 1121 | 1253 | 1392 | 1524 | 1656 | 1795 | 1927 | 2058 | 2217 | 2343 | 2461 | 2607 | 2746 | 2898 | 3050 | 3189 | 3341 | 3493 | 3639 | 3781 | 3923 | 4046 | 4150 | 4280 | 4410 | 4559 | 4701 | 4831 | 4973 | 5109 | 5251 | 5387 | 5495 | 5598 | 5685 | 5793 | 5794
|  |  |  | BCWP | 102 | 199 | 294 | 396.9789 | 482.56 | 627.698
|  |  |  | ACWP | 111.7184 | 218.6445 | 309.5976 | 416.8916 | 597.4836 | 693.7456
|  |  |  | CPI | 0.91301 | 0.91015 | 0.94962 | 0.95224 | 0.80765 | 0.9048
|  |  |  | SPI | 0.98077 | 1 | 1 | 0.99995 | 0.99909 | 0.99952
|  | Larry Dudek |  | BCWS | 196.37 | 690.46 | 1538.33 | 2264.53 | 2812.1 | 4016.71 | 4658.28 | 5149.27 | 5882.45 | 6497.46 | 7096.72 | 7662.46 | 8182.73 | 8624.2 | 9191.45 | 9574.35 | 9943.17 | 10410.45 | 10909.5 | 11609.63 | 12479.77 | 13189.46 | 13931.69 | 14584.93 | 15242.67 | 15912.07 | 16501.39 | 17046.56 | 17656.73 | 18487.05 | 19060.56 | 19477.56 | 20021.56 | 20410.56 | 20972.56 | 21591.56 | 22073.56 | 22501.56 | 22859.56 | 23234.56 | 23558.56 | 23968.56 | 24343.56 | 24661.56 | 24692.56
|  |  |  | BCWP | 122 | 778 | 1447 | 2191.7652 | 2900.1205 | 3794.506
|  |  |  | ACWP | 305.793 | 823.5043 | 1302.9008 | 2004.9938 | 2727.8868 | 3154.7718
|  |  |  | CPI | 0.39896 | 0.94474 | 1.1106 | 1.0932 | 1.0631 | 1.2028
|  |  |  | SPI | 0.62128 | 1.1268 | 0.94063 | 0.96787 | 1.0313 | 0.94468
|  | Phil Heitzeroeder |  | BCWS | 424 | 1042 | 1650 | 2147 | 2580 | 3188 | 3601.6 | 3946.5 | 4451.7 | 4869.5 | 5331.3 | 5750 | 6125.5 | 6770.3 | 7627 | 8626.1 | 9569.8 | 10380.2 | 10897.2 | 11266.8 | 11709.2 | 12131.5 | 12544.2 | 12948.8 | 13250.3 | 13613 | 13896.7 | 14088.7 | 14297.7 | 14635.7 | 14930.7 | 15181.7 | 15464.7 | 15702.7 | 15950.7 | 16143.7 | 16293.7 | 16458.7 | 16616.7 | 16781.7 | 16939.7 | 17096.7 | 17246.7 | 17373.7 | 17526.7 | 17530.7
|  |  |  | BCWP | 300 | 817 | 1546 | 1938.6461 | 2268.7 | 2722.1431
|  |  |  | ACWP | 317.203 | 705.0554 | 1005.8607 | 1659.2607 | 2055.8407 | 2404.7427
|  |  |  | CPI | 0.94577 | 1.1588 | 1.537 | 1.1684 | 1.1035 | 1.132
|  |  |  | SPI | 0.70755 | 0.78407 | 0.93697 | 0.90296 | 0.87934 | 0.85387
|  | Al vonHalle |  | BCWS | -103 | -102 | -101 | -99 | -98 | -95 | -92 | -90 | -87 | -84 | -81 | -78 | -75 | -72 | -69 | -66 | -63 | -2 | 75 | 169 | 283 | 365 | 471 | 575 | 671 | 791 | 964 | 1227 | 1414 | 1656 | 1917 | 2143 | 2393 | 2665 | 3013 | 3266 | 3463 | 3631 | 3743 | 3798 | 3857 | 4026 | 4136 | 4230 | 4329
|  |  |  | BCWP | -103 | -102 | -101 | -98.3768 | -97.12 | -94.8
|  |  |  | ACWP | -104.2596 | -104.2596 | -104.3015 | -104.3015 | -104.6585 | -104.6585
|  |  |  | CPI | 0.98792 | 0.97833 | 0.96835 | 0.9432 | 0.92797 | 0.9058
|  |  |  | SPI | 1 | 1 | 1 | 0.9937 | 0.99102 | 0.99789
|  | TOTAL PROJECT |  | BCWS | 621.37 | 1829.46 | 3381.33 | 4709.53 | 5777.1 | 7737.71 | 8922.88 | 9855.77 | 11236.15 | 12403.96 | 13600.02 | 14726.46 | 15757.23 | 16978.5 | 18544.45 | 20061.45 | 21507.97 | 23005.65 | 24224.7 | 25506.43 | 27078.97 | 28431.96 | 29844.89 | 31158.73 | 32352.97 | 33657.07 | 34855.09 | 36001.26 | 37149.43 | 38701.75 | 39954.26 | 40952.26 | 42159.26 | 43188.26 | 44495.26 | 45702.26 | 46661.26 | 47564.26 | 48328.26 | 49065.26 | 49742.26 | 50586.26 | 51324.26 | 51950.26 | 52341.26 | 23324.7 | 0
|  |  |  | BCWP | 421 | 1692 | 3186 | 4429.0134 | 5554.2605 | 7049.5471
|  |  |  | ACWP | 630.4547 | 1642.9445 | 2514.0576 | 3976.8446 | 5276.5526 | 6148.6016
|  |  |  | CPI | 0.66777 | 1.0299 | 1.2673 | 1.1137 | 1.0526 | 1.1465
|  |  |  | SPI | 0.67754 | 0.92486 | 0.94223 | 0.94044 | 0.96143 | 0.91106
|  | Mod Coil Design |  | BCWS | 219 | 518 | 827 | 1070 | 1184 | 1418 | 1500 | 1538 | 1580 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606
|  | 1416/1421/1429 |  | BCWP | 96 | 292 | 797 | 897.5716 | 918.5 | 1122.391
|  |  |  | ACWP | 123.9413 | 257.935 | 406.7498 | 700.8288 | 828.5818 | 943.1298
|  |  |  | CPI | 0.77456 | 1.1321 | 1.9594 | 1.2807 | 1.1085 | 1.1901
|  |  |  | SPI | 0.43836 | 0.56371 | 0.96372 | 0.83885 | 0.77576 | 0.79153
|  | Field Period Assy |  | BCWS | 254.37 | 497.46 | 838.33 | 1170.53 | 1417.1 | 1754.71 | 1998.28 | 2223.27 | 2531.45 | 2783.46 | 3079.72 | 3346.46 | 3596.73 | 3831.2 | 4258.45 | 4570.35 | 4851.17 | 5164.45 | 5448.5 | 5663.63 | 5966.77 | 6353.46 | 6781.69 | 7133.93 | 7480.67 | 7795.07 | 8142.39 | 8432.56 | 8725.73 | 8964.05 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56
|  | 1802/1810/1815 |  | BCWP | 254 | 494 | 808 | 1064.6539 | 1359.15 | 1600.257
|  |  |  | ACWP | 191.2809 | 363.5801 | 571.3968 | 851.3268 | 1075.1188 | 1226.7268
|  |  |  | CPI | 1.3279 | 1.3587 | 1.4141 | 1.2506 | 1.2642 | 1.3045
|  |  |  | SPI | 0.99855 | 0.99304 | 0.96382 | 0.90955 | 0.95911 | 0.91198
|  | Mod Coil Winding Ops |  | BCWS | 237 | 408 | 639 | 821 | 957 | 1170 | 1358 | 1491 | 1713 | 1924 | 2107 | 2316 | 2509 | 2665 | 2752 | 2768 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769
|  | 1451 |  | BCWP | 236 | 412 | 711 | 946.222 | 1184 | 1439.27
|  |  |  | ACWP | 283.7075 | 502.5031 | 659.7907 | 900.0867 | 1090.4237 | 1245.0187
|  |  |  | CPI | 0.83184 | 0.8199 | 1.0776 | 1.0513 | 1.0858 | 1.156
|  |  |  | SPI | 0.99578 | 1.0098 | 1.1127 | 1.1525 | 1.2372 | 1.2301
|  | Mod Coil Winding Ops Punch list |  | BCWS | 0 | 4 | 23 | 43 | 90 | 147 | 190 | 216 | 258 | 301 | 343 | 369 | 393 | 418 | 444 | 477 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501
|  | 1459 |  | BCWP | 0 | 18 | 32 | 44.1632 | 135.3 | 168.318
|  |  |  | ACWP | 42.2044 | 97.4829 | 149.185 | 213.991 | 289.453 | 339.23
|  |  |  | CPI | 0 | 0.18465 | 0.2145 | 0.20638 | 0.46743 | 0.49618
|  |  |  | SPI |  | 4.5 | 1.3913 | 1.0271 | 1.5033 | 1.145
|  | Engr Mgmt & Sys Eng Sup |  | BCWS | 82 | 158 | 221 | 290 | 343 | 404 | 457 | 497 | 556 | 612 | 668 | 727 | 783 | 839 | 898 | 954 | 1010 | 1071 | 1119 | 1164 | 1220 | 1273 | 1332 | 1391 | 1444 | 1503 | 1562 | 1618 | 1674 | 1733 | 1784 | 1827 | 1880 | 1933 | 1994 | 2053 | 2106 | 2165 | 2221 | 2280 | 2336 | 2384 | 2430 | 2469 | 2517 | 2519
|  | 8202 |  | BCWP | 108 | 208 | 295 | 289.203 | 342.46 | 403.1
|  |  |  | ACWP | 59.5964 | 118.2282 | 176.8311 | 264.2051 | 318.4291 | 373.1311
|  |  |  | CPI | 1.8122 | 1.7593 | 1.6683 | 1.0946 | 1.0755 | 1.0803
|  |  |  | SPI | 1.3171 | 1.3165 | 1.3348 | 0.99725 | 0.99843 | 0.99777
|  | Design Integration |  | BCWS | 33 | 65 | 97 | 132 | 161 | 196 | 226 | 249 | 282 | 314 | 346 | 379 | 411 | 443 | 476 | 508 | 540 | 575 | 602 | 628 | 660 | 690 | 723 | 756 | 786 | 819 | 852 | 884 | 916 | 949 | 978 | 1002 | 1032 | 1062 | 1097 | 1130 | 1160 | 1193 | 1225 | 1258 | 1290 | 1322 | 1352 | 1378 | 1410 | 1412
|  | 8203 |  | BCWP | 31 | 60 | 89 | 130.9084 | 160.47 | 194.2511
|  |  |  | ACWP | 5.0798 | 10.3179 | 11.959 | 22.052 | 36.561 | 55.866
|  |  |  | CPI | 6.1027 | 5.8151 | 7.4421 | 5.9363 | 4.3891 | 3.4771
|  |  |  | SPI | 0.93939 | 0.92308 | 0.91753 | 0.99173 | 0.99671 | 0.99108
|  | Systems Analysis |  | BCWS | 37 | 73 | 109 | 148 | 180 | 207 | 231 | 249 | 275 | 300 | 325 | 351 | 376 | 401 | 427 | 452 | 477 | 504 | 525 | 545 | 570 | 594 | 620 | 646 | 670 | 696 | 722 | 747 | 772 | 798 | 820 | 839 | 863 | 887 | 914 | 940 | 964 | 990 | 1015 | 1041 | 1066 | 1091 | 1115 | 1135 | 1160
|  | 8204 |  | BCWP | 35 | 69 | 103 | 147.9102 | 180.95 | 207.311
|  |  |  | ACWP | 42.5836 | 95.7359 | 142.8443 | 193.3133 | 225.4093 | 272.0633
|  |  |  | CPI | 0.82191 | 0.72073 | 0.72106 | 0.76513 | 0.80276 | 0.762
|  |  |  | SPI | 0.94595 | 0.94521 | 0.94495 | 0.99939 | 1.0053 | 1.0015
|  | Dimensional Cont Coordin |  | BCWS | 0 | 27 | 54 | 84 | 102 | 123 | 143 | 158 | 180 | 205 | 240 | 277 | 312 | 330 | 342 | 354 | 366 | 379 | 393 | 407 | 425 | 443 | 459 | 475 | 489 | 500 | 509 | 518 | 527 | 536 | 542 | 545 | 549 | 553 | 557 | 561 | 565 | 569 | 573 | 577 | 581 | 585 | 589 | 592
|  | 8205 |  | BCWP | 0 | 21 | 42 | 75.2674 | 76 | 87.581
|  |  |  | ACWP | 17.5068 | 37.5899 | 60.0821 | 81.5541 | 92.0961 | 96.1341
|  |  |  | CPI | 0 | 0.55866 | 0.69904 | 0.92291 | 0.82522 | 0.91103
|  |  |  | SPI |  | 0.77778 | 0.77778 | 0.89604 | 0.7451 | 0.71204
|  | Diagnostic |  | BCWS | 14 | 31 | 55 | 153 | 192 | 252 | 278 | 297 | 309 | 312 | 314 | 317 | 319 | 321 | 324 | 326 | 328 | 331 | 333 | 335 | 338 | 340 | 368 | 395 | 425 | 452 | 455 | 458 | 460 | 498 | 531 | 553 | 586 | 622 | 668 | 690 | 695 | 701 | 706 | 712 | 717
|  | 3101;3601;3801;3901 |  | BCWP | 14 | 58 | 114 | 148.2661 | 155.7805 | 160.581
|  |  |  | ACWP | 29.6873 | 49.7738 | 94.6838 | 129.3728 | 141.1718 | 145.5328
|  |  |  | CPI | 0.47158 | 1.1653 | 1.204 | 1.146 | 1.1035 | 1.1034
|  |  |  | SPI | 1 | 1.871 | 2.0727 | 0.96906 | 0.81136 | 0.63723
|  | PF Coil Des/Procurement |  | BCWS | 5 | 5 | 5 | 14 | 44 | 79 | 104 | 134 | 182 | 214 | 251 | 282 | 322 | 458 | 631 | 956 | 1226 | 1409 | 1510 | 1566 | 1629 | 1694 | 1758 | 1827 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1861 | 1873 | 1887
|  | 1302;1352 |  | BCWP | 5 | 5 | 5 | 47.3325 | 60.35 | 61.085
|  |  |  | ACWP | 4.26 | 5.8007 | 7.206 | 13.784 | 44.385 | 47.602
|  |  |  | CPI | 1.1737 | 0.86197 | 0.69387 | 3.4339 | 1.3597 | 1.2832
|  |  |  | SPI | 1 | 1 | 1 | 3.3809 | 1.3716 | 0.77323
|  | TF Fabrication |  | BCWS | 8 | 73 | 133 | 168 | 228 | 289 | 348 | 404 | 463 | 521 | 625 | 682 | 739 | 795 | 898 | 952 | 1004 | 1004
|  | 1361 |  | BCWP | 4 | 49 | 108 | 199.4121 | 267.65 | 331.282
|  |  |  | ACWP | -6.0157 | 34.3792 | 88.8075 | 185.3505 | 271.3235 | 340.5435
|  |  |  | CPI | -0.66492 | 1.4253 | 1.2161 | 1.0759 | 0.98646 | 0.9728
|  |  |  | SPI |  | 0.67123 | 0.81203 | 1.187 | 1.1739 | 1.1463
|  | Mod Coil Type AB Fnl Dsn |  | BCWS | 219 | 518 | 827 | 1070 | 1184 | 1418 | 1500 | 1538 | 1580 | 1606
|  | 1416;1421;1429 |  | BCWP | 96 | 292 | 797 | 897.5716 | 918.5 | 1122.391
|  |  |  | ACWP | 123.9413 | 257.935 | 406.7498 | 700.8288 | 828.5818 | 943.1298
|  |  |  | CPI | 0.77456 | 1.1321 | 1.9594 | 1.2807 | 1.1085 | 1.1901
|  |  |  | SPI | 0.43836 | 0.56371 | 0.96372 | 0.83885 | 0.77576 | 0.79153
|  | Coil Structure Dsn/Proc |  | BCWS | 7 | 38 | 70 | 128 | 164 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 218 | 327 | 458 | 589 | 732 | 825 | 876 | 939 | 999 | 1065 | 1131 | 1191 | 1257 | 1260
|  | 1501;1550 |  | BCWP | 2 | 45 | 75 | 81.9424 | 136.7 | 145.001
|  |  |  | ACWP | 54.1006 | 101.4754 | 138.5961 | 174.6521 | 176.9141 | 160.0001
|  |  |  | CPI | 0.036968 | 0.44346 | 0.54114 | 0.46917 | 0.77269 | 0.90626
|  |  |  | SPI | 0.28571 | 1.1842 | 1.0714 | 0.64017 | 0.83354 | 0.77958
|  | Coil Service Design |  | BCWS | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 34 | 61 | 88 | 116 | 143 | 191 | 222 | 269 | 327 | 404 | 465 | 518 | 544 | 564 | 587 | 610 | 630 | 653 | 676 | 697 | 701 | 743 | 785 | 824 | 858 | 861
|  | 1601 |  | BCWP | 0 | 6 | 6 | 6.2288 | 14.6 | 14.598
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI |  | 1 | 1 | 1.0381 | 2.4333 | 2.433
|  |  | Stellarator Core Mngtt&Integr | BCWS | 34 | 66 | 98 | 133 | 162 | 200 | 233 | 258 | 294 | 328 | 362 | 398 | 432 | 466 | 502 | 536 | 569 | 609 | 640 | 670 | 707 | 742 | 780 | 818 | 853 | 891 | 929 | 966 | 999 | 1039 | 1073 | 1102 | 1138 | 1174 | 1216 | 1256 | 1292 | 1332 | 1370 | 1410 | 1448 | 1493 | 1536 | 1573 | 1618
|  |  | 1901 | BCWP | 34 | 66 | 98 | 132.6417 | 161.56 | 199.131
|  |  |  | ACWP | 36.462 | 53.934 | 64.981 | 96.648 | 109.709 | 119.964
|  |  |  | CPI | 0.93248 | 1.2237 | 1.5081 | 1.3724 | 1.4726 | 1.6599
|  |  |  | SPI | 1 | 1 | 1 | 0.99731 | 0.99728 | 0.99565
|  |  | CS Structure Procurement | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 12 | 28 | 30 | 32 | 79 | 131 | 176 | 214 | 261 | 308 | 339
|  |  | 1353 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Trim Coil Design/Procurement | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 29.6 | 74.5 | 145.7 | 191.5 | 259.3 | 327 | 355.5 | 519.3 | 733 | 958.1 | 1172.8 | 1341.2 | 1431.2 | 1488.8 | 1584.2 | 1671.5 | 1713.2 | 1736.8 | 1738.3 | 1803 | 1867.7 | 1867.7
|  |  | 1354 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 9.652
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
|  |  |  | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | I&C Proc & Coil Assy | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 12 | 17 | 20 | 27 | 31 | 31 | 46 | 58 | 61 | 67 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 73
|  |  | 1355 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Cryostat Dsn/Proc | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 14 | 24 | 46 | 89 | 133 | 154 | 177 | 200 | 207 | 207 | 281 | 345 | 399 | 451 | 487 | 518 | 532
|  |  | 1701;1751 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | -0.23265 | 2.8487 | 4.3022 | 4.3022 | 5.2332 | 5.2332
|  |  |  | CPI | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | SPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Base support Structure Dsn/Proc | BCWS | 0 | 0 | 0 | 0 | 0 | 43 | 79 | 107 | 148 | 163 | 165 | 166 | 167 | 173 | 191 | 208 | 226 | 246 | 252 | 253 | 254 | 255
|  |  | 1702;1752 | BCWP | 0 | 0 | 0 | 0 | 10.83
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | FP Assembly | BCWS | 9 | 24 | 41 | 67 | 92 | 120 | 139 | 164 | 201 | 236 | 271 | 307 | 339 | 371 | 404 | 438 | 477 | 496 | 503 | 510 | 517
|  |  | 1806 | BCWP | 0 | 3 | 25 | 27.7447 | 36.15
|  |  |  | ACWP | 0 | 0 | -0.128 | 2.007 | 2.007
|  |  |  | CPI | #DIV/0! | #DIV/0! | -195.3125 | 13.824 | 18.012
|  |  |  | SPI | 0 | 0.125 | 0.60976 | 0.4141 | 0.39293

## BCWS by JOB
[5 empty] | BCWS Monthly |  |  |  |  | BCWS Monthly | [11 empty] | BCWS Monthly | [11 empty] | FY 2010 BCWS Monthly | [11 empty] | FY 2011 BCWS Monthly
RLM | JOB | notes | BTC | BCWS May 1,2007 - Oct 31,2007 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 |  | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12 | JUN fy12 | JUL fy12 | AUG fy12 | SEP fy12
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON |  | 3844 | 372 | 61 | 54 | 54 | 59 | 49 | 95 | 83 | 62 | 91 | 87 | 87 | 91 | 87 | 87 | 91 | 87 | 87 | 107 | 84 | 79 | 98 | 93 | 102 | 102 | 93 | 102 | 102 | 98 | 98 | 95 | 82 | 69 | 87 | 87 | 100 | 95 | 87 | 95 | 91 | 95 | 91 | 80 | 76 | 64 | 80
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON |  | 497 | 75 | 13 | 12 | 12 | 13 | 11 | 14 | 13 | 10 | 14 | 13 | 13 | 14 | 13 | 13 | 14 | 13 | 13 | 14 | 12 | 11 | 13 | 13 | 14 | 14 | 13 | 14 | 14 | 13 | 13 | 9 | 8 | 7 | 8 | 8 | 9 | 9 | 8 | 9 | 9 | 9 | 9 | 5 | 5 | 4 | 5
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY |  | 1453 | 181 | 30 | 29 | 29 | 31 | 26 | 36 | 31 | 23 | 34 | 32 | 32 | 34 | 32 | 32 | 34 | 32 | 31 | 38 | 30 | 28 | 35 | 33 | 36 | 36 | 33 | 36 | 36 | 35 | 31 | 38 | 33 | 28 | 35 | 35 | 40 | 38 | 35 | 38 | 36 | 38 | 36 | 23 | 22 | 19 | 23 | 1
| Total Jim Anderson |  | 5794 | 628 | 104 | 95 | 95 | 103 | 86 | 145 | 127 | 95 | 139 | 132 | 132 | 139 | 132 | 132 | 139 | 132 | 131 | 159 | 126 | 118 | 146 | 139 | 152 | 152 | 139 | 152 | 152 | 146 | 142 | 142 | 123 | 104 | 130 | 130 | 149 | 142 | 130 | 142 | 136 | 142 | 136 | 108 | 103 | 87 | 108 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK |  | 409 | 73 |  | 17 | 25 | 4 |  | 27 | 29 | 2 |  |  |  | 30 | 27 | 12 | 12 | 12 | 12 | 1 | [11 empty] | 60 | 88 | 34 | 17
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** |  | -252 | -252 | -162 |  |  | -90
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI |  | 348 | 203 | 17 | 24 | 51 | 56 | 29 | 26 | 22 | 28 | 41 | 35 | 11 | 5 | 3
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK |  | 1039 | 815 | 144 | 7 | 103 | 82 | 27 | 452 | 64 | 22 | 25 | 23 | 20 | 11 | 10 | 10 | 10 | 6 | 6 | [12 empty] | 12 | 4 | 1
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI |  | 2769 | 1170 | 237 | 171 | 231 | 182 | 136 | 213 | 188 | 133 | 222 | 211 | 183 | 209 | 193 | 156 | 87 | 16 | 1
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  | 501 | 147 |  | 4 | 19 | 20 | 47 | 57 | 43 | 26 | 42 | 43 | 42 | 26 | 24 | 25 | 26 | 33 | 24
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA |  | 1987 | 332 | 64 | 47 | 47 | 52 | 43 | 79 | 58 | 43 | 63 | 60 | 86 | 71 | 67 | 66 | 68 | 64 | 63 | 89 | 65 | 60 | 74 | 81 | 84 | 83 | 74 | 68 | 62 | 59 | 59 | 61 | 27
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK |  | 522 | 160 |  | 11 | 54 | 42 | 23 | 30 | 24 | 35 | 81 | 46 | 43 | 13 | 9 |  |  |  | 36 | 39 | 31 | 5
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA |  | 5751.56 | 1422.71 | 190.37 | 196.09 | 293.87 | 280.2 | 203.57 | 258.61 | 185.57 | 181.99 | 245.18 | 192.01 | 210.26 | 195.74 | 183.27 | 168.47 | 204.25 | 192.9 | 204.82 | 221.28 | 189.05 | 115.13 | 171.14 | 256.69 | 252.23 | 167.24 | 160.74 | 136.4 | 113.32 | 108.17 | 108.17 | 113.32 | 51.51
D - Larry Dudek | Job: 1815 - Field Period Assy |  | 1335 | 0 | [14 empty] | 155 | 55 | 13 | 3 | 30 | 40 | 58 | 49 | 92 | 102 | 112 | 110 | 172 | 123 | 126 | 64 | 31
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD |  | 69 | 0 | [28 empty] | 13 | 21 | 3 | 2 | 3 | 2 | 0 | 2 | 12 | 11
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD |  | 170 | 0 | [20 empty] | 22 | 20 | 25 | 3 | [5 empty] | 0 | 7 | 15 | 19 | 19 | 22 | 16 | 2
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON |  | 290 | 239 | 12 | 15 | 22 | 96 | 37 | 57 | 24 | 17 | 9 | 1
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON |  | 31 | 0 | [29 empty] | 9 | 8 | 1 | 2 | 2 | 7 | 2
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON |  | 263 | 0 | [22 empty] | 25 | 24 | 28 | 24 |  |  |  | 23 | 20 | 17 | 26 | 29 | 33 | 14
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON |  | 133 | 13 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 6 | 5 | 4 | 5 | 5 | 6 | 6 | 5 | 6 | 5 | 6 | 5
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK |  | 46 | 0 | [17 empty] | 13 | 1 | 1 | 2 | 2 | 1 | 5 | 11 | 8 | 2
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER |  | 654 | 0 | [17 empty] | 23 | 18 |  | 59 | 35 | 21 | 23 | 17 |  |  | 30 | 44 | 61 | 57 | 49 | 55 | 42 | 32 | 29 | 26 | 30 | 2 | 1
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK |  | 105 | 0 | [17 empty] | 18 | 18 | 11 | 13 | 10 |  |  | 15 | 16 | 4
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH |  | 573 | 0 | [23 empty] | 7 | 8 | 23 | 24 | 21 | 23 | 25 | 57 | 58 | 73 | 68 | 60 | 57 | 45 | 24
D - Larry Dudek | Job: 7301 - Platform Design & |  | 202 | 0 | [16 empty] | 5 | 43 | 74 | 68 | 12
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY |  | 1416 | -306 | -308 |  |  |  |  | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 | 12 | 5 | 71 | 63 | 68 | 66 | 60 | 66 | 66 | 62 | 61 | 64 | 54 | 45 | 56 | 55 | 86 | 85 | 79 | 85 | 83 | 84 | 81 | 79 | 77 | 70 | 4
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY |  | 1406 | 0 | [20 empty] | 10 | 38 | 42 | 42 | 38 | 42 | 42 | 40 | 42 | 42 | 40 | 44 | 40 | 38 | 83 | 87 | 83 | 87 | 87 | 87 | 87 | 83 | 87 | 91 | 4
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY |  | 4511 | 0 | [18 empty] | 59 | 393 | 369 | 129 | 103 | 102 | 108 | 147 | 75 | 74 | 107 | 243 | 98 | 128 | 224 | 105 | 206 | 295 | 206 | 172 | 181 | 197 | 151 | 248 | 211 | 157 | 23
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY |  | 414 | 0 | [20 empty] | 6 | 24 | 26 | 26 | 24 | 26 | 26 | 25 | 25 | 26 | 23 | 19 | 24 | 24 | 27 | 26 | 24 | 13
| Total Larry Dudek |  | 24692.56 | 4016.71 | 196.37 | 494.09 | 847.87 | 726.2 | 547.57 | 1204.61 | 641.57 | 490.99 | 733.18 | 615.01 | 599.26 | 565.74 | 520.27 | 441.47 | 567.25 | 382.9 | 368.82 | 467.28 | 499.05 | 700.13 | 870.14 | 709.69 | 742.23 | 653.24 | 657.74 | 669.4 | 589.32 | 545.17 | 610.17 | 830.32 | 573.51 | 417 | 544 | 389 | 562 | 619 | 482 | 428 | 358 | 375 | 324 | 410 | 375 | 318 | 31 | 0 | 0 | 0 | 0 | 0 | 0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH |  | 258 | 79 | 5 |  |  | 9 | 30 | 35 | 25 | 30 | 48 | 32 | 33 | 11
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH |  | 1629 | 0 | [10 empty] | 4 | 20 | 40 | 136 | 173 | 325 | 270 | 183 | 101 | 56 | 63 | 65 | 64 | 69 | 32 | [8 empty] | 2 | 12 | 14
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN |  | 339 | 0 | [23 empty] | 4 | 8 | 16 | 2 | 2 | 47 | 52 | 45 | 38 | 47 | 47 | 31
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH | updated baseline to include trim coil 36 coil set | 1867.7 | 0 | [6 empty] | 29.6 | 44.9 | 71.2 | 45.8 | 67.8 | 67.7 | 28.5 | 163.8 | 213.7 | 225.1 | 214.7 | 168.4 | 90 | 57.6 | 95.4 | 87.3 | 41.7 | 23.6 | 1.5 | 64.7 | 64.7
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH |  | 73 | 0 | [9 empty] | 4 | 4 | 4 | 5 | 3 | 7 | 4 |  | 15 | 12 | 3 | 6 | 4 | [12 empty] | 2
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH |  | 1004 | 289 | 8 | 65 | 60 | 35 | 60 | 61 | 59 | 56 | 59 | 58 | 104 | 57 | 57 | 56 | 103 | 54 | 52
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod |  | -36 | -36 | -36
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER |  | -84 | -84 | 5 | 1 |  | -90
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON |  | 280 | 186 | 12 | 23 | 8 | 15 | 12 | 116 | 56 | 19 | 17 | 2
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON |  | 1208 | 1114 | 177 | 276 | 250 | 191 | 102 | 118 | 26 | 19 | 25 | 24
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER |  | 118 | 118 | 30 |  | 51 | 37
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN |  | 186 | 186 | 7 | 31 | 32 | 58 | 36 | 22 | 0
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN |  | 1074 | 0 | [13 empty] | 32 | 109 | 131 | 131 | 143 | 93 | 51 | 63 | 60 | 66 | 66 | 60 | 66 | 3
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON |  | 861 | 6 | 6 | [7 empty] | 28 | 27 | 27 | 28 | 27 | 48 | 31 | 47 | 58 | 77 | 61 | 53 | 26 | 20 | 23 | 23 | 20 | 23 | 23 | 21 | 4 | 42 | 42 | 39 | 34 | 3
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER |  | 207 | 0 | [17 empty] | 6 | 4 | 4 | 10 | 22 | 43 | 44 | 21 | 23 | 23 | 7
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN |  | 164 | 43 | [5 empty] | 43 | 36 | 28 | 41 | 15 | 1
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER |  | 325 | 0 | [29 empty] | 74 | 64 | 54 | 52 | 36 | 31 | 14
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN |  | 91 | 0 | [10 empty] | 1 | 1 | 1 | 6 | 18 | 17 | 18 | 20 | 6 | 1 | 1 | 1 | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs |  | 517 | 120 | 9 | 15 | 17 | 26 | 25 | 28 | 19 | 25 | 37 | 35 | 35 | 36 | 32 | 32 | 33 | 34 | 39 | 19 | 7 | 7 | 7
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE |  | 1618 | 200 | 34 | 32 | 32 | 35 | 29 | 38 | 33 | 25 | 36 | 34 | 34 | 36 | 34 | 34 | 36 | 34 | 33 | 40 | 31 | 30 | 37 | 35 | 38 | 38 | 35 | 38 | 38 | 37 | 33 | 40 | 34 | 29 | 36 | 36 | 42 | 40 | 36 | 40 | 38 | 40 | 38 | 45 | 43 | 37 | 45
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN |  | 2519 | 404 | 82 | 76 | 63 | 69 | 53 | 61 | 53 | 40 | 59 | 56 | 56 | 59 | 56 | 56 | 59 | 56 | 56 | 61 | 48 | 45 | 56 | 53 | 59 | 59 | 53 | 59 | 59 | 56 | 56 | 59 | 51 | 43 | 53 | 53 | 61 | 59 | 53 | 59 | 56 | 59 | 56 | 48 | 46 | 39 | 48 | 2
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN |  | 1412 | 196 | 33 | 32 | 32 | 35 | 29 | 35 | 30 | 23 | 33 | 32 | 32 | 33 | 32 | 32 | 33 | 32 | 32 | 35 | 27 | 26 | 32 | 30 | 33 | 33 | 30 | 33 | 33 | 32 | 32 | 33 | 29 | 24 | 30 | 30 | 35 | 33 | 30 | 33 | 32 | 33 | 32 | 32 | 30 | 26 | 32 | 2
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS |  | 1160 | 207 | 37 | 36 | 36 | 39 | 32 | 27 | 24 | 18 | 26 | 25 | 25 | 26 | 25 | 25 | 26 | 25 | 25 | 27 | 21 | 20 | 25 | 24 | 26 | 26 | 24 | 26 | 26 | 25 | 25 | 26 | 22 | 19 | 24 | 24 | 27 | 26 | 24 | 26 | 25 | 26 | 25 | 25 | 24 | 20 | 25
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS |  | 592 | 123 |  | 27 | 27 | 30 | 18 | 21 | 20 | 15 | 22 | 25 | 35 | 37 | 35 | 18 | 12 | 12 | 12 | 13 | 14 | 14 | 18 | 18 | 16 | 16 | 14 | 11 | 9 | 9 | 9 | 9 | 6 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks |  | 19 | 19 | 15 | 4
H - Phil Heitzenroeder | Job: 8215 Plant Design |  | 129 | 18 |  |  |  | 8 | 7 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3
| Total Phil Heitzenroeder |  | 17530.7 | 3188 | 424 | 618 | 608 | 497 | 433 | 608 | 413.6 | 344.9 | 505.2 | 417.8 | 461.8 | 418.7 | 375.5 | 644.8 | 856.7 | 999.1 | 943.7 | 810.4 | 517 | 369.6 | 442.4 | 422.3 | 412.7 | 404.6 | 301.5 | 362.7 | 283.7 | 192 | 209 | 338 | 295 | 251 | 283 | 238 | 248 | 193 | 150 | 165 | 158 | 165 | 158 | 157 | 150 | 127 | 153 | 4 | 0 | 0 | 0 | 0 | 0
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN |  | 52 | -104 | -104 | [16 empty] | 0 | 0 | 0 | 12 | 11 | 14 | 4 | 3 | 1 | 1 | 3 | 6 | 6 | 4 | 3 | 8 | 27 | 29 | 15 | 6 | 3
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN |  | 604 | 1 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 38 | 31 | 41 | 53 | 18 | 1 | 1 | 1 | 1 | 14 | 74 | 1 | 0 | 62 | 52 | 66 | 66 | 72
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN |  | 1084 | 0 | [21 empty] | 11 | 26 | 33 | 32 | 41 | 42 | 60 | 69 | 103 | 73 | 55 | 67 | 75 | 111 | 97 | 91 | 56 | 31 | 10 | 1
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN |  | 682 | 0 | [17 empty] | 21 | 23 | 20 | 18 | 17 | 37 | 34 | 29 | 37 | 43 | 40 | 37 | 39 | 22 | 18 | 19 | 13 |  |  | 3 | 35 | 33 | 35 | 56 | 53
V - Al vonHalle | Job: 5101 - Network and Fiber |  | 151 | 0 | [26 empty] | 3 | 2 | 2 | 2 | 14 | 14 | 18 | 23 | 32 | 31 | 10
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA |  | 197 | 0 | [22 empty] | 5 | 3 | 2 | 2 | 21 | 25 | 24 | 15 | 6 | 5 | 7 | 9 | 5 | 14 | 20 | 22 | 12
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA |  | 165 | 0 | [24 empty] | 4 | 7 | 11 | 21 | 7 | 7 | 12 | 10 | 12 | 9 | 10 | 13 | 17 | 15 | 10
V - Al vonHalle | Job: 5401 - Facility Timing & |  | 204 | 0 | [26 empty] | 5 | 4 | 3 | 16 | 25 | 24 | 15 | 16 | 32 | 24 | 10 | 15 | 12 | 3
V - Al vonHalle | Job: 5501 - Real Time Control |  | 131 | 0 | [26 empty] | 5 | 7 | 6 | 6 | 8 | 7 | 9 | 14 | 21 | 25 | 9 | 13 | 1
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA |  | 221 | 0 | [25 empty] | 2 | 2 | 3 | 4 | 19 | 20 | 17 | 18 | 18 | 34 | 32 | 29 | 7 | 11 | 5
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA |  | 71 | 8 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE |  | 767 | 0 | [18 empty] | 22 | 32 | 29 | 24 | 21 | 27 | 24 | 27 | 24 | 22 | 26 | 27 | 14 | 20 | 9 | [8 empty] | 116 | 110 | 94 | 99
| Total Al vonHalle |  | 4329 | -95 | -103 | 1 | 1 | 2 | 1 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 61 | 77 | 94 | 114 | 82 | 106 | 104 | 96 | 120 | 173 | 263 | 187 | 242 | 261 | 226 | 250 | 272 | 348 | 253 | 197 | 168 | 112 | 55 | 59 | 169 | 110 | 94 | 99 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 52346.26 | 7737.71 | 621.37 | 1208.09 | 1551.87 | 1328.2 | 1067.57 | 1960.61 | 1185.17 | 932.89 | 1380.38 | 1167.81 | 1196.06 | 1126.44 | 1030.77 | 1221.27 | 1565.95 | 1517 | 1446.52 | 1497.68 | 1219.05 | 1281.73 | 1572.54 | 1352.99 | 1412.93 | 1313.84 | 1194.24 | 1304.1 | 1198.02 | 1146.17 | 1148.17 | 1552.32 | 1252.51 | 998 | 1207 | 1029 | 1307 | 1207 | 959 | 903 | 764 | 737 | 677 | 844 | 738 | 626 | 391
23005.65
corrected

## ACWP by JOB
|  |  |  | ACWP Monthly |  |  |  |  | ACWP Monthly
RLM | JOB | ACWP May 1,2007 - Oct 31,2007 |  | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12 | JUN fy12 | JUL fy12 | AUG fy12 | SEP fy12
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON | 339.8648 | 8101 | 55.8777 | 58.9419 | 48.7333 | 48.726 | 80 | 47.586
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON | 124.583 | 8102 | 30.964 | 22.991 | 13.862 | 23.695 | 17.316 | 15.755
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY | 229.2978 | 8998 | 24.8767 | 24.9933 | 28.3578 | 34.873 | 83.276 | 32.921
| Total Jim Anderson | 693.7456 |  | 111.7184 | 106.9261 | 90.9531 | 107.294 | 180.592 | 96.262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 166.3099 | 1204 | 16.0209 | 1.3261 | 5.4769 | 16.8 | 100.76 | 25.926
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -251.7703 | 1250 | -161.88 | 0 | -92.5573 |  | 2.667
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 105.1314 | 1408 | 23.8679 | 11.6976 | 31.1989 | 21.389 | 8.337 | 8.641
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 304.0759 | 1431 | 144.2801 | 0 | 47.0428 |  | 96.358 | 16.395
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1245.0187 | 1451 | 283.7075 | 218.7955 | 157.2876 | 240.296 | 190.337 | 154.595
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 339.23 | 1459 | 42.2044 | 55.2785 | 51.7021 | 64.806 | 75.462 | 49.777
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA | 376.0357 | 1802 | 84.3784 | 51.4086 | 66.9277 | 81.881 | 56.68 | 34.76
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 156.7959 | 1803 | 34.185 | 34.0075 | 22.4994 | 37.434 | 13.088 | 15.582
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 850.6911 | 1810 | 106.9026 | 120.8905 | 140.889 | 198.049 | 167.112 | 116.848
D - Larry Dudek | Job: 1815 - Field Period Assy | 0
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD | 0
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON | 122.5926 | 3101 | 27.0665 | 15.8846 | 38.1895 | 30.572 | 9.403 | 1.477
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON | 0
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON | 22.9402 | 3901 | 2.6208 | 4.2019 | 6.7205 | 4.117 | 2.396 | 2.884
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK | 0
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER | 0
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK | 0
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 0
D - Larry Dudek | Job: 7301 - Platform Design & | 0
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -282.2793 | 7401 | -297.561 | 4.2205 | 4.0193 | 6.749 | 0.293 | 0
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY | 0
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY | 0
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY | 0
| Total larry Dudek | 3154.7718 |  | 305.793 | 517.7113 | 479.3966 | 702.093 | 722.893 | 426.885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 47.602 | 1302 | 4.26 | 1.5406 | 1.4053 | 6.578 | 30.601 | 3.217
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH | 0
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN | 0
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH | 9.652 | 1354 | [5 empty] | 9.652
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH | 340.5435 | 1361 | -6.0157 | 40.395 | 54.4283 | 96.543 | 85.973 | 69.22
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod | -34.9474 | 1404 | -35.9384 | 0 | 0 | 0.835 | 0.156 | 0
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -65.1126 | 1411 | 7.495 | 2.0635 | -92.7721 |  | 18.101
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 87.2639 | 1416 | 12.3179 | 9.522 | 18.891 | 27.345 | -0.069 | 19.257
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 769.6327 | 1421 | 81.6509 | 107.2854 | 109.3563 | 253.823 | 122.667 | 94.85
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER | 86.2332 | 1429 | 29.9725 | 17.1863 | 20.5674 | 12.911 | 5.155 | 0.441
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN | 160.0001 | 1501 | 54.1006 | 47.3749 | 37.1207 | 36.056 | 2.262 | -16.914
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 | 1550 | [5 empty] | 0
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON | 0
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER | 5.2332 | 1701 | -0.23265 | 3.0813 | 1.4536 |  | 0.931
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN | 32.6 | 1702 | [5 empty] | 32.6
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs | 2.007 |  |  |  | -0.128 | 2.135
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 119.964 | 1901 | 36.462 | 17.472 | 11.047 | 31.667 | 13.061 | 10.255
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 373.1311 | 8202 | 59.5964 | 58.6317 | 58.6029 | 87.374 | 54.224 | 54.702
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN | 55.866 | 8203 | 5.0798 | 5.2382 | 1.641 | 10.093 | 14.509 | 19.305
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS | 272.0633 | 8204 | 42.5836 | 53.1523 | 47.1084 | 50.469 | 32.096 | 46.654
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS | 96.1341 | 8205 | 17.5068 | 20.0831 | 22.4922 | 21.472 | 10.542 | 4.038
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks | 46.8765 | 8210 | 8.3642 | 4.8261 | 9.5912 | 16.099 | 6.371 | 1.625
H - Phil Heitzenroeder | Job: 8215 Plant Design | 0
| Total Phil Heitzenroeder | 2404.7427 |  | 317.203 | 387.8524 | 300.8052 | 653.4 | 396.58 | 348.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | -104.1027 | 4101 | -104.1027 | 0 | 0
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN | 0
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN | 0
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | -0.55581 | 4501 | -0.15696 | 0 | -0.041849 |  | -0.357
V - Al vonHalle | Job: 5101 - Network and Fiber | 0
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA | 0
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA | 0
V - Al vonHalle | Job: 5401 - Facility Timing & | 0
V - Al vonHalle | Job: 5501 - Real Time Control | 0
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 0
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE | 0
| Total Al vonHalle | -104.6585 |  | -104.2596 | 0 | -0.041849 | 0 | -0.357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total project | 6148.6016 |  | 630.4547 | 1012.4898 | 871.113 | 1462.787 | 1299.708 | 872.049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
corrected

## BCWP by JOB
|  |  | BCWP Monthly |  |  |  |  | BCWP Monthly | [59 empty] | BCWP Cum |  |  | BCWP Cum | [11 empty] | FY 2009 BCWP Cum | [11 empty] | FY 2010 BCWP Cum
RLM | JOB | BCWP May 1,2007 - Oct 31,2007 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | Sum of EVC
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON | 373.246 | 59 | 56 | 54 | 60.1165 | 48.9835 | 95.146 | [59 empty] | 169 | 229.1165 | 278.1 | 373.246 | [41 empty] | A | 8101 | 373.2469
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON | 75.048 | 13 | 12 | 12 | 12.6048 | 10.8152 | 14.628 | [59 empty] | 37 | 49.6048 | 60.42 | 75.048 | [42 empty] | 8102 | 75.048
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY | 179.404 | 30 | 29 | 29 | 30.2576 | 25.7824 | 35.364 | [59 empty] | 88 | 118.2576 | 144.04 | 179.404 | [42 empty] | 8998 | 179.4042
| Total Jim Anderson | 627.698 | 102 | 97 | 95 | 102.9789 | 85.5811 | 145.138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 294 | 396.9789 | 482.56 | 627.698 | [41 empty] | A Total |  | 627.6991
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 119.183 |  | 55 | 9 | 4.4894 | 14.5406 | 36.153 | [59 empty] | 64 | 68.4894 | 83.03 | 119.183 | [41 empty] | D | 1204 | 119.1836
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -251.695 | -162 |  | -90 | 0.30528 | 0.00472 | -0.005 | [59 empty] | -252 | -251.6947 | -251.69 | -251.695 | [42 empty] | 1250 | -251.6947
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 203.968 | 7 | 33 | 23 | 93.4268 | 5.9732 | 41.568 | [59 empty] | 63 | 156.4268 | 162.4 | 203.968 | [42 empty] | 1408 | 203.9684
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 589.7 | 81 | 77 |  | 98.8971 | 52.7029 | 280.1 | [59 empty] | 158 | 256.8971 | 309.6 | 589.7 | [42 empty] | 1431 | 589.746
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1439.27 | 236 | 176 | 299 | 235.222 | 237.778 | 255.27 | [59 empty] | 711 | 946.222 | 1184 | 1439.27 | [42 empty] | 1451 | 1439.2702
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 168.318 |  | 18 | 14 | 12.1632 | 91.1368 | 33.018 | [59 empty] | 32 | 44.1632 | 135.3 | 168.318 | [42 empty] | 1459 | 168.3665
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA | 306.71 | 64 | 47 | 47 | 52.1107 | 42.5393 | 54.06 | [59 empty] | 158 | 210.1107 | 252.65 | 306.71 | [42 empty] | 1802 | 306.7178
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 68.51 |  | 12 | 42 | 10.0883 | 4.2117 | 0.21 | [59 empty] | 54 | 64.0883 | 68.3 | 68.51 | [42 empty] | 1803 | 68.5159
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 1293.547 | 190 | 193 | 267 | 204.5431 | 251.9569 | 187.047 | [59 empty] | 650 | 854.5431 | 1106.5 | 1293.547 | [42 empty] | 1810 | 1293.58
D - Larry Dudek | Job: 1815 - Field Period Assy | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 1815 | 0
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 2101 | 0
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 2201 | 0
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON | 146.533 | 12 | 42 | 54 | 30.94 | 5.4811 | 2.1119 | [59 empty] | 108 | 138.94 | 144.4211 | 146.533 | [42 empty] | 3101 | 146.5334
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 3601 | 0
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 3801 | 0
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON | 14.048 | 2 | 2 | 2 | 3.3261 | 2.0333 | 2.6886 | [59 empty] | 6 | 9.3261 | 11.3594 | 14.048 | [42 empty] | 3901 | 14.0484
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 6101 | 0
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 6201 | 0
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 6301 | 0
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 6401 | 0
D - Larry Dudek | Job: 7301 - Platform Design & | 2.614 |  | 1 | 2 | -0.44672 | -0.003282 | 0.064 | [59 empty] | 3 | 2.5533 | 2.55 | 2.614 | [42 empty] | 7301 | 2.6149
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -306.2 | -308 |  |  | -0.3 | 0 | 2.1 | [59 empty] | -308 | -308.3 | -308.3 | -306.2 | [42 empty] | 7401 | -306.1947
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 7501 | 0
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 7503 | 0
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 7601 | 0
| Total larry Dudek | 3794.506 | 122 | 656 | 669 | 744.7652 | 708.3553 | 894.3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 1447 | 2191.7652 | 2900.1205 | 3794.506 | [41 empty] | D Total |  | 3794.6557
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 61.085 | 5 |  |  | 42.3325 | 13.0175 | 0.735 | [59 empty] | 5 | 47.3325 | 60.35 | 61.085 | [41 empty] | H | 1302 | 61.2847
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 1352 | 0
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 1353 | 0
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 1354 | 0
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 1355 | 0
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH | 331.282 | 4 | 45 | 59 | 91.4121 | 68.2379 | 63.632 | [59 empty] | 108 | 199.4121 | 267.65 | 331.282 | [42 empty] | 1361 | 331.2825
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod | -35.94 | -36 |  |  | 0.06 | 0 | 0 | [59 empty] | -36 | -35.94 | -35.94 | -35.94 | [42 empty] | 1404 | -35.94
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -80.39 | 6 | 4 | -90 | -0.3908 | 0.0008 | 0 | [59 empty] | -80 | -80.3908 | -80.39 | -80.39 | [42 empty] | 1411 | -80.3908
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 103.832 | 4 | 29 | 55 | 15.1533 | 0.046734 | 0.632 | [59 empty] | 88 | 103.1533 | 103.2 | 103.832 | [42 empty] | 1416 | 103.5594
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 940.494 | 62 | 167 | 406 | 76.1819 | 30.1181 | 199.194 | [59 empty] | 635 | 711.1819 | 741.3 | 940.494 | [42 empty] | 1421 | 940.2338
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER | 78.065 | 30 |  | 44 | 9.2365 | -9.2365 | 4.065 | [59 empty] | 74 | 83.2365 | 74 | 78.065 | [42 empty] | 1429 | 78.0654
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN | 145.001 | 2 | 43 | 30 | 6.9424 | 54.7576 | 8.301 | [59 empty] | 75 | 81.9424 | 136.7 | 145.001 | [42 empty] | 1501 | 145.0015
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 1550 | 0
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON | 14.598 |  | 6 |  | 0.2288 | 8.3712 | -0.002 | [59 empty] | 6 | 6.2288 | 14.6 | 14.598 | [42 empty] | 1601 | 14.5983
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 1701 | 0
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN | 11.09 |  |  |  | 0 | 10.83 | 0.26 | [59 empty] | 0 | 0 | 10.83 | 11.09 | [42 empty] | 1702 | 11.0903
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 1751 | 0
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 1752 | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs | 39.838 |  | 3 | 22 | 2.7447 | 8.4053 | 3.688 | [59 empty] | 25 | 27.7447 | 36.15 | 39.838 | [42 empty] | 1806 | 39.8389
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 199.131 | 34 | 32 | 32 | 34.6417 | 28.9183 | 37.571 | [59 empty] | 98 | 132.6417 | 161.56 | 199.131 | [42 empty] | 1901 | 199.1319
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 403.1 | 108 | 100 | 87 | -5.797 | 53.257 | 60.64 | [59 empty] | 295 | 289.203 | 342.46 | 403.1 | [42 empty] | 8202 | 403.1012
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN | 194.2511 | 31 | 29 | 29 | 41.9084 | 29.5616 | 33.7811 | [59 empty] | 89 | 130.9084 | 160.47 | 194.2511 | [42 empty] | 8203 | 194.2511
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS | 207.311 | 35 | 34 | 34 | 44.9102 | 33.0398 | 26.361 | [59 empty] | 103 | 147.9102 | 180.95 | 207.311 | [42 empty] | 8204 | 207.311
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS | 87.581 |  | 21 | 21 | 33.2674 | 0.73264 | 11.581 | [59 empty] | 42 | 75.2674 | 76 | 87.581 | [42 empty] | 8205 | 87.9122
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks | 18.814 | 15 | 4 |  | -0.1858 | -0.0042 | 0.004 | [59 empty] | 19 | 18.8142 | 18.81 | 18.814 | [42 empty] | 8210 | 18.8142
H - Phil Heitzenroeder | Job: 8215 Plant Design | 3 |  |  |  | 0 | 0 | 3 | [59 empty] | 0 | 0 | 0 | 3 | [42 empty] | 8215 | 2.9601
| Total Phil Heitzenroeder | 2722.1431 | 300 | 517 | 729 | 392.6461 | 330.0539 | 453.4431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 1546 | 1938.6461 | 2268.7 | 2722.1431 | [41 empty] | H Total |  | 2722.1059
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | -104.1 | -104 |  |  | -0.1 | 0 | 0 | [59 empty] | -104 | -104.1 | -104.1 | -104.1 | [41 empty] | V | 4101 | -104.1
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 4301 | 1.0132
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 4401 | 0
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 4501 | 0
V - Al vonHalle | Job: 5101 - Network and Fiber | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 5101 | 0
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 5201 | 0
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 5301 | 0
V - Al vonHalle | Job: 5401 - Facility Timing & | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 5401 | 0
V - Al vonHalle | Job: 5501 - Real Time Control | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 5501 | 0
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 5601 | 0
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 9.3 | 1 | 1 | 1 | 2.7232 | 1.2568 | 2.32 | [59 empty] | 3 | 5.7232 | 6.98 | 9.3 | [42 empty] | 5801 | 9.2529
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE | 0 |  |  |  | 0 | 0 | 0 | [59 empty] | 0 | 0 | 0 | [43 empty] | 8501 | 0
| Total Al vonHalle | -94.8 | -103 | 1 | 1 | 2.6232 | 1.2568 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | -101 | -98.3768 | -97.12 | -94.8 | [41 empty] | V Total |  | -93.8339
|  | 7049.5471 | 421 | 1271 | 1494 | 1243.0134 | 1125.2471 | 1495.2866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3186 | 4429.0134 | 5554.2605 | 7049.5471 | [41 empty] | Grand Total |  | 7050.6268
corrected
corrected

## Contingency
| period ending | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12
Cost
| Baseline | 14380 | 14380 | 14380 | 14380 | 14380 | 14380
| ECP drawdown | 0 | 0 | 0 | 0
| (ECP Number) | none | none | none | none | none | none
| EAC (overrun)/underrun | 0 | 0 | 0 | 0 | -531 | -42.7469
| Cost Variance (overrun)/underrun | -209.4547 | 49.0555 | 671.9424 | 452.1688 | 278 | 900.9455
| Schedule Slip (@$202k/mo.) | 0 | 0 | 0 | -221.2381 | -548.2857 | -375.114
| FREE BALANCE ($K) | 14170.5453 | 14429.0554 | 15051.9424 | 14610.9308 | 13578.7143 | 14863.0846
| BCWR | 50433 | 49162 | 47668 | 46424 | 45299 | 43803.4529
| FREE BALANCE (% of ETC) | 28.1% | 29.35% | 31.58% | 31.47% | 29.98% | 33.93%
| Target Drawdown Rate (%) | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3%
| BCWR | 50004 | 48796 | 47244 | 45880 | 44747 | 42784 | 41635 | 40752 | 39450 | 38335 | 37213 | 36161 | 35165 | 34114 | 32769 | 31484 | 30259 | 28922 | 27784 | 26546 | 25056 | 23790 | 22420 | 21112 | 19903 | 18646 | 17495 | 16340 | 15192 | 13640 | 12387 | 11389 | 10182 | 9153 | 7846 | 6639 | 5680 | 4777 | 4013 | 3276 | 2599 | 1755 | 1017 | 391 | 0
| BCWS | 621 | 1208 | 1552 | 1364 | 1133 | 1963 | 1149 | 883 | 1302 | 1115 | 1122 | 1052 | 996 | 1051 | 1345 | 1285 | 1225 | 1337 | 1138 | 1238 | 1490 | 1266 | 1370 | 1308 | 1209 | 1257 | 1151 | 1155 | 1148 | 1552 | 1253 | 998 | 1207 | 1029 | 1307 | 1207 | 959 | 903 | 764 | 737 | 677 | 844 | 738 | 626 | 391 |  | 50625
| Target Contingency Freebalance ($K) | 14151.132 | 13809.268 | 13370.052 | 12984.04 | 12663.401 | 12107.872 | 11782.705 | 11532.816 | 11164.35 | 10848.805 | 10531.279 | 10233.563 | 9951.695 | 9654.262 | 9273.627 | 8909.972 | 8563.297 | 8184.926 | 7862.872 | 7512.518 | 7090.848 | 6732.57 | 6344.86 | 5974.696 | 5632.549 | 5276.818 | 4951.085 | 4624.22 | 4299.336 | 3860.12 | 3505.521 | 3223.087 | 2881.506 | 2590.299 | 2220.418 | 1878.837 | 1607.44 | 1351.891 | 1135.679 | 927.108 | 735.517 | 496.665 | 287.811 | 110.653 | 0
Schedule
| Baseline | 11 | 11 | 11 | 11 | 11 | 11
| ECP Schedule Drawdown | 0 | 0 | 0 | 0 | 0 | 0
| Critical path Schedule Slip (months) | 0 | 0 | 0 | -1.0952 | -2.7143 | -1.857
| FREE BALANCE (months) | 11 | 11 | 11 | 9.9048 | 8.2857 | 9.143
| Target (months) | 10.8036 | 10.6071 | 10.4107 | 10.2143 | 10.0179 | 9.8214 | 9.625 | 9.4286 | 9.2321 | 9.0357 | 8.8393 | 8.6429 | 8.4464 | 8.25 | 8.0536 | 7.8571 | 7.6607 | 7.4643 | 7.2679 | 7.0714 | 6.875 | 6.6786 | 6.4821 | 6.2857 | 6.0893 | 5.8929 | 5.6964 | 5.5 | 5.3036 | 5.1071 | 4.9107 | 4.7143 | 4.5179 | 4.3214 | 4.125 | 3.9286 | 3.7321 | 3.5357 | 3.3393 | 3.1429 | 2.9464 | 2.75 | 2.5536 | 2.3571 | 2.1607 | 1.9643 | 1.7679 | 1.5714 | 1.375 | 1.1786 | 0.98214 | 0.78571 | 0.58929 | 0.39286 | 0.19643 | 7.272e-15

## COST PERFORMANCE BY RLM & JOB
NCSX Cost Performance Report
Period May 1, 2007 through October 31, 2007
(Measured against unofficial proposed baseline)
|  | CUMULATIVE | [6 empty] | MONTHLY
RLM | JOB | BCWS | BCWP | ACWP | SPI | CPI | schedule variance | cost variance | BCWS | BCWP | ACWP | SPI | CPI | sched variance | cost variance | BUDGET to COMPLETE (from May 1,2007) | % plan | % work completed | % spent | EAC | C=calculated JM=Job Mgr estimate | overrun/ (under) | Job Manager assessment
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON | 372 | 373.246 | 339.8648 | 1.0033 | 1.0982 | 1.246 | 33.3812 | 95 | 95.146 | 47.586 | 1.0015 | 1.9995 | 0.146 | 47.56 | 3843 | 9.68% | 9.712% | 8.844% | 3843 | RLS | 0 | 3843
| Job: 8102 - NCSX MIE Management ORNL-LYON | 75 | 75.048 | 124.583 | 1.0006 | 0.60239 | 0.048 | -49.535 | 14 | 14.628 | 15.755 | 1.0449 | 0.92847 | 0.628 | -1.127 | 499 | 15.03% | 15.04% | 24.97% | 499 | JL | 0 | 499
| Job: 8998 - Allocations-STRYKOWSKY | 181 | 179.404 | 229.2978 | 0.99118 | 0.78241 | -1.596 | -49.8938 | 36 | 35.364 | 32.921 | 0.98233 | 1.0742 | -0.636 | 2.443 | 1453 | 12.46% | 12.35% | 15.78% | 1536 | RLS | 83 | 1536
| Total Jim Anderson | 628 | 627.698 | 693.7456 | 0.99952 | 0.9048 | -0.302 | -66.0476 | 145 | 145.138 | 96.262 | 1.001 | 1.5077 | 0.138 | 48.876 | 5795 | 10.84% | 10.83% | 11.97% | 5878 |  | 83 | 5878
[8 empty] | #REF! | [6 empty] | 0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 73 | 119.183 | 166.3099 | 1.6326 | 0.71663 | 46.183 | -47.1269 | 27 | 36.153 | 25.926 | 1.339 | 1.3945 | 9.153 | 10.227 | 408 | 17.89% | 29.21% | 40.76% | 408 | JM | 0 | 408
| Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -252 | -251.695 | -251.7703 | 0.99879 | 0.9997 | 0.305 | 0.0753 | 0 | -0.005 | 0 | #DIV/0! | #DIV/0! | -0.005 | -0.005 | -252 | 100% | 99.88% | 99.91% | -252 | JM | 0 | -252
| Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 203 | 203.968 | 105.1314 | 1.0048 | 1.9401 | 0.968 | 98.8366 | 26 | 41.568 | 8.641 | 1.5988 | 4.8106 | 15.568 | 32.927 | 350 | 58% | 58.28% | 30.04% | 350 | JM | 0 | 350
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 815 | 589.7 | 304.0759 | 0.72356 | 1.9393 | -225.3 | 285.6241 | 452 | 280.1 | 16.395 | 0.61969 | 17.0845 | -171.9 | 263.705 | 1039 | 78.44% | 56.76% | 29.27% | 1039 | JM | 0 | 1039 | 92449
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1170 | 1439.27 | 1245.0187 | 1.2301 | 1.156 | 269.27 | 194.2513 | 213 | 255.27 | 154.595 | 1.1985 | 1.6512 | 42.27 | 100.675 | 2867 | 40.81% | 50.2% | 43.43% | 2867 | JM | 0 | 2867 | 115418
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 147 | 168.318 | 339.23 | 1.145 | 0.49618 | 21.318 | -170.912 | 57 | 33.018 | 49.777 | 0.57926 | 0.66332 | -23.982 | -16.759 | 501 | 29.34% | 33.6% | 67.71% | 671 | JM | 170 | 671 | 92448
| Job: 1802 - FP Assy Oversight&Support-VIOLA | 332 | 306.71 | 376.0357 | 0.92383 | 0.81564 | -25.29 | -69.3257 | 79 | 54.06 | 34.76 | 0.6843 | 1.5552 | -24.94 | 19.3 | 1989 | 16.69% | 15.42% | 18.91% | 1989 | JM | 0 | 1989
| Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 160 | 68.51 | 156.7959 | 0.42819 | 0.43694 | -91.49 | -88.2859 | 30 | 0.21 | 15.582 | 0.007 | 0.013477 | -29.79 | -15.372 | 522 | 30.65% | 13.12% | 30.04% | 522 | JM | 0 | 522 | 92447 | 115417
| Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 1422.71 | 1293.547 | 850.6911 | 0.90921 | 1.5206 | -129.163 | 442.8559 | 258.61 | 187.047 | 116.848 | 0.72328 | 1.6008 | -71.563 | 70.199 | 5745 | 24.76% | 22.52% | 14.81% | 5845 | JM | 100 | 5845
| Job: 1815 - Field Period Assy | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1334 | 0% | 0% | 0% | 1334 | C | 0 | 1334
| Job: 2101 - Fueling Systems-BLANCHARD | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 69 | 0% | 0% | 0% | 69 | C | 0 | 69
| Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 172 | 0% | 0% | 0% | 172 | C | 0 | 172
| Job: 3101 - Magnetic Diagnostics-STRATTON | 239 | 146.533 | 122.5926 | 0.61311 | 1.1953 | -92.467 | 23.9404 | 57 | 2.1119 | 1.477 | 0.037051 | 1.4299 | -54.8881 | 0.63493 | 291 | 82.13% | 50.35% | 42.13% | 291 | JM | 0 | 291
| Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 31 | 0% | 0% | 0% | 31 | C | 0 | 31
| Job: 3801 - Electron Beam Mapping-STRATTON | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 263 | 0% | 0% | 0% | 263 | C | 0 | 263
| Job: 3901 - Diagnostics sys Integration-STRATTON | 13 | 14.048 | 22.9402 | 1.0806 | 0.61237 | 1.048 | -8.8922 | 3 | 2.6886 | 2.884 | 0.89619 | 0.93223 | -0.31144 | -0.19544 | 132 | 9.848% | 10.64% | 17.38% | 215.5544 | C | 83.5544 | 215.5544
| Job: 6101 - Water Systems-DUDEK | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 46 | 0% | 0% | 0% | 46 | C | 0 | 46
| Job: 6201 - Cryogenic Syst-GETTELFINGER | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 655 | 0% | 0% | 0% | 655 | C | 0 | 655
| Job: 6301 - Utility Systems-DUDEK | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 105 | 0% | 0% | 0% | 105 | C | 0 | 105
| Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 573 | 0% | 0% | 0% | 573 | C | 0 | 573
| Job: 7301 - Platform Design & | 0 | 2.614 | 0 | #DIV/0! | #DIV/0! | 2.614 | 2.614 | 0 | 0.064 | 0 | #DIV/0! | #DIV/0! | 0.064 | 0.064 | 204 | 0% | 1.281% | 0% | 204 | C | 0 | 204
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -306 | -306.2 | -282.2793 | 1.0007 | 1.0847 | -0.2 | -23.9207 | 2 | 2.1 | 0 | 1.05 | #DIV/0! | 0.1 | 2.1 | 1417 | -21.59% | -21.61% | -19.92% | 1417 | RLS | 0 | 1417
| Job: 7501 - Construction Support Crew-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1407 | 0% | 0% | 0% | 1407 | C | 0 | 1407
| Job: 7503 - Machine Assembly (station 6)-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 4511 | 0% | 0% | 0% | 4511 | C | 0 | 4511
| Job: 7601 - Tooling Design & Fabrication-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 412 | 0% | 0% | 0% | 412 | C | 0 | 412
| Total Larry Dudek | 4016.71 | 3794.506 | 3154.7718 | 0.94468 | 1.2028 | -222.204 | 639.7342 | 1204.61 | 894.3855 | 426.885 | 0.74247 | 2.0951 | -310.2245 | 467.5005 | 24791 | 16.2% | 15.31% | 12.73% | 25144.5544 |  | 353.5544 | 25144.5544
0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 79 | 61.085 | 47.602 | 0.77323 | 1.2832 | -17.915 | 13.483 | 35 | 0.735 | 3.217 | 0.021 | 0.22847 | -34.265 | -2.482 | 257 | 30.74% | 23.77% | 18.52% | 257 | JM | 0 | 257
| Job: 1352 - PF Coil Procurement-KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1630 | 0% | 0% | 0% | 1630 | C | 0 | 1630
| Job: 1353 - CS Structure Procurement-DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 337 | 0% | 0% | 0% | 337 | C | 0 | 337
| Job: 1354 - Trim Coil Design &Procurement-KALISH | 0 | 0 | 9.652 | #DIV/0! | 0 | 0 | -9.652 | 0 | 0 | 9.652 | #DIV/0! | 0 | 0 | -9.652 | 162 | 0% | 0% | 5.958% | 162 | C | 0 | 162
| Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 73 | 0% | 0% | 0% | 73 | C | 0 | 73
| Job: 1361 - TF Fabrication-KALISH | 289 | 331.282 | 340.5435 | 1.1463 | 0.9728 | 42.282 | -9.2615 | 61 | 63.632 | 69.22 | 1.0431 | 0.91927 | 2.632 | -5.588 | 1003 | 28.81% | 33.03% | 33.95% | 1003 | JM | 0 | 1003
| Job: 1404 - MCWF R&D 1st Prod | -36 | -35.94 | -34.9474 | 0.99833 | 1.0284 | 0.06 | -0.99262 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | -36 | 100% | 99.83% | 97.08% | -36 | JM | 0 | -36
| Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -84 | -80.39 | -65.1126 | 0.95702 | 1.2346 | 3.61 | -15.2774 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | -80 | 105% | 100.5% | 81.39% | -80 | JM | 0 | -80
| Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 186 | 103.832 | 87.2639 | 0.55824 | 1.1899 | -82.168 | 16.5681 | 116 | 0.632 | 19.257 | 0.0054483 | 0.032819 | -115.368 | -18.625 | 280 | 66.43% | 37.08% | 31.17% | 280 | JM | 0 | 280
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 1114 | 940.494 | 769.6327 | 0.84425 | 1.222 | -173.506 | 170.8613 | 118 | 199.194 | 94.85 | 1.6881 | 2.1001 | 81.194 | 104.344 | 1207 | 92.29% | 77.92% | 63.76% | 1207 | JM | 0 | 1207
| Job: 1429 - MC Interface R&D-GETTELFINGER | 118 | 78.065 | 86.2332 | 0.66157 | 0.90528 | -39.935 | -8.1682 | 0 | 4.065 | 0.441 | 0 | 9.2177 | 4.065 | 3.624 | 118 | 100% | 66.16% | 73.08% | 118 | JM | 0 | 118
| Job: 1501 - Coil Structures Design-DAHLGREN | 186 | 145.001 | 160.0001 | 0.77958 | 0.90626 | -40.999 | -14.9991 | 22 | 8.301 | -16.914 | 0.37732 | -0.49078 | -13.699 | 25.215 | 186 | 100% | 77.96% | 86.02% | 186 | JM | 0 | 186
| Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1076 | 0% | 0% | 0% | 1076 | C | 0 | 1076
| Job: 1601 - Coil Services Design-GORANSON | 6 | 14.598 | 0 | 2.433 | #DIV/0! | 8.598 | 14.598 | 0 | -0.002 | 0 | 0 | #DIV/0! | -0.002 | -0.002 | 861 | 0.6969% | 1.695% | 0% | 861 | C | 0 | 861
| Job: 1701 - Cryostat Design-GETTLEFINGER | 0 | 0 | 5.2332 | #DIV/0! | 0 | 0 | -5.2332 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 207 | 0% | 0% | 2.528% | 207 | JM | 0 | 207
| Job: 1702 - Base Support Struct Design-DAHLGREN | 43 | 11.09 | 32.6 | 0.25791 | 0.34018 | -31.91 | -21.51 | 43 | 0.26 | 32.6 | 0.0060465 | 0.0079755 | -42.74 | -32.34 | 163 | 26.38% | 6.804% | 20% | 163 | JM | 0 | 163
| Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 325 | 0% | 0% | 0% | 325 | C | 0 | 325
| Job: 1752 - Base Support Proc-DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 89 | 0% | 0% | 0% | 89 | C | 0 | 89
| Job: 1806 - FP Assembly specs | 120 | 39.838 | 2.007 | 0.33198 | 19.8495 | -80.162 | 37.831 | 28 | 3.688 | 0 | 0.13171 | 0 | -24.312 | 3.688 | 514 | 23.35% | 7.751% | 0.3905% | 514 | JM | 0 | 514
| Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 200 | 199.131 | 119.964 | 0.99565 | 1.6599 | -0.869 | 79.167 | 38 | 37.571 | 10.255 | 0.98871 | 3.6637 | -0.429 | 27.316 | 1620 | 12.35% | 12.29% | 7.405% | 975.9489 | C | -644.0511 | 975.9489
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 404 | 403.1 | 373.1311 | 0.99777 | 1.0803 | -0.9 | 29.9689 | 61 | 60.64 | 54.702 | 0.9941 | 1.1086 | -0.36 | 5.938 | 2649 | 15.25% | 15.22% | 14.09% | 2452.0572 | C | -196.9428 | 2452.0572
| Job: 8203 - Design Integration-BROWN | 196 | 194.2511 | 55.866 | 0.99108 | 3.4771 | -1.7489 | 138.3851 | 35 | 33.7811 | 19.305 | 0.96517 | 1.7499 | -1.2189 | 14.4761 | 1408 | 13.92% | 13.8% | 3.968% | 1408 | JM | 0 | 1408
| Job: 8204 - Systems Analysis-BROOKS | 207 | 207.311 | 272.0633 | 1.0015 | 0.762 | 0.311 | -64.7523 | 27 | 26.361 | 46.654 | 0.97633 | 0.56503 | -0.639 | -20.293 | 1154 | 17.94% | 17.96% | 23.58% | 1514.4447 | C | 360.4447 | 1514.4447
| Job: 8205 - Dimensional Control Coordin-ELLIS | 123 | 87.581 | 96.1341 | 0.71204 | 0.91103 | -35.419 | -8.5531 | 21 | 11.581 | 4.038 | 0.55148 | 2.868 | -9.419 | 7.543 | 598 | 20.57% | 14.65% | 16.08% | 656.4003 | C | 58.4003 | 656.4003
| Job: 8210 - FY07 Rebaseling tasks | 19 | 18.814 | 46.8765 | 0.99021 | 0.40135 | -0.186 | -28.0625 | 0 | 0.004 | 1.625 | 0 | 0.0024615 | 0.004 | -1.621 | 19 | 100% | 99.02% | 246.7% | 47.3399 | C | 28.3399 | 47.3399
| Job: 8215 Plant Design | 18 | 3 | 0 | 0.16667 | #DIV/0! | -15 | 3 | 3 | 3 | 0 | 1 | #DIV/0! | 0 | 3 | 121 | 14.88% | 2.479% | 0% | 121 | C | 0 | 121
| Total Phil Heitzenroeder | 3188 | 2722.1431 | 2404.7427 | 0.85387 | 1.132 | -465.8569 | 317.4004 | 608 | 453.4431 | 348.902 | 0.74579 | 1.2996 | -154.5569 | 104.5411 | 15941 | 20% | 17.08% | 15.09% | 15547.1911 |  | -393.8089 | 15547.1911
#DIV/0!
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | -104 | -104.1 | -104.1027 | 1.001 | 0.99997 | -0.1 | 0.00269 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 55 | -189.1% | -189.3% | -189.3% | 55.0014 |  | 0.0014212 | 55.0014
| Job: 4301 - DC Systems-RAMAKRISHNAN | 1 | 0 | 0 | 0 | #DIV/0! | -1 | 0 | 1 | 0 | 0 | #DIV/0! | #DIV/0! | -1 | 0 | 603 | 0.1658% | 0% | 0% | 603 |  | 0 | 603
| Job: 4401 - Control & Protection-RAMAKRISHNAN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1084 | 0% | 0% | 0% | 1084 |  | 0 | 1084
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 0 | 0 | -0.55581 | #DIV/0! | 0 | 0 | 0.55581 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 683 | 0% | 0% | -0.08138% | 683 |  | 0 | 683
| Job: 5101 - Network and Fiber | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 150 | 0% | 0% | 0% | 150 |  | 0 | 150
| Job: 5201 - I&C Systems-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 196 | 0% | 0% | 0% | 196 |  | 0 | 196
| Job: 5301 - Data Acquisition-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 165 | 0% | 0% | 0% | 165 |  | 0 | 165
| Job: 5401 - Facility Timing & | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 205 | 0% | 0% | 0% | 205 |  | 0 | 205
| Job: 5501 - Real Time Control | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 129 | 0% | 0% | 0% | 129 |  | 0 | 129
| Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 222 | 0% | 0% | 0% | 222 |  | 0 | 222
| Job: 5801 - Central I&C Integr& Oversight-SICHTA | 8 | 9.3 | 0 | 1.1625 | #DIV/0! | 1.3 | 9.3 | 2 | 2.32 | 0 | 0.86207 | #DIV/0! | 0.32 | 2.32 | 69 | 11.59% | 13.48% | 0% | 69 |  | 0 | 69
| Job: 8501 - Integrated Systems Testing-GENTILE | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 765 | 0% | 0% | 0% | 765 |  | 0 | 765
| Total Al vonHalle | -95 | -94.8 | -104.6585 | 0.99789 | 0.9058 | 0.2 | 9.8585 | 3 | 2.32 | 0 | 0.77333 | #DIV/0! | -0.68 | 2.32 | 4326 | -2.196% | -2.191% | -2.419% | 4326.0014 |  | 0.0014212 | 4326.0014
| Total project (May 1 through completion) | 7737.71 | 7049.5471 | 6148.6016 | 0.91106 | 1.1465 | -688.1629 | 900.9455 | 1960.61 | 1495.2866 | 872.049 | 0.76266 | 1.7147 | -465.3234 | 623.2376 | 50853 | 15.22% | 13.86% | 12.09% | 50895.7469 |  | 42.7469 | 50895.7469
[15 empty] | Contigency = | 14380
| * Note; Revised estimates being processed to reflect scope "add-backs" per the August Legman review recommendation. | [13 empty] | Cost through April 30,2007 | 67178.138
[15 empty] | TOTAL TEC = | 132411.138
| ornl jobs | 1701 | 1372.941 | 1103.4506 | 0.80714 | 1.2442 |  | 269.4904 | 314 | 255.711 | 140.117 | 0.81437 | 1.825 |  | 115.594
| pppl jobs | 6036.71 | 5676.6061 | 5045.151 | 0.94035 | 1.1252 |  | 631.4551 | 1646.61 | 1239.5756 | 731.932 | 0.7528 | 1.6936 |  | 507.6436
| highlighted schedule variances = | 3631.71 | 2932.089 | 2083.2026 | 0.80736 | 1.4075 | -699.621 | 848.8864 | 886.61 | 670.239 | 243.675 | 0.75596 | 2.7505 | -216.371 | 426.564
| highlighted cost variances = | 1107 | 970.898 | 1428.708 | 0.87705 | 0.67956 | -136.102 | -457.81 | 229 | 136.578 | 145.614 | 0.59641 | 0.93795 | -92.422 | -9.036
|  | 356 | 262.7611 | 212.6619 | 0.73809 | 1.2356 | -93.2389 | 50.0992
corrected
corrected

## TOTAL PROJECT REPORT
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
TOTAL PROJECT |  |  |  | Jim Anderson |  | 2007-10-31
Highlights and Progress:
[7 empty] | 1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 | 2007-10-31 | 2007-12-01 | 2
[7 empty] | INTRF-055 | AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 27NOV07* | 2007-11-01 | 2
Issues (not currently impacting technical, cost, or schedule but being watched): | [6 empty] | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2
Problems and work around plans : | [6 empty] | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Milestones | Total float
-39
Schedule | [6 empty] | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Milestones | Total float
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level | INTRF-045 | FDR prep outboard shims | 1421 | DW | 2007-07-18 | 29JUN07A |  | 3 |  |  | Activity ID | Activity description | Milestones | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish | Variance target 1 early finish | Variance target 1 early finish
Stage 3 support FDR | 1803 | TB | 2007-07-13 | 17JUL07A |  | 3 | 1803-3.4 | Stage 3 support FDR | 1803 | TB | 2007-07-13 | 17JUL07A |  | 3 |  | - | METFY07R1 | Dimensional control plans for station 2 | 3 | 8205 | BE | 01JUN07* | 2007-08-31 | 01JUN07A | 2007-09-21 | -14 | -14
Coils Support Structure - PDR | 1501 | FD | 2007-07-20 | 20JUL07A |  | 3 | 1501-525P | Coils Support Structure - PDR | 1501 | FD | 2007-07-20 | 20JUL07A |  | 3 |  | - | 1803-205 | Station 2 Assembly Drawings | 3 | 1806 | MC | 11JUN07* | 2007-09-11 | 11JUN07A | 2007-10-03 | -16 | -16
ROWGOSKI COIL - FDR | 3101 | BS | 2007-09-06 | 09AUG07A |  | 3 | 3101-326 | ROWGOSKI COIL - FDR | 3101 | BS | 2007-09-06 | 09AUG07A |  | 3 |  | - | INTRF-045 | FDR prep outboard shims | 3 | 1421 | DW | 2007-07-05 | 2007-07-18 | 25JUN07A | 29JUN07A | 12 | 12
** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 | 18Oct 07 A | 2007-12-01 | 2 | [8 empty] | 337 | - | 1803-201 | Station 2 Assembly Specification | 3 | 1806 | MC | 11JUN07* | 2007-09-11 | 01JUL07A | 2007-10-12 | -23 | -23
Dimensional control plans for station 2 | 8205 | BE | 2007-08-31 | 2007-11-13 |  | 3 | METFY07R1 | Dimensional control plans for station 2 | 8205 | BE | 2007-08-31 | 2007-11-13 |  | 3 | 1179 | - | 1416-506 | Check and promote top-level models/drawings | 3 | 1416 | DW | 2007-08-01 | 2007-11-21 | 01JUL07A | 2007-11-21 | 0 | 0
Fab, Test & Deliver Coil #6 | 1361 | MK | 2007-11-23 | 2007-11-26 |  | 3 | 1361C-106 | Fab, Test & Deliver Coil #6 | 1361 | MK | 2007-11-23 | 2007-11-26 |  | 3 | 403 | - | 1803-3.4 | Stage 3 support FDR | 3 | 1803 | TB | 13JUL07* | 2007-07-13 | 02JUL07A | 17JUL07A | -2 | -2
Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2007-11-27 |  | 3 | 1803-205 | Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2007-11-27 |  | 3 | 1178 | - | 1501-525P | Coils Support Structure - PDR | 3 | 1501 | FD | 20JUL07* | 2007-07-20 | 20JUL07A | 20JUL07A | 0 | 0
AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 27NOV07* | 2007-11-01 | 2 | [8 empty] | -38 | - | 3101-326 | ROWGOSKI COIL - FDR | 3 | 3101 | BS |  | 2007-09-06 |  | 09AUG07A | 19 | 19
Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2007-11-30 |  | 3 | METDCP-3 | Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2007-11-30 |  | 3 | 24 | - | S21-5.04X | Shims required for 1st 3 pack MC assy | 2 | 1431 | LD | 2007-09-20 |  | 2007-09-24 |  | -2 | -2
Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2007-12-07 |  | 3 | 1501-541 | Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2007-12-07 |  | 3 | 111 | - | METDCP-3 | Dimensional control plans for station 3 | 3 | 8205 | BE | 2007-09-04 | 2007-10-15 | 2007-09-24 | 2007-11-02 | -14 | -14
Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2007-12-11 |  | 3 | 1803-201 | Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2007-12-11 |  | 3 | 1161 | - | 1416-601 | Prepare EM and structural analysis of leads | 3 | 1416 | DW | 01OCT07* | 2007-11-06 | 01OCT07* | 2007-11-06 | 0 | 0
Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 3 | 1416-506 | Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 3 | 53 | - | INTRF-055 | AB/BC/AA inboard interface - FDR | 2 | 1421 | DW |  | 2007-09-04 |  | 05OCT07* | -23 | -23
Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-01-07 |  | 3 | 1421-3144 | Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-01-07 |  | 3 | 449 | - | 1302-225M | PF Coil PDR | 2 | 1302 | MK |  | 2007-12-11 |  | 2007-10-19 | 1900-02-03 | 35
Final Scan of VVSA #3 Station 1 complete | 1810 | MV | 2008-02-06 | 2008-01-07 |  | 3 | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 1810 | MV | 2008-02-06 | 2008-01-07 |  | 3 | 319 | - | 1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** | 2 | 1361 | MK |  | 2007-09-28 |  | 2007-10-19 | -15 | -15
Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2 | [8 empty] | -39 | - | 1803-5.6 | Station 5 FDR | 3 | 1803 | TB |  | 2007-11-21 |  | 2007-10-29 | 1900-01-16 | 17
Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2008-01-31 |  | 3 | 1416-601 | Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2008-01-31 |  | 3 | 25 | - | METDCP-5 | Dimensional control plans for station 5 | 3 | 8205 | BE | 2007-10-16 | 2008-02-15 | 2007-11-05 | 2008-03-06 | -14 | -14
PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-02-05 |  | 3 | 1302-270 | PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-02-05 |  | 3 | 49 | - | 1361C-106 | Fab, Test & Deliver Coil #6 | 3 | 1361 | MK | 23NOV07* | 2007-11-23 | 23NOV07* | 2007-11-23 | 0 | 0
Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 3 | 1803-5.6 | Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 3 | 72 | - | 1302-270 | PF Coils - FDR | 3 | 1302 | MK | 2008-03-21 | 2008-03-24 | 2007-12-19 | 2007-12-20 | 1900-02-28 | 60
[17 empty] | 1421-3144 | C-C Joint - FDR | 3 | 1421 | DW |  | 2008-01-07 |  | 2008-02-07 | -23 | -23
|  |  | Cost and schedule Performance |  |  |  | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Milestones | Total float |  | 1501-541 | Coil Support Structures - FDR | 3 | 1501 | FD | 2007-09-21 | 2007-09-21 | 2008-02-21 | 2008-02-21 | -100 | -100
[5 empty] | From May 1,2007 | Current Month | INTRF-045 | FDR prep outboard shims | 1421 | DW | 2007-07-18 | 29JUN07A |  | 3 |  |  | 141-036 | PF Coils Awarded | 2 | 1352 | MK |  | 2008-05-27 |  | 2008-03-03 | 1900-02-28 | 60
|  |  |  | BCWS = | 7737.71 | 1960.61 | 1803-3.4 | Stage 3 support FDR | 1803 | TB | 39276 | 17JUL07A |  | 3 |  |  | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 3 | 1810 | MV | 2008-02-01 | 2008-02-06 | 2008-03-04 | 2008-03-07 | -22 | -22
|  |  |  | BCWP = | 7049.5471 | 1495.2866 | 1501-525P | Coils Support Structure - PDR | 1501 | FD | 39283 | 20JUL07A |  | 3 |  |  | METDCP-6 | Dimensional control plans for station 6 | 3 | 8205 | BE | 2008-02-18 | 2008-06-09 | 2008-03-07 | 2008-06-27 | -14 | -14
|  |  |  | ACWP = | 6148.6016 | 872.049 | 3101-326 | ROWGOSKI COIL - FDR | 3101 | BS | 39331 | 09AUG07A |  | 3 |  |  | 1702-525M | Base Support Structure FDR | 2 | 1702 | FD |  | 2008-02-04 |  | 2008-03-27 | -38 | -38
|  |  |  | CV = | 900.9455 |  | 1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 | 19OCT07A | 2007-12-01 | 2
|  |  |  | SV = | -688.1629 |  | METFY07R1 | Dimensional control plans for station 2 | 8205 | BE | 2007-08-31 | 2007-11-13 |  | 3 | -10
|  |  |  | CPI = | 1.1465 | 1.7147 | 1361C-106 | Fab, Test & Deliver Coil #6 | 1361 | MK | 2007-11-23 | 2007-11-26 |  | 3 | 403
|  |  |  | SPI = | 0.91106 | 0.76266 | 1803-205 | Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2007-11-27 |  | 3 | -18
|  |  |  | BAC = | 118031.138 |  | INTRF-055 | AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 27NOV07* | 2007-11-01 | 2 | -38
|  |  |  | EAC = | 118073.8849 |  | METDCP-3 | Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2007-11-30 |  | 3 | 24
|  |  |  | Projected cost variance = |  |  | 1501-541 | Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2007-12-07 |  | 3 | 111
|  |  |  | EAC Variance Explanation |  |  | 1803-201 | Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2007-12-11 |  | 3 | -28
[7 empty] | 1416-506 | Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 3 | 26
[7 empty] | 1421-3144 | Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-01-07 |  | 3 | 449
Analysis | [6 empty] | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 1810 | MV | 2008-02-06 | 2008-01-07 |  | 3 | 312
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2 | -39
[7 empty] | 1416-601 | Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2008-01-31 |  | 3 | -2
[7 empty] | 1302-270 | PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-02-05 |  | 3 | 49
[7 empty] | 1803-5.6 | Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 3 | 69
INTRF-045
1803-3.4
1501-525P
Changes/Additions to the risk registry | [6 empty] | 3101-326
Description |  |  | Likelihood of Occurrence | Cost and schedule impact |  |  | 1361C-104M |  |  |  |  | X
METFY07R1
1361C-106
1803-205
INTRF-055
METDCP-3
1501-541
1803-201
1416-506
1421-3144
R1810-1329
S21-5.04X
1416-601
1302-270
1803-5.6
X
X
X
X
X
X

## Monthly Report-JIM
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Project Management |  |  |  | Jim Anderson |  | 2007-10-31
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
PPPL Project Management Job 8101 | JA
ORNL Project Management Job 8102 | JL
Allocations Job 8998 | RLS
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 628 | 145
|  |  |  | BCWP = | 627.698 | 145.138
|  |  |  | ACWP = | 693.7456 | 96.262
|  |  |  | CV = | -66.0476
|  |  |  | SV = | -0.302
|  |  |  | CPI = | 0.9048 | 1.5077
|  |  |  | SPI = | 0.99952 | 1.001
|  |  |  | BAC = | 11057.504
|  |  |  | EAC = | 11140.504
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 | [5 empty] | Stage 3 support FDR |  | * | 2007-07-13 | 3 | 2007-07-13
3101-326 0 0 0 | [5 empty] | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 | [5 empty] | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 | [5 empty] | Station 5 FDR |  |  | 2007-11-21 | 3 | 2008-02-01
P3-171V 11 11 0 | [5 empty] | Final Scan |  |  | 2008-02-06 | 3 | 2008-05-12
PLCT-C6 14 14 0 | [5 empty] | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 | [5 empty] | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 | [5 empty] | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 | [5 empty] | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
[6 empty] | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
[6 empty] | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
[6 empty] | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
[6 empty] | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2
N/A

## Monthly Report-LARRY
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
NCSX Construction |  |  |  | Larry Dudek |  | 2007-10-31
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Mod Coil Fab Jobs 1408/1451/1459 | JC |  | Fueling & Vacuum WBS 21 & 22 |  | BB
Cryo Systems WBS 62 | GG |  | Diagnostics WBS 3 |  | BS
Assy Tooling design/fab Job 1803 | TB |  | Water/Utilities WBS 61/63 |  | LD
Field Period Assy Jobs 1802/1810/1815 | MV |  | Bakeout Systems WBS 64 |  | MK
Final Machine Assy WBS 75 | EP
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule (Total Float <1 in RED)
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Milestones | Total float
Stage 3 support FDR | 1803 | TB | 2007-07-13 | 17JUL07A |  | 3 | 1803-3.4 | Stage 3 support FDR | 1803 | TB | 2007-07-13 | 17JUL07A |  | 3 |  |  | Activity ID | Activity description | Milestones | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish | Variance target 1 early finish
ROWGOSKI COIL - FDR | 3101 | BS | 2007-09-06 | 09AUG07A |  | 3 | 3101-326 | ROWGOSKI COIL - FDR | 3101 | BS | 2007-09-06 | 09AUG07A |  | 3 |  | - | 1803-3.4 | Stage 3 support FDR | 3 | 1803 | TB | 13JUL07* | 39276 | 02JUL07A | 17JUL07A | -2
Final Scan of VVSA #3 Station 1 complete | 1810 | MV | 2008-02-06 | 2008-01-07 |  | 3 | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 1810 | MV | 2008-02-06 | 2008-01-07 |  | 3 | 319 | - | 3101-326 | ROWGOSKI COIL - FDR | 3 | 3101 | BS |  | 39331 |  | 09AUG07A | 19
Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2 | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2 | -39 | - | S21-5.04X | Shims required for 1st 3 pack MC assy | 2 | 1431 | LD | 2007-09-20 |  | 2007-09-24 |  | -2
Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 3 | 1803-5.6 | Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 3 | 72 | - | 1803-5.6 | Station 5 FDR | 3 | 1803 | TB |  | 39407 |  | 2007-10-29 | 17
COMPLETE VPI OF 18th MOD COIL | 1451 | JC | 2008-07-15 | 2008-05-12 | 2008-11-01 | 2 | P3-171VM | COMPLETE VPI OF 18th MOD COIL | 1451 | JC | 2008-07-15 | 2008-05-12 | 2008-11-01 | 2 | 85 | - | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 3 | 1810 | MV | 2008-02-01 | 39484 | 2008-03-04 | 2008-03-07 | -22
Station 6 FDR | 1803 | TB | 2008-06-04 | 2008-06-04 |  | 3 | 1803-6.6 | Station 6 FDR | 1803 | TB | 2008-06-04 | 2008-06-04 |  | 3 | 69
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 4016.71 | 1204.61
|  |  |  | BCWP = | 3794.506 | 894.3855
|  |  |  | ACWP = | 3154.7718 | 426.885
|  |  |  | CV = | 639.7342
|  |  |  | SV = | -222.204
|  |  |  | CPI = | 1.2028 | 2.0951
|  |  |  | SPI = | 0.94468 | 0.74247
|  |  |  | BAC = | 45219.331
|  |  |  | EAC = | 45572.8854
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
NCSX
COST and SCHEDULE
PERFORMANCE REPORTS
OCTOBER 2007

## Monthly Report- PHIL
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Stellarator CoreDesign and Procurement |  |  |  | Phil Heitzenroeder |  | 2007-10-31
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Conventional Coils WBS 13 | Mike Kalish |  | Modular Coils Jobs 1416/1421/1429/1431 |  | Dave Williamson
Coil Services WBS 16 | Paul Goranson |  | Coil Structures & Base Support Structure WBS 15 |  | Fred Dahlgren
Cryostat Job 1701/1751 | Geoff Gettelfinger |  | Assembly Specs & Dwgs Job 1806 |  | Mike Cole
Assy tooling & constructability Job 1803 | Tom Brown |  | Systems Analysis Job 8204 |  | Art Brooks
Dimensional Control Job 8205 | Bob Ellis |  | Systems Engineering & Support Job 8202 |  | Wayne Reiersen
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule (Total Float <1 in RED)
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Milestones | Total float
FDR prep outboard shims | 1421 | DW | 2007-07-18 | 29JUN07A |  | 3 | INTRF-045 | FDR prep outboard shims | 1421 | DW | 2007-07-18 | 29JUN07A |  | 3
Coils Support Structure - PDR | 1501 | FD | 2007-07-20 | 20JUL07A |  | 3 | 1501-525P | Coils Support Structure - PDR | 1501 | FD | 2007-07-20 | 20JUL07A |  | 3
** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 | 18Oct 07 A | 2007-12-01 | 2 | 1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 | 2007-10-31 | 2007-12-01 | 2 | 337
Dimensional control plans for station 2 | 8205 | BE | 2007-08-31 | 2007-11-13 |  | 3 | METFY07R1 | Dimensional control plans for station 2 | 8205 | BE | 2007-08-31 | 2007-11-13 |  | 3 | 1179
Fab, Test & Deliver Coil #6 | 1361 | MK | 2007-11-23 | 2007-11-26 |  | 3 | 1361C-106 | Fab, Test & Deliver Coil #6 | 1361 | MK | 2007-11-23 | 2007-11-26 |  | 3 | 403
Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2007-11-27 |  | 3 | 1803-205 | Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2007-11-27 |  | 3 | 1178
AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 27NOV07* | 2007-11-01 | 2 | INTRF-055 | AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 27NOV07* | 2007-11-01 | 2 | -38
Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2007-11-30 |  | 3 | METDCP-3 | Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2007-11-30 |  | 3 | 24
Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2007-12-07 |  | 3 | 1501-541 | Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2007-12-07 |  | 3 | 111
Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2007-12-11 |  | 3 | 1803-201 | Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2007-12-11 |  | 3 | 1161
Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 3 | 1416-506 | Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 3 | 53
Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-01-07 |  | 3 | 1421-3144 | Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-01-07 |  | 3 | 449
Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2008-01-31 |  | 3 | 1416-601 | Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2008-01-31 |  | 3 | 25
PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-02-05 |  | 3 | 1302-270 | PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-02-05 |  | 3 | 49
Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 | 2008-03-06 |  | 3 | 1416-605 | Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 | 2008-03-06 |  | 3 | 25
Base support - PDR | 1702 | FD | 2007-11-26 | 2008-03-06 |  | 3 | 1702-515 | Base support - PDR | 1702 | FD | 2007-11-26 | 2008-03-06 |  | 3 | 0
PF Coils Awarded | 1352 | MK | 2008-05-27 | 2008-04-08 | 2008-09-01 | 2 | 141-036 | PF Coils Awarded | 1352 | MK | 2008-05-27 | 2008-04-08 | 2008-09-01 | 2 | 49
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 3188 | 608
|  |  |  | BCWP = | 2722.1431 | 453.4431
|  |  |  | ACWP = | 2404.7427 | 348.902
|  |  |  | CV = | 317.4004
|  |  |  | SV = | -465.8569
|  |  |  | CPI = | 1.132 | 1.2996
|  |  |  | SPI = | 0.85387 | 0.74579
|  |  |  | BAC = | 56600.653
|  |  |  | EAC = | 56206.8441
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact

## Monthly Report-AL
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Electrical, I&C and Startup |  |  |  | Al vonHalle |  | 2007-07-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Electrical Powers Systems WBS 4 | RR
Instrumentation and Controls | PS
Startup | CG
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level
[10 empty] | Activity ID | Activity description | Early start | Early finish | Milestones | Job Number | Job Manager
[10 empty] | 1803-3.4 | Stage 3 support FDR | 13JUL07* | 2007-07-13 | 3 | 1803 | TB
[10 empty] | 3101-326 | FDR - ROWGOSKI COIL |  | 2007-09-06 | 3 | 3101 | BS
[10 empty] | S21-5.04X | Shims required for 1st 3 pack MC assy |  | 2007-09-20 | 2 | 1431 | LD
[10 empty] | 1803-5.6 | Station 5 FDR |  | 2007-11-21 | 3 | 1803 | TB
[10 empty] | R1810-1329 | Final Scan | 2008-02-01 | 2008-02-06 | 3 | 1810 | MV
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | -95 | 1
BCWP =
ACWP =
CV =
SV =
CPI =
SPI =
|  |  |  | BAC = | 5081.65
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 | [5 empty] | Stage 3 support FDR |  | * | 2007-07-13 | 3 |  |  | 2007-07-13
3101-326 0 0 0 | [5 empty] | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 | [5 empty] | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 | [5 empty] | Station 5 FDR |  |  | 2007-11-21 | 3 |  |  | 2008-02-01
P3-171V 11 11 0 | [5 empty] | Final Scan |  |  | 2008-02-06 | 3 |  |  | 2008-05-12
PLCT-C6 14 14 0 | [5 empty] | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 | [5 empty] | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 | [5 empty] | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 | [5 empty] | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
[6 empty] | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
[6 empty] | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
[6 empty] | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
[6 empty] | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2
No Milestones during the period

## EAC calculation
Project start | current date | Baseline Finish | current total float (work days from primavera) | available 2 shift operation remaining on CP (mo.) | Projected Finish | Projected slip (mo.)
2007-05-01 | 2007-09-30 | 2011-01-11 | -57 | 18 | 2014-05-14 14:39 | 40.1188
[6 empty] | 8103.991 | = Stretchout cost impact @( $202k/mo.)
[6 empty] | 576 | = second shift supervision cost @ $64k/mo.
|  |  | BAC | EAC (from cpr)
|  |  | 50853 | 50895.7469 | ETC increase = | 42.7469
[5 empty] | Total Increase = | 8722.7379
[5 empty] | Projected EAC = | 126753.7379
[5 empty] | TEC = | 132412
[5 empty] | (under)/over = | -5658.2621
Formulas:
Projected Finish = ((([Baseline Finish]-[Project start])/(([current date]-[Project start]+(F6*7/5))/([current date]-[Project start]))+([Project start])))-(G6/2*30.4)

## Summary analysis
NCSX Summary Performance
October 2007
Cost Performance |  |  | BCWS | BCWP | ACWP
| Cumulative from May 1st, 2007 = |  | 7737.71 | 7049.5471 | 6148.6016
| Cost Through April 2007 = |  |  |  | 67178
| Cost to date = |  |  |  | 73326.6016
| BCWR (work to go) = |  |  | 43803.4529
| Contingency = |  |  | 14380
| Total TEC = |  |  | 132411
| CPI = | 1.1465 | Cost Variance = |  | 900.9455 | Major Cost Variances
| SPI = | 0.91106 | Schedule Variance = |  | -688.1629 |  | Mod Coil Punch List |  |  | CPI = .5 | CV = -171
[7 empty] | FP Assy tooling (job 1803) |  |  | CPI = .44 | CV = -88
[7 empty] | Systems Analysis (job 8204) |  |  | CPI = .76 | CV = -65
Critical path assessment
| Modular coil interface design (job 1421) |  |  | SPI =.84 | SV = -174
On Critical path. Current FDR date forecast for 11/27/07 slipped from September 4th.
Constrains shim and puck procurement and susequent station 2 field period assy.
Current critical path = -39 days (-1.9 months) as measured against revised assembly sequence plan rev 9.
This translates into a 1.9 month slip in the project schedule.
[7 empty] | Baseline | Forecast | DOE Committment
Level II milestone status (near term) |  |  | ** DELIVER TF COILS FOR FPA #1 ASSY ** |  |  |  | 2007-09-28 | 19OCT07A | 2007-12-01
|  |  | AB/BC/AA inboard interface - FDR |  |  |  | 2007-09-04 | 27NOV07* | 2007-11-01
|  |  | Shims required for 1st 3 pack MC assy |  |  |  | 2007-09-20 | 2008-01-11 | 2007-12-01
|  |  | PF Coils Awarded |  |  |  | 2008-05-27 | 2008-04-08 | 2008-09-01
|  |  | Award Coil Support Structure |  |  |  | 16JUN08* | 28APR08* | 2008-10-01
|  |  | Base Support Structure FDR |  |  |  | 2008-02-04 | 2008-04-28 | 2008-05-01
|  |  | COMPLETE VPI OF 18th MOD COIL |  |  |  | 2008-07-15 | 2008-05-12 | 2008-11-01
Contingency |  | Planned = | $14,380 K | 28.3%
|  | Drawdown to date = | 0
|  | Current free balance contingency on remaining scope = |  |  |  | 33%
Risks (from updated risk registry)
Retired
Added
COMMENTS
1) A revised trim coil estimate reflecting a 36 coil design has been estimated for inclusion into the project baseline.
Although not officially baselined, due to its criticality this preliminary plan has been included in the current schedule and will be reported against.
The formal cost and schedule documentation is currently being prepared.
2) An updated assembly sequence plan was developed and subsequently re-estimated. While this plan is currently un undergoing
review and optimization, I have based the critical path analysis on this new plan since it reflects the projects'
best and current thinking on field period assembly. The formal cost and schedule documentation is currently being prepared.
Contents
Page
[12 empty] | Summary |  | 3
[12 empty] | Cost Performance Report (CPR) |  | 4-5
[12 empty] | Performance Curves |  | 6-9
[12 empty] | Milestones |  | 10-11
[12 empty] | Contingency Analysis |  | 12
[12 empty] | Critical Path |  | 13

## Baseline Reconciliation
NCSX EAC - Reconciliation Detail
|  | WBS II |  | JOB | COST TO DATE 4/1/03 - 4/30/07 |  | ETC 5/1/07 THROUGH COMPLETION |  |  |  |  | TOTAL |  | ecp31 | deltas
[7 empty] | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | ETC | TOTAL EAC
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18
|  | 12 - Vacuum Vessel Systems | Phil | 1201 - Vacuum Vessel Prelim Dsn | 424 | [6 empty] | 0 | 424 | 424 | 0 | 0% | 1201
|  |  | Phil | 1202 - Vacuum Vessel R&D | 1770.9 | [6 empty] | 0 | 1770.9 | 1791 | -20.1 | -1.122% | 1202
|  |  | Phil | 1203 - Vacuum Vessel Final Dsn | 1217 | [6 empty] | 0 | 1217 | 944 | 273 | 28.92% | 1203
1204-VV Sys Procurements (non VVSA) |  |  | Larry | 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 535.9 |  | 47 | 162 | 1 | 198 | 0 | 408 | 943.9 | 557 | 386.9 | 69.46% | 1204
|  |  | Phil | 1206 - VV Field Weld Joint R&D | 15.954 | [6 empty] | 0 | 15.954 | 74 | -58.046 | -78.44% | 1206
|  |  | Larry | 1250 - Vacuum Vessel Fabrication | 5788.9 |  | -252 | 0 | 0 | 0 | 0 | -252 | 5536.9 | 5741 | -204.1 | -3.555% | 1250
|  |  |  | Subtotal | 9752.654 |  | -205 | 162 | 1 | 198 | 0 | 156 | 9908.654 | 9531 | 377.654 | 3.962%
[15 empty] | 0 | #DIV/0!
|  | 13 - Conventional Coils | Phil | 1301 - TF Design | 970.1 | [6 empty] | 0 | 970.1 | 837 | 133.1 | 15.9% | 1301
1302 - PF Design |  |  | Phil | 1302 - PF Design -KALISH | 19.338 |  | 44 | 213 | 0 | 0 | 0 | 257 | 276.338 | 253 | 23.338 | 9.225% | 1302
|  |  | Phil | 1303 - Central Solenoid Support Design | 154.9 | [6 empty] | 0 | 154.9 |  | 154.9 | #DIV/0!
|  |  | Phil | 1350 - TF Coil Fabr Prep | 535.99 | [6 empty] | 0 | 535.99 | 400 | 135.99 | 34% | 1350
|  |  | Phil | 1351 - TF Coil Fabr Supplies | 482.959 | [6 empty] | 0 | 482.959 | 1318 | -835.041 | -63.36% | 1351
|  |  | Phil | 1352 - PF Coil Procurement-KALISH |  |  | 0 | 968 | 634 | 28 | 0 | 1630 | 1630 | 1362 | 268 | 19.68% | 1352
|  |  | Phil | 1353 - CS Structure Procurement-DAHLGREN |  |  | 0 | 0 | 78 | 259 | 0 | 337 | 337 | 270 | 67 | 24.81% | 1353
|  |  | Phil | 1354 - Trim Coil Design &Procurement-KALISH |  |  | 0 | 0 | 162 | 0 | 0 | 162 | 162 | 258 | -96 | -37.21% | 1354
|  |  | Phil | 1355 - WBS 13 I&C Proc and Coil Assy-KALISH |  |  | 0 | 32 | 39 | 2 | 0 | 73 | 73 | 92 | -19 | -20.65% | 1355
|  |  | Phil | 1361 - TF Fabrication-KALISH | 1062.999 | (1) | 228 | 775 | 0 | 0 | 0 | 1003 | 2065.999 |  | 2065.999 | #DIV/0!
|  |  |  | Subtotal | 3226.286 |  | 272 | 1988 | 913 | 289 | 0 | 3462 | 6688.286 | 4790 | 1898.286 | 39.63%
[15 empty] | 0 | #DIV/0!
|  | 14 - Modular Coils | Phil | 1401 - Mod Coil Prel.Dsn | 304.5 | [6 empty] | 0 | 304.5 | 303 | 1.5 | 0.495% | 1401
|  |  | Phil | 1402 - Mod.Coil Analyses | 239.14 | [6 empty] | 0 | 239.14 | 239 | 0.14 | 0.05858% | 1402
|  |  | Phil | 1403 modular coil winding form design | 3310.9 | [6 empty] | 0 | 3310.9 | 3149 | 161.9 | 5.141% | 1403
|  |  | Phil | 1404-MCWF R&D & 1st Prod Casting | 2554.9 |  | -36 | 0 | 0 | 0 | 0 | -36 | 2518.9 | 2534 | -15.1 | -0.5959% | 1404
|  |  | Phil | 1405-Mod Coil Winding R&D Prep | 168 | [6 empty] | 0 | 168 | 168 | 0 | 0% | 1405
|  |  | Phil | 1406 - Mod. Coil Winding Facility | 2263 | [6 empty] | 0 | 2263 | 2214 | 49 | 2.213% | 1406
|  |  | Phil | 1407 -Mod Coil Winding Facility | 2569 | [6 empty] | 0 | 2569 | 2523 | 46 | 1.823% | 1407
1408-Mod Coil Winding Supplies |  |  | Larry | 1408 - MC Winding Supplies-CHRZANOWSKI | 2353 |  | 178 | 172 | 0 | 0 | 0 | 350 | 2703 | 1836 | 867 | 47.22% | 1408
|  |  | Phil | 1409 - Mod. Coil Test Stand | 832.9 | [6 empty] | 0 | 832.9 | 488 | 344.9 | 70.68% | 1409
|  |  | Phil | 1410 MC Twisted Racetrack Fabr | 1049.908 | [6 empty] | 0 | 1049.908 | 799 | 250.908 | 31.4% | 1410
1411-MCWF Fabrication S005242 |  |  | Phil | 1411 - MCWF Fabr. S005242-HEITZENROEDER | 9965 |  | -80 | 0 | 0 | 0 | 0 | -80 | 9885 | 8329 | 1556 | 18.68% | 1411
|  |  | Phil | 1412 - Complete Winding Facilities | 540.732 | [6 empty] | 0 | 540.732 | 310 | 230.732 | 74.43% | 1412
|  |  | Phil | 1413 - Mod Coil Fracture Analysis | 27.819 | [6 empty] | 0 | 27.819 | 23 | 4.819 | 20.95% | 1413
|  |  | Phil | 1414 - Coil Testing | 638.674 | [6 empty] | 0 | 638.674 |  | 638.674 | #DIV/0!
|  |  | Phil | 1415 - Dimensional Control Testing | 24.038 | [6 empty] | 0 | 24.038 |  | 24.038 | #DIV/0!
Mod Coil Design 1416 Coil Design, Job 1421 Interface design |  |  | Phil | 1416 &1421 - Mod Coil Interface Design-WILLIAMSON | 1108.49 |  | 1066 | 422 | 0 | 0 | 0 | 1488 | 2596.49 |  | 2596.49 | #DIV/0!
Job 1429 Interface R&D/Test |  |  | Phil | 1429 - MC Interface R&D-GETTELFINGER | 157.99 |  | 118 | 0 | 0 | 0 | 0 | 118 | 275.99 |  | 275.99 | #DIV/0!
|  |  | Phil | 1419 - Winding Facility Modification | 48.434 | [6 empty] | 0 | 48.434 |  | 48.434 | #DIV/0!
|  |  | Phil | 1431 - Mod. Coil Interface Hardware-DUDEK |  |  | 362 | 660 | 0 | 17 | 0 | 1039 | 1039 | 86 | 953 | 1108% | 1431
1451 - Mod Coil Winding (incl 1459 punch list and unplanned work) |  |  | Larry | 1451 - Mod Coil Winding-CHRZANOWSKI | 5982.2 | (1) | 1054 | 1813 | 0 | 0 | 0 | 2867 | 8849.2 | 5091 | 3758.2 | 73.82% | 1451
|  |  | Larry | 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  |  | 90 | 411 | 0 | 0 | 0 | 501 | 501 |  | 501 | #DIV/0!
|  |  | Phil | 1460 - 3rd Winding Fixture | 57.337 | [6 empty] | 0 | 57.337 |  | 57.337 | #DIV/0!
|  |  |  | Subtotal | 34195.962 |  | 2752 | 3478 | 0 | 17 | 0 | 6247 | 40442.962 | 28092 | 12350.962 | 43.97%
[15 empty] | 0 | #DIV/0!
1501 - Structures Design |  | 15 - Coil Structures | Phil | 1501 - Coil Structures Design-DAHLGREN | 330.94 | (1) | 164 | 22 | 0 | 0 | 0 | 186 | 516.94 | 221 | 295.94 | 133.9% | 1501
1550 - Structures Procurement |  |  | Phil | 1550 - Coil Struct. Procurement -DAHLGREN | 4.061 |  | 0 | 403 | 673 | 0 | 0 | 1076 | 1080.061 | 1191 | -110.939 | -9.315% | 1550
|  |  |  | Subtotal | 335.001 |  | 164 | 425 | 673 | 0 | 0 | 1262 | 1597.001 | 1412 | 185.001 | 13.1%
[15 empty] | 0 | #DIV/0!
1601 - Coil Services |  | 16 - Coil Services | Phil | 1601 - Coil Services Design-GORANSON | 2.614 |  | 6 | 323 | 372 | 160 | 0 | 861 | 863.614 | 1140 | -276.386 | -24.24% | 1601
[15 empty] | 0 | #DIV/0!
1701-Cryostat design |  | 17 - Cryostat and Base Support Structure | Phil | 1701 - Cryostat Design-GETTLEFINGER | 431.073 |  | 0 | 0 | 207 | 0 | 0 | 207 | 638.073 | 504 | 134.073 | 26.6% | 1701
|  |  | Phil | 1702 - Base Support Struct Design-DAHLGREN |  |  | 0 | 163 | 0 | 0 | 0 | 163 | 163 | 541 | -378 | -69.87% | 1751
|  |  | Phil | 1751 - Cryostat Procurement-GETTLEFINGER |  |  | 0 | 0 | 0 | 325 | 0 | 325 | 325 | 315 | 10 | 3.175% | 1752
|  |  | Phil | 1752 - Base Support Proc-DAHLGREN |  |  | 0 | 61 | 28 | 0 | 0 | 89 | 89 |  | 89 | #DIV/0!
|  |  |  | Subtotal | 431.073 |  | 0 | 224 | 235 | 325 | 0 | 784 | 1215.073 | 1360 | -144.927 | -10.66%
[15 empty] | 0 | #DIV/0!
|  | 18 - Field Period Assembly | Larry | 1801-Field Period Assy | 64.38 | [6 empty] | 0 | 64.38 | 61 | 3.38 | 5.541% | 1801
1802 - FP Assy Oversight Support |  |  | Larry | 1802 - FP Assy Oversight&Support-VIOLA | 986.703 | (1) | 253 | 790 | 858 | 88 | 0 | 1989 | 2975.703 | 1444 | 1531.703 | 106.1% | 1802
1803- FP Assy Tooling/Constructability |  |  | Larry | 1803 - FP Asy Tooling/Constrblty-BROWN | 1142.2 |  | 131 | 316 | 75 | 0 | 0 | 522 | 1664.2 | 1220 | 444.2 | 36.41% | 1803
|  |  | Larry | 1804-FP Assy Measurement | 558.937 | [6 empty] | 0 | 558.937 | 502 | 56.937 | 11.34% | 1804
|  |  | Larry | 1805 - FP Assy Hardware & Fixt Procurement | 6.876 | [6 empty] | 0 | 6.876 |  | 6.876 | #DIV/0!
1806 - FP Assy Specs and Drawings |  |  | Larry | 1806 - FP Assembly specs | 26.517 |  | 92 | 382 | 40 | 0 | 0 | 514 | 540.517 |  | 540.517 | #DIV/0!
1810 - Field Period Assembly plus 1859 unplanned work |  |  | Larry | 1810-Field Period Assy -Station 1 2 3 VIOLA | 693.632 | (1) | 1266 | 2353 | 1961 | 165 | 0 | 5745 | 6438.632 | 2203 | 4235.632 | 192.3% | 1810
|  |  | Larry | 1815 - Field Period Assy |  |  | 0 | 223 | 1017 | 94 | 0 | 1334 | 1334 |  | 1334 | #DIV/0!
|  |  |  | Subtotal | 3479.245 |  | 1742 | 4064 | 3951 | 347 | 0 | 10104 | 13583.245 | 5430 | 8153.245 | 150.2%
[15 empty] | 0 | #DIV/0!
1901 - Stellarator Core Mngt & Integr |  | 19 - Stellarator Core Management and Integration | Phil | 1901 - Stellarator Core Mngtt&Integr-COLE | 2128.2 |  | 162 | 408 | 432 | 448 | 170 | 1620 | 3748.2 | 2752 | 996.2 | 36.2% | 1901
|  |  |  | SUB TOTAL WBS 1 | 53551.035 |  | 4893 | 11072 | 6577 | 1784 | 170 | 24496 | 78047.035 | 54507 | 23540.035 | 43.19%
[15 empty] | 0 | #DIV/0!
[15 empty] | 0 | #DIV/0!
2001-VPS Gas& Cond Sys Oversight |  | 21 - Fueling Systems | Larry | 2101 - Fueling Systems-BLAMCHARD | 62.893 |  | 0 | 0 | 13 | 56 | 0 | 69 | 131.893 | 151 | -19.107 | -12.65% | 2101
|  | 22 - Torus Vacuum Pumping Systems | Larry | 2201 - Vacuum Pumping Systems-BLANCHARD |  |  | 0 | 0 | 70 | 102 | 0 | 172 | 172 | 349 | -177 | -50.72% | 2201
|  | 25 Neutral Beam Refurbishment | Larry | 2501 - Neutral Beam Refurbishment | 284.946 |  | 0 | 0 | 0 | 0 | 0 | 0 | 284.946 | 284 | 0.946 | 0.3331% | 2501
|  |  |  | SUB TOTAL WBS 2 | 347.839 |  | 0 | 0 | 83 | 158 | 0 | 241 | 588.839 | 784 | -195.161 | -24.89%
[15 empty] | 0 | #DIV/0!
3101 Magnetic Diagnostics |  | 31 - Magnetic Diagnostics | Larry | 3101 - Magnetic Diagnostics-STRATTON | 611.4 | (1) | 184 | 107 | 0 | 0 | 0 | 291 | 902.4 | 426 | 476.4 | 111.8% | 3101
|  | 36 - Edge and Divertor Diagnostics | Larry | 3601 - Edge Divertor Diagnostics-STRATTON |  |  | 0 | 0 | 0 | 31 | 0 | 31 | 31 | 46 | -15 | -32.61% | 3601
|  | 38 - Electron Beam (EB) Mapping | Larry | 3801 - Electron Beam Mapping-STRATTON |  |  | 0 | 0 | 101 | 162 | 0 | 263 | 263 | 310 | -47 | -15.16% | 3801
3901 - Diagnostics sys Integration |  | 39 - Diagnostics Integration | Larry | 3901 - Diagnostics sys Integration-STRATTON | 342.506 |  | 11 | 29 | 30 | 62 | 0 | 132 | 474.506 | 361 | 113.506 | 31.44% | 3901
|  |  |  | SUB TOTAL WBS 3 | 953.906 |  | 195 | 136 | 131 | 255 | 0 | 717 | 1670.906 | 1143 | 527.906 | 46.19%
[15 empty] | 0 | #DIV/0!
4101 - AC Power |  | 41 - AC Power | Al | 4101 - AC Power-RAMAKRISHNAN | 107.351 |  | -104 | 0 | 57 | 102 | 0 | 55 | 162.351 | 430 | -267.649 | -62.24% | 4101
4301 - DC Systems |  | 43 - DC Systems | Al | 4301 - DC Systems-RAMAKRISHNAN | 369.4 |  | 0 | 11 | 274 | 318 | 0 | 603 | 972.4 | 454 | 518.4 | 114.2% | 4301
4401 - Control & Protection |  | 44 - Control and protection Systems | Al | 4401 - Control & Protection-RAMAKRISHNAN | 80.521 |  | 0 | 0 | 314 | 770 | 0 | 1084 | 1164.521 | 1309 | -144.479 | -11.04% | 4401
4501 - Power Sys Dsn & Integr |  | 45 - Power System Design and Integration | Al | 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 161.056 |  | 0 | 0 | 356 | 274 | 53 | 683 | 844.056 | 1107 | -262.944 | -23.75% | 4501
|  | 46 FCPC Bldg Mods | Al | 4601 - FCPC Bldg Mods | 1.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1 | 0.3 | 30% | 4601
|  |  |  | SUB TOTAL WBS 4 | 719.628 |  | -104 | 11 | 1001 | 1464 | 53 | 2425 | 3144.628 | 3301 | -156.372 | -4.737%
[15 empty] | 0 | #DIV/0!
|  | 51 - Network and Fiber Infrastructure | Al | 5101 - Network and Fiber |  |  | 0 | 0 | 7 | 143 | 0 | 150 | 150 |  | 150 | #DIV/0!
|  | 52 - Central Instrumentation & Control | Al | 5201 - I&C Systems-SICHTA |  |  | 0 | 0 | 81 | 115 | 0 | 196 | 196 | 611 | -415 | -67.92% | 5201
|  | 53 - Data Acquisition & Facility Computing | Al | 5301 - Data Acquisition-SICHTA |  |  | 0 | 0 | 51 | 114 | 0 | 165 | 165 | 351 | -186 | -52.99% | 5301
|  | 54 - Facility Timing & Synchronization | Al | 5401 - Facility Timing & |  |  | 0 | 0 | 12 | 193 | 0 | 205 | 205 | 221 | -16 | -7.24% | 5401
|  | 55 - Real Time Plasma & Power Supply Control Sys | Al | 5501 - Real Time Control |  |  | 0 | 0 | 17 | 112 | 0 | 129 | 129 | 162 | -33 | -20.37% | 5501
|  | 56 - Central Safety and Interlock Systems | Al | 5601 - Central Safety &Interlock Sys-SICHTA |  |  | 0 | 0 | 12 | 210 | 0 | 222 | 222 | 382 | -160 | -41.88% | 5601
5801 -Central I&C Integr |  | 58 - Central I&C management and Integration | Al | 5801 - Central I&C Integr& Oversight-SICHTA | 33.022 |  | 7 | 24 | 19 | 19 | 0 | 69 | 102.022 | 323 | -220.978 | -68.41% | 5801
|  |  |  | SUB TOTAL WBS 5 | 33.022 |  | 7 | 24 | 199 | 906 | 0 | 1136 | 1169.022 | 2050 | -880.978 | -42.97% |  | 2373
[15 empty] | 0 | #DIV/0!
|  | 61 - Water Systems | Larry | 6163 - Facility Systems Support FY04 | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0% | 6163
|  |  | Larry | 6101 - Water Systems-DUDEK |  |  | 0 | 0 | 46 | 0 | 0 | 46 | 46 | 95 | -49 | -51.58% | 6101
|  | 62 - Cryogenic Systems | Larry | 6201 - Cryogenic Systems-DUDEK |  |  | 0 | 0 | 271 | 384 | 0 | 655 | 655 | 463 | 192 | 41.47% | 6201
|  | 63 - Utility Systems | Larry | 6301 - Utility Systems-DUDEK |  |  | 0 | 0 | 105 | 0 | 0 | 105 | 105 | 109 | -4 | -3.67% | 6301
|  | 64 - PFC/VV Heating & Cooling (Bakeout) | Larry | 6401 - PFC/VV Htng/Cooling(bakeout)- DUDEK |  |  | 0 | 0 | 107 | 466 | 0 | 573 | 573 |  | 573 | #DIV/0!
|  |  |  | SUB TOTAL WBS 6 | 24 |  | 0 | 0 | 529 | 850 | 0 | 1379 | 1403 | 691 | 712 | 103%
[15 empty] | 0 | #DIV/0!
|  | 71 Shield Wall | Larry | 7101 - Shield Wall Modif | 32.605 |  | 0 | 0 | 0 | 0 | 0 | 0 | 32.605 | 80 | -47.395 | -59.24% | 7101
7301 - Platform Design & |  | 73 - Platform Design & Fabrication | Larry | 7301 - Platform Design & | 75.836 |  | 2 | 5 | 197 | 0 | 0 | 204 | 279.836 | 164 | 115.836 | 70.63% | 7301
7401 - TC Prep & Mach Assy Planning |  | 74 - Machine Assembly Planning and Oversight | Larry | 7401 - TC Prep & Mach Assy Planning-PERRY | 854.9 |  | -308 | 23 | 615 | 857 | 230 | 1417 | 2271.9 | 1565 | 706.9 | 45.17% | 7401
|  | 75 - Test Cell and Basement Assembly Operations | Larry | 7501 - Construction Support Crew-PERRY |  |  | 0 | 0 | 336 | 806 | 265 | 1407 | 1407 | 1111 | 296 | 26.64% | 7501
|  | 75 - Test Cell and Basement Assembly Operations | Larry | 7503 - Machine Assembly (station 6)-PERRY |  |  | 0 | 0 | 1668 | 2205 | 638 | 4511 | 4511 | 1254 | 3257 | 259.7% | 7503
|  | 76 - Tooling Design & Fabrication | Larry | 7601 - Tooling Design & Fabrication-PERRY |  |  | 0 | 0 | 207 | 205 | 0 | 412 | 412 | 238 | 174 | 73.11% | 7601
|  |  |  | SUB TOTAL WBS 7 | 963.341 |  | -306 | 28 | 3023 | 4073 | 1133 | 7951 | 8914.341 | 4412 | 4502.341 | 102%
[15 empty] | 0 | #DIV/0!
8101 - Project Management & Control |  | 81 - Project Management and Control | Jim | 8101 - Project Management & Control-NEILSON | 2822.4 | (1) | 278 | 1034 | 1158 | 1074 | 299 | 3843 | 6665.4 | 4197 | 2468.4 | 58.81% | 8101
8102 - NCSX MIE Management ORNL |  |  | Jim | 8102 - NCSX MIE Management ORNL-LYON | 553.747 |  | 60 | 159 | 159 | 102 | 19 | 499 | 1052.747 | 387 | 665.747 | 172% | 8102
8202 - Engr Mgmt & Sys Eng Support |  | 82 - Project Engineering | Phil | 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2646.4 | (1) | 476 | 665 | 663 | 660 | 185 | 2649 | 5295.4 | 2835 | 2460.4 | 86.79% | 8202
8203 - Design Integration |  |  | Phil | 8203 - Design Integration-BROWN | 985.511 | (1) | 160 | 377 | 376 | 374 | 121 | 1408 | 2393.511 | 1116 | 1277.511 | 114.5% | 8203
8204 - Systems Analysis |  |  | Phil | 8204 - Systems Analysis-BROOKS | 1276.406 | (1) | 181 | 295 | 293 | 292 | 93 | 1154 | 2430.406 | 601 | 1829.406 | 304.4% | 8204
8205 - Dimensional Control Coord. |  |  | Phil | 8205 - Dimensional Control Coordin-REIERSEN | 301.9 |  | 102 | 266 | 162 | 56 | 12 | 598 | 899.9 | 332 | 567.9 | 171.1% | 8205
8210 - Project Rebaseline Estimating |  |  | Phil | 8210 - FY07 Rebaseling tasks | 37.646 |  | 19 | 0 | 0 | 0 | 0 | 19 | 56.646 |  | 56.646 | #DIV/0!
|  |  | Phil | 8215 Plant Design |  |  | 15 | 32 | 32 | 32 | 10 | 121 | 121 |  | 121 | #DIV/0!
|  |  | Jim | 8998 - Allocations-STRYKOWSKY | 1415.99 | (1) | 144 | 384 | 406 | 431 | 88 | 1453 | 2868.99 | 1577 | 1291.99 | 81.93% | 8998
|  | 84 Project Physics | Jim | 8401 - Project Physics | 323.9 | [6 empty] | 0 | 323.9 | 324 | -0.1 | -0.03086% | 8401
|  |  | Jim | 8402 - Project Physics MIE ORNL | 146.467 | [6 empty] | 0 | 146.467 | 146 | 0.467 | 0.3199% | 8402
|  | 85 - Integrated Systems Testing | Al | 8501 - Integrated Systems Testing-GENTILE |  |  | 0 | 0 | 276 | 70 | 419 | 765 | 765 | 1189 | -424 | -35.66% | 8501
8998 - Allocations |  |  |  | SUB TOTAL WBS 8 | 10510.367 |  | 1435 | 3212 | 3525 | 3091 | 1246 | 12509 | 23019.367 | 12704 | 10315.367 | 81.2%
|  |  |  | TOTAL | 67103.138 |  | 6120 | 14483 | 15068 | 12581 | 2602 | 50854 | 117957.138 | 79592 | 38365.138 | 48.2%
|  |  |  | DCMA | 75 | [7 empty] | 75
|  | CC - Contingency |  | Contingency-Project |  |  | 144 | 2205 | 3492 | 4450 | 4089 | 14380 | 14380 | 12804
|  |  |  | TOTAL | 67178.138 |  | 6264 | 16688 | 18560 | 17031 | 6691 | 65234 | 132412.138 | 92401
|  |  |  | (1) ADJUSTED FOR PLANNED RETROACTIVE G&A rate reduction in FY07 (estimated) | [10 empty] | 30463.293 |  | 79.4%
|  |  | Jim |  | 5262.504 |  | 482 | 1577 | 1723 | 1607 | 406 | 5795 | 11057.504 | 6631 | 4426.504
|  |  | Larry |  | 20428.331 |  | 2748 | 6786 | 7718 | 5881 | 1133 | 24266 | 44694.331 | 25685 | 19009.331
|  |  | Phil |  | 40659.653 |  | 2987 | 6085 | 4151 | 2653 | 591 | 16467 | 57126.653 | 40736 | 16390.653
|  |  | AL |  | 752.65 |  | -97 | 35 | 1476 | 2440 | 472 | 4326 | 5078.65 | 6540 | -1461.35
[5 empty] | 67103.138 |  | 6120 | 14483 | 15068 | 12581 | 2602 | 50854 | 117957.138 | 79592 | 38365.138