## Schedule
| Updated 8/4/06 |  |  |  | FY 2006 | [34 empty] | FY 2007 | [8 empty] | FY 2008
|  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUG |  |  |  | SEPT |  |  | OCT |  |  |  |  | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A
ITEM | TASK | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30
Target - Finish Last Field Period Assembly
VV period Arrival dates
1 | VV PREP STATION (Build to Print)
1.01 | Concept definition and requirements | Complete
1.02 | VV Support Fixture plus dwgs | Complete
1.03 | Metrology layout | Complete
1.04 | Structural Analysis | Complete
1.05 | Fab Activities - VV Support Stand
2.06 | VV Assembly Operations | [8 empty] | 1st VV
2nd VV
3rd VV
[38 empty] | A1 | [5 empty] | B4 |  | B6 |  | A5 |  | C6
2 | HALF PERIOD ASMBLY (Build to Print)
[10 empty] | C1 |  | C2 | [5 empty] | C3 |  |  | C4 | [6 empty] | C5 | [8 empty] | D: A2; J: A3; FY 2007 F: B1; FY 2007 M: A4; FY 2007 A: B2; FY 2007 M: B3; FY 2007 J: B5; FY 2008 N: A6
| Stage 2 review & left side weldment details | [29 empty] | PDR | [5 empty] | N: FDR
Mag alignment & match plate component
2.01 | Concept definition and requirements
2.02 | Left side HP Support Stand Weldment | Model and Drawings Complete
2.03 | Right side HP support stand | Canceled | [34 empty] | J: A1 / B1 / C1
2.04 | Magnetic alignment instrument | Canceled | [34 empty] | FY 2007 M: A2 / B2 / C2 MA; FY 2008 M: A6 / B6 / C6
2.05 | Machine hole match plate and support | May be Canceled | [34 empty] | FY 2007 S: A5 / B5 / C5
2.06 | Structural Analysis | 0 % done
2.07 | Fab Activities - Left side HP support fixture | [35 empty] | FY 2007 S: A4 / B4 / C4 MA
| - Fab remaining components | [35 empty] | FY 2007 A: A3 / B3 / C3
3 | MC INSTALLATION (Build to Print) | [21 empty] | PDR | [5 empty] | FDR
3.01 | Concept definition and requirements | Complete
3.02 | MC Crane Load Support System | Model Complete
3.03 | Laser Screen Guides modifications | Model Complete
3.04 | VV support stand and Misc fixtures | Model Complete
3.05 | Mechanical screw drive system | 50 % done
3.06 | Metrology layout
3.07 | Structural Analysis
3.08 | Fab Activities
3.09 | Assembly Activities
- Trial Runs - no VV
- MC Installation (1 Station)
4 | TF HP ASSEMBLY (Build to Print)
[27 empty] | PDR |  |  |  |  | FDR
4.01 | Concept definition and requirements | Complete
4.02 | TF support and rotation Fixture
4.03 | Metrology layout
4.04 | Structural Analysis
4.05 | Fab Activities -
4.06 | TF HP Assembly Operations
5 | FINAL FP ASSEMBLY (Build to Print) | [29 empty] | PDR | [5 empty] | D: FDR
5.01 | Concept definition and requirements
5.02 | MC Support Stand
5.03 | FP Assembly platforms
5.04 | Metrology layout
5.05 | Structural Analysis
5.06 | Fabrication - follow-up activities
| - FP Assembly | [35 empty] | FY 2007 J: FPA-1; FY 2008 F: FPA-3
FPA-2
Models
All Dwgs
Models / Dwgs
Models / Dwgs
Models

## Timeline
6 MONTH MANPOWER ESTIMATE
ITEM | TASK | mhrs | START | END | Resource | COMMENTS
FIELD PERIOD ASSEMBLY TOOLING/CONSTRUCTABILITY
Stage 2 | HALF PERIOD ASSEMBLY (Build to Print) |  |  |  |  | Remaining Activities
| Assy sequence plan drafted | 24 |  |  | Brown
Stage 3 | MC INSTALLATION (Outside design & Fab)
3.1 | Release dwg for actuator lifting system |  |  | 2007-01-26 | Morris | Drawing ready for signature
3.2 | Spec for actuator lifting system | 24 |  |  | Viola
3.3 | Complete stage 3 dwgs w/o laser modification |  | WIP | 2007-01-25 | Morris
3.4 | Re-set laser track on left side |  | 2007-01-29 | 2007-01-31 | Brown
3.5 | Complete stage 3 dwgs with laser mod - left side |  | 2007-01-29 | 2007-02-02 | Morris
3.6 | Re-set laser track on right side |  |  | 2007-02-02 | Brown
3.7 | Modify stage 3 dwgs with laser mod - right side |  | 2007-02-05 | 2007-02-09 | Morris | May not be required
3.8 | Update FEA models |  |  | 2007-02-14 | Morris
3.9 | Perform stress analysis |  | 2007-02-15 | 2007-02-28 | Fan | This need to be confirmed
4 | re-estimate fabrication costs |  |  | 2007-02-28 | Brown
4.1 | FDR |  |  | 2007-03-06 |  | I have Jury Duty Feb 26 thru March 2
4.2 | Revise drawings as needed per FDR input |  | 2007-03-07 | 2007-03-09 | Morris
4.3 | Release drawings for fabrication |  |  | 2007-03-12 | Morris | Fixtures needed 6/27/07, 3 months to fab parts (looks OK)
4.4 | VV/MC clearance report (for VVSA1, 2 and 3) | 72 |  |  | Brown
4.5 | Generate laser trace drawing for each screen | 40 | 2007-03-12 | 2007-03-16 | Morris
4.6 | Assembly sequence plan drafted | 24 |  |  | Brown
Stage 4 | TF HP ASSEMBLY (Build to Print) |  |  |  |  | No longer needed
Stage 5 | FINAL FP ASSEMBLY (Build to Print)
5.1 | Update Stage 5 PD consistent with TF asmbly plan | 80 | 2007-03-19 | 2007-03-30 | Morris
5.2 | Develop Stage 5 model details | 80 | 2007-04-02 | 2007-04-13 | Morris
5.3 | Develop Stage 5 drawings | 80 | 2007-04-16 | 2007-04-27 | Morris
5.4 | Develop Stage 5 FEA models | 24 | 2007-04-30 | 2007-05-02 | Morris
5.5 | Perform stress analysis |  | 2007-05-03 | 2007-05-17 | Fan
5.6 | re-estimate fabrication costs |  |  | 2007-05-17 | Morris
5.7 | FDR |  |  | 2007-05-18
5.8 | Revise drawings as needed per FDR input |  | 2007-05-21 | 2007-05-25 | Morris
5.9 | Release drawings for fabrication |  |  | 2007-05-28 | Morris | Fixtures needed 8/15/07, ~3 months to fab parts (looks OK)
6 | Assembly sequence plan drafted | 24 |  |  | Brown
DESIGN INTEGRATION
1 | Type-A inspection/interface reqmt report | 24 |  |  | Brown
2 | Type-B inspection/interface reqmt report | 24 |  |  | Brown
3 | Type-C inspection/interface reqmt report | 24 |  |  | Brown
4 | Develop Inboard MC bolt arrangement | 16 |  |  | Brown
5 | Review C-to-C fit-up data | 16 |  |  | Brown
6 | Q/A B5, A5, A6, B6, C6 | 40 |  |  | Brown
7 | Develop loop models/drawings for spool | 120 |  |  | Morris
8 | VV Stage 1 back office support |  | 10% |  | Brown
9 | Support NCSX drawing checking/sign-off process |  | 5% |  | Brown
10 | Mics NCSX project support activities |  | 15% |  | Brown
11 | MC Stage 2 back office support |  | 40% |  | Brown | Activities start in June time period
12 | Stage 3 back office support |  | 40% |  | Brown
13 | Stage 5 back office support |  | 10% |  | Brown
14 | Final machine assembly back office support |  | 20% |  | Brown
15 | Updated machine/test cell assembly model | 320 |  |  | Morris

## Cost Summary
| Field Period Hardware Cost Estimates | [5 empty] | PPPL Shop Rate ($/hr) = | 81
Unit
|  | Weight | $ per | Unit |  | Total |  | Equiv |  |  |  | Man-
| Description | (lbs) | Lb | Cost ($) | Qnty | Cost ($) | Comments | hrs |  |  | Hware | power
Stage 1 - VV Support Stand Cost
| Support Stand Weldment | 290 | 7 | 2030 | 2 | 4060 |  | 50.1235
| Support Axle Weldment | 47 | 15 | 705 | 2 | 1410 |  | 17.4074
| Axle locking clamp | 19 | 15 | 285 | 2 | 570 |  | 7.037
| Port 12 blank-off cover | 115 | 7 | 805 | 2 | 1610 |  | 19.8765
| Lateral support Weldment | 46 | 15 | 690 | 1 | 690 |  | 8.5185
| Worm Gear mounting bracket | 20 | 30 | 600 | 1 | 600 |  | 7.4074
| Machine hoist ring |  |  | 210.48 | 2 | 420.96 | McMaster-Carr
| Worm Gear |  |  | 294 | 1 | 294 | Boston Gear G1104
| Worm |  |  | 322 | 1 | 322 | Boston Gear H1104
| Hand Wheel |  |  | 153.72 | 1 | 153.72 | McMaster-Carr
| Base-Mount Ball Bearings |  |  | 39.65 | 1 | 39.65 | McMaster-Carr
| Misc Hardware |  |  |  |  | 500
| Assembly Cost |  |  |  |  | 2720 |  | 33.5802
| Contingency, % | 20 |  |  |  | 2678.066 |  | 33.0625
[6 empty] | 16068.396 |  | 177.0132 | 4.4253 | wks
Stage 2 - MCHP Assembly Cost
| Measurement Support Stand Weldment | 250 | 4 | 1000 | 4 | 4000 | weldment plus some machined structure | 49.3827
| Misc Hardware |  |  |  |  | 500
| Contingency, % | 20 |  |  |  | 900
[6 empty] | 5400 |  | 49.3827 | 1.2346 | wks
Stage 3 - MC Assembly Cost
| Laser Screen Modification parts | 300 | 4 | 1200 | 2 | 2400 |  | 29.6296
| Reworked Laser Screen Weldment |  |  |  | 2 | 3240 | based on 1 wk shop hours | 40
| Test cell hook adaptor plate | 300 | 7 | 2100 | 1 | 2100 |  | 25.9259
| SISSCO 3 Actuator Lift System |  |  |  |  | 0 | Cost included in Mike Viola's WBS
| MC I-beam upper support at Type-A | 579 | 4 | 2316 | 1 | 2316 | weldment plus some machined structure
| MC upper support at Type-C | 160 | 4 | 640 | 1 | 640 | weldment plus some machined structure
| MC upper support at Type-C | 60 | 7 | 420 | 3 | 1260 | weldment plus some machining
| MC base support system | 2938 | 4 | 11752 | 1 | 11752 | weldment plus some machined structure | 145.0864
| VV support system | 1411 | 4 | 5644 | 1 | 5644 | weldment plus some machined structure | 69.679
| Hilman roller - 8-0T plus R & U guides |  |  | 950 | 8 | 7600 | Based on Hilman phone quote
| AirLoc Wedgmount Precision Levelers |  |  | 315 | 3 | 945 | Based on phone quote
| Bushnell Laser Boresighter |  |  | 34.97 | 6 | 209.82 | Internet price
| Flange bolt access platform |  |  |  |  | 0 | Shop supplied per Edwards comment | 0
| Hardware & Misc items |  |  |  |  | 1500
| Misc assembly Cost |  |  |  |  | 3240 | based on 1 wk shop hours | 40
| Contingency, % | 20 |  |  |  | 8569.364 |  | 105.7946
[6 empty] | 49016.184 |  | 456.1156 | 11.4029 | wks
Stage 4 - TF 3-Coil Assembly Cost | [6 empty] | No longer needed
Stage 5 - FP Assembly Cost
| MC support stand | 3159 | 4 | 12636 | 1 | 12636 |  | 156
| TF HP assembly structure | 5041 | 4 | 20164 | 1 | 20164 | A redesign may reduce the cost | 248.9383 |  |  | 5000
| TF casters |  |  | 117.85 | 3 | 353.55 | McMaster-Carr (23515T11)
| MCHP tilt support fittings | 20 | 15 | 300 | 2 | 600 |  | 7.4074
| TF support roller bearings |  |  | 400 | 2 | 800
| VV port instl platform |  |  |  |  | 20000 | Use existing platforms? | 40
| Hardware |  |  |  |  | 500
| Misc assembly Cost |  |  |  |  | 3240 |  | 40
| Contingency, % | 30 |  |  |  | 17488.065 |  | 215.902
[5 empty] | Stage 5 is being redesigned based on no Stage 4 | 75781.615 |  | 708.2477 | 17.7062 | wks
[5 empty] | TOTAL FIELD PERIOD ASSEMBLY FIXTURE HARDWARE COST | 146266.195
[6 empty] | 124797.799 | Cost of Stage 3 and 5 only
Rate
| Manpower Cost Estimate | Month | % time | Hours | ($/hr)
| Drafting | 8 | 1 | 1150.6667 | 115 | 132326.6667
| Electrical drafting |  |  | 0 | 102 | 0 | was 120 hrs
| Engineering | 8 | 0.5 | 575.3333 | 172 | 98957.3333
| Stress Analysis |  |  | 480 | 172 | 82560 | [5 empty] | 1376
[6 empty] | 313844 | [5 empty] | 4600
5976
[5 empty] | TOTAL FPA COST | 460110.195 | Includes contingencies
TOTAL COST TO COMPLETE
[5 empty] | FPA Hardware Cost | 130197.799 | Includes Stage 2 through Stage 5
[5 empty] | FPA Hardware Cost less Contingency | #REF!
[5 empty] | Manpower Cost Estimate | 313844
[5 empty] | Total Cost less contingency | #REF! | This assumes one unit of each built
[5 empty] | Scaled down FPA Cost | #REF! | This assumes one unit of each built |  |  |  | #REF! | savings
[6 empty] | 4500 | Added cost for second Stage 2 (Hardware only)
[6 empty] | 43129.55 | Added cost for second Stage 5 (Hardware only)
[5 empty] | TOTAL COST | #REF! | Assumed scaled down FPA cost

## Mag Measurement Cost
MAGNETIC MEASUREMENT COST ESTIMATE
LABOR COSTS
| Hr per | nb of | Total
| Template | Template | Man-hours | Fabrication Activity
|  |  | 16 | Program set up and cut loops
| 1 | 20 | 20 | Locate template
| 1 | 20 | 20 | Wind loop wire
| 1 | 20 | 20 | Terminate wires
|  |  | 8 | Add junction box
|  |  | 8 | Misc activities
|  |  | 92 | Loop assembly
|  |  | 40 | Machine tube, cut vertical panel and assemble
|  | Total labor costs | 10692 | Labor cost at hourly of: | 81
MATERIAL COSTS
Total
| Qnty | Unit Cost | Cost
| 2 | 143.62 | 287.24 | .043" x 36" x 48" sheet per McMaster-Carr
| 1 |  | 2417 | 24" OD x 6' acrylic tube per GE Cast Acrylic Tube | (see note 1)
|  |  | 2500 | Vertical panel
|  |  | 250 | hardware
5454.24
|  |  | 16146.24 | Magnetic Measurement Cost Estimate
note 1: spoke with Keith at GE Polimer Shapes
phone no: 866-437-7427