## Timeline
2007-01-24 | 6 MONTH MANPOWER ESTIMATE
ITEM | TASK | mhrs | START | END | Resource | COMMENTS
FIELD PERIOD ASSEMBLY TOOLING/CONSTRUCTABILITY
Stage 2 | HALF PERIOD ASSEMBLY (Build to Print) |  |  |  |  | Remaining Activities
| Assy sequence plan drafted | 24 |  |  | Brown
Stage 3 | MC INSTALLATION (Outside design & Fab)
3.1 | Release dwg for actuator lifting system |  |  | 2007-01-26 | Morris | Drawing ready for signature
3.2 | Spec for actuator lifting system | 24 |  |  | Viola
3.3 | Complete stage 3 dwgs w/o laser modification |  | WIP | 2007-01-25 | Morris
3.4 | Re-set laser track on left side |  | 2007-01-29 | 2007-01-31 | Brown
3.5 | Complete stage 3 dwgs with laser mod - left side |  | 2007-01-29 | 2007-02-02 | Morris
3.6 | Re-set laser track on right side |  |  | 2007-02-02 | Brown
3.7 | Modify stage 3 dwgs with laser mod - right side |  | 2007-02-05 | 2007-02-09 | Morris | May not be required
3.8 | Update FEA models |  |  | 2007-02-14 | Morris
3.9 | Perform stress analysis |  | 2007-02-15 | 2007-02-28 | Fan | This need to be confirmed
4 | re-estimate fabrication costs |  |  | 2007-02-28 | Brown
4.1 | FDR |  |  | 2007-03-06 |  | I have Jury Duty Feb 26 thru March 2
4.2 | Revise drawings as needed per FDR input |  | 2007-03-07 | 2007-03-09 | Morris
4.3 | Release drawings for fabrication |  |  | 2007-03-12 | Morris | Fixtures needed 6/27/07, 3 months to fab parts (looks OK)
4.4 | VV/MC clearance report (for VVSA1, 2 and 3) | 72 |  |  | Brown
4.5 | Generate laser trace drawing for each screen | 40 | 2007-03-12 | 2007-03-16 | Morris
4.6 | Assembly sequence plan drafted | 24 |  |  | Brown
Stage 4 | TF HP ASSEMBLY (Build to Print) |  |  |  |  | No longer needed
Stage 5 | FINAL FP ASSEMBLY (Build to Print)
5.1 | Update Stage 5 PD consistent with TF asmbly plan | 80 | 2007-03-19 | 2007-03-30 | Morris
5.2 | Develop Stage 5 model details | 80 | 2007-04-02 | 2007-04-13 | Morris
5.3 | Develop Stage 5 drawings | 80 | 2007-04-16 | 2007-04-27 | Morris
5.4 | Develop Stage 5 FEA models | 24 | 2007-04-30 | 2007-05-02 | Morris
5.5 | Perform stress analysis |  | 2007-05-03 | 2007-05-17 | Fan
5.6 | re-estimate fabrication costs |  |  | 2007-05-17 | Morris
5.7 | FDR |  |  | 2007-05-18
5.8 | Revise drawings as needed per FDR input |  | 2007-05-21 | 2007-05-25 | Morris
5.9 | Release drawings for fabrication |  |  | 2007-05-28 | Morris | Fixtures needed 8/15/07, ~3 months to fab parts (looks OK)
6 | Assembly sequence plan drafted | 24 |  |  | Brown
DESIGN INTEGRATION
1 | Type-A inspection/interface reqmt report | 24 |  |  | Brown
2 | Type-B inspection/interface reqmt report | 24 |  |  | Brown
3 | Type-C inspection/interface reqmt report | 24 |  |  | Brown
4 | Develop Inboard MC bolt arrangement | 16 |  |  | Brown
5 | Review C-to-C fit-up data | 16 |  |  | Brown
6 | Q/A B5, A5, A6, B6, C6 | 40 |  |  | Brown
7 | Develop loop models/drawings for spool | 120 |  |  | Morris
8 | VV Stage 1 back office support |  | 10% |  | Brown
9 | Support NCSX drawing checking/sign-off process |  | 5% |  | Brown
10 | Mics NCSX project support activities |  | 15% |  | Brown
11 | MC Stage 2 back office support |  | 40% |  | Brown | Activities start in June time period
12 | Stage 3 back office support |  | 40% |  | Brown
13 | Stage 5 back office support |  | 10% |  | Brown
14 | Final machine assembly back office support |  | 20% |  | Brown
15 | Updated machine/test cell assembly model | 320 |  |  | Morris