## Station 2-1st Article
| Station 2 - 1st Article (Half Period Assembly) | See last page for Rev changes
NO. | ASSEMBLY STEP | COMMENTS
1 | MC fit-up pre-check and surface insulation
1.01 | Verify that mating MC's of a MCHP will come together without interferences by pre-fitting mating coils. This will include the Type-C coil with its interfacing Period Type-C coil. | The full assembly layout of the mating MC's can be found in Table 1 and Figure 3 below. Some of this effort may be done before the half period assembly activity begins.
1.02 | Epoxy paint all close fitting interfacing surfaces.
2 | Pre-measurement of MCHP Type A, B and C coils flanges plus interfacing Type-A coil flange | See MCHP component designation in Table 1 of this document. MCHP Assembly Dimensional Control Plan: NCSX-PLAN-HPADC-00
2.01 | Follow the steps defined in Section 2 of the Metrology Plan for racking coils and lower the Type-A modular coil onto the jacks, “A” flange (datum "D") down and rack the "A" coil into its proper shape. | The acceptance criterion is .005" RMS deviation in alignment to the set of tooling balls. With a successful alignment a set of global fiducial monuments will have been established. Subsequent alignments of the laser tracker will be to the global monuments, and the criterion of .002” RMS deviation will apply
2.02 | Scan the “B” flange (datum E) and the MC shell VV boss interface.
2.03 | Remove Type-A coil from stand and move to holding area.
2.04 | Follow the steps defined in Section 2 of the Metrology Plan for racking coils and lower the Type-B modular coil onto the jacks, “B” flange (datum "E") down and rack the "B" coil into its proper shape. | The acceptance criterion is .005" RMS deviation in alignment to the set of conical seats. With a successful alignment a set of global fiducial monuments will have been established. Subsequent alignments of the laser tracker will be to the global monuments, and the criterion of .002” RMS deviation will apply
2.05 | Scan the "A" flange (datum D). | Flange measurement is needed for the A side (only) for the Type-B coil.
2.06 | Remove Type-B coil from stand and store coil.
2.07 | Follow the steps defined in Section 2 of the Metrology Plan for racking coils and lower the Type-C modular coil onto the jacks, “B” flange (datum "E") down and rack the "C" coil into its proper shape. | The acceptance criterion is .005" RMS deviation in alignment to the set of conical seats. With a successful alignment a set of global fiducial monuments will have been established. Subsequent alignments of the laser tracker will be to the global monuments, and the criterion of .002” RMS deviation will apply
2.08 | Scan the "A" flange (datum D). | Flange measurement is needed for the A side (only) for the Type-C coil.
2.09 | Remove Type-C coil from stand and store coil.
3 | Shim sizing / preparations | Metrology procedure covering Station 2:
3.01 | Using flange measurement of the coils, define the A/B shim thickness. | This is a back office calculation where shim thickness is predetermined based on the scanned flange surface data.
3.02 | Compress alumina coated shims and sort by thickness the shim set that will be installed on the MCHP. | Care must be taken when handling alumina shims to mitigate any possible surface contamination conditions.
4 | A-B modular coil assembly | See MCHP component designation in Table 1 of this document. MCHP Assembly Dimensional Control Plan: NCSX-PLAN-HPADC-00 Reference Drawings: SE140-003 and se140-046
4.01 | Follow the steps defined in Section 2 of the Metrology Plan for racking coils, lower the Type-A modular coil onto the jacks, “A” flange (datum "D") down and rack the "A" coil into its proper shape. | The acceptance criterion is .005" RMS deviation in alignment to the set of conical seats. With a successful alignment a set of global fiducial monuments will have been established. Subsequent alignments of the laser tracker will be to the global monuments, and the criterion of .002” RMS deviation will apply
4.02 | Using the Type-A (B-flange) inboard shim template mark the nose shim locations and puck locations. Remove the template. | Use a thin equivalent washer of the puck diameter (or some other method) to provide a positoinal "feel" to allow measuring puck height in the A -B installed position.
4.03 | Place an initial set of alumina shims (4) on the Type-A coil in designated locations for the initail alignment of the mating coil. | See document XXXX for shim size and location.
4.04 | Place unfilled shim bags in the wing areas
4.05 | Lower the mating “B” coil into position.
4.06 | Install the jack screws and dial indicators for horizontal positioning.
4.07 | Using three selected monuments on the “B” coil, position the coil accurately in the Z-direction and within 1/16" in the X - Y plane. | IT MAY BE BETTER TO ACCURACY POSITION THE "B" COIL
4.08 | Install the remaining alumina coated shims; install studs, supernuts, and torque to 50% of final value.
4.09 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck.
4.1 | After tightening, measure the position of all monuments per the Dimensional Control Plan, following steps 2.3.3 through 2.3.7. | IF WE ARE NOT FULLY POSITIONED WHAT ALIGNMENT ACCURACY SHOULD WE REQUIRE?
4.11 | Measure the shim puck height (at a numer of points around the puck surface) at each of the nose shim puck locations. Use the data to define each puck height.
4.12 | Unfasten bolts and raise the "B" coil in height to remove the puck locating rings and allow the installation of all nose shims with the properly sized pucks. Use tempory shims to support the Type-B flex shims.
4.13 | "Lightly" tack weld the nose flex shims to the perspective "A" and "B" coils.
4.14 | Unfasten all bolts and remove the "B" coil and place it on a separate fixture, with the Type-B coil side "A" flange (datum "D") facing up.
4.15 | Recheck the part alignment of the "A" coil to make sure it is still within alignment and then weld all Type-A flex shims to the plasma side, following the weld sequence plan.
4.16 | After welding the "A" coil nose shims recheck alignment to determine if the part still meets the metrology acceptance criterion.
4.17 | Time needs to be alocated for a back office assessment of the part after welding. | If Control Plan acceptance criterion is not met project input is needed to determine how to proceed.
4.18 | On the separate fixture measure the "B" faducials to establish a reference coordinate system prior to welding the "B" coil nose shims.
4.19 | With the seccessful "A" coil weld operation, weld all Type-B (A-flange) flex shims to the plasma side, following the weld sequence plan.
4.2 | After welding the "B" coil nose shims recheck the part to determine if still meets the metrology acceptance criterion.
4.21 | Time needs to be alocated for a back office assessment of the part after welding. | If Control Plan acceptance criterion is not met project input is needed to determine how to proceed.
4.22 | Remove all alumina shims except for the (4) initial locaiting shims on the Type-A coil in designated locations for the initail alignment of the mating coil. | I WASN'T SURE ABOUT THIS. CAN WE LEAVE ALL THE SHIMS ON THE "A" COIL AND ASSUME THAT THE "B" COIL WILL COME INTO ALIGNMENT?
4.23 | Lower the mating “B” coil into position.
4.24 | Using three selected monuments on the “B” coil, position the coil accurately in the X -Y plane. | An accuracy of .002” or better is expected and required for this step.
4.25 | Raise the "B" coil slightly and install the remaining alumina coated shims; install Fuji paper on all outboard shims, install studs, supernuts, and torque to 50% of final value.
4.26 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck.
4.27 | After tightening, measure the position of all monuments per the Dimensional Control Plan, following steps 2.3.3 through 2.3.7. | The maximum deviation from the “realigned” points should be .007” or less.
4.28 | Unfasten the bolts, lift the “B” coil enough to remove the Fuji paper, and examine the load sharing. At the same time, the “back office” will analyze the measurements of the monument positions. A revised set of shim thicknesses, to provide adequate load sharing and dimensional accuracy, will be generated if required.
4.29 | If a revised set of shims is required, install the new shims and Fuji paper. Lower and reposition the “B” coil. Repeat steps 4.26 thru 4.28.
4.3 | With a successful Fuji load pattern, unfasten the bolts, lift the “B” coil enough to remove the Fuji paper and initial shims. Install an equivalent set of alumina coated shims without Fuji paper, lower and position the “B” coil, install all bushings and other parts of the bolt kits, and tighten the bolts to 50% value. | Send the Fuji paper test shims out to be cleaned.
4.31 | After super bolt tightening, measure the position of all monuments per the Dimensional Control Plan, following steps 2.3.3 through 2.3.7. | The maximum deviation from the “realigned” points should be .007” or less.
4.32 | Install wing support hardware | Assume three welded chair supports with nut-plates on each wing
4.33 | Load support hardware to pre-weld condition. | NEED TO DEFINE HOW MUCH LOAD TO APPLY…. OR DO WE DO NOTHING AND MOVE THIS STEP TO AFETER THE WELD AND THEN ADJUST WING TO MEED POSITION CRITERIA IF NEEDED?
4.34 | After tightening wing hardware, measure the position of all monuments per the Dimensional Control Plan, following steps 2.3.3 through 2.3.7. | The maximum deviation from the “realigned” points should be .012” RMS or less.
4.35 | Tighten all bolts to their final torque.
4.36 | Weld the A / B nose region solenoid side following the weld procedure.
4.37 | Measure the positions of all monuments per the process defined in the Metrology Plan, steps 2.3.3 through 2.3.7. | The maximum deviation from the “realigned” points should be .015” RMS or less. IS THIS THE CORRECT VALUE?
4.38 | Identify, if possible, a set of monuments that have moved less than .005” from their original positions. The alignment that will be necessary for mating to the “C” coil will use monuments from among this set.
4.39 | Fill all lose bushings with Stycast 2850FT
4.4 | Scan the "B" flange (datum “E”) of the “B” coil, for the purpose of defining the shim thickness for the mating to the “C” coil. Save the measurement file and back it up.
4.41 | Using the "B" flange (datum "E") measurement of the Type-B coil and the earlier "A" flange (datum "E") measurement of the Type-C coil, define all B/C flange shim thickness. | This is a back office calculation where shim thickness is predetermined based on the scanned flange surface data.
5 | (A-B) to C modular coil assembly (MCHP) | See MCHP component designation in Table 1 of this document. MCHP Assembly Dimensional Control Plan: NCSX-PLAN-HPADC-00 Reference Drawings: SE140-003 and se140-046
5.01 | Bolt the "A" coil to its fixture and lift the (A-B) coil, along with the fixture, onto another wedge with its top surface tilted at 20 degrees from horizontal. Bolt the fixtures together.
5.02 | Select a subset of monuments identified in step 4.23 that will be used for the initial alignment in this next phase of half period assembly.
5.03 | Align to the set of monuments selected in 5.02. Acceptance criterion is .005” RMS deviation. | ARE WE STILLING HOLDING THE .005" RMS CRITERION?
5.04 | Establish a set of global monuments, including three positions on the fixture and five on the building.
5.05 | Using the Type-B coil (B-flange) inboard shim template mark the nose region shim locations for the "B" coil, side "B" flange (datum E). Remove the template, place all B coil flex shims and weld them along the plasma side, following the weld sequence plan.
5.06 | Recheck part alignment to determine if the part is still meets the metrology acceptance criterion. | If Control Plan acceptance criterion is not met project input is needed to determine how to proceed.
5.07 | On a separate fixture, with the Type-C coil side "A" flange (datum "D") facing up, mark the nose region shim locations using the Type-C (A-flange) inboard shim template. Remove the template, place all Type-C flex shims and weld them along the plasma side, following the weld sequence plan. | Recheck part alignment to determine if the part is still meets the metrology acceptance criterion.
5.08 | Place an initial set of metal shims (4) on the Type-B coil in designated locations for alignment of the mating coil.
5.09 | Place unfilled shim bags in the wing areas
5.1 | Lower the mating “C” coil into position.
5.11 | Install the jack screws and dial indicators for horizontal positioning.
5.12 | Using three selected monuments on the “C” coil, position the coil horizontally.
5.13 | Install the remaining outboard metal shims; install Fuji paper, install studs, supernuts, and torque to 50% of final value.
5.14 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten the bolts to 50% value.
5.15 | After tightening, measure the position of all monuments per the Dimensional Control Plan, following steps 2.3.3 through 2.3.7. | The maximum deviation from the “realigned” points should be .010” or less. WHAT IS THE CORRECT VALUE HERE?
5.16 | Unfasten the bolts, lift the “C” coil enough to remove the Fuji paper, and examine the load sharing. At the same time, the “back office” will analyze the measurements of the monument positions. A revised set of shim thicknesses, to provide adequate load sharing and dimensional accuracy, will be generated if required.
5.17 | If a revised set of shims is required, install the new shims and Fuji paper. Lower and reposition the “C” coil. Repeat steps 5.14 thru 5.16.
5.18 | After the proper load sharing and dimensional accuracy is verified, raise the "C" coil in height to install nose shim limiter pucks. Secure "C" coil in raised position.
5.19 | Install fixed height shim pucks with mold set surface layer at all puck locations.
5.2 | Lower the mating “C” coil into position and tighten bolts (maybe not all bolts) to 50% of final value.
5.21 | Unfasten bolts and raise the "C" coil in height to allow removal of nose shim limiter pucks. Secure "C" coil in raised position. Remove "gage" shim pucks and replace each with matching machined (or ground) replacement pucks.
5.22 | Install the equivalent set of alumina coated shims without Fuji paper, lower and position the “C” coil, install all bushings and other parts of the bolt kits, and tighten the bolts to 50% value.
5.22a | After super bolt tightening, measure the position of all monuments per the Dimensional Control Plan, following steps 2.3.3 through 2.3.7. | The maximum deviation from the “realigned” points should be .007” or less.
5.22b | Install wing support hardware
5.22c | Fill A B / C wing bladder and cure
5.22d | Apply a nominal load to bladder from wing support hardware | ??? How much load… finger tight??????????
5.23 | Measure the tooling balls on all coils. Save the data file and back it up. Print reports of all alignments used, and nonconformance reports, and keep with run copies of the assembly procedure. | The maximum deviation from the “realigned” points should be .010” or less. If the deviation is greater that .010", Project input is needed to determine how to proceed. WHAT IS THE NEW VALUE?
5.23a | Weld the nose region solenoid side. | Should we weld when complete A/B/C?
5.23b | Fill all lose bushings with Stycast 2850FT
6 | Weld inboard shims on solenoid side.
6.01 | Weld all inboard shims on solenoid side following the weld procedure.
6.02 | Measure the tooling balls on all coils. Save the data file and back it up. Print reports of all alignments used, and nonconformance reports, and keep with run copies of the assembly procedure. | The maximum deviation from the “realigned” points should be ????” or less. If the deviation is greater that ????", Project input is needed to determine how to proceed. WHAT IS THE NEW VALUE?
7 | Inflate all wing shim bags
Fill all wing bladders and cure
8 | Install trim coil
8.01 | Trim coils will be install on all Type-A coils. The best access may be at Station 2. We need to review this once the trim coil details are better understood.
9 | Complete local service and interface details | Reference drawing: xxxxxxx
9.01 | Install all wing support bladders between wing surfaces (A/B, B/C) and on the C wing (MCHP - Right Side only).
9.02 | Make local service runs/connections on the shell of each MC. | Verify what is involved here.
9.03 | Inject stycast or some compound to fill in all shim spaces in order to prevent VV/MC insulation from falling out. | This could be done earlier
10 | Final measurements / transfer completed MCHP to holding area | Reference drawing: xxxxxxx
10.01 | Install or identify three primary fiducials that will be used in positioning the Period in Station 3.
10.02 | Scan the “B” flange of Type-C coil as well as the interfacing base support feet (see Figure 4. Record the results.
10.03 | Using tension tester measure bolt length on all tension fasteners and record the results.
10.04 | Mark part for identification | Part identification should indicate the period and subparts (ex. MCHP - Left Side C1/B1/A!)
10.05 | Install lift support beams
10.06 | Remove from stand and measure weight of completed assembly
10.07 | Move to holding area.
Change in Rev 8:
1 | Updated sequence plan for Station 2 to meet welded nose approach and following Dimensional Control Plan: NCSX-PLAN-HPADC-00-dC
Change in Rev 7:
1 | Updated sequence plan per Ron's schedule: NCSX Prelimary CP Sched 20070531
Change from Rev 4:
1 | Developed a Station 2 - 1st article sequence plan that includes the addition of metal shims and Fuji paper to use for shim qualification test.
2 | Reintroduced the A - A pre-fit up to establish a success oriented full period installation operation.
3 | Added a shim sizing / preparation step
4 | Developed a Station 2 - Production article sequence plan that excludes Fuji paper and installs all alumina coated shims on the first pass.
Change from Rev 3:
1 | The Pre-assemble A-A (old step 4.0) has been eliminated in favor of alignment of separate MCHP.
2 | Fuji paper will no longer be included in the installation process although it may be used on the first MCHP article (separate plan).
3 | Alumina coated shims with close tolerance bolt hole installed on first pass.
4 | Assembly tolerance increase to .010" from .007" in (A-B) to C fit-up.
Table 1.0 Period Assembly Make-up Period 1: MCHP – Left Side MCHP – Right Side C1 / B1 / A1 A2 / B2 / C2 Period 2: MCHP – Left Side MCHP – Right Side C3 / B3 / A3 A4 / B4 / C4 Period 3: MCHP – Left Side MCHP – Right Side C6 / B5 / A5 A6 / B6 / C5
Figure 3. MC arrangement for the full machine assembly
Trim Coils
MCHP – Left Side
MCHP – Right Side
Figure 4. Measurement of MCHP feet
Surface area needing measurement