## A
SNS SURVEY & ALIGNMENT
Alignment Support for Princeton Plasma Physics Laboratory (NSCX)
|  |  |  | Labor | Labor
|  | Required | Equipment | Hours | Hours | Required | Parts / Etc. | Unit | Parts | TRAVEL
| Activity | Equipment | Costs | Engineers | Technicians | Parts / Etc. | Quantity | Cost | EXT | COSTS | Notes
1. | Design Global Survey Network to Support NSCX | NA | NA | NA | NA | NA | NA | NA | NA | NA | SNS S&A has prepared an initial
| Installation / Alignment | [9 empty] | global survey network for PPPL.
No cost initial network
2. | Lay out locations of 40 floor & 60 wall monuments | Total | Shipping | 48 | NA | *Floor | 40 | 80 | 3200 | TRIP ONE | a. 3 days includes travel and work performed
| at PPPL | Station Inst. |  |  |  | Monuments |  |  |  | [Travel, Car, Lodging, etc | b. Total Station Inst. Supplied by SNS
for 2 people] paid by
[6 empty] | * Wall Monumuments | 60 | 75 | 4500 | PPPL | c. Monument costs if supplied by SNS
PPPL may purchase directly
3. | 1. Core necessary holes for floor monuments |  |  | NA | NA | [5 empty] | a. work to be performed by PPPL
2. Drill & Epoxy wall monuments
4. | Measure Network | 1. Laser Tracker |  | 80 | 80 |  |  |  |  | TRIP TWO | a. laser tracker supplied by PPPL
|  | 2. Digital Level | Shipping | [6 empty] | [Travel, Car, Lodging, etc | b. Digital Level supplied by SNS
|  | 3. Digital Level Rods | Shipping | [6 empty] | for 4 people] paid by | c. Level rods supplied by SNS
|  | 4. H.I. Illuminator | Shipping | [6 empty] | PPPL | d. High-intensity illuminator by SNS
5. | Network Data Adjustment and Analysis |  |  | 40 | NA | [5 empty] | a. performed at SNS
6. | 1. Network re-observation to detect deformation (annual) | 1. Laser Tracker |  | 80 | 80 |  |  |  |  | TRIP THREE (and more) | a. laser tracker supplied by PPPL
|  | 2. Digital Level | Shipping | [6 empty] | [Travel, Car, Lodging, etc | b. Digital Level supplied by SNS
|  | 3. Digital Level Rods | Shipping | [6 empty] | for 4 people] paid by | c. Level rods supplied by SNS
|  | 4. H.I. Illuminator | Shipping | [6 empty] | PPPL | d. High-intensity illuminator by SNS
| 2. Network Data Adjustment and Analysis |  |  | 40 | NA | [5 empty] | e. performed at SNS
7. | 1. "Surge" of new monuments to augment network above platform | 1. Laser Tracker |  | 80 | 80 |  |  |  |  | TRIP THREE | a. laser tracker supplied by PPPL
| (prior to platform installation) |  |  |  |  | * Wall Monumuments | 20 | 75 | 1500 | [Travel, Car, Lodging, etc | b. monuments installed by PPPL
| ** might be possible to accomplish during a | [8 empty] | for 4 people] paid by
| re-observation campaign ** | [8 empty] | PPPL
| 2. Network Data Adjustment and Analysis |  |  | 40 | NA | [5 empty] | c. performed at SNS
8. | Optical Tooling Training Class | [9 empty] | a. 24 hours (no charge)
9. | Optical Instrument Calibration for PPPL | [9 empty] | a. no charge for initial instruments
|  |  | Total ---> | 408 | 240 |  |  |  | 9200
|  |  |  | Engineer | Technician
|  |  |  | Hours | Hours