## Design Status
NCSX Design Status Summary 3/6/08
WBS | Scope | Job Mgr. | CDR | PDR | FDR | Start fab./ Award
Stellarator Core out to MC Shell & VV port flanges
12 | Vacuum Vessel | Goranson
14 | Modular Coil Assemblies | Williamson
14 | MC AA, AB, BC Interface | Williamson / Cole |  | X | X | X
14 | MC CC Interface | Williamson / Cole |  |  | X
18 | FPA Tooling:
18 | Station 3 stands and lift fixtures | Brown |  |  | X | X
18 | Station 3 module alignment system | Brown |  |  | 2008-03-11 | 2008-04-28
82 | Assembly Sequence Plan Maturity |  | Assessment | Envisioned future changes
82 | Station 2 | Brown | 99% | probably none
82 | Station 3 | Brown | 90% | module alignment system
Stellarator Core Beyond MC Shell & VV port flanges
12 | NB Transition Ducts | Goranson |  | 2008-06-26 | 2008-09-25
13 | PF Coils | Chrzanowski |  | X | 2008-03-04 | 2008-05-06
13 | Trim Coils | Kalish | X | 2008-03-11 | 2008-04-30 | 2008-06-21
15 | Coil Structures | Dahlgren |  |  | 2008-03-31
16 | LN2 Manifolds | Goranson |  | 2008-04-02 | 2008-07-07
16 | Electrical Leads | Goranson |  | 2008-08-21 | 2009-03-29
17 | Base Structure | Dahlgren |  | X | 2008-03-15
17 | Cryostat | Raftopoulos | Starting to update concept & estimates; start Title I in FY-08
18 | FPA Tooling:
18 | Station 5 base | Brown |  | 2008-03-11 | 2008-04-03 | 2008-07-28
18 | Station 5 lift fixture | Brown |  | 2008-03-11 | 2008-04-22 | 2008-08-22
18 | Station 6 module supports ("sleds") | Brown |  | 2008-06-11 | 2008-07-09 | 2009-01-05
18 | Station 6 spool piece support | Brown |  | 2008-06-11 | 2008-08-06 | 2009-02-05
82 | Assembly Sequence Plan Maturity |  | Assessment | Envisioned future changes
82 | Station 5 | Brown | 90% | coil support details, cryostat supports, lifting features
82 | Station 6 | Brown | 75% | cryostat details, carts-base integration, racks, cable trays, unknowns
Facility Beyond Stellarator Core
12 | Heater control sys | Gernhardt |  | 2009-04-24 | 2009-06-22
2 | Fueling and vacuum | Blanchard
3 | Diagnostics | Stratton
4 | Coil Protection System | Ramakrishnan | X
4 | Power Systems | Ramakrishnan |  | 2008-09-15
5 | Central I&C | Sichta
61 | Water System | Dudek
62 | Cryogenic Systems | Raftopoulos
63 | Utility Systems | Dudek
64 | VV heating and cooling system | Kalish
85 | Startup | Gentile | Starting safety docs. & ISTPs in FY-08
Legend
Review completed before August 2007 Lehman Review
|  |  | X | Review completed since August 2007 Lehman Review
|  |  | 2008-02-20 | Job manager's current forecast

## FY08 MR worksheet
NCSX FY08 Alternate Plan
FY08 Budget |  |  | FY08 Plan (base plus ETC's) |  |  | Acceleration Candidates (proposed by Strykowsky, Dec., '07) |  |  |  | Job Manager assigned | Status / Plans
| 15.9 | BA |  | 1.96 | spent oct & nov |  | Design accelerations- Priority 1 Scope
| 1.777 | fy07 c/o |  | 13.515 | current plan BCWR (dec-sept) |  |  | 0.069 | NBI port exte dsn | Goranson | Scheduled for FY-09
| 17.677 | fyg08 budget | [5 empty] | 0.028 | CS structure bus dsn/analysis
| 3 | additional funding | [5 empty] | 0.352 | coil service leads (ornl) | Goranson | PDR scheduled for Aug. '08
| 20.677 | total planning budget for alternate plan |  | 15.475 |  |  |  | 0.207 | cryostat | Raftopoulos
[8 empty] | 0.198 | cryogenic sys design
|  |  | APPARENT FREE BALANCE = | 5.202 |  |  |  | 0.109 | fueling (3 injectors)
[8 empty] | 0.213 | VPS
|  |  | ETC's (estimated) |  |  |  |  | 0.025 | water systems
|  |  |  | -0.4 | rate reductions ~-5 points |  |  | 0.138 | bakeout sys
|  |  |  | 0.2 | wbs 82 simmons/phil +.65 fte |  |  | 0.065 | WBS 5 I&C Adv Concep design
|  |  |  | 0.1 | plant design +.5 fte designer |  |  | 0.215 | power systems design wbs 4
|  |  |  | 0.137 | Project mgr |  |  | 1.619
|  |  |  | 0.037 | allocations
|  |  |  | -0.2 | wbs 19 stell core mgt (ornl) |  | Procurement commitments carried over into fy09 (M&S loaded)
|  |  |  | 0.15 | make FPA schedule slip |  |  | 0.342 | PF
|  |  | ADJUSTED FREE BALANCE = | 5.226 |  |  |  | 0.472 | Trim Coils
[8 empty] | 0.55 | Coil Support Struct
[8 empty] | 0.055 | Station 6 Fixtures
1.419
Other accelerations- Priority 2 Scope
[8 empty] | 0.1 | e-beam mapping
[8 empty] | 0.1 | coil protection wbs4
[8 empty] | 0.2 | ISTP documentation (~50% )
[8 empty] | 0.444 | Award/Commit Lead HW
[8 empty] | 0.168 | Award/Commit LN2 distr sys HW
1.012
[7 empty] | Remaining unplanned free balance = | 1.176
Other candidates
NON MIE Scope-Long Lead Upgrade Scope
NB Armor Design (ornl)
[8 empty] | 1600 | 1 fte analysis engr
3.8 fte designer
2.1 fte engr
[8 empty] | 1206 | NB #1&#2 refurbishment

## Nov. 07 Assessment
WBS | Item |  | PDR | FDR | Award | Deliver | Install / Assemble | Comment
18 | Station 5 Tooling | Forecast |  | 2008-02-19 |  |  |  | Schedule at risk due to design engineering availability.
|  | Baseline | 2007-11-07 | 2007-11-21 |  | 2008-04-01 | 2008-09-08
13 | TF Coils | Baseline |  |  |  | 2008-09-18 | 2009-02-26 | Looks OK
13 | PF Coils | Forecast | 2007-12-12 | 2008-02-13 | 2008-04-16 | 2008-10-13 |  | Looks OK if vendor fab schedule is credible.
|  | Baseline | 2007-12-11 | 2008-03-20 | 2008-05-27 | 2008-11-20 | 2009-03-02
|  | Milestones | 2008-03-31 |  | 2008-09-30
13 | Trim Coils | Forecast | 2008-02-25 | 2008-04-17 | 2008-05-30 | 2008-11-25 | 2009-03-03 | Looks OK if design resources are available and vendor fab schedule is credible.
13 | TF/PF Local I&C | Forecast |  | 2008-05-23 | 2008-06-23 | 2008-08-19
|  | Baseline |  | 2008-05-23 | 2008-06-23 | 2008-08-19
15 | Coil Structures | Forecast | 2007-07-20 | 2007-12-07 | 2007-04-28 | 2009-05-13 |  | Design behind schedule. Check delivery-installation schedule logic.
|  | Baseline | 2007-07-20 | 2007-09-21 | 2008-06-16 | 2009-07-01 | 2009-03-02
|  | Milestones |  |  | 2008-10-31 | 2009-12-31
17 | Base Support | Forecast | 2008-03-06 | 2008-04-28 | 2008-07-09 | 2008-10-09 |  | Design behind schedule. Can still meet FDR milestone and support installation schedule.
|  | Baseline | 2007-11-26 | 2008-02-04 | 2008-06-19 | 2008-09-22 | 2009-01-12
|  | Milestones |  | 2008-05-31 |  |  | 2009-07-31