- Keystone tests- (John Desandro).. Begin week of January 26, 2004

- Conductor Property Tests-

  - Generate test specification (ORNL)

  - Fabricate Molds (Steve Raftopoulos)

    - First tensile specimen mold by January 23, 2004

    - Second bundle specimen mold by January 30, 2004

  - Fabricate specimens (Tom Meighan, Buddy Kearns & Mike Hause)

    - Straight tee section….	Prepare and VPI specimen

    - Tensile specimens….	Begin preparation and VPI of samples by January 26, 2004

    - Bundle specimens

  - Test in-house  (Tom Kozub, Steve Jurczynski)

    - Write test plan (how to)

    - Begin testing – Be prepared for tensile specimens by February 2, 2004

- Winding of Inch worm  (Mike Anderson & Frank Terlitz)

  - Winding form………	Complete except for mounting brackets

  - Winding clamps…	In fabrication needed by January 23, 2004

  - Winding station…	Mount casting to turntable January 19, 2004

Conductor payout spools

Begin winding trials week of January 26, 2004

- Twisted Racetrack Coil

Coil will be wound in the D-site Test Cell using a Turning fixture in a clean room atmosphere.

Coil will be VPI’d in Autoclave

  - Casting- delivery by April 1st. 2004

  - Winding clamps- supplement the clamps used in Inch worm trials

  - Chill plates & coil clamps- designs to be provided by ORNL

  - Begin winding by April 19, 2004

- Winding Facility-

  - Autoclave  (Steve Raftopoulos, Frank Jones)

    - Work well underway

    - Upper dome on Sellers for machining

    - Lower dome- ports being added

    - Main chamber- upper flange being welded

    - Electrical controls under construction

    - Vacuum pumps- retrieved from PBX basement, some rework required

    - Gate valves for heating ductwork has been found

    - Catwalk components fabricated

    - Ports, conflats and man door in-house

    - Electrical components in house?????

  - Turning fixtures…	Work has begun on fixture frames and floor mounting plates

  - Conductor payout spool  (Lew Morris needs to design)

  - Epoxy stands…. Design in progress near completion (Lew Morris)

  - Clean rooms… Plans are to procure custom rooms and assemble by PPPL staff  (Jim Chrzanowski/Lou Morris)

  - Winding clamps…Finalize design

  - Winding Facility Layout. (Lew Morris and Jim C.) assume (2) winding station layout

  - Miscellaneous tooling. As required

- Manufacturing Inspection and Test Plan (Jim Chrzanowski, Tom Meighan & Steve Raftopoulos)

  - JC to generate MIT plan

  - TM and SR to support with procedure writing

# Text boxes

32-in

61-in

35-in