## Sheet1
Name | Description | CC * | WP | Job # | Hours | Total
Chrzanowski, Jim | Mod Coil Final Design | 1850 | 1*** | 1403 | 80
| Mod Coil Winding R&D Preparation | 1850 | 1*** | 1405 | 224
| Mod coil winding R&D | 1850 | 1*** | 1406 | 476
| Mod Coil winding tooling | 1850 | 1*** | 1407 | 230 | 1010
Bush, Harry | Mod coil winding R&D | 1850 | 1*** | 1406 | 144
| Mod Coil winding tooling | 1850 | 1*** | 1407 | 80 | 224
Raftopoulos, Steve | Mod Coil Winding R&D Preparation | 1850 | 1*** | 1405 | 256
| Mod coil winding R&D | 1850 | 1*** | 1406 | 80
| Mod Coil winding tooling | 1850 | 1*** | 1407 | 528 | 864
Paul, Bruce | Mod Coil Winding R&D Preparation | 1850 | 1*** | 1405 | 430
| Mod Coil winding tooling | 1850 | 1*** | 1407 | 430 | 860
Mechanical Designers (TBD) | Mod Coil winding tooling | 1850 | 1*** | 1407 | 720 | 720
Meighan, Tom | Mod Coil Winding R&D Preparation | 1850 | 1*** | 1405 | 120
| Mod coil winding R&D | 1850 | 1*** | 1406 | 1276 | 1396
Kearns, Buddy | Mod coil winding R&D | 1850 | 1*** | 1406 | 1726 | 1726
* Note: 1850 will change to 9450 at the end of continuing resolution
Job Descriptions
Mod Coil Winding R&D Preparation | Includes: Design and fabrication of prototypes and molds; procurement of supplies & equipment for R&D trials | 1850 | 1*** | 1405
Mod coil winding R&D | Includes: all R&D trials( keystone tests, VPI trials, etc.) | 1850 | 1*** | 1406
Mod Coil winding tooling | Includes: all design work for winding modular coils: fabrication/procurement of the hold-down clamps and taping machine. | 1850 | 1*** | 1407