|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

Stellarator Core Integration

M. J. Cole for the NCSX Design Team

Stellarator Core Integration Overview

|  | SC Project Review of NCSX, April 8-10, 2008 M. J. Cole - page 2 |  |
| --- | --- | --- |

Integration at Oak Ridge

- Subsystem/component Interfaces

- Manpower Loading

- Risk Mitigation Activities

|  | SC Project Review of NCSX, April 8-10, 2008 M. J. Cole - page 3 |  |
| --- | --- | --- |

This WBS provides integration support during fabrication and assembly

at PPPL

- Integration support consist of:

- Installation oversight and inspection of Stellarator Core components

- Verifying fabrication problems very early before fabrication starts is key to

preventing delays that impact cost and schedule

- Provide as built drawings and models to document the fabrication details

- Address risk mitigation activities and integrating results into the assembly

|  | SC Project Review of NCSX, April 8-10, 2008 M. J. Cole - page 4 |  |
| --- | --- | --- |

• Installation oversight and inspection of Stellarator Core components

It is important to walk around even though you are not addressing a specific problem – it is amazing what you can learn

Integration at Oak Ridge/PPPL

|  | SC Project Review of NCSX, April 8-10, 2008 M. J. Cole - page 5 |  |
| --- | --- | --- |

• Verifying fabrication problems very early before fabrication starts is key

to preventing delays that impact cost and schedule

|  | Station 6 machine assembly does not start for several years. Addressing problems early saves time and money if problems can be identified and solutions resolved. |
| --- | --- |

Integration and Subsystem/component

Interfaces

|  | SC Project Review of NCSX, April 8-10, 2008 M. J. Cole - page 6 |  |
| --- | --- | --- |

Managing assembly interfaces is critical to meeting cost and schedule

objectives

- During the design phase, interface requirements are met by

- Reviewing and checking interfaces with mating components

- Coordinating requirements with responsible individuals of mating components

- Checking released information to verify requirements have been incorporated and interfaces are correct

- Checking CAD models for interferences

- During assembly operations

- Reviewing top level assembly models before assembly to assure assembly is possible and space is available using CAD models that have “as inspected” data reflected in the model

• Reviewing and checking interfaces with mating components

|  | Integration is not always using the latest 3D Cad model |
| --- | --- |

|  | SC Project Review of NCSX, April 8-10, 2008 M. J. Cole - page 7 |  |
| --- | --- | --- |

•Checking released information to verify requirements have been incorporated and interfaces are correct

Manpower Loading

|  | SC Project Review of NCSX, April 8-10, 2008 M. J. Cole - page 8 |  |
| --- | --- | --- |

| Task | FY08 | Manpower Loading, FTE FY09 FY10 FY11 |  |  | FY12 | Totals |
| --- | --- | --- | --- | --- | --- | --- |
| Installation oversight and inspection | 0.20 | 0.40 | 0.40 | 0.40 | 0.00 | 1.40 |
| Verify fabrication problems very early | 0.10 | 0.40 | 0.40 | 0.40 | 0.00 | 1.30 |
| Provide as built fabrication dwgs | 0.10 | 0.20 | 0.20 | 0.20 | 0.00 | 0.70 |
| Risk mitigation activities | 0.20 | 0.80 | 0.70 | 0.40 | 0.00 | 2.10 |
| Reassigned staff availabe for support | 0.00 | 0.60 | 0.60 | 0.60 | 0.00 | 1.80 |
| Totals by Year | 0.60 | 2.40 | 2.30 | 2.00 | 0.00 |  |

Risk Mitigation Activities

SC Project Review of NCSX, April 8-10, 2008

M. J. Cole - page 9

• Risk have been identified in the Risk Register, RR-28a, as shown below

Summary

|  | SC Project Review of NCSX, April 8-10, 2008 M. J. Cole - page 10 |  |
| --- | --- | --- |

Integration is an important part of the project

- Performing oversight is not just showing up when there is a problem. It is

about being involved.

- If a problem can be identified early and a solution found instead of waiting

until assembly the return in lower cost and lost schedule is significant

- Our Cad systems are almost as good as the real thing but sometimes a

stereo lithography model, prototype, or full scale mockup is really important.

- Risk Mitigation activities have been included to address critical issues as

early as possible to avoid possible schedule, cost, and assembly issues