TO:   		Phil Heitzenroeder

FROM:  	Fred Dahlgren

SUBJECT:	Coil Support Structure  Job-1501

Date:10/02/2008

# Scope

This job covers the design and analysis of the structural supports for the TF & PF coils for NCSX, including the short column weldments which interface the core to the base support structure. Completion of this job is required prior to the start of component procurements in job 1553.

Status

This job has completed an FDR and includes a complete set of drawings and bill of materials ready for procurement & fabrication as well as documentation of the analysis in support of the design.

Interfaces

Key interfaces include the PF & TF coils, Trim coils, MCWF shell, C.S. support assembly, and base support structure.  Undefined subsystems which will also interface with these supports include the cryogen supply and return manifolds, cryostat, and buswork supporting/mounting hardware for TF, PF, MC, and Trim coils. Other instrumentation leads TBD may also utilize portions of these support brackets.

Specifications

NCSX-BSPEC-15-00

A formal FMECA was not anticipated but a failure mode and mitigation plan was included in the PDR.

Schematics and PIDs

N/A

Models

The model supporting the analyses for the Coil Support Structure is provided in its native format as a backup to the calculation.

Drawings

Top Assembly Drawings:

se151-110 –Rev0

se151-109-Rev0

se151-108-Rev0

se151-107-Rev0

Note: detail drawings, and sub-assemblies can be found on the parts list of the main assemblies cited above or the full listing on the BOM.

Analysis

NCSX-CALC-15-001-01

Testing

The only testing performed was verification of magnetic permeability of commercially procured parts specified on the BOM. Samples of all parts specified meet the project permeability requirements in the locations they are to be used (as specified in the GRD).

Costs

The initial budgetary quotes received for fabrication of this job are now 18 months out of date (as of 10/02/2008) and will need to be escalated based on current market conditions. This was done for the most recent Lehman review but would need to be re-visited were this project to be re-started. Hardware costs in the latest estimates (04/21/2008) are current as of that date as are material costs.

Remaining Work

Four chits from the PDR and 2 chits from the FDR remain unresolved pending input from other subsystems.

A detailed analysis of the local bolting stresses to resolve any issues there is also pending and would be required prior to fabrication.

Lessons Learned:

The initial design for this job was well along (at or near the PDR stage) in the fall of CY’06 when I was first assigned to this task. This initial design, based on stainless steel castings, was tightly integrated into the overall machine core design and assembly plan, and provided a fairly robust solution for supporting the various coil systems. Some detailed drawings were already in progress. Unfortunately budgetary quotes received in Dec. ’06 suggested the cost of castings was going to be significantly higher than had been previously estimated and budgeted for this sub-system, with quotes of 1.7-1.9M$ vs. <1M$ in the budget. To reduce costs a new design based on either aluminum or stainless weldments, was developed. While budgetary quotes received for the weldment design were significantly less than the castings, the added labor cost in design, drafting, and analysis for the new configuration probably diminished any savings over the casting design and required a significant  effort in time and labor to update the CAD and FEA models. In retrospect it might have been more time conserving and cost effective to just re-baseline this job at the 2M$ level and proceed with the casting option.

Conclusion:   A detailed analysis of the most critical bolted connections should be performed which could permit the use of 316 bolting hardware in many locations with Inconel 718 hardware used only where needed. This could reduce costs for bolting materials by 50% or more. Over 6 tons of 304L stainless remains in the PPPL materials yard and was earmarked for use on this job. The majority is ½” thick although some is 5/8” Testing performed indicated all this material had a relative magnetic permeability of less than 1.02. Use of this yard material could save as much as 150K$.  Full solution annealing of 304L can lower the permeability of cold worked and welded 304L and should be considered if permeability issues arise.