|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

NCSX Coil Services

P.L. Goranson

Work Package 161, 162, and 163

Coil Services System Description

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

The coil services consist of the cryogenic feeds and electrical leads

inside the cryostat, serving all of the coils, including conventional.

It includes the specification of requirements

for the coil protection system.

Lower-level elements include:

LN2 Distribution System (WBS 161);

Coil Electrical Leads (WBS 162); and

Coil Protection Requirements (WBS 163)

SC Project Review of NCSX, April 8-10, 2008

NCSX Coils

WBS 161 LN2 Distribution System

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

Description

This element covers the distribution of liquid nitrogen (LN2) coolant within

the cryostat. The system serves all the actively cooled coils:

TF (WBS 131)

PF (WBS 132)

Modular (WBS 14)

Scope

Work includes engineering design, procurement, and fabrication of

manifolds, cooling hoses, jumper hosing, valving, and associated supports.

Work in this WBS ends with delivery of components to machine assembly

operations.

Interfaces

I&C is procured in 1408. WBS161 includes routing and distribution of

coolant between coil input/output terminations and the supply/return

manifolds. WBS17 provides supply/return headers and hook up interfaces

in the Cryostat. Valves are included in WBS1 61.

PF1a coils from

NSTX are baseline

Baseline Configuration

Upgrade Configuration

- Baseline is PF1a, PF4, PF5, and PF6 (2 each, upper and lower).

- Device can be upgraded if desired, where PF1a is replaced by PF1, PF2, PF3.

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

Central Solenoid, TF, and PF

Configurations

Modular Coil and Conventional Coil Cooling

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

Requirements

- Operate at 77 K with LN2.

- Operating pressure minimum 5 atmospheres absolute.

- Electric breaks in MC coil coolant lines poloidally.

- Electrical current limitation between cooling components. (bypass resistors

isolate hoses to ground)

- TF and PF hoses electrically isolated at coil terminations as

well as headers

- Provide flow balance between systems.

PF Coil pair 4, 
5, or 6

1-6

2	1

1	2

4

1

48

5 6 7 45 46 47

1	2	3	4

TF Coils

1	2	34561	2

Supply Header

One side of a Modular Coil shown

Poloidal break

Insulated jumper

PF (4, 5, 6)

TF

PF1

MC

Outer

Inner

Return Header

PF Coil pair

TF Coils

2 1	2	14

1

1	2	3	4	56 745464748

Spares

1-14

PF pair

MC hook up 1-48

Return Header

Flow balance

Dual supply and return manifolds

- Individual controls are not required, a single valve in MC return balances both manifolds

- Valve and monitoring is outside cryostat where it is accessible - Individual circuits are passively (self) balanced

Costs reflect design in

Cooling System Diagram shown below

plg 3/20/08

SC Project Review of NCSX, April 8-10, 2008

Cryostat Boundary

PF Coil pair 1, 2, or3

MC hook up 1-48

Spares

1-14

Field Period Supply Header

1	2

23456

Resistor

G-10 Insulator

Flow volume

1-6

Flow distribution

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 8 |  |
| --- | --- | --- |

PF1A is used in CD4, replace by PF1, PF2, and PF3 in future operation.

Pressure drops fall in two well defined groups.

|  | ID (in) | Length of tracing (ft) | Length of hose (ft) | Minimum flow required (gpm) | Actual flow (gpm) | Pressure drop (atmos) |
| --- | --- | --- | --- | --- | --- | --- |
| MC | 0.18 | 4 | 18 | 1.1 | 1.2 | 2.42 |
| PF1 | 0.354 | 304 | 24 | 1.1 | 1.1 | 2.42 |
| PF2 | 0.354 | 304 | 24 | 1.1 | 1.1 | 2.42 |
| PF3 | 0.354 | 304 | 24 | 1.1 | 1.1 | 2.42 |
| PF1A | 0.354 | 178 | 24 | 1.1 | 1.2 | 2.42 |
| spares |  |  |  | 0.5 | 0.5 | 2.42 |
| PF4 | 0.354 | 861 | 21 | 1.1 | 1.4 | 4.51 |
| PF5 | 0.354 | 1100 | 21 | 1.1 | 1.2 | 4.51 |
| PF6 | 0.354 | 786 | 18 | 1.1 | 1.4 | 4.51 |
| TF | 0.312 | 355 | 18 | 1.6 | 1.6 | 4.51 |

manifold

• Manifolds lie outside TF coils

- supply near bottom of VV

- return near top of VV

SC Project Review of NCSX, April 8-10, 2008

Typical manifold

Transition to flex hosing at the winding form

Manifold Jumpers

Resistor

G10 CR Male / Female coupling

316 SS Yor-Lok 5/16 OD tube one end and 1/4J NPT on other end

316 SS braided hose with 5/16 OD straight tube coupling at both ends

Hoses are isolated from the

manifolds by G10 plugs

- prototype will be tested

at 77K

-orientation of individual

connections is TBD

Manifold hose insulators

SC Project Review of NCSX, April 8-10, 2008

Cost Estimate Basis

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 12 |  |
| --- | --- | --- |

LN2 hoses are catalog items.

– Lengths are based on ProE models.

- Manifold designs and prices are based on a similar design used

on the VV.

– Sizing is based on thermo hydraulics performed by

Engineering.

- Material cost is estimated on a $ per lb at current market.

- Supports are based on a $/length of hose.

- Engineering time is based on number and type of drawings for

each element, specifications, and the analyses anticipated.

|  |  |  |  | s i m u l a t i o |  |
| --- | --- | --- | --- | --- | --- |

Description:

Labor

w

This effort covers all R&D, Title I, II, and III engineering for the LN2 distribution system inside the cryostat,which includes all the necessarymanifolding

n

and connections to interface with the ex-cryostatLN2 supply system. This system will be fabricated in-house by PPPL. All Title III engr associated with installation is included in WBS 7.

| p e s s u r |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

HOURS

Number of

Units	Hours

Task ID	Multiplier	Unit

Title I an II Design

|  | o SC Project Review of NCSX, April 8-10, 2008 f t |  |
| --- | --- | --- |

Pro-E models (avg)	8	hrs/model	21	168	168

i

assy dwgs	16	hrs/dwg	24	384	384

z

Detail drawings	8	hrs/dwg	13	104	104

e

installation dwg	16	hrs/dwg	14	224	224

d

cooling schematic	20	hrs/dwg	1	20	20

electrical schematic	0	hrs/dwg	1	0	0

L

I&C schematic	20	hrs/dwg	1	20	20

stress analysis	40	hrs/calc	1	40	40

N 
2

thermal analysis	40	hrs/calc	1	40	40

special analysis (electromagnetics)	160	hrs/calc	0	0	0

fab specifications	160	hrs/spec	2	320320

a

preliminary and final design reviews	80	hrs/rev	2	160	160

n

| Resolve PDR Comments | 40 hrs/PDR 1 40 40 d |
| --- | --- |

meetings/reporting/presentations	10%	% of tot hrs	152	152

Subtotal Title I & II Design	1672	1672	0	0	0	0	0	0	0

v

| R&D Activities R&D pressure drop simulation with pressurized LN2 and valve. Design of test unit. | a l 40 40 v e |
| --- | --- |

|  |  | 38 | 0 | 0 | 0 | 0 | 0 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 |

.

g

n

222	0	104 0	78	40

i

Title III

Disposition of deviation requests and

non-conformances	1	hrs per	38	38

As-built drawings	2	# dwgs	52	104

Procurement coordination	80

Subtotal Title III Design

0	0	0	0

Total	1934

Materials and Supplies

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 14 |  |
| --- | --- | --- |

Description:

This effort covers procurement of materials for the LN2 distribution system by fixed price subcontract.

Assumptions:

outside engr rate =	120$ per hour

outside fab rate =	60$ per hour

outside inspection/technician rate =	80 $ per hour

MDL labor	80$per hour

| Purchased parts: coolant line pigtails from coils to manifolds Insulating Jumper hoses Manifolds for cooling lines valves orifices & other hardware | $19,800 see notes below $4,320 $9,085 $9,000 see notes below $10,000 |
| --- | --- |

Thermocouples	$0 included in job 1408 for

R&D material and labor from below	$18,000 the modular coil

subtotal, purchased parts $70,205 fabrication

Fabrication and Assembly

Description:

This effort covers all the fabrication of the LN2 system inside the cryostat including headers.

Worksheets

coolant line pigtails from coils to manifolds Average length of pigtail

Total

No. of coils

circuits per coil at header

total circuits

Total number of pigtails

|  | 3 ft TF Modular PF1 |  | PF2 | PF3 | PF4 | PF5 | PF6 | Trim |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 60 | 18 18 | 2 | 2 | 2 | 2 | 2 | 2 | 12 |
|  | 1 8 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |
| 168 | 18 144 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |
| 336 | supply and return per circuit |  |  |  |  |  |  |  |

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 15 |  |
| --- | --- | --- |

Manifolds for cooling lines

Assume 2 pairs of 1.5 inch manifolds for each field period, one above and one below the midplane inside the PF5 coil Each set of manifolds will have 1/3 of the required cooling connections plus 25% spare

The manifolds will connect via vertical pipes to the supply system below the cryostat

avg toroidal perimeter of field period	16 ft

avg vertical height of connection lines	9 ft

no of headers/FP	4

cost of tubing	$15 per foot, 316 SSt

cost per field period	$1,488

total number of coolant connections, all

headers	840

hours to weld each connection	0.5 hr per connection

shifts to form manifold tube	0.5 per manifold pair

crew size for forming	2

hours to cut vertical pipes	2 hrs per pipe

hours to weld vertical pipes to header	2 hrs per pipe

total shifts for manifolds	71

tech hours for manifolds	564 hours

technical oversight, inspection	141 hrs

total hours for manifolds	705 hrs

Schedule & Staffing

Schedule

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 16 |  |
| --- | --- | --- |

| Staff |  |  |  |  | Paul | Sorin | Scott |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Goranson Homescu |  | Dixon | total | Total |
|  |  |  |  |  | 40% | 100% | 100% | work hours | WAF |
| Jobs | start | end | days | weeks | hrs | hrs | hrs | available | hours |
| leads(162) | 14-Mar | 1-Feb-09 | 324 | 46.3 | 692.6 | 1351.4 |  | 2044 | 2044 |
| headers(161) | 1-Jan | 1-Oct-08 | 274 | 39.1 | 522.3 | 500 | 1565.7 | 2088 | 1934 |

Cost Estimate Risks

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 17 |  |
| --- | --- | --- |

• LN2 Distribution System (WBS 161)

Design is straight forward and procured items are by and large

commercially stocked. Manifolding is similar to gas system on VV,

which is complete and costs are well documented.

Maturity – medium

Routing and interfaces are in early design phase and design is pre

PDR. R&D required.

Complexity – low

Risk Mitigation

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 18 |  |
| --- | --- | --- |

Schedule Milestones

- An extra full time designer was assigned to Coil Services to assure schedule is met.

- Hoses will be 100% leak checked at delivery to prevent delays after installation. (lesson learned from VV)

Design Integrity

- R&D at MDL will confirm functionality of G10 insulators and flow rate in corrugated hoses.

WBS 162 Coil Electrical Leads

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

Description

This element covers the electrical leads within the cryostat, serving all the

coils: the TF, PF, External Trim (WBS 133), and Modular Coils.

Scope

Work includes engineering design, procurement, and fabrication of cables,

mounting brackets, thermal transition boxes, and associated supports. Work in

this WBS ends with delivery of components to machine assembly operations.

Interfaces

The WBS161 interface begins at coil terminations and ends at the cryostat

thermal transition/terminal box. It does not include I&C, bus work, or routing in

the test area.

Requires penetration of cryostat.

Share real estate used by core structural support, floor mounted utilities, bus

supplies, diagnostics, etc.

Lead Requirements

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 20 |  |
| --- | --- | --- |

Connect between bus supply in test cell and coil terminals inside

cryostat.

- Operate nominally at 77-80 K but no active cooling is required, Cryo

environment is sufficient to return temperature to operating level

between shots.

- Provide Cryostat seal interface.

– Minimize icing

– Maintain positive pressure in Cryostat

- React internal magnetic loads.

- Cancel (minimize) field errors.

Status

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 21 |  |
| --- | --- | --- |

MC design is most mature.

- To date, most of design effort has

concentrated in this area as it is the more

challenging.

- Conventional coils will be handled in a

similar manner and use similar

components.( cable, brackets, terminations,

spacers, etc.)

MC Lead Configuration

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 22 |  |
| --- | --- | --- |

1” long spider/loom

Casting

Standard

1.5” Pipe Clamp 
(1/8” thk x 1” Wide)

5/16” Stud

Cable is 250 MCM

SC Project Review of NCSX, April 8-10, 2008 
P. L. Goranson - page 23

System Layout

MC leads

PF leads

TF & TC leads

Service routing to test cell penetrations

MC Lead Stub Connections

MC A lead 
stub

MC B lead 
stub

SC Project Review of NCSX, April 8-10, 2008 
P. L. Goranson - page 25

Lead Routing

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 26 |  |
| --- | --- | --- |

Services will be routed to each of the three C-C

interfaces.

Hard Bus to 
power supplies

Pipe Chase

Cryostat Floor	Leads Junction Box

(Clear cover removed)

Top View of an 8” diameter pipe chase showing the

(6) modular coil leads cables from a field period

Leads transition thru the cryostat, to

room temp.

Modular coil Interface at Cryostat

SC Project Review of NCSX, April 8-10, 2008 
P. L. Goranson - page 27

Cost Estimate Basis

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 28 |  |
| --- | --- | --- |

Cables are catalog items

– Lengths are based on sketches in work sheet.

- Material cost of supports, spacers, and terminations is

estimated on either:

- $ per lb at current market or:

- $/length of cable.

- Engineering time is based on number and type of drawings for

each element, specifications, and the analyses anticipated.

SC Project Review of NCSX, April 8-10, 2008

Total	2042

HOURS

1892

172

40

40

40

40

24

0

0

112

0

464

320

240

400

84

8

10

8

110

84

8

10

8

40 40

172

40

40

40

40

24

0

0

112

0

464

320

240

400

Hours

Subtotal Title III Design

| Title III |  |  |  |
| --- | --- | --- | --- |
| vendor inspection & oversight | 8 | hrs per | 1 |
| Disposition of deviation requests and non- conformances | 0.5 | hrs/wk | 20 |
| In-House fab/assy oversight & inspection | 2 | hrs/wk | 4 |
| As-built drawings | 1 | hrs/dwg | 84 |

R&D Activities

R&D design time to build mounts (clamp, spider), lead terminations

Subtotal Title I & II Design

meetings/reporting/presentations

Resolve PDR comments

preliminary and final design reviews

Procuremnt Specifications

special analysis (electromagnetics)

thermal analysis

stress analysis

I&C schematic

electrical schematic

cooling schematic

installation dwg

Detail drawings

assy dwgs

Title I an II Design 
Pro-E models (avg)

Task ID

| Multiplier | Unit | Number of Units |
| --- | --- | --- |
| 8 | hrs/model | 50 |
| 16 | hrs/dwg | 15 |
| 8 | hrs/dwg | 40 |
| 16 | hrs/dwg | 29 |
| 0 | hrs/dwg | 1 |
| 8 | hrs/dwg | 14 |
| 8 | hrs/dwg | 0 |
| 0 | hrs/calc | 0 |
| 24 | hrs/calc | 1 |
| 40 | hrs/calc | 1 |
| 40 | hrs/spec | 1 |
| 40 | hrs/rev | 1 |
| 40 | hrs/pdr | 1 |
| 10% | % of tot hrs |  |

This effort covers all R&D, Title I, II, and III engineering design of the coil electrical leads inside the cryostat connecting the coils to the power supply bus or cables outside the cryostat.

Labor

Description:

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 30 |  |
| --- | --- | --- |

M&S

Description:

This effort covers all coil leads that connect the coil terminals to the buswork at the boundary of the cryostat. Assumptions:

outside engr rate =	120 $ per hour

outside fab rate =	60 $ per hour

outside inspection/technician rate =	80 $ per hour

Purchased parts:

set of cables	$32,552

misc attachment hardware	$16,162 @10$/ft

thermal transition box material	$0

| subtotal, purchased parts | $48,715 |
| --- | --- |

Lead bundles consist of six, 250 MCM cable with teflon sleeve. Lead ends are cooled by bleed liquid nitrogen supplied by the coil coolant header (WBS 161) Leads connect from coil terminals to buswork at bottom of machine.

Each coil is connected separately except PF1 and PF2, which are connected in series within the central solenoid assembly

Schedule & Staffing

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 31 |  |
| --- | --- | --- |

Schedule

Staff

Paul G	Sorin H	Scott	total	Total

40%	100%	100% work hours WAF

Jobs	start	end	days	weeks	hrs	hrs	hrs	available	hours

| leads(162) |  |  | 14-Mar 1-Feb-09 324 46.3 692.6 1351.4 2044 2044 |
| --- | --- | --- | --- |

Cost Estimate Risks

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 32 |  |
| --- | --- | --- |

Coil Electrical Leads (WBS 162)

Maturity – medium

Routing and interfacing is in early stages of design.

Design of cables is not firmly established, satisfying field

error requirements could require more costly solutions and

longer lead time.

Complexity – low

Design is straight forward and large ticket procured items

(cable and mounts) are commercially stocked.

No complications such as active cooling are required.

Risk Mitigation

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 33 |  |
| --- | --- | --- |

Schedule Milestones

- The Designer was assigned to Leads full time and his LN2 System

responsibilities reassigned.

- Permitted acceleration of design schedule to assure

critical components (coil stubs) will be procured for Station

5 assembly.

- Field error calculations are being performed up front to minimize

the risk that designs will have to be redone.

Design Integrity

- The terminations and clamps will be prototyped at MDL to confirm

their design is acceptable.

WBS 163 Coil Protection System

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

Description

This element covers the specification of coil protection requirements for the

coil protection system.

Scope

Work covers Title I, II, and III Engineering support for development of the

system, including any drawings, electrical and I&C schematics, or analyses.

There is no design, fabrication, or hardware included under this package.

The results of thermal, electrical and mechanical analysis will be used to define

allowable operating limits for the coils for commissioning, normal research

operations, and fault conditions. Appropriate diagnostics and permissive,

alarm, and failsafe signals to the power supply controllers and I&C systems will

be defined.

20

40

0

40

0

0

0	120

0

0

0

0

0

0

meetings/reporting/presentations

preliminary and final design reviews

Procurement Specifications

special analysis (electromagnetics)

thermal analysis

stress analysis

I&C schematic

electrical schematic

cooling schematic

installation dwg

Detail drawings

assy dwgs

Title I an II Design Pro-E models (avg)

Task ID

| Multiplier | Unit | Number of Units Hours |  |  |
| --- | --- | --- | --- | --- |
| 8 | hrs/model |  | 0 | 0 |
| 24 | hrs/dwg | 120 | 0 | 0 |
| 16 | hrs/dwg |  | 0 | 0 |
| 16 | hrs/dwg |  | 0 | 0 |
| 0 | hrs/dwg |  | 0 | 0 |
| 8 | hrs/dwg |  | 0 | 0 |
| 20 | hrs/dwg | 120 | 4 | 80 |
| 0 | hrs/calc |  | 0 | 0 |
| 24 | hrs/calc |  | 0 | 0 |
| 40 | hrs/calc |  | 2 | 80 |
| 16 | hrs/spec |  | 0 | 0 |
| 40 | hrs/rev |  | 1 | 40 |
| 10% | % of tot hrs |  |  | 20 |

This effort covers all Title I, II, and III engineering for the Coil Protection System. No hardware is anticipated for this job, only design interface with WBS 4 and 5.

Description:

Cost

SC Project Review of NCSX, April 8-10, 2008

Subtotal Title I & II Design	220

100 120

Schedule & Staffing

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

Schedule

Staffing

Jeff Harris – 270 hours in 2009

Cost Estimate Risks

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 37 |  |
| --- | --- | --- |

Coil Protection Requirements (WBS 163)

Maturity – low

Job is at conceptual design stage. It interacts simultaneously with a

several other WBS and relies on ongoing analysis. Number of

documents is not established.

Complexity – low

Specifications may be replaced with data sheets where procured items

are available as stock items.

Many parameters are supplied from other WBS areas and are already

available.

Protocols and systems must be compatible with both initial

commissioning and full research operations.