NCSX

TO:   		M. Cole

FROM:  	P. L. Goranson

SUBJECT:	NCSX Electrical Lead Closeout Summary

23June-08-PG

# Scope

This effort covers all R&D, Title I, II, and III engineering design of the coil electrical leads inside the cryostat, connecting the coils to the power supply bus or cables outside the cryostat.

Work includes engineering design, procurement, and fabrication of leads, terminations, thermal transition boxes (TTB), and associated support hardware. Work in this WBS ends with delivery of components to machine assembly operations.

Status

At the time of closeout Conceptual Design of the Leads was in work with a PDR scheduled for 8/22/08.

Interfaces

TF (WBS 131)

PF (WBS 132)

Modular (WBS 14)

Cryostat (WBS 17)

Specifications

No work had begun on a system requirements document or CSPEC for the leads.

A formal FMECA was not anticipated.

Schematics

None

Models Completed

Pro E models of the following were made and are posted on the web:

MC coil stub leads.

Concepts for lead routing between the PF, TF, and MC coils and the Cryostat.

Conceptual design and location for thermal transition boxes.

Lead structural attachments

The overall configuration was shown in a presentation before the Lehman Review on 4/0/08 and is captured in that document (attached).

Drawings

None, but models are sufficient for a PDR. Some preliminary drawings would be ready at the time of the review.

Analyses

None completed by ornl Engineering. Lead attachment field error calculations were performed by A Brooks at pppl.

Testing

None

Costs

Cost estimates were updated on the latest WAF and were included in the 08 Lehmann review presentation (attached).

Remaining Work

- R&D to build and test lead spiders and mount brackets.

- The routing path for the leads.

- Location of TTB boxes.

- Analyses to confirm lead sizes.

The R&D was not required for the PDR.

Preliminary work (models) of two configurations of routing of leads and locating of TTB boxes were complete. Work would progress quickly (~2 weeks) once a choice was made.

Hand calculations of lead sizes were made, simply not formalized yet.

Conclusion

The work was in a preliminary phase, but was on schedule to meet the PDR schedule.

NCSX Coil Services

P.L. Goranson

Work Package  162

(Excerts from the April 2008 Lehman Review)

Coil Services System Description

The coil services consist of the cryogenic feeds and electrical leads

inside the cryostat, serving all of the coils, including conventional.

It includes the specification of requirements

for the coil protection system.

Lower-level elements include:

LN2 Distribution System (WBS 161);

Coil Electrical Leads (WBS 162); and

Coil Protection Requirements (WBS 163)

WBS 162 Coil Electrical Leads

Description

This element covers the electrical leads within the cryostat, serving all the

coils: the TF, PF, External Trim (WBS 133), and Modular Coils.

Scope

Work includes engineering design, procurement, and fabrication of cables,

mounting brackets, thermal transition boxes, and associated supports. Work in

this WBS ends with delivery of components to machine assembly operations.

Interfaces

The WBS161 interface begins at coil terminations and ends at the cryostat

thermal transition/terminal box. It does not include I&C, bus work, or routing in

the test area.

Requires penetration of cryostat.

Share real estate used by core structural support, floor mounted utilities, bus

supplies, diagnostics, etc.

Lead Requirements

- Connect between bus supply in test cell and coil terminals inside

cryostat.

- Operate nominally at 77-80 K but no active cooling is required, Cryo

environment is sufficient to return temperature to operating level

between shots.

- Provide Cryostat seal interface.

– Minimize icing

– Maintain positive pressure in Cryostat

- React internal magnetic loads.

- Cancel (minimize) field errors.

Status

- MC design is most mature.

- To date, most of design effort has

concentrated in this area as it is the more

challenging.

- Conventional coils will be handled in a

similar manner and use similar

components.( cable, brackets, terminations,

spacers, etc.)

MC Lead Configuration

Cable is 250 MCM

MC Lead Stub Connections

Lead Routing

Services will be routed to each of the three C-C

interfaces.

Cost Estimate Basis

- Cables are catalog items

– Lengths are based on sketches in work sheet.

- Material cost of supports, spacers, and terminations is

estimated on either:

- $ per lb at current market or:

- $/length of cable.

- Engineering time is based on number and type of drawings for

each element, specifications, and the analyses anticipated.

M&S

Description:

This effort covers all coil leads that connect the coil terminals to the buswork at the boundary of the cryostat. Assumptions:

outside engr rate =	120 $ per hour

outside fab rate =	60 $ per hour

outside inspection/technician rate =	80 $ per hour

Purchased parts:

set of cables	$32,552

misc attachment hardware	$16,162 @10$/ft

thermal transition box material	$0

| subtotal, purchased parts | $48,715 |
| --- | --- |

Lead bundles consist of six, 250 MCM cable with teflon sleeve. Lead ends are cooled by bleed liquid nitrogen supplied by the coil coolant header (WBS 161) Leads connect from coil terminals to buswork at bottom of machine.

Each coil is connected separately except PF1 and PF2, which are connected in series within the central solenoid assembly

Schedule & Staffing

Schedule

Staff

Paul G	Sorin H	Scott	total	Total

40%	100%	100% work hours WAF

Jobs	start	end	days	weeks	hrs	hrs	hrs	available	hours

| leads(162) |  |  | 14-Mar 1-Feb-09 324 46.3 692.6 1351.4 2044 2044 |
| --- | --- | --- | --- |

Cost Estimate Risks

Coil Electrical Leads (WBS 162)

Maturity – medium

Routing and interfacing is in early stages of design.

Design of cables is not firmly established, satisfying field

error requirements could require more costly solutions and

longer lead time.

Complexity – low

Design is straight forward and large ticket procured items

(cable and mounts) are commercially stocked.

No complications such as active cooling are required.

Risk Mitigation

Schedule Milestones

- The Designer was assigned to Leads full time and his LN2 System

responsibilities reassigned.

- Permitted acceleration of design schedule to assure

critical components (coil stubs) will be procured for Station

5 assembly.

- Field error calculations are being performed up front to minimize

the risk that designs will have to be redone.

Design Integrity

- The terminations and clamps will be prototyped at MDL to confirm

their design is acceptable.

# Text boxes

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

SC Project Review of NCSX, April 8-10, 2008

NCSX Coils

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 20 |  |
| --- | --- | --- |

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 21 |  |
| --- | --- | --- |

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 22 |  |
| --- | --- | --- |

1” long spider/loom

Casting

Standard

1.5” Pipe Clamp 
(1/8” thk x 1” Wide)

5/16” Stud

SC Project Review of NCSX, April 8-10, 2008 
P. L. Goranson - page 23

System Layout

MC leads

PF leads

TF & TC leads

Service routing to test cell penetrations

MC A lead 
stub

MC B lead 
stub

SC Project Review of NCSX, April 8-10, 2008 
P. L. Goranson - page 25

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 26 |  |
| --- | --- | --- |

Hard Bus to 
power supplies

Pipe Chase

Cryostat Floor	Leads Junction Box

(Clear cover removed)

Top View of an 8” diameter pipe chase showing the

(6) modular coil leads cables from a field period

Leads transition thru the cryostat, to

room temp.

Modular coil Interface at Cryostat

SC Project Review of NCSX, April 8-10, 2008 
P. L. Goranson - page 27

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 28 |  |
| --- | --- | --- |

SC Project Review of NCSX, April 8-10, 2008

Total	2042

HOURS

1892

172

40

40

40

40

24

0

0

112

0

464

320

240

400

84

8

10

8

110

84

8

10

8

40 40

172

40

40

40

40

24

0

0

112

0

464

320

240

400

Hours

Subtotal Title III Design

| Title III |  |  |  |
| --- | --- | --- | --- |
| vendor inspection & oversight | 8 | hrs per | 1 |
| Disposition of deviation requests and non- conformances | 0.5 | hrs/wk | 20 |
| In-House fab/assy oversight & inspection | 2 | hrs/wk | 4 |
| As-built drawings | 1 | hrs/dwg | 84 |

R&D Activities

R&D design time to build mounts (clamp, spider), lead terminations

Subtotal Title I & II Design

meetings/reporting/presentations

Resolve PDR comments

preliminary and final design reviews

Procuremnt Specifications

special analysis (electromagnetics)

thermal analysis

stress analysis

I&C schematic

electrical schematic

cooling schematic

installation dwg

Detail drawings

assy dwgs

Title I an II Design 
Pro-E models (avg)

Task ID

| Multiplier | Unit | Number of Units |
| --- | --- | --- |
| 8 | hrs/model | 50 |
| 16 | hrs/dwg | 15 |
| 8 | hrs/dwg | 40 |
| 16 | hrs/dwg | 29 |
| 0 | hrs/dwg | 1 |
| 8 | hrs/dwg | 14 |
| 8 | hrs/dwg | 0 |
| 0 | hrs/calc | 0 |
| 24 | hrs/calc | 1 |
| 40 | hrs/calc | 1 |
| 40 | hrs/spec | 1 |
| 40 | hrs/rev | 1 |
| 40 | hrs/pdr | 1 |
| 10% | % of tot hrs |  |

This effort covers all R&D, Title I, II, and III engineering design of the coil electrical leads inside the cryostat connecting the coils to the power supply bus or cables outside the cryostat.

Labor

Description:

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 30 |  |
| --- | --- | --- |

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 31 |  |
| --- | --- | --- |

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 32 |  |
| --- | --- | --- |

|  | SC Project Review of NCSX, April 8-10, 2008 P. L. Goranson - page 33 |  |
| --- | --- | --- |