## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
Description:
The external trim coil set is intended to provide low poloidal mode number (m=2,3) field error correction. These will be conventionally wound coils in a windowpane configuration. They are provided in two concentric rings at the top and bottom of the Coil Support Structure (WBS 151) primarily to reduce low poloidal mode number (m) resonant errors that may result from manufacturing or assembly errors in the modular coil geometry.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
Description:
Title I and II Engineering for Coils and Title III Support of Fabrication Effort.
|  | FY07$K |  |  |  |  | HOURS
Task ID |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EADM | Basis of Estimate
TRIM COILS and TRIM COIL SUPPORTS
Title I & II Design
| Complete Coil SRD | [11 empty] | 24 |  | Based on Experience with PF TF Coil Design
| Preliminary Trim Coil Concept and Requirements | [11 empty] | 120 |  | Actual time spent in January and February
| Analysis | [11 empty] | 160 |  | Estimate from analysist after reviewing scope of work
| Layout / Design Coils & Supports | [11 empty] | 80 | 312 | Based on Estimate from Designer who is 50% through with scope of work
| Prepare for PDR | [11 empty] | 40 | 24 | Based on Experience with PF TF Coil Design
| Modifications to allow for Midplane Coils | [11 empty] | 40 | 80 | Based on Experiance to date with layouts of upper Trim Coils
| PDR | [11 empty] | 8 | 4 | Based on Experience with PF TF Coil Design
| Prepare Procurement Coil Spec, Four Coils | [11 empty] | 40 | 8 | Based on Experience with PF TF Coil Design
| Detailed Drawings Coils and Supports | [11 empty] | 68.4 | 228 | 38 Drawings avg. 6 hrs/ drawing, 30% eng support
| Assembly Drawings and Parts Lists | [11 empty] | 36 | 120 | Based on Experience with PF TF Coil Support job, and 30% eng support
| Prepare for FDR | [11 empty] | 40 | 24 | Based on Experience with PF TF Coil Design
| FDR | [11 empty] | 8 | 4 | Based on Experience with PF TF Coil Design
| Disposition FDR Chits | [11 empty] | 24 |  | Based on Experience with PF TF Coil Design
Title III Design
| Coil Procurement Support | [11 empty] | 80 | 16 | Past experience in procuring simple coils
| Fabrication Support | [11 empty] | 288 | 80 | 9months, 1day per week, +drafting support for vendor coordination and ECNs - Minimal oversight due to simple conventional coil design, based on experience supporting manufacture of TF Coils
| Bracket Procurement Support | [11 empty] | 80 |  | 4 visits to a vendor + on going support
| Material Procurement Support | [11 empty] | 40 |  | procurement of fasteners and material for in house fabrications
| In house Fabrication Support | [11 empty] | 24 |  | visits to shop for in house build of some of the hardware
| Fabrication Support Travel |  |  |  | 10 | [7 empty] | 48 |  | Two trips to west coast assuming vendor is in Ca (worst case assumption)
| Incoming Inspection | [10 empty] | 144 | 72 |  | For electrical testing and handling of Coil
Sub-Totals |  |  |  |  | 10 | [6 empty] | 144 | 1320.4 | 900
SUPPORT BRACKETS | [12 empty] | DELETED incorporated into coil estimate
Trim Coil Structure, Materials & Fabrication
Order Materials
Trim Coil Structure, Design & Analysis | [14 empty] | Four days for each of four support types
Structure Detail | [14 empty] | Two days per support
Trim Coil Structure, Part Procurement and Fabrication
Sub-Totals | [12 empty] | 0 | 0
Grand Total |  | 0 | 0 | 0 | 10 | [6 empty] | 144 | 1320.4 | 900

## Table II - M&S
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
Materials and Subcontracts (M&S)
|  | Trim1 | Trim2 | Trim3 | Trim4
This table to be replaced with attachement !!
Winding geometry
radius | m | 0.52194 | 0.52194 | 0.52194 | 0.52194
bundle dr | mm | 28.8 | 28.8 | 28.8 | 28.8
bundle dz | mm | 28.8 | 28.8 | 28.8 | 28.8
no. of turns |  | 4 | 4 | 4 | 4
packing fraction |  | 0.75 | 0.75 | 0.75 | 0.75
length per turn | m | 4.6175 | 3.0775 | 3.0775 | 3.0775
total length of cu per coil | m | 18.47 | 12.31 | 12.31 | 12.31
turn height | mm | 13 | 13 | 13 | 13
turn width | mm | 13 | 13 | 13 | 13
coolant hole dia. | mm | 0 | 0 | 0 | 0
corner radii | mm | 1.016 | 1.016 | 1.016 | 1.016
conductor area | mm^2 | 168.1139 | 168.1139 | 168.1139 | 168.1139
calculated coil Cu wt. | kg | 26.6414 | 17.7562 | 17.7562 | 17.7562
Cu density | 8.58e-06
Trim Coil Material Estimate
|  | Trim1 | Trim2 | Trim3 | Trim4 | Total # Coils
II. Materials M&S
Number of Coils |  | 6 | 12 | 6 | 24 | 48
Copper Cost Per Meter |  | 28.4515 | 28 | 28 | 28
copper cost per coil | $ | 525.5 | 344.68 | 344.68 | 344.68
misc matl -$ per lb of Cu in coils | 2 | $/kg | $/kg | $/kg | $/kg
glass insul width | mm | 25.4 | 25.4 | 25.4 | 25.4
turn insul.: length/meter of cond./layer | m/m | 2.0472 | 2.0472 | 2.0472 | 2.0472
turn ins. Tape Thickness | mm | 0.19 | 0.19 | 0.19 | 0.19
No. half lapped layers | # | 2 | 2 | 2 | 2
meters of ins. /roll | m | 182 | 182 | 182 | 182
no. rolls/coil | # | 0.83105 | 0.55388 | 0.55388 | 0.55388
insulation waste factor | multiplier | 1.3 | 1.3 | 1.3 | 1.3
total rolls of turn ins. reqd.per coil | # | 1.0804 | 1.4401 | 1.4401 | 1.4401
turn insulation cost per roll | $/roll | 728 | 728 | 728 | 728
insul width | mm | 25.4 | 25.4 | 25.4 | 25.4
turn insul. length/meter of cond./layer | m/m | 2.0472 | 2.0472 | 2.0472 | 2.0472
turn ins. Tape Thickness | mm | 0.19 | 0.19 | 0.19 | 0.19
No. half lapped layers | # | 2 | 2 | 2 | 2
meters of ins. /roll | m | 182 | 182 | 182 | 182
no. rolls/coil | # | 0.83105 | 0.55388 | 0.55388 | 0.55388
insulation waste factor | multiplier | 1.3 | 1.3 | 1.3 | 1.3
total rolls of turn ins. reqd N Coils | # | 6.4822 | 8.6405 | 4.3203 | 17.2811
turn insulation cost per roll | $/roll | 728 | 728 | 728 | 728
turn insulation cost per coil | $ | 786.502 | 524.1928 | 524.1928 | 524.1928
Length of Kapton | m | 37.8126 | 25.2016 | 25.2016 | 25.2016
Cost per Meter of Kapton | $/m | 1.258 | 1.258 | 1.258 | 1.258
Kapton Cost per Coil | $ | 47.5682 | 31.7036 | 31.7036 | 31.7036
ground wall tape thickness | mm | 0.38 | 0.38 | 0.38 | 0.38
No. half lapped layers | # | 4 | 4 | 4 | 4
total ground wall thick. | mm | 3.04 | 3.04 | 3.04 | 3.04
ground wall tape width | cm | 6 | 6 | 6 | 6
gw tape length reqd. | m | 35.4624 | 23.6352 | 23.6352 | 23.6352
meters of ins. /roll | m | 10 | 10 | 10 | 10
no. rolls/coil | # | 3.5462 | 2.3635 | 2.3635 | 2.3635
insulation waste factor | multiplier | 1.3 | 1.3 | 1.3 | 1.3
no. rolls of GW insulation, for all coils | # | 27.6607 | 36.8709 | 18.4355 | 73.7418
GW tape cost per roll | $ | 50 | 50 | 50 | 50
GW insulation cost per coil | $ | 230.5056 | 153.6288 | 153.6288 | 153.6288
Epoxy volume reqd. (15% void fraction) | l | 0.57449 | 0.38289 | 0.38289 | 0.38289
Epoxy cost/liter | $/l | 150 | 150 | 150 | 150
Epoxy cost per coil | $ | 86.1736 | 57.4335 | 57.4335 | 57.4335
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Material Costs Inuslation per Coil |  | 1150.7495 | 735.2551 | 735.2551 | 735.2551
Material Cost Including Copper Condutor per Coil |  | 1676.2495 | 1079.9351 | 1079.9351 | 1079.9351
Material Costs Inuslation Total |  | 6904.4972 | 8823.0611 | 4411.5306 | 17646.1222
Material Cost Including Copper Condutor Total |  | 10057.4972 | 12959.2211 | 6479.6106 | 25918.4422 | 55414.771
Everson Budgetary Estimate | [6 empty] | Contingency
Total Material Cost All Trim Coils | [5 empty] | 55414.771
Cost from Everson Budgetary Estimate out of Plane |  | 8450 | 7575 | 7575 | 7575
Adjusted Cost for Planar Coils |  | 8450 | 7575 | 6438.75 | 6438.75
Total Cost for Fixtures |  | 40000 | 30000 | 30000 | 30000 | 130000
Recurring Costs for N Coils no materials |  | 50700 | 90900 | 38632.5 | 154530 | 334762.5
Total Cost For N Coils with Materials |  | 100757.4972 | 133859.2211 | 75112.1106 | 210448.4422
Total Cost All Coils | [5 empty] | 520177.271
Everson Budgetary Estimate (adjusted for uncertainty)
Total Material Cost All Trim Coils | [5 empty] | 83122.1565 | 50%
Manufacturing Cost from Everson Budgetary Estimate |  | 8450 | 7575 | 6438.75 | 6438.75 |  |  | `
Total Cost for Fixtures |  | 40000 | 30000 | 30000 | 30000 | 195000 | 50%
Recurring Costs for N Coils no materials |  | 50700 | 90900 | 38632.5 | 154530 | 502143.75 | 50%
Total Cost For N Coils with Materials |  | 100757.4972 | 133859.2211 | 75112.1106 | 210448.4422
Total Cost All Coils | [5 empty] | 780265.9065
Support Brackets
$ per lb for plate (316 SS $8/lb AL $5/lb, $40/lb inconel) | 40
Weight LB per meter | 16.56
$$ per coil for brackets material per coil |  | 3058.632 | 2038.536 | 2038.536 | 2038.536
Cost of Material for Brackets Total |  | 18351.792 | 24462.432 | 12231.216 | 48924.864
Fabrication Cost per meter | 340
Cost Bracket Fabrication per coil |  | 1569.95 | 1046.35 | 1046.35 | 1046.35
Cost Bracket Fabrication Total |  | 9419.7 | 12556.2 | 6278.1 | 25112.4
Cost Bracket Fabrication with Materials Total |  | 27771.492 | 37018.632 | 18509.316 | 74037.264 | 157336.704 | 50%
Cost for Clamps per Coil |  | 1157.1455 | 771.2215 | 771.2215 | 771.2215
Hardware Cost per 3/8 Bolt (Inconnel) |  | 18 | 18 | 18 | 18
Cost for Bolts and Studs per coil |  | 498.69 | 332.37 | 332.37 | 332.37
Cost for all Bolts and Studs & Brackets Total |  | 9935.013 | 13243.098 | 6621.549 | 26486.196 | 56285.856 | 50%
Cost for Mockups of Each Coil |  | 5700 | 3800 | 3800 | 3800 | 17100 | 50%
Cost For Installation Fixtures |  | 3000 | 3000 | 3000 | 3000 | 12000 | 50%
Cost for Hardware | [5 empty] | 242722.56
Cost for Support Brackets adjusted for uncertainty | [5 empty] | 364083.84
Installation Man Hour Estimate (budgeted in job 1815 station 5 assembly)
Tooling / Training / Preperation |  | 20 | 20 | 20 | 20
Hours to Position Coil and mark locations |  | 6 | 6 | 6 | 6
Hours per bracket |  | 1 | 1 | 1 | 1
Hours per coil for brackets |  | 6.9262 | 4.6162 | 4.6162 | 4.6162
Hours per coil for coil Installation |  | 6 | 6 | 6 | 6
Metrology for bracket installation |  | 100.1681 | 164.5463 | 89.7731 | 314.0925
Total Hours for Tech (2 work at once) |  | 267.115 | 438.79 | 239.395 | 837.58 | 1782.88
Determine Metrology Procedure and Setup |  | 20 | 20 | 20 | 20
Interpret Results and Report |  | 20 | 20 | 20 | 20
Charicterize Coils Before Assembly |  | 2 | 2 | 2 | 2
Hours to Measure Coil Location per Coil |  | 4 | 4 | 4 | 4
Total Hours for post Installation Metrology (2 Eng.) |  | 188.1681 | 300.5462 | 177.7731 | 546.0925 | 1212.58
| 1849 | 144 |  | 1993 |  | 161433 |  | 81
632 | 1934 | 192 | 940 | 3698 |  | 628660 |  | 170
1934442.7465
Weeks for two technicians per Field Period |  | 7.4287 |  |  | Cost Total M&S | 1144349.7465
Weeks for four technicians per Field Period |  | 3.7143
[5 empty] | Total Hours | 2995.46
[5 empty] | Technicican Rate | 85
[5 empty] | Eng Rate | 160
[5 empty] | Cost Man-hours | 345557.6
[5 empty] | Total Cost | 1489907.3465

## Table III - FabAssy & Instl
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
In-house Fabrication and Assembly and Installation
Description: Incl in M&S Table II

## Table IV - Conting & Risk
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X |  | PDR not yet held, conceptual design almost complete
-10%/+15%
| Design Complexity |  | X |  |  | Coils are wound from solid copper conductor. Generally conventional type construction.
Brackets are numerous and do not require advanced technology,
but the large variation in mounting locations and number of parts
increases the complexity with respect to fit up issues and assembly time
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
1354 | DELETED! Additional trim coils may be required to suppress field errors from n>1 modes |  |  |  | U | Analysis being performed to firm up requirements | Costs could more than double the present estimate | 200 | 400 | 0 | 0
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Basis of Estimate
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
M&S Estimate Backup