## Table I - Dsn Labor
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Structure Design and Procurement
Job Manager: Mike Kalish
Description:
Title I and II Engineering for Coils and Title III Support of Fabrication Effort. | [15 empty] | Basis of Estimate
| FY07$K |  |  |  |  | HOURS
Task ID | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EADM | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
Trim Coil Structure, Materials & Fabrication | 90 | [10 empty] | 40 | [10 empty] | See Spreadsheet
Order Materials | [11 empty] | 40
Trim Coil Structure, Design & Analysis | [11 empty] | 120 | 128 | [9 empty] | Four days for each of four support types
Structure Detail | [11 empty] | 40 | 64 | [9 empty] | Two days per support
Trim Coil Structure, Part Procurement and Fabrication | [11 empty] | 80
Trim Coil Structure Installation | [10 empty] | 1849 | 184.9 | [10 empty] | See Spreadsheet
Trim Coil Metrology | [11 empty] | 1429 | [10 empty] | See Spreadsheet
[11 empty] | 1849 | 1933.9 | 192