## Table II - M&S
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
Materials and Subcontracts (M&S) | [7 empty] | Basis of Estimate | Category | Amount ($)
|  | Trim1 | Trim2 | Trim3 | Trim4
Winding geometry
radius | m | 0.52194 | 0.52194 | 0.52194 | 0.52194
bundle dr | mm | 28.8 | 28.8 | 28.8 | 28.8
bundle dz | mm | 28.8 | 28.8 | 28.8 | 28.8
no. of turns |  | 4 | 4 | 4 | 4
packing fraction |  | 0.75 | 0.75 | 0.75 | 0.75
length per turn | m | 4.6175 | 3.0775 | 3.0775 | 3.0775
total length of cu per coil | m | 18.47 | 12.31 | 12.31 | 12.31
turn height | mm | 13 | 13 | 13 | 13
turn width | mm | 13 | 13 | 13 | 13
coolant hole dia. | mm | 0 | 0 | 0 | 0
corner radii | mm | 1.016 | 1.016 | 1.016 | 1.016
conductor area | mm^2 | 168.1139 | 168.1139 | 168.1139 | 168.1139
calculated coil Cu wt. | kg | 26.6414 | 17.7562 | 17.7562 | 17.7562
Cu density | 8.58e-06
Trim Coil Material Estimate
|  | Trim1 | Trim2 | Trim3 | Trim4 | Total # Coils
II. Materials M&S
Number of Coils |  | 6 | 12 | 6 | 24 | 48
Conductor With Insulation Cost Per LB |  | 11.65 | 11.65 | 11.65 | 11.65 |  | Vendor quote
Conductor With Insulation Cost Per Coil | $ | 684.3722 | 456.1246 | 456.1246 | 456.1246
Epoxy volume reqd. (15% void fraction) | l | 0.57449 | 0.38289 | 0.38289 | 0.38289
Epoxy cost/liter | $/l | 79.2 | 79.2 | 79.2 | 79.2 |  | $300 per gallon as paid for Modular coils. Vendor under Contract
Epoxy cost per coil | $ | 45.4997 | 30.3249 | 30.3249 | 30.3249
Material Costs Epoxy all Coils |  | 272.9981 | 363.8989 | 181.9494 | 727.7978
Material Costs Conductor with Insulation all Coils |  | 1637.9884 | 4366.7866 | 1091.6967 | 17467.1464
Material Costs Total |  | 1910.9865 | 4730.6855 | 1273.6461 | 18194.9442 | 26110.2623
Everson Budgetary Estimate | [6 empty] | Contingency
Total Material Cost All Trim Coils | [5 empty] | 26110.2623
Cost from Everson Budgetary Estimate out of Plane |  | 8450 | 7575 | 7575 | 7575
Adjusted Cost for Planar Coils |  | 8450 | 7575 | 6438.75 | 6438.75
Total Cost for Fixtures |  | 40000 | 30000 | 30000 | 30000 | 130000
Recurring Costs for N Coils no materials |  | 50700 | 90900 | 38632.5 | 154530 | 334762.5
Total Cost For N Coils with Materials |  | 92610.9865 | 125630.6855 | 69906.1461 | 202724.9442
Total Cost All Coils | [5 empty] | 490872.7623
Everson Budgetary Estimate (adjusted for uncertainty)
Total Material Cost All Trim Coils | [5 empty] | 39165.3934 | 50%
Manufacturing Cost from Everson Budgetary Estimate |  | 8450 | 7575 | 6438.75 | 6438.75 |  |  |  | `
Total Cost for Fixtures |  | 40000 | 30000 | 30000 | 30000 | 195000 | 50%
Recurring Costs for N Coils no materials |  | 50700 | 90900 | 38632.5 | 154530 | 502143.75 | 50%
Total Cost For N Coils with Materials |  | 92610.9865 | 125630.6855 | 69906.1461 | 202724.9442
Total Cost All Coils | [5 empty] | 736309.1434
Support Brackets
$ per lb for plate (316 SS $8/lb AL $5/lb, $40/lb inconel) | 40
Weight LB per meter | 16.56
$$ per coil for brackets material per coil |  | 3058.632 | 2038.536 | 2038.536 | 2038.536
Cost of Material for Brackets Total |  | 18351.792 | 24462.432 | 12231.216 | 48924.864
Fabrication Cost per meter | 340
Cost Bracket Fabrication per coil |  | 1569.95 | 1046.35 | 1046.35 | 1046.35
Cost Bracket Fabrication Total |  | 9419.7 | 12556.2 | 6278.1 | 25112.4
Cost Bracket Fabrication with Materials Total |  | 27771.492 | 37018.632 | 18509.316 | 74037.264 | 157336.704 | 50%
Cost for Clamps per Coil |  | 1157.1455 | 771.2215 | 771.2215 | 771.2215
Hardware Cost per 3/8 Bolt (Inconnel) |  | 18 | 18 | 18 | 18
Cost for Bolts and Studs per coil |  | 498.69 | 332.37 | 332.37 | 332.37
Cost for all Bolts and Studs & Brackets Total |  | 9935.013 | 13243.098 | 6621.549 | 26486.196 | 56285.856 | 50%
Cost for Mockups of Each Coil |  | 5700 | 3800 | 3800 | 3800 | 17100 | 50%
Cost For Installation Fixtures |  | 3000 | 3000 | 3000 | 3000 | 12000 | 50%
Cost for Hardware | [5 empty] | 242722.56
Cost for Support Brackets adjusted for uncertainty | [5 empty] | 364083.84
Installation Man Hour Estimate (Budgeted in job 1815 station 5 assembly)
Tooling / Training / Preperation |  | 20 | 20 | 20 | 20
Hours to Position Coil and mark locations |  | 6 | 6 | 6 | 6
Hours per bracket |  | 1 | 1 | 1 | 1
Hours per coil for brackets |  | 6.9262 | 4.6162 | 4.6162 | 4.6162
Hours per coil for coil Installation |  | 6 | 6 | 6 | 6
Metrology for bracket installation |  | 100.1681 | 164.5463 | 89.7731 | 314.0925
Total Hours for Tech (2 work at once) |  | 267.115 | 438.79 | 239.395 | 837.58 | 1782.88
Determine Metrology Procedure and Setup |  | 20 | 20 | 20 | 20
Interpret Results and Report |  | 20 | 20 | 20 | 20
Charicterize Coils Before Assembly |  | 2 | 2 | 2 | 2
Hours to Measure Coil Location per Coil |  | 4 | 4 | 4 | 4
Total Hours for post Installation Metrology (2 Eng.) |  | 188.1681 | 300.5462 | 177.7731 | 546.0925 | 1212.58
| 1849 | 144 |  | 1993 |  | 161433 |  |  | 81
632 | 1934 | 192 | 940 | 3698 |  | 628660 |  |  | 170
1890485.9834
Weeks for two technicians per Field Period |  | 7.4287 |  |  | Cost Total M&S | 1100392.9834
Weeks for four technicians per Field Period |  | 3.7143
[5 empty] | Total Hours | 2995.46
[5 empty] | Technicican Rate | 85
[5 empty] | Eng Rate | 160
[5 empty] | Cost Man-hours | 345557.6
[5 empty] | Total Cost | 1445950.5834
[9 empty] | Category | Amount ($) | % of ETC ($)
CATEGORIZATION CODES:
|  |  |  | 1 - National Standards |  |  |  |  | 1 | 0 | #REF!
|  |  |  | 2 - Engineering Judgement/Experience |  |  |  |  | 2 | 0 | #REF!
|  |  |  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  |  |  | 3 | 0 | #REF!
|  |  |  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  |  |  | 4 | #REF! | #REF!
|  |  |  | 5 - Prototype Data/Test Results |  |  |  |  | 5 | 0 | #REF!
|  |  |  | 6 - Catelogue Price/Vendor Quote |  |  |  |  | 6 | 0 | #REF!
|  |  |  | 7 - Placed Contracts |  |  |  |  | 7 | 0 | #REF!
|  |  |  | 8 - Actual Costs/Schedule for NCSX Work |  |  |  |  | 8 | 0 | #REF!
|  |  |  | 9 - Other |  |  |  |  | 9 | 0 | #REF!
[7 empty] | Totals |  |  | #REF! | #REF!