## Sheet1
Assumptions and Conditions:
1 | Coils would be fabricated in the NCSX coil area [Station 3]
2 | Conductors would be extruded copper conductor
3 | Cost of conductor and insulation not included in estimate
4 | Conductors would be insulated in-line with taping machine [presently on loan to Everson Electric for TF program]
5 | Coils would be wound on TF turntable
6 | Conductors would be induction brazed together [extend loan from Argon for use of their braze unit presently located at Everson for TF program]
7 | Assumes 8 hour work day x single shift
8 | Mandrel and base plate would be used for winding and molding
9 | Coils would be VPI'd at location of station 1a. Forced air oven using blower and controlls from NSTX TF oven
10 | Existing VPI station would be used for delivering epoxy. [possibily moving tanks closer to coil.
|  | EAEM | EADM | EMSM | EMSM | EMTB | M&S | M&S
| TASK DESCRIPTION | Engr | Designer | Meighan | machinist | Tech
|  | hours | hours | hours | hours | hours | w/o G&A | w/G&A
ENGINEERING and OVERSIGHT
| Write procedures/ and planning activities | 160
| Manuacturing oversite | 800 |  | 400
|  | 960 |  | 400 | [5 empty] | 233680
|  | 180480 |  | 53200
EQUIPMENT and TOOLING COSTS
| Fabricate Coil WIndingTooling/Fixtures | 100
| Facility Layout/electrical design mods |  | 200
| Base plate [ winding and molding] |  | 60 |  |  | 200 | 15000 | 19050
| Mandrel and mold mold [PF-6] |  | 80 |  |  |  | 55000 | 69850
| Spreader bar for lifting | [5 empty] | 15000 | 19050
| Mandrel and mold [PF-5] |  | 80 |  |  |  | 55000 | 69850
| Install induction braze station |  |  |  |  | 40
| Winding clamp sets [100] |  | 80 |  |  |  | 10000 | 12700
| Ground wrapping stands |  |  |  |  | 100 | 5000 | 6350
| Tension unit |  | 80 |  |  | 200 | 5000 | 6350
| VPI manifold & sprues |  | 80 |  |  | 160 | 500 | 635
| Miscellaneous tools and equipment |  |  |  | 200 | 200 | 10000 | 12700
| Fabricate oven for VPI operation |  | 100 |  |  | 904 | 20000 | 25400
|  | 100 | 760 | 0 | 200 | 1804
| TOTALS | 18800 | 91960 |  | 26600 | 146124 |  | 241935 |  | 525419
MATERIAL & SUPPLIES
| 1) Insulation | [6 empty] | 0
| 2) Epoxy- CTD-101K | [5 empty] | 20000 | 25400
| 5) Copper conductor | [6 empty] | 0
| 6) G-11 fillers | [5 empty] | 20000 | 25400
| 7) Lead hardware | [5 empty] | 10000 | 12700
| 8) Safety and miscellaneous supplies | [5 empty] | 25000 | 31750
| 3) Disposable VPI hardware | [5 empty] | 20000 | 25400
[8 empty] | 120650 |  | 120650
|  |  | EETB | EMSM | EMTB | M&S | M&S |  | Demo | FY07 Rate/ Hr
| TASK DESCRIPTION |  | Tech | machinist | Tech |  |  |  | EAEM | 188
|  |  | hours | hours | hours | w/o G&A | w/G&A |  | SM | 133
| AREA PREPARATION | [7 empty] | TB | 81
| Modify cleanroom to accommodate PF coils |  | 320 |  | 400 | 10000 | 12700 |  | DM | 121
| Install winding table |  | 120 |  | 120
| Mount top plate and mandrel [initial installation] |  |  | 80 | 100
| Modify epoxy delivery system |  |  |  | 120
|  |  | 440 | 80 | 740
|  |  | 35640 | 10640 | 59940 |  | 12700 |  |  | 118920
|  | PF-6 | [5 empty] | PF-5
Task | TASK DESCRIPTION | Working | Shifts | No. of | No. of | No. of | No. of | Working | Shifts | No. of | No. of | No. of | No. of
No. |  | Days | per day | Tech. | man-hours | Items | man-hours | Days | per day | Tech. | man-hours | Items | man-hours
1 | Station No. 3- Coil Winding | 31.75 | [5 empty] | 49.75
1a | Prepare winding station PF-6 | 4 | 1 | 3 | 96 | 2 | 192 | 4 | 1 | 3 | 96 | 2 | 192
1b | Winding operation | 27 |  |  | 448 | 2 | 896 | 41 |  |  | 672 | 2 | 1344
| Position/braze & secure 1st. coil lead set | 2 | 1 | 2 | 32 |  |  | 2 | 1 | 2 | 32
| Wind turns [14 per PF-6 and 24 per PF-5] | 14 | 1 | 2 | 224 |  |  | 24 | 1 | 2 | 384
| Brazes joints | 8 | 1 | 2 | 128 |  |  | 12 | 1 | 2 | 192
| Position/braze & secure 2nd. coil lead | 2 | 1 | 2 | 32 |  |  | 2 | 1 | 2 | 32
| Transfer coil to GW station | 1 | 1 | 4 | 32 |  |  | 1 | 1 | 4 | 32
1c | Complete groundwrap installation | 4 | 1 | 2 | 64 | 2 | 128 | 4 | 1 | 2 | 64 | 2 | 128
1d | Perform pressure test of cooling system | 0.5 | 1 | 2 | 8 | 2 | 16 | 0.5 | 1 | 2 | 8 | 2 | 16
1e | Perform preliminary electrical test | 0.25 | 1 | 2 | 4 | 2 | 8 | 0.25 | 1 | 2 | 4 | 2 | 8
[7 empty] | 1240 | [5 empty] | 1688
[7 empty] | 100440 | [5 empty] | 136728 | 237168
|  | PF-6 | [5 empty] | PF-5
Task | TASK DESCRIPTION | Working | Shifts | No. of | No. of | No. of | No. of | Working | Shifts | No. of | No. of | No. of | No. of
No. |  | Days | per day | Tech. | man-hours | Items | man-hours | Days | per day | Tech. | man-hours | Items | man-hours
2 | Final coil prep; Mold Assembly and VPI | 14.5 | [5 empty] | 14.5
2a | Install outer and top plates | 2 | 1 | 4 | 64 | 2 | 128 | 2 | 1 | 4 | 64 | 2 | 128
2b | Install epoxy sprues | 2 | 1 | 2 | 32 | 2 | 64 | 2 | 1 | 2 | 32 | 2 | 64
2c | Leak check mold | 1 | 1 | 2 | 16 | 2 | 32 | 1 | 1 | 2 | 16 | 2 | 32
2d | Connect fill lines, manifolds, hookup thermocouples & leak check | 2 | 1 | 2 | 32 | 2 | 64 | 2 | 1 | 2 | 32 | 2 | 64
2e | VPI coil
| Vacuum pumpdown and heat mold | 1 | 1 | 2 | 16 | 2 | 32 | 1 | 1 | 2 | 16 | 2 | 32
| Epoxy fill and cure | 2.5 | 3 | 2 | 120 | 2 | 240 | 2.5 | 3 | 2 | 120 | 2 | 240
2f | Clean and restore epoxy delivery system | 4 | 1 | 2 | 64 | 2 | 128 | 4 | 1 | 2 | 64 | 2 | 128
[7 empty] | 688 | [5 empty] | 688
[7 empty] | 55728 | [5 empty] | 55728 | 111456
|  | PF-6 | [5 empty] | PF-5
Task | TASK DESCRIPTION | Working | Shifts | No. of | No. of | No. of | No. of | Working | Shifts | No. of | No. of | No. of | No. of
No. |  | Days | per day | Tech. | man-hours | Items | man-hours | Days | per day | Tech. | man-hours | Items | man-hours
3 | Post VPI | 9.5 | [5 empty] | 9.5
3a | Dissassemble mold | 1.5 | 1 | 3 | 36 | 2 | 72 | 1.5 | 1 | 3 | 36 | 2 | 72
3b | Remove coil from baseplate | 1 | 1 | 3 | 24 | 2 | 48 | 1 | 1 | 3 | 24 | 2 | 48
3c | Clean and inspect coil, silver plate leads | 2 | 1 | 2 | 32 | 2 | 64 | 2 | 1 | 2 | 32 | 2 | 64
4c | Perform electrical & Pressure Tests | 1 | 1 | 2 | 16 | 2 | 32 | 1 | 1 | 2 | 16 | 2 | 32
5c | Clean mold components | 4 | 1 | 2 | 64 | 2 | 128 | 4 | 1 | 2 | 64 | 2 | 128
[7 empty] | 344 | [5 empty] | 344
[7 empty] | 27864 | [5 empty] | 27864 | 55728
[13 empty] | Total Est. | 1403021
SCHEDULE
Duration
| Task Description | Work Days
Schedule is in work days and assumes that the tasks are done sequencially
| Equipment design and fabricate equipment/modify cleanroom | 150
| Winding LPF-6 | 32
| VPI | 14.5
| Post | 9.5
| Winding LPF-5 | 50
| VPI | 14.5 | 130 | 6.5
| Post | 9.5
| Winding UPF-6 | 32
| VPI | 14.5
| Post | 9.5
| Winding UPF-6 | 50
| VPI | 14.5
| Post | 9.5
|  |  | 280 | 14
Calculation of range of higher cost for in house build for risk register
[5 empty] | Plus 30% | -15%
|  |  | High Estimate | Low Estimate | High PPPL | Low PPPL
| Tooling |  | 0 | 375
| Estimate for Everson to Build PF5 |  | 415 | 88.9
| Estimate for Everson to Build PF6 |  | 485 | 98
|  |  | 900 | 561.9
| Title 3 Oversight | 784 | 147.392 | 147.392
| Total Cost PF5 & PF6 |  | 1047.392 | 709.292
| In House Build |  | 1403.021 |  | 1823.9273 | 1192.5678
| Delta Everson to In House Build |  | 355.629 |  | 776.5353 | 145.1758
|  |  | nominal | fyi | high | low