TO:   		Phil Heitzenroeder

FROM:  	Steve Raftopoulos

DATE:  	September 13, 2008

SUBJECT:	Cryostat Design & Fabrication: 9450-1***-1701

Cryostat Procurements: 9450-1***-1705

# Scope

This elements cover design and fabrication (1701) and M&S (1705) for the NCSX Cryostat, which is an insulating, semi-hermetic structure required to maintain a ~77Kelvin cryogenic environment around the NCSX device.

The scope included design, prototyping and fabrication (or procurement of vendor fabricated components).

Status

The Cryostat design had evolved through several iterations is currently considered in the conceptual phase.

The first version , described as Tub-Panel consisted of fiberglass ” tubs”, that were filled with insulating material, bolted together to form the cryostat structure.  The design incorporated pliable foam between tub panels to provide a compliant, semi-hermetic seal  that would function at LN2 temperatures.  Due to high fabricating cost, and little fabricating vendor interest, this design was abandoned.

The second design concept, which was not developed further developed in CAD, consisted of a system of  G-11 boards with a 6-inch layer of foam panel insulation  (six, one-inch thick boards laminated to each other  to form a stepped pyramid shape).  The panels are supported on a light, inexpensive space frame and pliable (solomide) foam is used to seal joints between panels.  Although considerably less expensive and easier to custom fabricate in the field, the main drawback of this design is the significant use of open cell foam to provide seals between panels.

The third concept was being developed when the project was terminated.  Based on feedback from external cryogenic experts, we were adopting a strategy that prototyping the seal design (between adjacent removable panels), was a critical step prior to detailing those elements.  Prototype test fixtures were being developed so that various insulating/seal concepts could be validated.  Parallel to this effort, the System Integration Engineer was designing the inner and outer boundaries of the cryostat, and interfacing this design with present design of other NCSX systems.  The degree of panelization of the cryostat was also being examined in an effort to reduce the number of panels.

Interfaces

The Cryostat interfaces with the entire NCSX – Everything is either within or passes through the cryostat.  Specific system that pass through the cryostat include, the coil buss systems, LN2 supply for Coil cooling and structure cooling, vacuum vessel ports, cabling for power, signal and instrumentation.

Specifications

A draft B_SPEC (NCSX-BSPEC-171-00-dB) was developed and was being updated as the requirements and design were evolving.  A copy is posted on the NCSX Engineering Web.

Schematics and PIDs

N/A.

Models

Models of the cryostat concept are posted in Intralink. Several recent conceptual ideas for a cryostat shell and prototype text fixture are attached to this close out note.  These include a report from a March 2007 Working Group, a design concept proposed by ORNL, and a prototype test fixture also proposed by ORNL.

Drawings

No detailed drawings were generated

Analyses

An FEA thermal and stress analysis of the Tub panel design was prepared for the April 2005 preliminary design review and the results are tabulated in that PDR report.  However, this design has now been superseded.

In addition, several analyses presentation of proposed design configurations are also attached and include a report from a March 2007 working group, a support thermal analysis, and a shell temperature distribution analysis.

Testing

Still need to identify any testing completed and a summary of the status/results.

Costs

Cost estimates were being developed for the conceptual and preliminary phases of the design.  These are available through the project office.

Remaining Work

- Evaluate and determine best compromise between high degree of panelization (many slam panels that allows access) vs. smaller number of larger cryostat sections (increases cryostat reliability).

- Prototype and test sealing options.

- Design cryostat shell.

- Fabricate

Lessons Learned:

- Incorporate the help of the cryogenic community sooner in project

Conclusions:

- The success of the cryostat as an operating system will be largely determined by the integrity of the sealing mechanism between joints.  After this challenge is met, designing the shape around the NCSX will be straightforward.

- In mid-April 2005, a preliminary design review of both the cryogenics and cryostat was conducted. The design presented at this review was subsequently revisited. A copy of the material presented at this review is posted on the NCSX Engineering Web under the Design Review tab (marked as superseded).

- A peer review of the cryostat systems was conducted in late April 2008 with a team of cryogenic systems experts.  This is posted on the NCSX Engineering Web page under the Design Review tab.  The concept presented at this peer review reflects the current design concepts at the time of NCSX Project termination.

Cryostat Design Concepts Following the 2005 PDR

- March 2007 Working Group Presentation

- May 2008 Cryostat Design Concept (ORNL)

- May 2008 Cryostat Prototype Test Fixture Concept (ORNL)

Analyses Presentations

- Support Thermal Analyis

- Thermal Deflection Analysis

- Shell Temperature Distribution Analysis