## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 54
WBS Title: Facility Timing & Synchronization Systems
Job Number: 5401
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Description:
The Facility Timing and Synchronization System will provide the hardware and software that facilitates the synchronization of NCSX hardware and equipment to the ‘microsecond’ degree, and computer programs on NCSX computers to the ‘seconds’ degree. These systems will utilize new timing and synchronization technology since the existing CAMAC system is obsolete.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 54
WBS Title: Facility Timing & Synchronization Systems
Job Number: 5401
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort.
FY07$K
Activity ID | Activity Description | 41MS | 43MS/CC | 48MS | 37STK | 35TRVL | ECEM | ECTB | EMTB | EASB | EEEM | EETB | Basis of Estimate
54-10 | Preliminary System Design | [5 empty] | 40 | [5 empty] | Estimate based on experience with similar activities for NSTX.
54-20 | Final SystemDesign | [5 empty] | 40 | [5 empty] | Estimate based on experience with similar activities for NSTX.
54-30 | Preliminary Design - Clock Dist. | [5 empty] | 20 |  |  |  | 40 |  | Estimate based on experience with similar activities for NSTX.
54-40 | Final Design - Clock Dist. | [5 empty] | 20 |  |  |  | 120 |  | Estimate based on experience with similar activities for NSTX.
54-50 | Test - Clock Dist. | [5 empty] | 20 |  |  |  | 100 | 120 | Estimate based on experience with similar activities for NSTX.
54-60 | Procurement | 16 | 14 |  | 4 |  | 40 | [5 empty] | Estimate based on experience with similar activities for NSTX.
54-70 | UNT - Timing & Seq Emulation (FPGA Pgm) | [6 empty] | 160 |  |  |  |  | Estimate based on experience with similar activities for NSTX.
54-80 | UNT - Device Driver Prog (EPICS/MDSplus) | [5 empty] | 160 | [5 empty] | Estimate based on experience with similar activities for NSTX.
54-90 | Central Clock (EPICS) Programming | [5 empty] | 80 | [5 empty] | Estimate based on experience with similar activities for NSTX.
54-100 | Installation | [5 empty] | 40 | 80 | 120 | 40 |  |  | Estimate based on experience with similar activities for NSTX.
54-110 | Test | [5 empty] | 40 | 40 |  |  |  |  | Estimate based on experience with similar activities for NSTX.
| Subtotal Job 5401 | 16 | 14 | 0 | 4 | 0 | 500 | 280 | 120 | 40 | 260 | 120
| M&S Details (Exp Class 41, 43, & 37): | K$
| Central Clock (PC, timers, SW) | [11 empty] | Based on recent purchased of parts for NSTX and other lab infratstructure projects
| Complete prototype UNT (Universal Timer) | 3 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infratstructure projects
| Design & fab proto fiber optic xmit | 10 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infratstructure projects
| UNT Production (10 units) | 10 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infratstructure projects
| Clock Distribution modules production (6 units) | 6 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infratstructure projects
| misc | 5 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infratstructure projects
| Total M&S | 34
Copies of P.O.'s or reqns?

## Table II - M&S
WBS Number: 54
WBS Title: Facility Timing & Synchronization Systems
Job Number: 5401
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 54
WBS Title: Facility Timing & Synchronization Systems
Job Number: 5401
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
In-house Fabrication and Assembly and Installation
See Table I

## Table IV - Conting & Risk
WBS Number: 54
WBS Title: Facility Timing & Synchronization Systems
Job Number: 5401
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity |  | X |  |  | This design is at the advanced conceptual design phase.
-15%/+25%
| Design Complexity |  | X |  |  | Similar equipment and software have been used on NSTX.
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)