## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 58
WBS Title: Central I&C Integration
Job Number: 5801
Job Title: Central I&C Integration
Job Manager: Paul Sichta
Description:
The Central I&C Integration provides oversight and interface coordination with other WBS elements as the NCSX design progresses.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 58
WBS Title: Central I&C Integration
Job Number: 5801
Job Title: Central I&C Integration
Job Manager: Paul Sichta
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort.
FY07$K
Activity ID | Activity Description | 41MS | 43MS/CC | 48MS | 37STK | 35TRVL | ECEM | ECTB | EMTB | EASB | EEEM | EETB | Basis of Estimate
LOE effort based on current Resource Loaded Schedule for NCSX Central I&C efforts. (Look at NSTX??)
58-10 | WBS58 -FY07 Management & Integration | [5 empty] | 50
58-20 | WBS58 -FY08 Management & Integration | [5 empty] | 160
58-30 | WBS58 -FY09 Management & Integration | [5 empty] | 120
58-40 | WBS58 -FY09 Management & Integration | [5 empty] | 120
| Subtotal Job 5801 | 0 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0

## Table II - M&S
WBS Number: 58
WBS Title: Central I&C Integration
Job Number: 5801
Job Title: Central I&C Integration
Job Manager: Paul Sichta
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 58
WBS Title: Central I&C Integration
Job Number: 5801
Job Title: Central I&C Integration
Job Manager: Paul Sichta
In-house Fabrication and Assembly and Installation
See Table I

## Table IV - Conting & Risk
WBS Number: 58
WBS Title: Central I&C Integration
Job Number: 5801
Job Title: Central I&C Integration
Job Manager: Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | LOE is for basic project management activities - based on previous I&C Project experience (e.g., NSTX)
-5%/+10%
| Design Complexity |  |  | X |  | LOE includes basic project management and as-needed conceptual design activities - based on previous I&C Project experience (e.g., NSTX)
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)