## Estimate
WBS5 M&S and Labor cost estimating
2007-03-21
P. Sichta
--- | Startup Testing 22JAN09 | milestone | 2009-01-22 | 2009-01-22
--- | CD-4 11MAR09 | milestone | 2009-03-11 | 2009-03-11
--- | NSTX Run Support | milestone | 2007-12-03 | 2008-06-06
[6 empty] | 177 | 82 | 82 | 122 | 177 | 82 | 1300 | 1300 | 1300
Activity ID | Activity Description | Duration | Start | Finish | Resources | ECEM | ECTB | EMTB | EASB | EEEM | EETB | 41MS | 43CC | 37STK | 35TRVL
51 | WBS51 - Networking Infrastructure
51-10 | Preliminary Design | 30 days | 2007-10-01 08:00 | 2007-11-09 17:00 | ECH*EM[30] | 30
51-20 | Final Design | 60 days | 2007-11-12 08:00 | 2008-02-01 17:00 | ECH*EM[30] | 30
51-30 | Procurement | 60 days | 2008-02-04 08:00 | 2008-04-25 17:00 | ECH*EM[20],41[39 K] | 20 | [5 empty] | 25 | 10 | 4
51-50 | Installation | 60 days | 2008-04-28 08:00 | 2008-07-18 17:00 | ECH*EM[60],EMT*TB[490], EADDSB[240], ECH*SB[20] | 60 | 20 | 490 | 240
51-60 | Test | 14 days | 2008-07-21 08:00 | 2008-08-07 17:00 | ECH*EM[20],ECH*SB[20] | 20 | 20
[6 empty] | 28320 | 3280 | 40180 | 29280 | 0 | 0 | 32500 | 13000 | 5200 | 0 | 151760 | 149000 | 2760 | 1.852%
52 | WBS52 - Central I&C
52-10 | Preliminary Design | 30 days | 2007-11-01 08:00 | 2007-12-12 17:00 | ECH*EM[40] | 40
52-20 | Final Design | 60 days | 2007-12-13 08:00 | 2008-03-05 17:00 | ECH*EM[40] | 40
52-30 | Procurement | 30 days | 2008-03-06 08:00 | 2008-04-16 17:00 | ECH*EM[20],41[38 K] | 20 | [5 empty] | 18 | 17 | 3
52-40 | EPICS Programming - Base | 10 days | 2008-04-17 08:00 | 2008-04-30 17:00 | ECH*EM[80] | 80
52-50 | EPICS Programming - VDCT db editor | 30 days | 2008-05-01 08:00 | 2008-06-11 17:00 | ECH*EM[40] | 40
52-60 | IOC Programming - MDSplus data & events | 30 days | 2008-05-01 08:00 | 2008-06-11 17:00 | ECH*EM[120] | 120
52-70 | OPC - EPICS/PLC Interface | 90 days | 2008-05-01 08:00 | 2008-09-03 17:00 | ECH*EM[160],41[2 K],TRVL[2 K] | 160 | [6 empty] | 2 |  | 2
52-80 | Programming - misc. | 90 days | 2008-10-02 08:00 | 2009-02-04 17:00 | ECH*EM[100] | 100
52-100 | Installation | 60 days | 2008-04-17 08:00 | 2008-07-09 17:00 | ECH*EM[40],EMT*TB[240], EADDSB[120],ECH*SB[100] | 40 | 100 | 240 | 120
52-110 | Test | 14 days | 2008-10-02 08:00 | 2008-10-21 17:00 | ECH*EM[40] | 40
[6 empty] | 120360 | 8200 | 19680 | 14640 | 0 | 0 | 23400 | 24700 | 3900 | 0 | 214880 | 136000 | 78880 | 58%
53 | WBS53 - Data Acquisition & Management
53-10 | Preliminary Design | 30 days | 2007-10-15 08:00 | 2007-11-23 17:00 | ECH*EM[40] | 40
53-20 | Final Design | 30 days | 2007-11-26 08:00 | 2008-01-04 17:00 | ECH*EM[80] | 80
53-30 | Procurement | 30 days | 2008-01-07 08:00 | 2008-02-15 17:00 | ECH*EM[20],41[22 K] | 20 | [5 empty] | 17 | 3 | 2
53-40 | Installation | 30 days | 2008-02-18 08:00 | 2008-03-28 17:00 | ECH*SB[40] |  | 40
53-50 | MDSplus Installation | 20 days | 2008-03-31 08:00 | 2008-04-25 17:00 | ECH*EM[80] | 80
53-60 | MDSplus Programming - Tree Design | 20 days | 2008-04-28 08:00 | 2008-05-23 17:00 | ECH*EM[80] | 80
53-70 | MDSplus Programming - Shot Sync | 20 days | 2008-05-26 08:00 | 2008-06-20 17:00 | ECH*EM[80] | 80
53-80 | MDSplus Programming - Dispatcher | 30 days | 2008-06-23 08:00 | 2008-08-01 17:00 | ECH*EM[160] | 160
53-90 | MDSplus Programming - Acquisition | 20 days | 2008-08-04 08:00 | 2008-08-29 17:00 | ECH*EM[80] | 80
53-110 | Programming - Misc. | 60 days | 2007-03-19 08:00 | 2007-06-08 17:00 | ECH*EM[160] | 160
53-120 | Test | 14 days | 2007-10-15 08:00 | 2007-11-01 17:00 | ECH*EM[40],ECH*SB[40] | 40 | 40
[6 empty] | 145140 | 6560 | 0 | 0 | 0 | 0 | 22100 | 3900 | 2600 | 0 | 180300 | 148000 | 32300 | 21.82%
54 | WBS54 - Facility Timing & Synch.
54-10 | Preliminary System Design | 30 days | 2007-10-01 08:00 | 2007-11-09 17:00 | ECH*EM[40] | 40
54-20 | Final SystemDesign | 40 days | 2007-11-12 08:00 | 2008-01-04 17:00 | ECH*EM[40] | 40
54-30 | Preliminary Design - Clock Dist. | 20 days | 2007-11-12 08:00 | 2007-12-07 17:00 | ECH*EM[20],EED*EM[40] | 20 |  |  |  | 40
54-40 | Final Design - Clock Dist. | 30 days | 2007-12-10 08:00 | 2008-01-18 17:00 | ECH*EM[20],EED*EM[120] | 20 |  |  |  | 120
54-50 | Test - Clock Dist. | 40 days | 2008-05-12 08:00 | 2008-07-04 17:00 | ECH*EM[20],EED*TB[120], EED*EM[100] | 20 |  |  |  | 100 | 120 | [5 empty] | 500
54-60 | Procurement | 90 days | 2008-01-07 08:00 | 2008-05-09 17:00 | ECH*EM[40],41[34 K] | 40 | [5 empty] | 16 | 14 | 4
54-70 | UNT - Timing & Seq Emulation (FPGA Pgm) | 90 days | 2007-10-01 08:00 | 2008-02-01 17:00 | ECH*SB[160] |  | 160
54-80 | UNT - Device Driver Prog (EPICS/MDSplus) | 120 days | 2008-03-12 08:00 | 2008-08-26 17:00 | ECH*EM[160] | 160
54-90 | Central Clock (EPICS) Programming | 30 days | 2008-08-27 08:00 | 2008-10-07 17:00 | ECH*EM[80] | 80
54-100 | Installation | 90 days | 2008-05-12 08:00 | 2008-09-12 17:00 | ECH*EM[40],ECH*SB[80], EMT*TB[120],EADDSB[40] | 40 | 80 | 120 | 40
54-110 | Test | 14 days | 2008-09-15 08:00 | 2008-10-02 17:00 | ECH*EM[40],ECH*SB[40] | 40 | 40
[6 empty] | 88500 | 22960 | 9840 | 4880 | 46020 | 9840 | 20800 | 18200 | 5200 | 0 | 226240 | 79000 | 147240 | 186.4%
55 | WBS55 - Real Time Control
55-10 | FCPC - Preliminary Design | 30 days | 2008-01-25 08:00 | 2008-03-06 17:00 | ECH*EM[40] | 40
55-20 | FCPC -Final Design | 60 days | 2008-03-07 08:00 | 2008-05-29 17:00 | ECH*EM[80] | 80
55-30 | FCPC - Procurement | 60 days | 2008-05-30 08:00 | 2008-08-21 17:00 | ECH*EM[20],41[14 K] | 20 | [5 empty] | 6 | 7 | 1
55-40 | LabVIEW Programming | 30 days | 2008-08-18 08:00 | 2008-09-26 17:00 | ECH*EM[120] | 120
55-50 | FCPC PLC Integration - EPICS Prog. | 30 days | 2008-08-18 08:00 | 2008-09-26 17:00 | ECH*EM[40] | 40
55-50 | FCPC - Installation | 60 days | 2008-08-22 08:00 | 2008-11-13 17:00 | ECH*EM[40],ECH*SB[40], EADDSB[80] | 40 | 40
55-60 | FCPC -Test | 14 days | 2008-11-14 08:00 | 2008-12-03 17:00 | ECH*EM[40],ECH*SB[20] | 40 | 20
55-70 | GISRTC - Preliminary Design | 30 days | 2007-12-10 08:00 | 2008-01-18 17:00 | ECH*EM[40] | 40
55-80 | GISRTC -Final Design | 60 days | 2008-01-21 08:00 | 2008-04-11 17:00 | ECH*EM[60] | 20
55-90 | GISRTC - Procurement | 60 days | 2008-04-14 08:00 | 2008-07-04 17:00 | ECH*EM[20],41[12 K] | 20 | [5 empty] | 6 | 5 | 1
55-100 | LabVIEW Programming | 30 days | 2008-07-07 08:00 | 2008-08-15 17:00 | ECH*EM[120] | 120
55-110 | GISRTC - Installation | 60 days | 2008-08-18 08:00 | 2008-11-07 17:00 | ECH*EM[20],ECH*SB[20], EADDSB[24] | 20 | 20 |  | 24
55-120 | GISRTC -Test | 14 days | 2008-11-10 08:00 | 2008-11-27 17:00 | ECH*EM[20] | 20
[6 empty] | 109740 | 6560 | 0 | 2928 | 0 | 0 | 15600 | 15600 | 2600 | 0 | 153028 | 91000 | 62028 | 68.16%
56 | WBS56 - Central Safety & Interlocks
56-10 | Requirements, Codes&Standards | 60 days | 2007-12-03 08:00 | 2008-02-22 17:00 | ECH*EM[40] | 40
56-20 | Preliminary Design | 30 days | 2008-02-25 08:00 | 2008-04-04 17:00 | ECH*EM[40] | 40
56-30 | PLC Training | 60 days | 2008-04-07 08:00 | 2008-06-27 17:00 | ECH*EM[80],41[2 K],TRVL[2 K] | 80 | [6 empty] | 2 |  | 2
56-40 | Final Design | 30 days | 2008-04-07 08:00 | 2008-05-16 17:00 | ECH*EM[140] | 140
56-40 | Procurement | 60 days | 2008-05-19 08:00 | 2008-08-08 17:00 | ECH*EM[40],41[40 K] | 40 | [5 empty] | 20 | 12 | 8
56-50 | PLC Programming | 90 days | 2008-08-11 08:00 | 2008-12-12 17:00 | ECH*EM[120] | 120
56-60 | Installation | 70 days | 2008-08-11 08:00 | 2008-11-14 17:00 | ECH*EM[60],EMT*TB[480], ECH*SB[80],EADDSB[240] | 60 | 80 | 480 | 240
56-70 | Test | 30 days | 2008-11-17 08:00 | 2008-12-26 17:00 | ECH*EM[80],ECH*SB[40] | 80 | 40
[6 empty] | 106200 | 9840 | 39360 | 29280 | 0 | 0 | 26000 | 18200 | 10400 | 0 | 239280 | 125000 | 114280 | 91.42%
57-10 | WBS57 - NCSX Control Room | 0 days
58-10 | WBS58 -FY07 Management & Integration | 130 days | 2007-04-02 08:00 | 2007-09-28 17:00 | ECH*EM[60] | 120
58-20 | WBS58 -FY08 Management & Integration | 262 days | 2007-10-01 08:00 | 2008-09-30 17:00 | ECH*EM[120] | 120
58-30 | WBS58 -FY09 Management & Integration | 218 days | 2008-10-01 08:00 | 2009-07-31 17:00 | ECH*EM[120] | 120
[6 empty] | 63720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63720 | 58000 | 5720 | 9.862%
[5 empty] | Totals | 3740 | 700 | 1330 | 664 | 260 | 120 | 108 | 72 | 23 | 4 | 1165488 | 786500
[6 empty] | hrs | hrs | hrs | hrs | hrs | hrs | $K | $K | $K | $K
|  |  | etc = | 1175
|  |  | ecp-53 = | 787
|  |  | increase = | 388

## M&S list
|  |  | NCSX WBS 5 M&S Summary, 3/15/2007 PS |  | ecem | emtb | easb | m&s | ectb
rev 2:20Mar2007 PS |  |  |  |  | 155 | 90 | 117 | 1.32 | 92.6
|  | unload cost |  |  | loaded cost | cont | total cost | cdr est
WBS51
ecem | 160 |  |  |  | 24800 | 8% | 26784
ectb | 20 |  |  |  | 1852 | 8% | 2000.16
emtb | 490 |  |  |  | 44100 | 8% | 47628
easm | 240 |  |  |  | 28080 | 8% | 30326.4
|  | 15 |  | Switches, etc.. | 19800 | 8% | 21384
|  | 5 |  | NCSX_TC WAP | 6600 | 8% | 7128
|  | 1.8 |  | media converters 6) | 2376 | 8% | 2566.08
|  | 7 |  | Terminations, F/O patch panels & cable mgmt., patch cables | 9240 | 8% | 9979.2
|  | 5 |  | Fiber Optic cable | 6600 | 8% | 7128
|  | 10 |  | misc. | 13200 | 8% | 14256
|  |  | 0 | Op. spares | 0 | 8% | 0
TOTAL |  | 43.8 |  |  | 156648 |  | 169179.84 | 752000
WBS52
ecem | 760 |  |  |  | 117800 | 8% | 127224
ectb | 100 |  |  |  | 9260 | 8% | 10000.8
emtb | 240 |  |  |  | 21600 | 8% | 23328
easm | 0 |  |  |  | 0 | 8% | 0
|  | 3 |  | NTC web cam (4) | 3960 | 8% | 4276.8
|  | 6 |  | PC - appl. TBD (2) | 7920 | 8% | 8553.6
|  | 3 |  | Linux soft IOC (2) | 3960 | 8% | 4276.8
|  | 10 |  | OPC client & server HW/SW/TRNG (for T/C) | 13200 | 8% | 14256
|  | 0 |  | EPICS server (use NSTX) | 0 | 8% | 0
|  | 8 |  | EPICS gateway | 10560 | 8% | 11404.8
|  | 10 |  | misc | 13200 | 8% | 14256
[5 empty] | 0 | 8% | 0
|  |  | 0 | Op. spares | 0 | 8% | 0
TOTAL |  | 40 |  |  | 201460 |  | 217576.8 | 1076000
WBS53
ecem | 880 |  |  |  | 136400 | 8% | 147312
ectb | 40 |  |  |  | 3704 | 8% | 4000.32
easm | 0 |  |  |  | 0 | 8% | 0
|  | 10 |  | Linux MDSplus Server | 13200 | 8% | 14256
|  | 1.5 |  | SAN - disk space (500 GB) | 1980 | 8% | 2138.4
|  | 5 |  | misc. | 6600 | 8% | 7128
|  | 5 |  | PC appl. TBD | 6600 | 8% | 7128
|  |  | 0 | Op. spares | 0 | 8% | 0
TOTAL |  | 21.5 |  |  | 168484 |  | 181962.72 | 743000
WBS54
ecem | 660 |  |  |  | 102300 | 14% | 116622
ectb | 280 |  |  |  | 25928 | 14% | 29557.92
emtb | 120 |  |  |  | 10800 | 8% | 11664
easm | 40 |  |  |  | 4680 | 8% | 5054.4
| 40 | 0 |  | Central Clock (PC, timers, SW) | 0 | 14% | 0
|  | 3 |  | Complete prototype UNT (Universal Timer) | 3960 | 14% | 4514.4
|  | 10 |  | Design & fab proto fiber optic xmit | 13200 | 14% | 15048
|  | 10 |  | UNT Production (10 units) | 13200 | 14% | 15048
|  | 6 |  | Clock Distribution modules production (6 units) | 7920 | 14% | 9028.8
|  | 5 |  | misc. | 6600 | 14% | 7524
|  | 0 |  |  | 0 | 14% | 0
|  |  | 0 | Op. Spares | 0 | 0 | 0
TOTAL |  | 34 |  |  | 188588 |  | 214061.52 | 772000
WBS55
ecem | 620 |  |  |  | 96100 | 10% | 105710
ectb | 60 |  |  |  | 5556 | 10% | 6111.6
emtb | 0 |  |  |  | 0 | 10% | 0
easm | 0 |  |  |  | 0 | 10% | 0
|  | 12 |  | PC/LabVIEW control of C-Site Power Supplies | 15840 | 10% | 17424
|  | 10.5 |  | PC/LabVIEW control of Gas Injection | 13860 | 10% | 15246
|  | 2 |  | misc. | 2640 | 10% | 2904
|  | 0 |  |  | 0 | 10% | 0
|  |  | 0 | Op. spares | 0 | 10% | 0
TOTAL |  | 24.5 |  |  | 133996 |  | 147395.6 | 404000
WBS56
ecem | 600 |  |  |  | 93000 | 10% | 102300
ectb | 80 |  |  |  | 7408 | 10% | 8148.8
emtb | 480 |  |  |  | 43200 | 10% | 47520
easm | 240 |  |  |  | 28080 | 10% | 30888
|  | 5 |  | travel & training | 6600 | 10% | 7260
|  | 5 |  | Kirk Locks, door sensors, e-stops | 6600 | 10% | 7260
|  | 5 |  | Safety Relays, enclosures | 6600 | 10% | 7260
|  | 15 |  | Small Safety PLC (possible, requires further design) | 19800 | 10% | 21780
|  | 10 |  | cabling & conduit | 13200 | 10% | 14520
TOTAL |  | 40 |  |  | 224488 |  | 246936.8 | 442000
WBS57
ecem | 0 |  |  |  | 0 | 3% | 0
ecsm | 0 |  |  |  | 0 | 3% | 0
easm | 0 |  |  |  | 0 | 3% | 0
|  | 0 |  | Raised Flooring (construction budget) | 0 | 3% | 0
|  | 0 |  | 20 4 0 Workstation Tables | 0 | 3% | 0
|  | 0 |  | 3 PTZ cameras Multiplexer, switch, monitors, control unit | 0 | 3% | 0
|  | 0 |  | PA system amplifier, microphones, diagnostic mics, speakers | 0 | 3% | 0
|  | 0 |  | 2 dual headed workstations for comfort display | 0 | 3% | 0
|  | 0 |  | Raised floor installation | 0 | 3% | 0
|  | 0 |  | Table installation | 0 | 3% | 0
|  |  | 0 | Op. spares | 0 | 3% | 0
TOTAL |  | 0 |  |  | 0 |  | 0 | 330000
Grand |  | 203.8 | 0 |  | 1073664 |  | 1177113.28 | 4519000