## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Description:
The Diagnostic Data Acquisition System will provide a data management software structure to catalog and manage experimental results for subsequent retrieval and analysis. The design will use the existing MIT developed MDSplus software for data acquisition, data archiving and display. Individual diagnostic local control and data acquisition hardware will be designed with standard PC architecture or in Compact PCI chassis. The workscope includes CD-4 and preparation for initial research operations.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Description:
Title I and II Engineering and Title III Support of Fabrication Effort.
|  | $ |  |  |  |  | Hours
Activity ID | Activity Description | 41MS | 43MS/CC | 48MS | 37STK | 35TRVL | ECEM | ECTB | EMTB | EASB | EEEM | EETB | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
53-10 | Preliminary Design | [5 empty] | 40 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 40
53-20 | Final Design | [5 empty] | 80 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 80
53-30 | Procurement | 22000 |  |  |  |  | 20 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 22000 | 20
53-40 | Installation | [6 empty] | 40 |  |  |  |  | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 40
53-50 | MDSplus Installation | [5 empty] | 80 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 80
53-60 | MDSplus Programming - Tree Design | [5 empty] | 80 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 80
53-70 | MDSplus Programming - Shot Sync | [5 empty] | 80 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 80
53-80 | MDSplus Programming - Dispatcher | [5 empty] | 160 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 160
53-90 | MDSplus Programming - Acquisition | [5 empty] | 80 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 80
53-100 | Applications Support (3 diags) | [5 empty] | 60 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 60
53-110 | Programming - Misc. | [5 empty] | 160 | [5 empty] | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 160
53-120 | Test (3 diags) | [5 empty] | 60 | 40 |  |  |  |  | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 100
| M&S Details (Exp Class 41, 43, & 37): | 22000 | 0 | 0 | 0 | 0 | 900 | 80 | 0 | 0 | 0 | 0 |  |  | 22000 | 980
| M&S Details: | K$
| Linux MDSplus Server | 3000 | [10 empty] | Estimate based on experience with similar activities for NSTX.
| SAN - disk space (0.5 TB) | 6000 | [10 empty] | Estimate based on experience with similar activities for NSTX.
| network i/f (3) | 2000 | [10 empty] | Estimate based on experience with similar activities for NSTX.
| misc. | 5000 | [10 empty] | Estimate based on experience with similar activities for NSTX.
| PC appl. TBD (2) | 6000 | [10 empty] | Estimate based on experience with similar activities for NSTX.
| Total M&S | 22000
[13 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
[10 empty] | 1 - National Standards |  |  |  | 1 | 0 | 0 | 0% | 0%
[10 empty] | 2 - Engineering Judgement/Experience |  |  |  | 2 | 0 | 0 | 0% | 0%
[10 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  |  | 3 | 0 | 0 | 0% | 0%
[10 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  |  | 4 | 22000 | 980 | 100% | 100%
[10 empty] | 5 - Prototype Data/Test Results |  |  |  | 5 | 0 | 0 | 0% | 0%
[10 empty] | 6 - Catelogue Price/Vendor Quote |  |  |  | 6 | 0 | 0 | 0% | 0%
[10 empty] | 7 - Placed Contracts |  |  |  | 7 | 0 | 0 | 0% | 0%
[10 empty] | 8 - Actual experirnce for NCSX Work |  |  |  | 8 | 0 | 0 | 0% | 0%
[10 empty] | 9 - Other |  |  |  | 9 | 0 | 0 | 0% | 0%
[13 empty] | Totals |  | 22000 | 980 | 100% | 100%

## Table II - M&S
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
In-house Fabrication and Assembly and Installation
See Table I

## Table IV - Conting & Risk
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity |  | X |  |  | CDR complete some more design needed to finalize.
-10%/+15%
| Design Complexity |  |  | X |  | Duplication of NSTX architecture
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
5301 | Loss of key indviduals from engineering positions impacts schedule, |  |  |  | L | Limited cross-training |  | Estimated impact is <0.5 months on the critical path. No impact on cost because impacted personnel would be assigned to other activities. | 0 | 0 | 0 | 0.5
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)