## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
Description:
This job will provide realtime, integrated control of the NCSX coil power supplies and the torus gas injectors. The system will be based on the NSTX control system. The workscope includes support for CD-4 and preparation for initial research operations.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort.
FY07$K
Activity ID | Activity Description | 41MS | 43MS/CC | 48MS | 37STK | 35TRVL | ECEM | ECTB | EMTB | EASB | EEEM | EETB | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
55-10 | FCPC - Preliminary Design | [5 empty] | 80 |  |  | 40 | 24 |  | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 144
55-20 | FCPC -Final Design | [5 empty] | 180 |  |  | 20 | 60 |  | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 260
55-30 | FCPC - Procurement | 126000 |  |  |  |  | 20 |  |  |  | 40 |  | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 126000 | 60
55-40 | Host programming | [5 empty] | 120 | [5 empty] | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 120
55-42 | ACQ programming | [5 empty] | 80 | [5 empty] | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 80
55-45 | PCS programming | [5 empty] | 120 | [5 empty] | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 120
55-48 | PSRTC programming | [5 empty] | 40 |  |  |  | 160 |  | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 200
55-50 | FCPC PLC Integration - EPICS Prog. | [5 empty] | 40 | [5 empty] | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 40
55-50 | FCPC Data Acq & Ctl Installation | [5 empty] | 40 | 60 | 120 |  | 40 | 80 | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 340
55-60 | FCPC -Test | [5 empty] | 100 | 20 |  |  | 80 | 40 | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 240
55-70 | GISRTC - Preliminary Design | [5 empty] | 40 |  |  | 40 |  |  | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 80
55-80 | GISRTC -Final Design | [5 empty] | 60 |  |  | 20 |  |  | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 80
55-90 | GISRTC - Procurement | 12000 |  |  |  |  | 40 | [5 empty] | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 12000 | 40
55-100 | GISRTC Programming | [5 empty] | 80 | [5 empty] | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 80
55-110 | GISRTC I/O - Installation | [5 empty] | 40 | 60 | 100 | 24 | 40 | 40 | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 304
55-120 | GISRTC -Test | [5 empty] | 80 | 20 |  |  | 20 | 20 | Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience on other similar projects. | 4 | 0 | 140
| Subtotal Job 5501 | 138000 | 0 | 0 | 0 | 0 | 1160 | 160 | 220 | 144 | 464 | 180 |  |  | 138000 | 2328
| M&S Details (Exp Class 41, 43, & 37): |  | Basis of M&S Estimate
| Realtime computer | 20000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| host server | 5000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| networking/comm cards | 5000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| fiber optic cables | 5000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| VME crates (5) | 15000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| Systran (4 links) | 25000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| SAD - digitizers (320 chans, 10 units) | 25000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| FIMM (5) | 10000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| FPDP I/O (6) | 8000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| Sample clock dist. (5) | 5000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| PCLIM (0) (no D-site) | 0 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| misc | 15000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4 |  |  |  |  | You will need to show what makes up the MISC.
| Total M&S | 138000
[13 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
[10 empty] | 1 - National Standards |  |  |  | 1 | 0 | 0 | 0% | 0%
[10 empty] | 2 - Engineering Judgement/Experience |  |  |  | 2 | 0 | 0 | 0% | 0%
[10 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  |  | 3 | 0 | 0 | 0% | 0%
[10 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  |  | 4 | 138000 | 2328 | 100% | 100%
[10 empty] | 5 - Prototype Data/Test Results |  |  |  | 5 | 0 | 0 | 0% | 0%
[10 empty] | 6 - Catelogue Price/Vendor Quote |  |  |  | 6 | 0 | 0 | 0% | 0%
[10 empty] | 7 - Placed Contracts |  |  |  | 7 | 0 | 0 | 0% | 0%
[10 empty] | 8 - Actual experirnce for NCSX Work |  |  |  | 8 | 0 | 0 | 0% | 0%
[10 empty] | 9 - Other |  |  |  | 9 | 0 | 0 | 0% | 0%
[13 empty] | Totals |  | 138000 | 2328 | 100% | 100%

## Table II - M&S
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
In-house Fabrication and Assembly and Installation
See Table I

## Table IV - Conting & Risk
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity |  | X |  |  | Although CDR, some more design needed to finalize.
-10%/+15%
| Design Complexity |  |  | X |  | Duplication of NSTX architecture
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
5301 | Loss of key indviduals from engineering positions impacts schedule, |  |  |  | L | Limited cross-training |  | Estimated impact is <0.5 months on the critical path. No impact on cost because impacted personnel would be assigned to other activities. | 0 | 0 | 0 | 0.5
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)