## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 51
WBS Title: Networking Infrastructure
Job Number: 5101
Job Title: Networking Infrastructure
Job Manager: Paul Sichta
Description:
The TCP/IP networking infrastructure will provide the common backbone for all data acquisition, and I&C communications. The workscope includes CD-4 and preparation for initial research operations.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 51
WBS Title: Networking Infrastructure
Job Number: 5101
Job Title: Networking Infrastructure
Job Manager: Paul Sichta
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort.
|  | $ |  |  |  |  | Hours
Activity ID | Activity Description | 41MS | 43MS/CC | 48MS | 37STK | 35TRVL | ECEM | ECTB | EMTB | EASB | EEEM | EETB | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
51-10 | Preliminary Design | [5 empty] | 40 | 10 |  | 20 |  |  | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 70
51-20 | Final Design | [5 empty] | 50 | 30 |  | 20 |  |  | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 100
51-30 | Procurement | 68000 |  |  |  |  | 24 | 12 |  |  |  |  | Estimate based on experience with similar activities for NSTX. | 4 | 68000 | 36
51-50 | Installation | [5 empty] | 68 | 50 | 570 | 240 |  | 20 | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 948
51-60 | Test | [5 empty] | 28 | 40 |  |  |  |  | Estimate based on experience with similar activities for NSTX. | 4 | 0 | 68
|  | 68000 | 0 | 0 | 0 | 0 | 210 | 142 | 570 | 280 | 0 | 20 |  |  | 68000 | 1222
| M&S Details (Exp Class 41, 43, & 37): | [11 empty] | Basis of M&S Estimate
| Switches, etc.. | 21000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| NCSX_TC WAP | 7500 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| media converters (6) | 2500 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| Terminations, F/O patch panels & cable mgmt., patch cables | 12000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| Fiber Optic cable | 7000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| misc. | 18000 | [10 empty] | Based on recent purchased of parts for NSTX and other lab infrastructure projects | 4
| Total M&S | 68000
[13 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
[10 empty] | 1 - National Standards |  |  |  | 1 | 0 | 0 | 0% | 0%
[10 empty] | 2 - Engineering Judgement/Experience |  |  |  | 2 | 0 | 0 | 0% | 0%
[10 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  |  | 3 | 0 | 0 | 0% | 0%
[10 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  |  | 4 | 1222 | 68000 | 100% | 100%
[10 empty] | 5 - Prototype Data/Test Results |  |  |  | 5 | 0 | 0 | 0% | 0%
[10 empty] | 6 - Catelogue Price/Vendor Quote |  |  |  | 6 | 0 | 0 | 0% | 0%
[10 empty] | 7 - Placed Contracts |  |  |  | 7 | 0 | 0 | 0% | 0%
[10 empty] | 8 - Actual expeerience for NCSX Work |  |  |  | 8 | 0 | 0 | 0% | 0%
[10 empty] | 9 - Other |  |  |  | 9 | 0 | 0 | 0% | 0%
[13 empty] | Totals |  | 1222 | 68000 | 100% | 100%

## Table II - M&S
WBS Number: 51
WBS Title: Networking Infrastructure
Job Number: 5101
Job Title: Networking Infrastructure
Job Manager: Paul Sichta
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 51
WBS Title: Networking Infrastructure
Job Number: 5101
Job Title: Networking Infrastructure
Job Manager: Paul Sichta
In-house Fabrication and Assembly and Installation
See Table I

## Table IV - Conting & Risk
WBS Number: 51
WBS Title: Networking Infrastructure
Job Number: 5101
Job Title: Networking Infrastructure
Job Manager: Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity |  | X |  |  | Although PDR, some more design needed to finalize.
-10%/+15%
| Design Complexity |  |  | X |  | Standard components
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)