NCSX Resistance heating system field installation by: Frank Jones

Materials total:		$42,894

Wire: #2 awg			$600

#4 awg			$180

#10 awg			$1000

2/0			$250

#6 & #8 awg		$140

Multi-conductor shielded (1000ft.), 105c

Power cable for heaters ($6/ft.)	$6000

Thermo-extension cable (2000ft.)

Type-E shielded-8pr.($4/ft.)		$8000

2-“GE” breakers & enclosures	$2000

42 ckt. “GE”  panelboard

3 ph. 4 wire

150A				$1500

480v, square-D 70a

Breaker (250 af)			$700

G-10 sheets

5-1/8” 24” x 36”			$260

2-1/8” 36” x 76”			$364

PVC shed. 40 conduit

50 ft.				$75

5-2.5kva MGE isolation

Transformers			$6000

5-20a plugmold strips		$550

5-emi/rfi filters			$1500

5 fan assemblies			$500

30-25amp 1 pole breakers		$1050

5-20amp 1 pole breakers		$175

Panduit 2” x 2” in rack		$250

4” x 18” fiberglass tray fittings

For thermo-wire			$1700

4 x 12” fiberglass tray fittings

For heater power			$1200

4” x 18” fiberglass straight tray

For thermo-wire			$2000

4 x 12” fiberglass straight tray

For heater power			$1200

Aluminum and fiberglass

Strut				$200

Isolation transformer

45 kva, 480v to 208/120v

41kvdc iso.			$5500

System Design & Construction package estimate

Design/drafting & supervision total: 42 man days

Task breakdown

Machine elevation & tray details	4 man days

Tray support fabrication detail	4

Rack internal layout details		3

Existing Panel draw rev.		1

New panel schedule dwg.		1

Shutdown dwg			1

AC power CWD for panel/xfmr	1

5 rack ac power CWDs		3

Heater power from rack to connector

Wiring diagrams & termination details 4

Thermocouple wiring from rack to

Machine and termination details	4

Tray test cell plan drawing		3

Material ordering and research	3

JHA, procedure, ECN, work order	3

Package issue and field walk down	2

Revisions/construction supervision	5

Construction/Electricians estimate

Total:	121 man days

Task breakdown

Install 70a, 3 pole 480v breaker

(coordinate panel PP_141 shutdown)	2 man days

Install conduit thru wall to test cell	2

Install 45 kva isolation transformer

(handling and secure to floor)		4

Install primary & secondary breaker	2

Install new panelboard

(assemble & install branch breakers)	2

Install conduit between xfmr and breaker

Enclosures			2

Install ac power conductors & terminate6

Install power and instrument dedicated trays

Around top and bottom of machine	16

Fabricate & Install tray support system	8

Install rack power conduit		4

Install 2-trays from machine to racks	8

Install 5 racks insulated to 5KV	8

Install 5 isolation xfmrs at racks

(install 5 filters and plugmold strips)	7

Hi-pot racks to verify isolation

(coordinate with TC work)		2

Install rack power wire 1/c #10	2

Install heater power from panel to rack

(30-120v circuits-fan out at racks)	10

Install/terminate heater power from racks to

Machine via tray(multi conductor)	12

Install/terminate thermocouple extension

Wire from rack to machine		24