## Sheet1
Thomson Scattering (LeBlanc & Feder)
10 channels-expandable to 60 channels, single 50 Hz laser
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Laser | 100
Physicist | 12 | 12 | 12 | 10 poly./det. w. electronics | 250
Mech. Eng. | 3 | 3 |  | fibers | 50
Elec. Eng. | 2 | 1 |  | fiber holder | 10
Designer | 3 | 3 |  | detection optics | 20
Diag. Tech | 6 | 6 |  | laser delivery optics | 20
Elec. Tech. | 3 | 3 |  | Support structure in TC | 75
Tech. Shop | 6 | 6 | 3 | setup laser/detector room | 30
Programmer |  | 3 | 3 | opt. table, cover, interlocks | 30
|  |  |  | laser chiller | 10
|  |  |  | 3 racks | 85.8
|  |  |  | 2 PCs | 4
|  |  |  | re-entrant port w. shut. wind. | 50
Total M&S (k$) |  |  |  |  | 680.8
CHERS (Bell & Feder)
40-50 channels, single spectrometer with single set of optics viewing DNB
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Spectrometer/detector | 75
Physicist | 9 | 9 | 12 | Fibers, Optics, etc. | 50
Mech. Eng. | 2 | 2 |  | Rack | 28.6
Elec. Eng. |  |  |  | Misc. | 20
Designer | 2 | 2 |  | re-entrant port w. shut. wind. | 50
Diag. Tech. | 4 | 4 |  | 1 PC | 2
Elec. Tech. | 1
Tech. Shop | 4 | 4
Programmer |  |  | 1
Total M&S (k$) |  |  |  |  | 225.6
Imaging x-ray cyrstal spectrometer (Bitter)
Spectrometer similar to C-Mod system with 3 PILATUS II detectors
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Detectors | 270
Physicist |  | 4 | 12 | Detector mods., cables, etc. | 30
Mech. Eng. |  | 1 |  | Quartz cyrstal | 2.5
Elec. Eng. |  |  |  | Spectrometer housing | 30
Designer |  | 1 |  | Be window | 15
Diag. Tech. |  | 2 | 1 | Rack | 28.6
Elec. Tech. |  |  |  | 3 PCs | 6
Tech. Shop
Programmer |  | 1
Total M&S (k$) |  |  |  |  | 382.1
Soft x-ray array (Tritz)
Single 20 channel ex-vesssel array moved from NSTX; possible in-vessel multi-color array
(would require cooling)
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Vacuum hardware | 20
Physicist | 0.5 | 3 | 6 | Cables, connectors, misc. | 5
Mech. Eng. |  | 1 |  | Rack | 28.6
Elec. Eng. |  |  |  | Filters | 5
Designer |  | 0.5
Diag. Tech. |  | 2 | 1
Tech. Shop |  | 1
Programmer
Total M&S (k$) |  |  |  |  | 58.6
MSE (Levinton)
5 spatial channels viewing DNB, expandable
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | re-entrant port w. shut. wind. | 50
Physicist | 4 | 4 | 9 | Optics, fiber, filters, det, etc.-1 | 29
Mech. Eng. | 3 |  |  | Optics, fiber, filters, det, etc.-2 | 80
Elec. Eng. |  |  |  | Optics, fiber, filters, det, etc.-3 | 10
Designer | 6 | 6 | 2
Diag. Tech. | 4 | 10 | 6
Tech. Shop | 3 | 5 | 2
Programmer |  | 2 | 2
Total M&S (k$) |  |  |  |  | 169
Interferometer (Taylor)
1 mm, Single chord-move NSTX system to NCSX, system repackaged to be portable.
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Viewport & mirror tile | 25
Physicist | 1 | 1 | 1 | Shutter | 15
Mech. Eng. | 1 | 1 |  | Misc. | 5
Elec. Eng.
Designer | 1
Diag. Tech. |  | 1 | 1
Tech. Shop |  | 1
Programmer |  |  | 1
Total M&S (k$) |  |  |  |  | 45
In-vessel magnetics (Kaita, Guttadora)
~50 sensors including cabling, feedthroughs
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission
Physicist | 1 | 1 | 4 | Macor for coil forms | 5
Mech. Eng. | 0.25 |  |  | Wire, etc. | 1
Elec. Eng. |  |  |  | Mounting bracket materials | 0.5
Designer | 0.5 |  |  | Feedthrus and connectors | 2
Diag. Tech. |  | 1 | 1 | Cable | 1
Tech. Shop | 4 | 1
Programmer
Total M&S (k$) |  |  |  |  | 9.5
Magnetics instrumentation (integrators/digitizers, PCs, etc. to support initial set of in-
and ex-vessel sensors) (Marsala)
300 sensors total (ex-vessel: 2 Rowgowski coils, 225 VV flux loops, 6 MC co-wound loops,
6 TF co-wound loops, 5 PF co-wound loops; in vessel: ~56 B-dot probes)
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | 200 Integrator Modules | 200
Physicist | 1 | 2 | 2 | 13 Timing Modules | 8
Mech. Eng. |  |  |  | 13 Integrator Chassis | 8
Elec. Eng. | 5 | 2 | 2 | 13 SADs, VME Crates | 19
Designer |  |  |  | 5 FIMMS, Clock Rec. | 9
Diag. Tech. | 3 | 4 | 2 | 3 PCs | 6
Tech. Shop | 6 | 4 |  | Lemo Cables & Patch Panels | 67
Programmer |  |  |  | Other Electroncis Chassis | 13
|  |  |  | 3 racks | 85.8
Total M&S (k$) |  |  |  |  | 415.8
DNB installation and services (Levinton)
AC power, water, stand, duct, valve, assumes duct pumping by machine turbopumps
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Install AC power & water | 60
Physicist | 2 | 2 | 8 | Bellows, elect. break | 20
Mech. Eng. |  |  |  | Gate valve | 10
Elec. Eng. |  |  |  | 1500 l/s turbopump | 0
Designer | 2 | 1 | 1 | Duct | 10
Diag. Tech. | 4 | 6 | 6 | Stand materials | 5
Elec. Tech |  |  |  | Misc. | 20
Tech. Shop | 4 | 4 | 1 | Rack | 28.6
Programmer |  | 1 | 2
Total M&S (k$) |  |  |  |  | 153.6
Bolometer array (Paul)
16 or 20 channels using IRD AXUV photodiode chip viewing core plasma
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Bolo. parts, incl. shutter | 25
Physicist | 1 | 3 | 6 | Data acq. hardware | 5
Mech. Eng. | 1 |  |  | 1 PC | 2
Elec. Eng. |  | 0.25
Designer | 1
Diag. Tech. |  | 2
Tech. Shop |  | 3
Programmer |  |  | 1
Total M&S (k$) |  |  |  |  | 32
UV spectrometer (Stratton)
NSTX SPRED moved to NCSX, dedicated stand and beamline on NCSX
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Stand materials | 0.5
Physicist | 0.5 | 0.5 | 2 | Bellows, elect. break | 2
Mech. Eng. | 0.5 |  |  | Gate valve | 2
Elec. Eng.
Designer | 1
Diag. Tech. |  | 1
Tech. Shop |  | 1
Programmer |  | 0.5 | 0.5
Total M&S (k$) |  |  |  |  | 4.5
PFC-mounted Langmiur probes (Maingi, Stratton)
10 probes, 5 on inner divertor plate and 5 on outer plate
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | FY09 M&S | 2.5
Physicist | 4 | 3 | 2 | FY10 M&S | 2.5
Mech. Eng. | 0.25 |  |  | FY11 M&S | 10
Elec. Eng. |  | 0.5 |  | (Kepco power supply, BOPs,
Designer | 0.25 |  |  | digitizers, PC, cabling, feedthru)
Diag. Tech. |  | 0.5 | 0.5
Tech. Shop
Programmer
Total M&S (k$) |  |  |  |  | 15
Filtered 2-D cameras (Stratton)
3 cameras, borrow from NSTX.
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | 3 windows | 10
Physicist |  | 1 | 2 | Mounting fixture materials | 1
Mech. Eng. |  | 0.5 |  | 3 shutters | 45
Elec. Eng.
Designer |  | 1
Diag. Tech. |  | 1
Tech. Shop |  | 1
Programmer
Total M&S (k$) |  |  |  |  | 56
Filtered 1-D camera (Stratton)
Borrow from NSTX.
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission
Physicist |  | 0.5 | 1 | Window | 2
Mech. Eng. |  | 0.25 |  | Mounting fixture materials | 0.5
Elec. Eng. |  |  |  | Shutter | 15
Designer |  | 0.5
Diag. Tech. |  | 0.5
Tech. Shop |  | 0.5
Programmer
Total M&S (k$) |  |  |  |  | 17.5
IR-camera (Stratton)
No periscope, standard frame rate. NSTX camera moved to NCSX.
Viewing inner/outer region of a top divertor near high flux expansion region.
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Mounting fixture materials | 0.5
Physicist | 0.5 | 0.5 | 2 | Zinc Selenide window | 5
Mech. Eng. | 0.5 |  |  | Shutter | 10
Elec. Eng. |  |  |  | Magnetic shield materials | 2
Designer | 0.5
Diag. Tech. |  | 0.5
Tech. Shop |  | 0.5
Programmer |  |  | 0.5
Total M&S (k$) |  |  |  |  | 17.5
Filterscopes (Maingi, Stratton)
8 channels: VB, H-alpha, C, O, B, and He and 2 more.
Move detectors/filters/data acq. from NSTX. NCSX to have dedicated fiber runs and telescopes.
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY06 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Window | 2
Physicist | 0.5 | 1 | 1 | Shutter | 15
Mech. Eng. | 0.5 |  |  | Fibers | 2
Elec. Eng. |  |  |  | 6 Telescopes | 6
Designer | 0.5
Diag. Tech. |  | 1 | 1
Tech. Shop |  | 1
Programmer |  |  | 0.5
Total M&S (k$) |  |  |  |  | 25
ECE (Taylor)
16 channel radiometer
|  | Labor (man months) |  | M&S (k$) costs
| Year 1 | Year 2 | Year 3 | Item | FY07 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | 60-90 GHz Frontend Sub-Assembly Components | 15
Physicist | 0.1 | 0.2 | 0.5 | (Including 2 Gunn Osc.,
Mech. Eng. | 0.1 | 0.1 | 0.1 | 4 15 GHz Bandwidth Amplifiers, 2 60db Step Att.,
Elec. Eng. | 0.1 | 0.1 | 0.1 | 2 mixers, 2 high pass filters, 1 notch filter
Designer |  |  |  | and 3dB coupler)
Diag. Tech |  | 0.4 | 0.5
Elec. Tech. | 0.1 | 1 |  | 16 Channel IF & Video Sub-Assembly Components | 20
Tech. Shop |  | 0.5 |  | (Including 16 bandpass filters, 16 Video Detectors
Programmer |  | 0.5 | 0.5 | 16 Video Amplifiers and 2 8-way splitters)
Total Labor | 0.4 | 2.8 | 1.7
|  |  |  | Machine Interface: Window, antenna & waveguide | 5
|  |  |  | 16-Channel Data Acquisition Card, Software & PC | 7
|  |  |  | 1 PC | 2
M&S (k$) |  |  |  |  | 47
Generic Costs:
Cost of installed rack (AC power and isolation trans.; no other cabling-Raki): |  |  |  |  | 28.6
Typical small shutter cost (Labik): |  | 15
PC: | 2
Need to include port extensions or are they budgeted elsewhere?