## Sheet1
Thomson Scattering (LeBlanc & Feder) | [12 empty] | OVERALL | OVERALL
10 channels-expandable to 60 channels, single 50 Hz laser | [12 empty] | TOTAL (k$): | TOTAL (k$):
|  | Labor (man months) |  |  | Labor (k$) |  |  | M&S (k$) costs |  |  |  |  | (w. physicist) | (w. o. physicist)
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Laser | 100 | 135.68
Physicist | 12 | 12 | 12 | 340.9362 | 352.532 | 364.5288 | 1057.997 | 10 poly./det. w. electronics | 250 |  | 345.6
Mech. Eng. | 3 | 3 |  | 85.4397 | 88.3456 |  | 173.7853 | fibers | 50 | 67.84
Elec. Eng. | 2 | 1 |  | 53.1502 | 27.479 |  | 80.6292 | fiber holder | 10 | 13.568
Designer | 3 | 3 |  | 54.9279 | 56.7961 |  | 111.7239 | detection optics | 20 | 27.136
Diag. Tech | 6 | 6 |  | 103.0105 | 106.5141 |  | 209.5245 | laser delivery optics | 20 | 27.136
Elec. Tech. | 3 | 3 |  | 53.3956 | 55.2117 |  | 108.6074 | Support structure in TC | 75 | 101.76
Tech. Shop | 6 | 6 | 3 | 77.2479 | 79.8753 | 41.2967 | 198.4199 | setup laser/detector room | 30 | 40.704
Programmer |  | 3 | 3 |  | 72.7012 | 75.1752 | 147.8764 | opt. table, cover, interlocks | 30 | 40.704
Total Labor | Labor (man months) FY09: 768.108; Labor (k$) FY10: 839.4549; Labor (k$) FY11: 481.0007 | 2088.5637 | laser chiller | 10 | 13.568
[8 empty] | 3 racks | 85.8 | 116.4134
[8 empty] | re-entrant port w. shut. wind. | ?
M&S (k$) | Labor (man months) FY09: 584.5094; Labor (k$) FY10: 345.6; Labor (k$) FY11: 0 |  |  | 680.8 | 584.5094 | 345.6
TOTAL (k$) | Labor (man months) FY09: 1352.6175; Labor (k$) FY10: 1185.0549; Labor (k$) FY11: 481.0007 | [6 empty] | 3018.6731 | 1960.6761
FIR Interferometer/Polarimeter (Brower)
10 channels-expandable
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Thz 3-color laser | 650 | 881.92
Physicist | 6 | 6 | 12 | 170.4681 | 176.266 | 364.5288 | 711.2629 | Detectors | 120 |  | 165.888
Mech. Eng. | 3 | 3 |  | 85.4397 | 88.3456 |  | 173.7853 | Optics | 30 |  | 41.472
Elec. Eng. | FY09: 1; Labor (man months) FY09: 26.5751 | 26.5751 | Tower materials | 30 |  | 41.472
Designer | 3 | 3 |  | 54.9279 | 56.7961 |  | 111.7239 | Rack | 28.6 |  | 39.5366
Diag. Tech. | 6 | 6 |  | 103.0105 | 106.5141 |  | 209.5245 | Misc. | 20 |  | 27.648
Tech. Shop | 3 | 3 |  | 38.624 | 39.9376 |  | 78.5616 | 2 racetrack flanges & windows |  |  | ?
Programmer | Labor (man months) FY11: 3; Labor (k$) FY11: 75.1752 | 75.1752 | 2 shutters | 30 |  | 41.472
Total Labor | Labor (man months) FY09: 479.0452; Labor (k$) FY10: 467.8594; Labor (k$) FY11: 439.704 | 1386.6086
M&S (k$) | Labor (man months) FY09: 881.92; Labor (k$) FY10: 357.4886; Labor (k$) FY11: 0 |  |  | 908.6 | 881.92 | 357.4886
TOTAL (k$) | Labor (man months) FY09: 1360.9652; Labor (k$) FY10: 825.348; Labor (k$) FY11: 439.704 | [6 empty] | 2626.0172 | 1914.7543
CHERS (Bell & Feder)
40-50 channels, single spectrometer with single set of optics viewing DNB
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Spectrometer/detector | 75 | 101.76
Physicist | 9 | 9 | 12 | 255.7021 | 264.399 | 364.5288 | 884.63 | Fibers, Optics, etc. | 50 |  | 69.12
Mech. Eng. | 2 | 2 |  | 56.9598 | 58.8971 |  | 115.8569 | Rack | 28.6 |  | 39.5366
Elec. Eng. | Labor (man months) FY09: 0 | 0 | Misc. | 20 |  | 27.648
Designer | 2 | 2 |  | 36.6186 | 37.864 |  | 74.4826 | re-entrant port w. shut. wind. | ?
Diag. Tech. | 4 | 4 |  | 68.6737 | 71.0094 |  | 139.683
Elec. Tech. | FY09: 1; Labor (man months) FY09: 17.7985
Tech. Shop | 4 | 4 |  | 51.4986 | 53.2502 |  | 104.7488
Programmer | Labor (man months) FY11: 1; Labor (k$) FY11: 25.0584 | 25.0584
Total Labor | Labor (man months) FY09: 487.2513; Labor (k$) FY10: 485.4197; Labor (k$) FY11: 389.5872 | 1344.4597
M&S (k$) | Labor (man months) FY09: 101.76; Labor (k$) FY10: 136.3046; Labor (k$) FY11: 0 |  |  | 173.6 | 101.76 | 136.3046
TOTAL (k$) | Labor (man months) FY09: 589.0113; Labor (k$) FY10: 621.7243; Labor (k$) FY11: 389.5872 | [6 empty] | 1600.3229 | 715.6929
Imaging x-ray cyrstal spectrometer (Bitter)
Spectrometer similar to C-Mod system with 3 PILATUS II detectors
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Detectors | 270 |  | 373.248
Physicist |  | 4 | 12 |  | 117.5107 | 364.5288 |  | Detector mods., cables, etc. | 30 |  | 41.472
Mech. Eng. | Labor (man months) FY10: 1; Labor (k$) FY10: 29.4485 |  | Quartz cyrstal | 2.5 |  | 3.456
Elec. Eng. | [7 empty] | Spectrometer housing | 30 |  | 41.472
Designer | Labor (man months) FY10: 1; Labor (k$) FY10: 18.932 |  | Be window | 15 |  | 20.736
Diag. Tech. |  | 2 | 1 |  | 35.5047 | 18.3565 |  | Rack | 28.6 |  | 39.5366
Elec. Tech.
Tech. Shop
Programmer | Labor (man months) FY10: 1; Labor (k$) FY10: 24.2337
Total Labor | Labor (k$) FY10: 225.6297; Labor (k$) FY11: 382.8853
M&S (k$) | Labor (k$) FY10: 519.9206 |  |  | 376.1 | 0 | 519.9206
TOTAL (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 745.5503; Labor (k$) FY11: 382.8853 | [6 empty] | 1128.4356 | 1128.4356
Soft x-ray array (Tritz)
Single 20 channel ex-vesssel array moved from NSTX; possible in-vessel multi-color array (would require cooling)
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Vacuum hardware | 20 |  | 27.648
Physicist | 0.5 | 3 | 6 | 14.2057 | 88.133 | 182.2644 | 284.6031 | Cables, connectors, misc. | 5 |  | 6.912
Mech. Eng. | Labor (man months) FY10: 1; Labor (man months) FY09: 0; Labor (k$) FY10: 29.4485 | 29.4485 | Rack | 28.6 |  | 39.5366
Elec. Eng. | Labor (k$) FY10: 0; Labor (k$) FY11: 0 | 0 | Filters | 5 |  | 6.912
Designer | Labor (man months) FY10: 0.5; Labor (man months) FY09: 0 | 0
Diag. Tech. |  | 2 | 1 | 0 | 35.5047 | 18.3565 | 53.8611
Tech. Shop | Labor (man months) FY10: 1; Labor (man months) FY09: 0; Labor (k$) FY10: 13.3125 | 13.3125
Programmer
Total Labor | Labor (man months) FY09: 14.2057; Labor (k$) FY10: 166.3988; Labor (k$) FY11: 200.6209 | 381.2253
M&S (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 81.0086; Labor (k$) FY11: 0 |  |  | 58.6 |  | 81.0086
TOTAL (k$) | Labor (man months) FY09: 14.2057; Labor (k$) FY10: 247.4074; Labor (k$) FY11: 200.6209 | [6 empty] | 462.234 | 177.6309
MSE (Levinton)
5 spatial channels viewing DNB, expandable
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | re-entrant port w. shut. wind. | ?
Physicist | 4 | 4 | 9 | 113.6454 | 117.5107 | 273.3966 | 504.5527 | Optics, fiber, filters, det, etc.-1 | 29 | 39.3472
Mech. Eng. | FY09: 3; Labor (man months) FY09: 85.4397 | 85.4397 | Optics, fiber, filters, det, etc.-2 | 80 |  | 110.592
Elec. Eng. | [7 empty] | Optics, fiber, filters, det, etc.-3 | 10 |  |  | 14.08
Designer | 6 | 6 | 2 | 109.8557 | 113.5921 | 39.1526 | 262.6004
Diag. Tech. | 4 | 10 | 6 | 68.6737 | 177.5234 | 110.1388 | 356.3358
Tech. Shop | 3 | 5 | 2 | 38.624 | 66.5627 | 27.5311 | 132.7178
Programmer |  | 2 | 2 |  | 48.4674 | 50.1168 | 98.5842
Total Labor | Labor (man months) FY09: 416.2384; Labor (k$) FY10: 523.6564; Labor (k$) FY11: 500.3359 | 1440.2307
M&S (k$) | Labor (man months) FY09: 39.3472; Labor (k$) FY10: 110.592; Labor (k$) FY11: 14.08 |  |  | 119 | 39.3472 | 110.592 | 14.08
TOTAL (k$) | Labor (man months) FY09: 455.5856; Labor (k$) FY10: 634.2484; Labor (k$) FY11: 514.4159 | [6 empty] | 1604.2499 | 1099.6972
Interferometer (Taylor)
1 mm, Single chord-move NSTX system to NCSX, system repackaged to be portable.
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Viewport & mirror tile | 25 |  | 34.56
Physicist | 1 | 1 | 1 | 28.4113 | 29.3777 | 30.3774 | 88.1664 | Shutter | 28.6 |  | 39.5366
Mech. Eng. | 1 | 1 |  | 28.4799 | 29.4485 |  | 57.9284 | Misc. | 5 |  | 6.912
Elec. Eng.
Designer | FY09: 1; Labor (man months) FY09: 18.3093 | 18.3093
Diag. Tech. |  | 1 | 1 |  | 17.7523 | 18.3565 | 36.1088
Tech. Shop | Labor (man months) FY10: 1; Labor (k$) FY10: 13.3125 | 13.3125
Programmer | Labor (man months) FY11: 1; Labor (k$) FY11: 25.0584 | 25.0584
Total Labor | Labor (man months) FY09: 75.2005; Labor (k$) FY10: 89.8911; Labor (k$) FY11: 73.7923 | 238.8839
M&S (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 81.0086; Labor (k$) FY11: 0 |  |  |  |  | 81.0086
TOTAL (k$) | Labor (man months) FY09: 75.2005; Labor (k$) FY10: 170.8997; Labor (k$) FY11: 73.7923 | [6 empty] | 319.8925 | 231.7261
In-vessel magnetics (Kaita, Guttadora)
~50 sensors including cabling, feedthroughs
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor
Physicist | 1 | 1 | 4 | 28.4113 | 29.3777 | 121.5096 | 179.2986 | Macor for coil forms | 5 | 6.784
Mech. Eng. | FY09: 0.25; Labor (man months) FY09: 7.12 | 7.12 | Wire, etc. | 1 | 1.3568
Elec. Eng. | [7 empty] | Mounting bracket materials | 0.5 | 0.6784
Designer | FY09: 0.5; Labor (man months) FY09: 9.1546 | 9.1546 | Feedthrus and connectors | 2 | 2.7136
Diag. Tech. |  | 1 | 1 |  | 17.7523 | 18.3565 | 36.1088 | Cable | 1 | 1.3568
Tech. Shop | 4 | 1 |  | 51.4986 | 13.3125 |  | 64.8112
Programmer
Total Labor | Labor (man months) FY09: 96.1846; Labor (k$) FY10: 60.4426; Labor (k$) FY11: 139.8661 | 296.4932
M&S (k$) | Labor (man months) FY09: 12.8896; Labor (k$) FY10: 0; Labor (k$) FY11: 0 |  |  | 9.5 | 12.8896
TOTAL (k$) | Labor (man months) FY09: 109.0742; Labor (k$) FY10: 60.4426; Labor (k$) FY11: 139.8661 | [6 empty] | 309.3828 | 130.0842
Magnetics instrumentation (integrators/digitizers, PCs, etc. to support initial set of in- and ex-vessel sensors) (Marsala)
300 sensors total (ex-vessel: 2 Rowgowski coils, 225 VV flux loops, 6 MC co-wound loops, 6 TF co-wound loops, 5 PF co-wound loops; in vessel: ~56 B-dot probes)
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | 200 Integrator Modules | 200 | 271.36
Physicist | 1 | 2 | 2 | 28.4113 | 58.7553 | 60.7548 | 147.9215 | 13 Timing Modules | 8 | 10.8544
Mech. Eng. | [7 empty] | 13 Integrator Chassis | 8 | 10.8544
Elec. Eng. | 5 | 2 | 2 | 132.8756 | 54.958 | 56.8282 | 244.6617 | 13 SADs, VME Crates | 19 | 25.7792
Designer | [7 empty] | 5 FIMMS, Clock Rec. | 9 | 12.2112
Diag. Tech. | 3 | 4 | 2 | 51.5052 | 71.0094 | 36.7129 | 159.2275 | 3 Computers | 10 |  | 13.824
Tech. Shop | 6 | 4 |  | 77.2479 | 53.2502 |  | 130.4981 | Lemo Cables & Patch Panels | 67 |  | 92.6208
Programmer | [7 empty] | Other Electroncis Chassis | 13 |  | 17.9712
Total Labor | Labor (man months) FY09: 290.0401; Labor (k$) FY10: 237.9728; Labor (k$) FY11: 154.2959 | 682.3088 | 3 racks | 85.8 |  | 118.6099
M&S (k$) | Labor (man months) FY09: 331.0592; Labor (k$) FY10: 243.0259; Labor (k$) FY11: 0 |  |  | 419.8 | 331.0592 | 243.0259
TOTAL (k$) | Labor (man months) FY09: 621.0993; Labor (k$) FY10: 480.9988; Labor (k$) FY11: 154.2959 | [6 empty] | 1256.394 | 1108.4725
Terminate ex-vessel magnetics sensors (Labik, Stratton)
286 sensors total (2 Rowgowski coils, 225 VV flux loops, 36 MC co-wound loops, 18 TF co-wound loops, 5 PF co-wound loops)
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Circuit boards, connectors, etc. | 10 | 13.568
Physicist
Mech. Eng. | Labor (man months) FY10: 0.5; Labor (k$) FY10: 14.7243
Elec. Eng.
Designer
Diag. Tech. | 1 | 5 |  | 17.1684 | 88.7617
Tech. Shop | FY09: 2; Labor (man months) FY09: 25.7493
Programmer
Total Labor | Labor (man months) FY09: 42.9177; Labor (k$) FY10: 103.486
M&S (k$) | Labor (man months) FY09: 13.568; Labor (k$) FY10: 0; Labor (k$) FY11: 0 |  |  | 10 | 13.568
TOTAL (k$) | Labor (man months) FY09: 56.4857; Labor (k$) FY10: 103.486 | [6 empty] | 159.9717 | 159.9717
DNB installation and services (Levinton)
AC power, water, stand, duct, valve, assumes duct pumping by machine turbopumps
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Install AC power & water | 60 | 81.408
Physicist | 2 | 2 | 8 | 56.8227 | 58.7553 | 243.0192 | 358.5972 | Bellows, elect. break | 20 |  | 27.648
Mech. Eng. | Labor (man months) FY09: 0; Labor (k$) FY10: 0 | 0 | Gate valve | 10 |  | 13.824
Elec. Eng. | Labor (man months) FY09: 0; Labor (k$) FY10: 0; Labor (k$) FY11: 0 | 0 | 1500 l/s turbopump | 0 |  | 0
Designer | 2 | 1 | 1 | 36.6186 | 18.932 | 19.5763 | 75.1269 | Duct | 10 |  | 13.824
Diag. Tech. | 4 | 6 | 6 | 68.6737 | 106.5141 | 110.1388 |  | Stand materials | 5 | 6.784
Elec. Tech | [7 empty] | Misc. | 20 | 6.784 | 13.824 | 7.04
Tech. Shop | 4 | 4 | 1 | 51.4986 | 53.2502 | 13.7656 | 118.5144 | Rack | 28.6 |  | 39.5366
Programmer |  | 1 | 2 |  | 24.2337 | 50.1168 | 74.3505
Total Labor | Labor (man months) FY09: 213.6136; Labor (k$) FY10: 261.6853; Labor (k$) FY11: 436.6166 | 911.9155
M&S (k$) | Labor (man months) FY09: 94.976; Labor (k$) FY10: 108.6566; Labor (k$) FY11: 7.04 |  |  | 153.6 | 94.976 | 108.6566 | 7.04
TOTAL (k$) | Labor (man months) FY09: 308.5896; Labor (k$) FY10: 370.342; Labor (k$) FY11: 443.6566 | [6 empty] | 1122.5881 | 763.9909
Bolometer array (Paul)
16 or 20 channels using IRD AXUV photodiode chip viewing core plasma
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Bolo. parts, incl. shutter | 25 |  | 34.56
Physicist | 1 | 3 | 6 | 28.4113 | 88.133 | 182.2644 | 298.8088 | Data acq. hardware | 5 |  | 1.3824
Mech. Eng. | FY09: 1; Labor (man months) FY09: 28.4799 | 28.4799
Elec. Eng. | Labor (man months) FY10: 0.25; Labor (k$) FY10: 6.8697 | 6.8697
Designer | FY09: 1; Labor (man months) FY09: 18.3093 | 18.3093
Diag. Tech. | Labor (man months) FY10: 2; Labor (k$) FY10: 35.5047 | 35.5047
Tech. Shop | Labor (man months) FY10: 3; Labor (k$) FY10: 39.9376 | 39.9376
Programmer | Labor (man months) FY11: 1; Labor (k$) FY11: 25.0584 | 25.0584
Total Labor | Labor (man months) FY09: 75.2005; Labor (k$) FY10: 170.4451; Labor (k$) FY11: 207.3228 | 452.9684
M&S (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 35.9424; Labor (k$) FY11: 0 |  |  |  |  | 35.9424
TOTAL (k$) | Labor (man months) FY09: 75.2005; Labor (k$) FY10: 206.3875; Labor (k$) FY11: 207.3228 | [6 empty] | 488.9108 | 190.102
UV spectrometer (Stratton)
NSTX SPRED moved to NCSX, dedicated stand and beamline on NCSX
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Stand materials | 0.5 |  | 0.6912
Physicist | 0.5 | 0.5 | 2 | 14.2057 | 14.6888 | 60.7548 | 89.6493 | Bellows, elect. break | 2 |  | 2.7648
Mech. Eng. | FY09: 0.5; Labor (man months) FY09: 14.2399 | 14.2399 | Gate valve | 2 |  | 2.7648
Elec. Eng.
Designer | FY09: 1; Labor (man months) FY09: 18.3093 | 18.3093
Diag. Tech. | Labor (man months) FY10: 1; Labor (k$) FY10: 17.7523 | 17.7523
Tech. Shop | Labor (man months) FY10: 1; Labor (k$) FY10: 13.3125 | 13.3125
Programmer |  | 0.5 | 0.5 |  | 12.1169 | 12.5292 | 24.6461
Total Labor | Labor (man months) FY09: 46.7549; Labor (k$) FY10: 57.8706; Labor (k$) FY11: 73.284 | 177.9095
M&S (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 6.2208; Labor (k$) FY11: 0 |  |  | 4.5 |  | 6.2208
TOTAL (k$) | Labor (man months) FY09: 46.7549; Labor (k$) FY10: 64.0914; Labor (k$) FY11: 73.284 | [6 empty] | 184.1303 | 94.481
PFC-mounted Langmiur probes (Maingi, Stratton)
10 probes, 5 on inner divertor plate and 5 on outer plate
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | FY09 M&S | 2.5 | 3.392
Physicist | 4 | 3 | 2 | 113.6454 | 88.133 | 60.7548 | 262.5332 | FY10 M&S | 2.5 |  | 3.456
Mech. Eng. | FY09: 0.25; Labor (man months) FY09: 7.12 | 7.12 | FY11 M&S | 10 |  |  | 13.824
Elec. Eng. | Labor (man months) FY10: 0.5; Labor (k$) FY10: 13.7395 | 13.7395 | (Kepco power supply, BOPs,
Designer | FY09: 0.25; Labor (man months) FY09: 4.5773 | 4.5773 | digitizers, PC, cabling, feedthru)
Diag. Tech. |  | 0.5 | 0.5 |  | 8.8762 | 9.1782 | 18.0544
Tech. Shop
Programmer
Total Labor | Labor (man months) FY09: 125.3427; Labor (k$) FY10: 110.7487; Labor (k$) FY11: 69.933 | 306.0244
M&S (k$) | Labor (man months) FY09: 3.392; Labor (k$) FY10: 3.456; Labor (k$) FY11: 13.824 |  |  | 15 | 3.392 | 3.456 | 13.824
TOTAL (k$) | Labor (man months) FY09: 128.7347; Labor (k$) FY10: 114.2047; Labor (k$) FY11: 83.757 | [6 empty] | 326.6964 | 64.1632
Filtered 2-D cameras (Stratton)
3 cameras, borrow from NSTX.
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | 3 windows | 10 |  | 13.824
Physicist |  | 1 | 2 |  | 29.3777 | 60.7548 | 90.1325 | Mounting fixture materials | 1 |  | 1.3824
Mech. Eng. | Labor (man months) FY10: 0.5; Labor (k$) FY10: 14.7243 | 14.7243 | 3 shutters | 45 |  | 62.208
Elec. Eng.
Designer | Labor (man months) FY10: 1; Labor (k$) FY10: 18.932 | 18.932
Diag. Tech. | Labor (man months) FY10: 1; Labor (k$) FY10: 17.7523 | 17.7523
Tech. Shop | Labor (man months) FY10: 1; Labor (k$) FY10: 13.3125 | 13.3125
Programmer
Total Labor | Labor (man months) FY09: 0; Labor (k$) FY10: 94.0988; Labor (k$) FY11: 60.7548 | 154.8536
M&S (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 77.4144; Labor (k$) FY11: 0 |  |  | 56 |  | 77.4144
TOTAL (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 171.5132; Labor (k$) FY11: 60.7548 | [6 empty] | 232.268 | 142.1356
Filtered 1-D camera (Stratton)
Borrow from NSTX.
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor
Physicist |  | 0.5 | 1 |  | 14.6888 | 30.3774 | 45.0662 | Window | 2 |  | 2.7648
Mech. Eng. | Labor (man months) FY10: 0.25; Labor (k$) FY10: 7.3621 | 7.3621 | Mounting fixture materials | 0.5 |  | 0.6912
Elec. Eng. | [7 empty] | Shutter | 15 |  | 20.736
Designer | Labor (man months) FY10: 0.5; Labor (k$) FY10: 9.466 | 9.466
Diag. Tech. | Labor (man months) FY10: 0.5; Labor (k$) FY10: 8.8762 | 8.8762
Tech. Shop | Labor (man months) FY10: 0.5; Labor (k$) FY10: 6.6563 | 6.6563
Programmer
Total Labor | Labor (man months) FY09: 0; Labor (k$) FY10: 47.0494; Labor (k$) FY11: 30.3774 | 77.4268
M&S (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 24.192; Labor (k$) FY11: 0 |  |  | 17.5 |  | 24.192
TOTAL (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 71.2414; Labor (k$) FY11: 30.3774 | [6 empty] | 101.6188 | 56.5526
IR-camera (Stratton)
No periscope, standard frame rate. NSTX camera moved to NCSX. Viewing inner/outer region of a top divertor near high flux expansion region.
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Mounting fixture materials | 0.5 |  | 0.6912
Physicist | 0.5 | 0.5 | 2 | 14.2057 | 14.6888 | 60.7548 | 89.6493 | Zinc Selenide window | 5 |  | 6.912
Mech. Eng. | FY09: 0.5; Labor (man months) FY09: 14.2399 | 14.2399 | Shutter | 10 |  | 13.824
Elec. Eng. | [7 empty] | Magnetic shield materials | 2 |  | 2.7648
Designer | FY09: 0.5; Labor (man months) FY09: 9.1546 | 9.1546
Diag. Tech. | Labor (man months) FY10: 0.5; Labor (k$) FY10: 8.8762 | 8.8762
Tech. Shop | Labor (man months) FY10: 0.5; Labor (k$) FY10: 6.6563 | 6.6563
Programmer | Labor (man months) FY11: 0.5; Labor (k$) FY11: 12.5292 | 12.5292
Total Labor | Labor (man months) FY09: 37.6003; Labor (k$) FY10: 30.2213; Labor (k$) FY11: 73.284 | 141.1055
M&S (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 24.192; Labor (k$) FY11: 0 |  |  |  |  | 24.192
TOTAL (k$) | Labor (man months) FY09: 37.6003; Labor (k$) FY10: 54.4133; Labor (k$) FY11: 73.284 | [6 empty] | 165.2975 | 75.6482
Filterscopes (Maingi, Stratton)
8 channels: VB, H-alpha, C, O, B, and He and two more. Move detectors/filters/data acq. from NSTX. NCSX to have dedicated fiber runs and telescopes.
| Labor (man months) FY10: Labor (man months); Labor (k$) FY10: Labor (k$) |  | M&S (k$) costs
| FY09 | FY10 | FY11 | FY09 | FY10 | FY11 |  | Item | FY06 cost (k$) | FY09 cost(k$) | FY10 cost (k$) | FY11 cost (k$)
Labor type | Design/Fab. | Fab./Install | Commission | Design/Fab. | Fab./Install | Commission | Total Labor | Window | 2 |  | 2.7648
Physicist | 0.5 | 1 | 1 | 14.2057 | 29.3777 | 30.3774 | 73.9607 | Shutter | 15 |  | 20.736
Mech. Eng. | FY09: 0.5; Labor (man months) FY09: 14.2399 | 14.2399 | Fibers | 2 |  | 2.7648
Elec. Eng. | [7 empty] | 6 Telescopes | 6 |  | 8.2944
Designer | FY09: 0.5; Labor (man months) FY09: 9.1546 | 9.1546
Diag. Tech. |  | 1 | 1 |  | 17.7523 | 18.3565 | 36.1088
Tech. Shop | Labor (man months) FY10: 1; Labor (k$) FY10: 13.3125 | 13.3125
Programmer | Labor (man months) FY11: 0.5; Labor (k$) FY11: 12.5292
Total Labor | Labor (man months) FY09: 37.6003; Labor (k$) FY10: 60.4426; Labor (k$) FY11: 61.2631 | 159.3059
M&S (k$) | Labor (man months) FY09: 0; Labor (k$) FY10: 34.56; Labor (k$) FY11: 0 |  |  | 25 |  | 34.56
TOTAL (k$) | Labor (man months) FY09: 37.6003; Labor (k$) FY10: 95.0026; Labor (k$) FY11: 61.2631 | [6 empty] | 193.8659 | 119.9051
[11 empty] | GRAND TOTAL (K$) |  | 15300.9496 | 10134.12
Labor rates (per man month):
|  | FY06 | FY09 | FY10 | FY11
Phys. | R**RH | 25.7 | 28.4113 | 29.3777 | 30.3774
Elec. Eng. | EE*EM | 24.039 | 26.5751 | 27.479 | 28.4141
Mech Eng | EAD*EM | 25.762 | 28.4799 | 29.4485 | 30.4507
Designer | EAD*SB | 16.562 | 18.3093 | 18.932 | 19.5763
Diag. Tech. | EM**SB | 15.53 | 17.1684 | 17.7523 | 18.3565
Tech Shop | EMT*TB | 11.646 | 12.8747 | 13.3125 | 13.7656
Sr. Elec. Tech. | EE**SB | 16.1 | 17.7985 | 18.4039 | 19.0302
Programmer | EC**EM | 21.2 | 23.4366 | 24.2337 | 25.0584
Assumes 3.4% annual inflation
M&S inflation factors:
|  | FY06 | FY09 | FY10 | FY11
|  | 1 | 1.06 | 1.08 | 1.1
Assumes 2.0% annual inflation
M&S overhead (MHX): factor: | Labor (man months) FY11: 1.28
Extrapolated FY09 and FY10 M&S costs include inflation and MHX overhead
Generic Costs:
Cost of installed rack (AC power and isolation trans.; no other cabling-Raki): | Labor (k$) FY10: 28.6
Typical small shutter cost (Labik): | Labor (man months) FY10: 15
Need to include port extensions
Need to budget termination of VV and coil co-wound loops