## Baseline
Baseline Half Period Assembly Outline
|  |  | $ M&S | #men | days | man-days
1 | Mount MCWF A on assembly stand. |  |  | 4 | 1
1 | Determine location with laser tracker. |  |  | 2 | 1 | 2
1 | [5 empty] | 0
1 | Inventory pre-fabricated shims (insulated on top & bottom) |  | 5000 |  |  | 0
1 |  | Each shim 4-5 bolts long |  |  |  | 0
1 |  | G-11 / steel / G-11 layup |  |  |  | 0
1 |  | Steel thickness can be pre-determined for a particular coil (based on meas. Data) |  |  |  | 0
1 | Install 3 point spherical balls into their locations. |  | 1000 | 1 | 1 | 1
| Use laser tracker to establish MCWF seat on B |  |  | 1 | 1 | 1
| Hone the seats as required (this applies to Type C 1-3 only - the others only have a counterbore to accept a socket insert piece)). |  |  | 1 | 1 | 1
1 | Use laser tracker or romer arm to set ball locations per CAD space. |  |  | 1 | 1 | 1
1 | Check that MCWF A has not moved and balls are correctly located. |  |  | 1 | 1 | 1
1 | Lower MCWF B onto A - visually guide into positon usinlg Hydroset. |  |  |  |  | 0
1 |  | Lateral positioning taken care of by spherical ball & seat. |  |  |  | 0
1 | Check fiducials on A - re-set to re-establish default coordinate system due to added weight deflecting things. |  |  | 2 | 2 | 4
1 | Check fiducials on A & B - hopefully positions will be right on; if not, determine correction required, adjust 3 points, and re-shim. |  |  | 1 | 1 | 1
1 | Tom Brown to review data & approve or set corrective action. |  |  | 1 | 1 | 1
2 | Check each shim location - verify that shim thicknesses are correct. If off by more than 0.005? Grind shim as req'd. or use peelable shims |  |  | 2 | 5 | 10
2a |  | Most likely grind the steel shim portion which will be ~3/8" thick |  |  |  | 0
3 | Separate A and B |  |  |  |  | 0
4 | Stud weld shear pin studs using a template. |  | 3000 | 4 | 4 | 16
4a |  | Clean weld splatter; Snap studs or grind to correct height. Install sleeve on studs? |  | 2 | 2 | 4
4b |  | Install G-11 insulators; Check fit-up with shim plate |  | 2 | 1 | 2
5 | Place std. shim packs in correct locations; re-position A over B with the 3 tooling balls. |  |  | 2 | 1 | 2
5a |  | Spring loaded balls used for this step ; |  |  |  | 0
5b |  | shims set Z location |  |  |  | 0
6 | Check for correct position of A and B |  |  | 2 | 1 | 2
| Install wing bladders |  | 1000 | 2 | 1 | 2
7 | Inject Stycast 2850 into shear plate holes (this assumes communication holes between shim plate holes and fill tubes) DO SIMLTANEOUS INJECTION OF A-B B-C |  | 200 | 3 | 1 | 3
7a |  | Alternate: Trowel into shims before coils are mated together. |  |  |  | 0
| Install the PJ bushings using his technique. | cost in LD's budget |  | 2 | 4 | 8
| Install studs / bolts; tighten in sequence. |  |  | 2 | 0.5 | 1
| Check MCWF positions again. |  |  | 2 | 1 | 2
| Allow 48 hrs. for Stycast to cure. |  |  | 0 | 2 | 0
| Repeat the process for B-C |  | 10200 |  |  | 65 | per joint
All tapped holes in B-C connection.
|  |  | Total Labor = |  |  | 795600
[5 empty] | M&S | 183600
[5 empty] | Grand total | 979200

## no inner shim
Baseline Half Period Assembly Outline
|  |  | $ M&S | #men | days | man-days
1 | Mount MCWF A on assembly stand. |  |  | 4 | 1
1 | Determine location with laser tracker. |  |  | 2 | 1 | 2
1 | [5 empty] | 0
1 | Inventory pre-fabricated shims (insulated on top & bottom) |  | 5000 |  |  | 0
1 |  | Each shim 4-5 bolts long |  |  |  | 0
1 |  | G-11 / steel / G-11 layup |  |  |  | 0
1 |  | Steel thickness can be pre-determined for a particular coil (based on meas. Data) |  |  |  | 0
1 | Install 3 point spherical balls into their locations. |  | 1000 | 1 | 1 | 1
| Use laser tracker to establish MCWF seat on B |  |  | 1 | 1 | 1
| Hone the seats as required (this applies to Type C 1-3 only - the others only have a counterbore to accept a socket insert piece)). |  |  | 1 | 1 | 1
1 | Use laser tracker or romer arm to set ball locations per CAD space. |  |  | 1 | 1 | 1
1 | Check that MCWF A has not moved and balls are correctly located. |  |  | 1 | 1 | 1
1 | Lower MCWF B onto A - visually guide into positon usinlg Hydroset. |  |  |  |  | 0
1 |  | Lateral positioning taken care of by spherical ball & seat. |  |  |  | 0
1 | Check fiducials on A - re-set to re-establish default coordinate system due to added weight deflecting things. |  |  | 2 | 2 | 4
1 | Check fiducials on A & B - hopefully positions will be right on; if not, determine correction required, adjust 3 points, and re-shim. |  |  | 1 | 1 | 1
1 | Tom Brown to review data & approve or set corrective action. |  |  | 1 | 1 | 1
2 | Check each shim location - verify that shim thicknesses are correct. If off by more than 0.005? Grind shim as req'd. or use peelable shims |  |  | 2 | 5 | 10
2a |  | Most likely grind the steel shim portion which will be ~3/8" thick |  |  |  | 0
3 | Separate A and B |  |  |  |  | 0
4 | Stud weld shear pin studs using a template. |  | 0 | 0 | 0 | 0
4a |  | Clean weld splatter; Snap studs or grind to correct height. Install sleeve on studs? |  | 0 | 0 | 0
4b |  | Install G-11 insulators; Check fit-up with shim plate |  | 0 | 0 | 0
5 | Place std. shim packs in correct locations; re-position A over B with the 3 tooling balls. |  |  | 2 | 1 | 2
5a |  | Spring loaded balls used for this step ; |  |  |  | 0
5b |  | shims set Z location |  |  |  | 0
6 | Check for correct position of A and B |  |  | 2 | 1 | 2
| Install wing bladders |  | 1000 | 2 | 1 | 2
7 | Inject Stycast 2850 into shear plate holes (this assumes communication holes between shim plate holes and fill tubes) DO SIMLTANEOUS INJECTION OF A-B B-C |  | 0 | 0 | 0 | 0
7a |  | Alternate: Trowel into shims before coils are mated together. |  |  |  | 0
| Install the PJ bushings using his technique. | cost in LD's budget |  | 2 | 4 | 8
| Install studs / bolts; tighten in sequence. |  |  | 2 | 0.5 | 1
| Check MCWF positions again. |  |  | 2 | 1 | 2
| Allow 48 hrs. for Stycast to cure. |  |  | 0 | 2 | 0
| Repeat the process for B-C |  | 7000 |  |  | 40 | per joint
All tapped holes in B-C connection.
|  |  | Total Labor = |  |  | 489600
[5 empty] | M&S | 126000
[5 empty] | Grand total | 615600 |  | 363600

## Optimized
Baseline Half Period Assembly Outline
|  |  | $ M&S | #men | days | man-days
1 | Mount MCWF A on assembly stand. |  |  | 4 | 1
1 | Determine location with laser tracker. |  |  | 2 | 1 | 2
1 | [5 empty] | 0
1 | Inventory pre-fabricated shims (insulated on top & bottom) |  | 5000 |  |  | 0
1 |  | Each shim 4-5 bolts long |  |  |  | 0
1 |  | G-11 / steel / G-11 layup |  |  |  | 0
1 |  | Steel thickness can be pre-determined for a particular coil (based on meas. Data) |  |  |  | 0
1 | Install 3 point spherical balls into their locations. |  | 1000 | 1 | 1 | 1
| Use laser tracker to establish MCWF seat on B |  |  | 1 | 1 | 1
| Hone the seats as required (this applies to Type C 1-3 only - the others only have a counterbore to accept a socket insert piece)). |  |  | 1 | 1 | 1
1 | Use laser tracker or romer arm to set ball locations per CAD space. |  |  | 1 | 1 | 1
1 | Check that MCWF A has not moved and balls are correctly located. |  |  | 1 | 1 | 1
1 | Lower MCWF B onto A - visually guide into positon usinlg Hydroset. |  |  |  |  | 0
1 |  | Lateral positioning taken care of by spherical ball & seat. |  |  |  | 0
1 | Check fiducials on A - re-set to re-establish default coordinate system due to added weight deflecting things. |  |  | 2 | 1 | 2
1 | Check fiducials on A & B - hopefully positions will be right on; if not, determine correction required, adjust 3 points, and re-shim. |  |  | 1 | 1 | 1
1 | Tom Brown to review data & approve or set corrective action. |  |  | 1 | 1 | 1
2 | Check each shim location - verify that shim thicknesses are correct. If off by more than 0.005? Grind shim as req'd. or use peelable shims |  |  | 2 | 5 | 10
2a |  | Most likely grind the steel shim portion which will be ~3/8" thick |  |  |  | 0
3 | Separate A and B |  |  |  |  | 0
4 | Stud weld shear pin studs using a template. |  | 0 | 0 | 0 | 0
4a |  | Clean weld splatter; Snap studs or grind to correct height. Install sleeve on studs? |  | 0 | 0 | 0
4b |  | Install G-11 insulators; Check fit-up with shim plate |  | 0 | 0 | 0
5 | Place std. shim packs in correct locations; re-position A over B with the 3 tooling balls. |  |  | 2 | 1 | 2
5a |  | Spring loaded balls used for this step ; |  |  |  | 0
5b |  | shims set Z location |  |  |  | 0
6 | Check for correct position of A and B |  |  | 2 | 1 | 2
| Install wing bladders |  | 1000 | 2 | 1 | 2
7 | Inject Stycast 2850 into shear plate holes (this assumes communication holes between shim plate holes and fill tubes) DO SIMLTANEOUS INJECTION OF A-B B-C |  | 0 | 0 | 0 | 0
7 |  | Alternate: Trowel into shims before coils are mated together. |  |  |  | 0
7 | Install the PJ bushings using his technique. | cost in LD's budget |  | 2 | 4 | 8
7 | Install studs / bolts; tighten in sequence. |  |  | 2 | 0.5 | 1
7 | Check MCWF positions again. |  |  | 2 | 1 | 2
7 | Allow 48 hrs. for Stycast to cure. |  |  | 0 | 0 | 0
7 | Repeat the process for B-C | All tapped holes in B-C connection. | 7000 | 29 | 23.5 | 38 | per joint
7
7
7 |  |  | Total Labor = |  |  | 465120
7 |  |  |  |  | M&S | 126000
7 |  |  |  |  | Grand total | 591120 |  | 388080
7
7

## Combined
| Baseline Half Period Assembly Outline | [6 empty] | No Inner Shim Assembly |  |  |  | Optimized Assembly |  |  |  | No ball-socket Assembly
|  |  | $ M&S | #men | days | man-days |  | $ M&S | #men | days | man-days | $ M&S | #men | days | man-days | $ M&S | #men | days | man-days
1 | Mount MCWF A on assembly stand. |  |  | 4 | 1 |  |  |  | 4 | 1 |  |  | 4 | 1 |  |  | 4 | 1
1 | Determine location with laser tracker. |  |  | 2 | 1 | 2 |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
1 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
1 | Inventory pre-fabricated shims (insulated on top & bottom) |  | 5000 |  |  | 0 |  | 5000 |  |  | 0 | 5000 |  |  | 0 | 5000 |  |  | 0
1 |  | Each shim 4-5 bolts long |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
1 |  | G-11 / steel / G-11 layup |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
1 |  | Steel thickness can be pre-determined for a particular coil (based on meas. Data) |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
1 | Install 3 point spherical balls into their locations. |  | 1000 | 1 | 1 | 1 |  | 1000 | 1 | 1 | 1 | 1000 | 1 | 1 | 1 | 1000 | X | X | X
| Use laser tracker to establish MCWF seat on B |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | X | X | X
| Hone the seats as required (this applies to Type C 1-3 only - the others only have a counterbore to accept a socket insert piece)). |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | X | X | X
1 | Use laser tracker or romer arm to set ball locations per CAD space. |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | X | X | X
1 | Check that MCWF A has not moved and balls are correctly located. |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1
1 | Lower MCWF B onto A - visually guide into positon usinlg Hydroset. |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
1 |  | Lateral positioning taken care of by spherical ball & seat. |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  | X | X | X
1 | Check fiducials on A - re-set to re-establish default coordinate system due to added weight deflecting things. |  |  | 2 | 2 | 4 |  |  | 2 | 2 | 4 |  | 2 | 1 | 2 |  | 2 | 1 | 2
1 | Check fiducials on A & B - hopefully positions will be right on; if not, determine correction required, adjust 3 points, and re-shim. |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1
1 | Tom Brown to review data & approve or set corrective action. |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1
2 | Check each shim location - verify that shim thicknesses are correct. If off by more than 0.005? Grind shim as req'd. or use peelable shims |  |  | 2 | 5 | 10 |  |  | 2 | 5 | 10 |  | 2 | 5 | 10 |  | 2 | 5 | 10
2a |  | Most likely grind the steel shim portion which will be ~3/8" thick |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
3 | Separate A and B |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
4 | Stud weld shear pin studs using a template. |  | 3000 | 4 | 4 | 16 |  | X | X | X | X | X | X | X | X | X | X | X | X
4a |  | Clean weld splatter; Snap studs or grind to correct height. Install sleeve on studs? |  | 2 | 2 | 4 |  |  | X | X | X |  | X | X | X |  | X | X | X
4b |  | Install G-11 insulators; Check fit-up with shim plate |  | 2 | 1 | 2 |  |  | X | X | X |  | X | X | X |  | X | X | X
5 | Place std. shim packs in correct locations; re-position A over B with the 3 tooling balls. |  |  | 2 | 1 | 2 |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
5a |  | Spring loaded balls used for this step ; |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
5b |  | shims set Z location |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
6 | Check for correct position of A and B |  |  | 2 | 1 | 2 |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
| Install wing bladders |  | 1000 | 2 | 1 | 2 |  | 1000 | 2 | 1 | 2 | 1000 | 2 | 1 | 2 | 1000 | 2 | 1 | 2
7 | Inject Stycast 2850 into shear plate holes (this assumes communication holes between shim plate holes and fill tubes) DO SIMLTANEOUS INJECTION OF A-B B-C |  | 200 | 3 | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7a |  | Alternate: Trowel into shims before coils are mated together. |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Install the PJ bushings using his technique. | cost in LD's budget |  | 2 | 4 | 8 |  |  | 2 | 4 | 8 |  | 2 | 4 | 8 |  | 2 | 4 | 8
| Install studs / bolts; tighten in sequence. |  |  | 2 | 0.5 | 1 |  |  | 2 | 0.5 | 1 |  | 2 | 0.5 | 1 |  | 2 | 0.5 | 1
| Check MCWF positions again. |  |  | 2 | 1 | 2 |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
| Allow 48 hrs. for Stycast to cure. |  |  | 0 | 2 | 0 |  |  | 0 | 2 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| Repeat the process for B-C |  | 10200 |  |  | 65 | per joint | 7000 |  |  | 40 | 7000 | 29 | 23.5 | 38 | 7000 | 25 | 19.5 | 34
All tapped holes in B-C connection.
|  |  | Total Labor = |  |  | 795600 |  | Total Labor = |  |  | 489600 | Total Labor = |  |  | 465120 | Total Labor = |  |  | 416160
[5 empty] | M&S | 183600 |  |  |  | M&S | 126000 |  |  | M&S | 126000 |  |  | M&S | 126000
[5 empty] | Grand total | 979200 |  |  |  | Grand total | 615600 |  |  | Grand total | 591120 |  |  | Grand total | 542160