## P3
ACT ID | DESC | 2OCT FY07 | 9OCT FY07 | 16OCT FY07 | 23OCT FY07 | 30OCT FY07 | 6NOV FY07 | 13NOV FY07 | 20NOV FY07 | 27NOV FY07 | 4DEC FY07 | 11DEC FY07 | 18DEC FY07 | 25DEC FY07 | 1JAN FY07 | 8JAN FY07 | 15JAN FY07 | 22JAN FY07 | 29JAN FY07 | 5FEB FY07 | 12FEB FY07 | 19FEB FY07 | 26FEB FY07 | 5MAR FY07 | 12MAR FY07 | 19MAR FY07 | 26MAR FY07 | 2APR FY07 | 9APR FY07 | 16APR FY07 | 23APR FY07 | 30APR FY07 | 7MAY FY07 | 14MAY FY07 | 21MAY FY07 | 28MAY FY07 | 4JUN FY07 | 11JUN FY07 | 18JUN FY07 | 25JUN FY07 | 2JUL FY07 | 9JUL FY07 | 16JUL FY07 | 23JUL FY07 | 30JUL FY07 | 6AUG FY07 | 13AUG FY07 | 20AUG FY07 | 27AUG FY07 | 3SEP FY07 | 10SEP FY07 | 17SEP FY07 | 24SEP FY07 | 1OCT FY08 | 8OCT FY08 | 15OCT FY08 | 22OCT FY08 | 29OCT FY08 | 5NOV FY08 | 12NOV FY08 | 19NOV FY08 | 26NOV FY08 | 3DEC FY08 | 10DEC FY08 | 17DEC FY08 | 24DEC FY08 | 31DEC FY08 | 7JAN FY08 | 14JAN FY08 | 21JAN FY08 | 28JAN FY08 | 4FEB FY08 | 11FEB FY08 | 18FEB FY08 | 25FEB FY08 | 3MAR FY08 | 10MAR FY08 | 17MAR FY08 | 24MAR FY08 | 31MAR FY08 | 7APR FY08 | 14APR FY08 | 21APR FY08 | 28APR FY08 | 5MAY FY08 | 12MAY FY08 | 19MAY FY08
| Metrology Utilization % | 0.5 | 0.8 | 0 | 0.5 | 0.8 | 0.8 | 0.8 | 0.5 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0.2 | 0.6 | 1 | 1 | 1 | 1 | 1 | 0.4 | 1 | 1 | 1 | 1 | 1 | 1.4 | 0.4 | 0.4 | 1 | 0.8 | 0.8 | 0.8 | 0.8 | 0.3 | 0.5 | 1.3 | 1.5 | 1.5 | 1.2 | 1.5 | 1.1 | 1.3 | 0.9 | 0.7 | 1.5 | 1.7 | 1.8 | 1.6 | 1.5 | 1.8 | 2.1 | 1.6 | 1.4 | 0.6 | 0.4 | 0.4 | 1 | 1.4 | 1.6 | 1.5 | 2.6 | 2.2 | 2.2 | 0 | 2 | 2.6 | 1.8 | 1.5 | 1.5 | 1.6 | 1.4 | 1.2 | 0.8 | 1 | 1.4 | 1.5 | 1.9 | 1.1 | 0.1 | 0.3 | 0.2 | 0.2 | 0.8 | 1.7 | 1.2
S1P1-101 | Receive VV and inspect
S1P1-101.1 | metrology setup training and calibration
S1P1-101A | Prep for mounting on fixture Instl flanges
S1P1-102 | Mount VV on VV Prep fixture (top side up)
S1P1-103 | Establish metrology setting; align VV base
S1P1-103.1 | Layout diagnostic&coolant paths on vsl w/templt
S1P1-104 | Install heater tape on vertical ports | 0.5 | 0.2
S1P1-105 | Verify installation of heater |  | 0.6
S1P1-105.1 | Check port weld fit-up
S1P1-106 | Attach studs for coolant lines
S1P1-107 | Install random magnetic diagnostic sensors |  |  |  | 0.5 | 0.8 | 0.8 | 0.8 | 0.5 | 0.8 | 0.6
S1P1-107.1 | Loop termination & verification
S1P1-107.2 | Install precision magnetic diagnostic sensors | [14 empty] | 0.6 | 1 | 1 | 1 | 1 | 1 | 0.4
S1P1-108 | Install cooling/htg lines to vac vsl
S1P1-109 | Verify Instl of H/C lines headers manifolds | [26 empty] | 0.8 | 0.2
S1P1-110 | Install local I&C (incl thermocouples)
S1P1-111 | Verify installation of local I&C | [28 empty] | 0.4 | 0.2
S1P1-112 | Final Scan | [29 empty] | 0.8 | 0.2
S1P1-116 | Prepare and transfer completed VV to holding are
S1P2-101 | Receive VV and inspect
S1P2-101A | Prep for mounting on fixture Instl flanges | [9 empty] | 0.2 | 0.8
S1P2-102 | Mount VV on VV Prep fixture (top side up)
S1P2-103 | Establish metrology setting; align VV base | [11 empty] | 0.6
S1P2-103.1 | Layout diagnostic&coolant paths on vessel | [21 empty] | 1 | 1 | 1 | 1 | 1 | 0.2
S1P2-104 | Install heater tape on vertical ports | [26 empty] | 0.4
S1P2-105 | Verify installation of heater | [27 empty] | 0.2
S1P2-105.1 | Check port weld fit-up
S1P2-106 | Attach studs forcoolant lines
S1P2-107 | Wind magnetic diagnostic sensors | [30 empty] | 0.6 | 0.8 | 0.8 | 0.8 | 0.2
S1P2-107.1 | Loop termination & verification
S1P2-108 | Install cooling/htg lines to vac vsl
S1P2-109 | Verify Instl of H/C lines headers manifolds | [42 empty] | 0.6 | 0.4
S1P2-110 | Install local I&C (incl thermocouples)
S1P2-111 | Verify installation of local I&C | [44 empty] | 0.2 | 0.4
S1P2-112 | Final Scan | [46 empty] | 0.6 | 0.4
S1P2-116 | Prepare and transfer completed VV to holding are
S1P3-103.2 | Perform full machine best fit | [11 empty] | 0.2 |  | 0.2
S1P3-101 | Receive VV and inspect
S1P3-101A | Prep for mounting on fixture Instl flanges
S1P3-102 | Mount VV on VV Prep fixture (top side up)
S1P3-103 | Establish metrology setting; align VV base
S1P3-103.1 | Layout diagnostic&coolant paths on vessel | [36 empty] | 0.8 | 1 | 1 | 0.8 | 1 | 0.4
S1P3-104 | Install heater tape on vertical ports | [41 empty] | 0.3 | 0.1
S1P3-105 | Verify installation of heater | [42 empty] | 0.2
S1P3-105.1 | Check port weld fit-up
S1P3-106 | Attach studs forcoolant lines
S1P3-107 | Wind magnetic diagnostic sensors | [48 empty] | 0.8 | 1 | 1 | 1 | 0.2
S1P3-107.1 | Loop termination & verification
S1P3-108 | Install cooling/htg lines to vac vsl
S1P3-109 | Verify Instl of H/C lines headers manifolds | [60 empty] | 0.6 | 0.4
S1P3-110 | Install local I&C (incl thermocouples)
S1P3-111 | Verify installation of local I&C | [65 empty] | 0.6
S1P3-112 | Final Scan | [66 empty] | 1
S1P3-116 | Prepare and transfer completed VV to holding are
S1SP-101 | Attachdiagnostics studs and coolant lines
S2P1-001 | Pre-fit C2-C3 (no re-work)
S2P1-003 | Pre-fit C1-C5
S2P1-005 | Pre-fit A1-A2
S2P1-007 | Pre-fit C6-C4
S2P1-010 | Test out equipt & procedures
S2P1-012 | Fit C1-B1
S2P1-014 | Fit B1-A1
S2P1-016 | Fit A2-B2
S2P1-018 | Fit B2-C2
S2P1-100 | Assemble/Align Mod-Coils A1/B1/C1 | [34 empty] | 0.1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.5
S2P1-200 | Assemble/Align Mod-Coils A2/B2/C2 | [41 empty] | 0.4 | 0.4 | 0.4 | 0.4
S2P1-201 | Assemble/Disassemble abc1 - abc2 | [45 empty] | 1 | 1 | 1
S2P2-100 | Assemble/Align Mod-Coils A3/B3/C3 | [48 empty] | 0.3 | 0.4 | 0.4 | 0.1
S2P2-200 | Assemble/Align Mod-Coils A4/B4/C4 | [52 empty] | 0.4 | 0.4 | 0.4
S2P2-201 | Assemble/Disassemble abc3 - abc4 | [55 empty] | 0.4 | 0.4 | 0.4
S2P3-100 | Assemble/Align Mod-Coils A5/B5/C5 | [58 empty] | 0.4 | 0.4 | 0.2 | 0.2
S2P3-200 | Assemble/Align Mod-Coils A6/B6/C6 | [65 empty] | 0.1 | 0.4 | 0.4 | 0.3
S2P3-201 | Assemble/Disassemble abc5 - abc6 | [68 empty] | 0.1 | 0.4 | 0.4 | 0.3
S3P1-001 | Test out station 3 equipment and procedures | [43 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0
S3P1-101 | VV to MC turning fixt base; metr check | [47 empty] | 0.4
S3P1-101.1 | Attach local protective strips to VV&locate sens
S3P1-102 | Mount MC on crane; perform metr checks | [48 empty] | 0.4
S3P1-103 | Rotate right MC to stand-off position&chk | [48 empty] | 0.1 | 0.1
S3P1-104 | Transfer load to sprt sys and recheck position
S3P1-105 | Move MC turning fixt; mount MC on crane
S3P1-106 | Rotate left MC to stand-off position and check p
S3P1-107 | Move left & right MC to final
S3P1-108 | Pot 3 packs together | [51 empty] | 0.4 | 1 | 0.6
S3P1-109 | Bolt together at flange interface. | [50 empty] | 0.4 | 0.6
S3P1-110 | Perform final metrology position check | [53 empty] | 0.4 | 0.2
S3P1-110.1 | Remove temp interference strips&sensors
S3P1-111 | Secure VV to MC's using temporary supports.
S3P1-112 | Prep& xfr completed assembly to Stage 4 area
S3P2-101 | Mount VV to MC turning fixt base; metr check | [57 empty] | 0.4
S3P2-101.1 | Attach local protective strips to VV&locate sens
S3P2-102 | Mount MC on crane; perform metr checks | [58 empty] | 0.4
S3P2-103 | Rotate right MC to stand-off position&chk | [58 empty] | 0 | 0
S3P2-104 | Transfer load to supt sys and recheck position
S3P2-105 | Move MC turning fixt; mount MC on crane
S3P2-106 | Rotate left MC to stand-off position and check p
S3P2-107 | Move left & right MC to final
S3P2-108 | Pot 3 packs together | [62 empty] | 0.8 | 1 |  | 0.2
S3P2-109 | Bolt together at flange interface. | [61 empty] | 0.8 | 0.2
S3P2-110 | Perform final metrology position check | [65 empty] | 0.4 | 0.2
S3P2-110.1 | Remove temp interference strips&sensors
S3P2-111 | Secure VV to MC's using temporary supports.
S3P2-112 | Prep& xfr completed assembly to Stage 4 area
S3P3-101 | Mount VV to MC turning fixt base; metr check | [67 empty] | 0.4
S3P3-101.1 | Attach local protective strips to VV&locate sens
S3P3-102 | Mount MC on crane; perform metr checks | [71 empty] | 0.2 | 0.2
S3P3-103 | Rotate right MC to stand-off position&chk | [72 empty] | 0.1
S3P3-104 | Transfer load to supt sysand recheck position
S3P3-105 | Move MC turning fixt; mount MC on crane
S3P3-106 | Rotate left MC to stand-off position and check p
S3P3-107 | Move left & right MC to final
S3P3-108 | Pot 3 packs together | [75 empty] | 0.8 | 1 | 0.2
S3P3-109 | Bolt together at flange interface. | [74 empty] | 0.8 | 0.2
S3P3-110 | Perform final metrology position check | [77 empty] | 0.6
S3P3-110.1 | Remove temp interference strips&sensors
S3P3-111 | Secure VV to MC's using temporary supports.
S3P3-112 | Prep& xfr completed assembly to Stage 4 area
184-000 | Test out station 4 equipment and procedures
184-100 | Assemble 3 TF coils&structure | [58 empty] | 0.4 | 1 | 0.6 | 1
184-105 | Assemble 3 TF coils&structure | [62 empty] | 1 | 1
184-105AD | Assemble/disassemble TF 6 pac | [65 empty] | 0.6 | 1 | 0.4
184-110 | Assemble 3 TF coils&structure | [67 empty] | 0.4 | 0.6 | 0.2
184-115 | Assemble 3 TF coils&structure | [69 empty] | 0.4 | 0.6 | 0.2
184-115AD | Assemble/disassemble TF 6 pac | [71 empty] | 0.4 | 0.2
184-120 | Assemble 3 TF coils&structure | [72 empty] | 0.4 | 0.6 | 0.2
184-125 | Assemble 3 TF coils&structure | [84 empty] | 0.5 | 0.6
184-125AD | Assemble/disassemble TF 6 pac
S4P1-100 | Testout Sta5 equipt & procedures
S4P1-101 | Mount MC/VV assembly to support frame a | [57 empty] | 0.2
S4P1-102 | Position and weld all ports to VV | [58 empty] | 0.2 | 0.2 | 0.1 | 0.2 | 0.2 | 0.2 |  | 0.1
S4P1-103 | Inspect Welds
S4P1-104 | Assemble left TF Coil Assembly check position | [68 empty] | 0.3 | 0.1
S4P1-105 | Change platforms
S4P1-106 | Assemble right TF Coil Assembly chk position | [69 empty] | 0.2 | 0.1
S4P1-107 | Attach TF coils to MC's | [70 empty] | 0.3
S4P1-108 | Change platforms
S4P1-109 | Position weld two large horizontal diag ports | [71 empty] | 0.1 | 0.1
S4P1-110 | Inspect Welds
S4P1-112 | Close up VV leak check
S4P1-113 | Adjust final support base interfaces
S4P1-113.5 | Final metrology outside & inside | [77 empty] | 1 | 1
S4P1-114 | Prepare Field Period for shipment
S4P1-115 | Transfer completed assy to C-site test cell
S4P2-101 | Mount MC/VV assembly to support frame a | [67 empty] | 0.2
S4P2-102 | Position and weld all ports to VV | [68 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
S4P2-103 | Inspect Welds
S4P2-104 | Assemble left TF Coil Assembly check position | [75 empty] | 0.4
S4P2-105 | Change platforms
S4P2-106 | Assemble right TF Coil Assembly chk position | [76 empty] | 0.3
S4P2-107 | Attach TF coils to MC's | [76 empty] | 0.2 | 0.1
S4P2-108 | Change platforms
S4P2-109 | Position weld two large horizontal diag ports | [77 empty] | 0 | 0.1 | 0
S4P2-110 | Inspect Welds
S4P2-112 | Close up VV leak check
S4P2-113 | Adjust final support base interfaces
S4P2-113.5 | Final metrology outside & inside | [83 empty] | 0.6 | 1 | 0.4
S4P2-114 | Prepare Field Period for shipment
S4P2-115 | Transfer completed assy to C-site test cell
S4P3-101 | Mount MC/VV assembly to support frame a | [79 empty] | 0.1 | 0.1
S4P3-102 | Position and weld all ports to VV*2 shift* | [80 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
S4P3-103 | Inspect Welds
S4P3-104 | Assemble left TF Coil Assembly check position
S4P3-105 | Change platforms
S4P3-106 | Assemble right TF Coil Assembly chk position
S4P3-107 | Attach TF coils to MC's
S4P3-108 | Change platforms
S4P3-109 | Position weld two large horizontal diag ports
S4P3-110 | Inspect Welds
S4P3-112 | Close up VV leak check
S4P3-113 | Adjust final support base interfaces
S4P3-113.5 | Final metrology outside & inside
S4P3-114 | Prepare Field Period for shipment
S4P3-115 | Transfer completed assy to C-site test cell