| Princeton Plasma Physics Laboratory Procedure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ‘ Procedure Title: Field Period Assembly Station Two |  |  |  |  |  |
| Number: D-NCSX-FPA-002 |  | Revision: 0-dB |  |  | Effective Date: December XX, 2007 Expiration Date: (2 yrs. unless otherwise stipulated) |
| Procedure Approvals |  |  |  |  |  |
| Author: Bill Sands |  |  |  |  |  |
| ATI: Mike Viola |  |  |  |  |  |
| RLM: Larry Dudek |  |  |  |  |  |
| Responsible Division: NCSX Project |  |  |  |  |  |
| Procedure Requirements Designated by RLM - LAB-WIDE: |  |  |  |  |  |
| X | Work Planning Form (ENG-032) #1224 |  |  | Lockout/Tagout (ESH-016) |  |
|  | Confined Space Permit (5008,SEC.8 Chap 5) |  |  | Lift Procedure (ENG-021) |  |
|  | Master Equipment List Mod (GEN-005) |  | X | ES&H Review (NEPA, IH, etc.) NEPA 1261 |  |
|  | RWP (HP-OP-20) |  |  | Independent Review |  |
|  | ATI Walkdown |  | X | Pre-Job Brief |  |
| X | Post-job Brief * |  | X | Hydrostatic and Pneumatic Testing. (ENG-014) |  |
| D-SITE SPECIFIC: |  |  |  |  |  |
| X | D-Site Work Permit (OP-AD-09) |  |  | Door Permit (OP-G-93) |  |
|  | Tritium Work Permit (OP-AD-49) |  |  | USQD (OP-AD-63) |  |
| X | Pre-Job Brief (OP-AD-79) |  |  | T-Mod (OP-AD-03) |  |
|  | **DCA/DCN (OP-AD-104) # |  |  |  |  |

* Required for installations involving internal vacuum installations, critical lifts, and for the initial installation of repetitive work.

** 	OP-AD-104 was voided by procedure ENG-032. However, DCA’s that were open at the time of adoption of ENG-032 are still considered valid for work approval purposes.

| REVIEWERS (designated by RLM) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Incorporated Comments |  |  |  |  |  |
| Accountable Technical Individual…………………………………… |  |  |  |  |  |
| Test Director |  |  |  |  |  |
| Independent Reviewer |  |  |  |  |  |
| D-Site Shift Supervisor |  |  |  |  |  |
| Independent |  |  |  |  |  |
| NCSX Dimensional Control Coordinator……………………………..…Bob Ellis |  |  |  |  |  |
| Vacuum Vessel Cognizant Engineer |  |  |  |  |  |
| PPPL Metrology Manager………………………………………………Steve Raftopoulos |  |  |  |  |  |
| NCSX Field Period Assembly Manager……………………………… Mike Viola |  |  |  |  |  |
| NCSX Field Supervisor…………………………………………………John Edwards |  |  |  |  |  |
| Project Engineer for Stellarator Systems (WBS 1) Manager………..Brad Nelson (ORNL) |  |  |  |  |  |
| FPA Tooling and Constructability …………………………………….Tom Brown |  |  |  |  |  |
| Quality Assurance/Quality Control…………………………….….J. Malsbury/C. Colin |  |  |  |  |  |
| Maintenance and Operations Division |  |  |  |  |  |
| Energy Conversion System/Motor Control Division |  |  |  |  |  |
| Engineering ……………………………………………………………Phil Heitzenroeder |  |  |  |  |  |
| Environmental Restoration & Waste Management Division |  |  |  |  |  |
| Environmental, Safety & Health……………………………………….Jerry Levine |  |  |  |  |  |
| Industrial Hygiene………………………………………………………...Bill Slavin |  |  |  |  |  |
| Health Physics……………………………………………………..……George Ascione |  |  |  |  |  |
| RLM………………………………………………………………….….Larry Dudek |  |  |  |  |  |
| TRAINING (designated by RLM) |  |  |  |  |  |
| No training required ______________ | Instructor John Edwards |  |  |  |  |
| Personnel (group, job title or individual name) |  | Read Only | Instruction ### Pre-job Briefing |  | Hands On |
| Lead Tech. |  |  | X |  |  |
| Technicians performing task |  |  | X |  |  |
| Field Supervisors |  |  | X |  |  |
| Quality Control Representative |  |  | X |  |  |
| Training Rep. |  |  |  |  |  |
| RLM Larry Dudek |  |  |  |  |  |

RECORD OF CHANGE

| Revision | Date | Description of Change |
| --- | --- | --- |
| 00 | January 4, 2008 | Initial release |

TABLE OF CONTENTS

1.	Introduction and Scope	1

1.1	Introduction	1

1.2	Scope	1

1.3	 Identification of Modular Coil Segments Being Assembled	1

2.	Applicable Documents	1

2.1	Manufacturing, Test, and Quality Assurance Plan (NCSX-MIT/QA-185)	1

2.2	Manufacturing Facility Operations Plan (NCSX-PLAN-MFOP)	1

2.3	Modular Coil Lift Procedure (D-L-NCSX-999 Wound Modular Coil Lift Procedure)	1

2.4	Field Period Assembly Station 2 Dimensional Control Plan ( D-NCSX-PLAN-FPA2DC)	1

3.	Safety Requirements	2

3.1	Job Hazard Analysis	2

4.	 Prerequisites & Condition	2

4.1	Pre-Job Briefing	2

4.2	Daily Operations Startup and Shutdown	2

5.	Materials and Parts forStation 2	3

6.	Assembly Process	3

6.1	Daily Startup Activities	3

6.2	  Daily Shutdown Activities	3

6.3	MC fit-up pre-check and surface insulation	3

6.4 	Racking of the Modular Coils	5

7. Pre-installation Station 2 Setup	8

8. A-B Modular Coil Assembly	8

9. (A-B) to C Modular Coil Assembly	13

10. Inflate all Wing Shim Bags	17

11. Complete Local Service and Interface Details	17

12. Final Measurements/Transfer Completed MCHP to Holding Area	18

13. “A-A” Shear Plate Weldment	19

Appendix A. Document Sign Off	A-1

1.3	     Vacuum Vessel Segment Identification	A-1

4.1	     Pre Job Briefing	A-1

6.3	     MCFfit-up Pre-check and Surface Insulation	A-1

6.4.6       Plane “G” Verification	A-1

6.4.17	Alignment Acceptance	A-1

6.5.1	       Pre Measurement of Modular Coils	A-1

6.5.8	        Data Saved	A-1

8.1.1	       Alignment Acceptance	A-2

8.1.11	Shim Adjustment Criterion Met	A-2

8.1.15	Alignment Acceptance	A-2

8.1.26	Alignment Acceptance	A-2

8.1.41 	Alignment Acceptance	A-2

8.1.45	Back Office Verification	A-2

9.1.4	       Alignment Acceptance	A-2

9.1.11	Coil Position	A-3

9.1.19	Alignment Acceptance	A-3

9.1.20	Alignment Acceptance	A-3

9.1.25	Dimensional Control Acceptance	A-3

9.1.28	Alignment Acceptance	A-3

9.1.29	Alignment Acceptance	A-3

9.1.36	Alignment Acceptance	A-4

9.1.38	Alignment Acceptance	A-4

9.1.42	Alignment Acceptance	A-4

9.1.43	Alignment Acceptance	A-4

9.1.44 	Stycast Application	A-4

10.0	       Inflate all Wing Shim Bags	A-4

11.1.1	Complete Local Service and Interface Details	A-4

12.1.6	Final Measurements and Move to Holding Area	A-4

13.1.2	“A-A” Shear Plate Weldment	A-5

LIST of TABLES

Table 1  Reference Drawings	3

Table 2  Figure Modular Coil Half Period (MCHP) Assembly Makeup	4

LIST OF FIGURES

Figure 1  MC Arrangement for The Full Machine Assembly	4

Figure 2   Datum's	6

Figure 3  Type “A” to Type “B” Setup	9

Figure 4  Mating “B” Coil into Position	10

Figure 5  MCHP  base supports	19

# Introduction and Scope

## 1.1	Introduction

The Field Period and Machine Assembly is divided into 5 workstations. Stations 1, 2, 3, and 5 deal with Field Period Assembly and Station 6 deals with final machine assembly. Each workstation has a specific set of tasks that will be performed as part of the overall assembly process.  This procedure addresses the manufacturing, inspection, test and QC inspection points for the Station No. 2 Half Period Assembly (HPA) Activities.

## 1.2	Scope

This procedure is used to describe the assembly sequence required for Station 2 Half Period      Assembly and includes:.

    - Installing Modular Coil on Stands;

    - Metrology measurements (all racking and interim measurements);

    - Coil A -B assembly; and

    - Coil (A-B) to C assembly

## 1.3		Identification of Modular Coil Segments Being Assembled

Assembly Coils involved: __________________________________________________

Lead Technician See Appendix A – Document Sigh-off-Record

# 2.	Applicable Documents

## Manufacturing Facility Operations Plan (NCSX-PLAN-MFOP)

The purpose of this operations plan is to describe how the activities within the NCSX Manufacturing Facility will meet PPPL Integrated Safety Management (ISM) requirements specified in laboratory policies, programs, and procedures. It will also provide an overview of the general processes that occur in the facility.  More detailed descriptions and processes for each process will be described in specific Manufacturing, Inspection and Test/Qualify Assurance (MIT/QA) plans and detailed manufacturing/assembly procedures.

## Manufacturing, Test, and Quality Assurance Plan (NCSX-MIT/QA-185)

This plan addresses the manufacturing, inspection, test and Quality Assurance (QA) plan to complete and deliver three (3) Field Period Assemblies for the NCSX Project to the NCSX test cell.

## 2.3	Modular Coil Lift Procedure (D-L-NCSX-999 Wound Modular Coil Lift Procedure)

This procedure describes the necessary equipment and methods to follow in lifting and transporting a wound modular coil assembly.

## 2.4	Field Period Assembly Station 2 Dimensional Control Plan (	D-NCSX-PLAN-FPA2DC)

This plan describes the dimensional control steps that will be taken to ensure adequate dimensional control of the Modular Coil Half Period (MCHP) that will occur at Station 2.  Each half period assembly consists of three modular coils, one each of type A, B, and C. The three coils are joined together with bolts and shims. Two half periods are joined, in stellarator symmetry, to form a full period. Adequate dimensional control will ensure that the coil current centers are within the specified

# 3.	Safety Requirements

All work will be performed in a safe manner in accordance with PPPL Environmental Safety & Health Directives ES&H 5008 and the “Integrated Safety Management” (ISM) policy.

## 3.1	Job Hazard Analysis

A JHA will be generated for each Vacuum Vessel Sub Assembly station, identifying existing or potential workplace hazards and to evaluate the risk of worker injury or illness associated with job tasks. (Reference document ESH-004 “Job Hazard Analysis”)  The IH representative will review the JHA’s for accuracy as well as completeness.  It will be reviewed with all activity participants at the Pre-Job briefings. These JHA’s will be regularly reviewed and updated as needed.  Any changes to the JHA’s must be reviewed by all active participants

Refer to JHA for All Hazardous Activities!

# 4.	 Prerequisites & Condition

## 4.1	Pre-Job Briefing

A pre-job briefing will be held, describing the processes and safety issues prior to starting any part of this procedure.	  Attendance shall be documented via training sign-in sheet.	 A copy of the sign-in sheet will be maintained with the run copy of the procedure. The original will be delivered in person to Human Resources, as required by ENG-030

Field Supervisor See Appendix A – Document Sign-off Record

Quality Control to verify all training has been performed See Appendix A – Document Sign-off Record

Assure all individuals working on FPA 2 have been trained as per requirements of the Field Period Assembly Training Matrix located at:

http://ncsx.pppl.gov/SystemsEngineering/Training/Training_Matrices/FPA_Training_MatrixR0.pdf

## 4.2	Daily Operations Startup and Shutdown

Each working day the Lead Technician it is required at the beginning of shift and at end of shift to record only significant changes. See Sections 6.1 and 6.2 for details.

# 5.	Materials and Parts forStation 2

Materials are listed in drawing bill of materials on the respective drawings in : .

| Title | Drawing Number |
| --- | --- |
| MC Half Period Assembly | SE140-003 |
| Wing Support Bladder | SE140-050 |
| AB Inboard Shim | SE140-052 |
| BC Inboard Shim | SE140-054 |
| Shim Puck | SE140-056 |
| Wing Support | SE140-060 |

Table 1  Reference Drawings

# 6.	Assembly Process

This assembly procedure is to be used as guide to complete the station no. 2 activities.  Deviation from this procedure for processes that DO NOT affect the design of the assembly can be made during the assembly process with the concurrence of the Field Supervisor.  All deviations shall be documented in the procedure and initialed by the HPA Field Supervisor prior to implementing the deviations.  Deviations that may affect the design of the assembly requires a Request for Deviation “RFD” approval.  The RFD must be approved prior to proceeding.  Procedure changes need to be incorporated into the document via “Minor Procedure Changes” or “Revisions”.

## 6.1	Daily Startup Activities

- Verify operation of all equipment needed that day.

- Check that safety equipment needed for day’s activities are available.

- Check that the day’s travelers (I.E. Appendix A) and procedures are in their document holder.

- Lead Technician should use a log book to pass useful information amonst Station technicians or when significant changes or events occur in Station 2 activities.  Log book records shall be dated, and initialed.

## 6.2			Daily Shutdown Activities

- Turn off power to equipment not in use.

- Lock Cabinets.

- Verify that all Traveler (I.E. Appendix A) and data sheet information is complete.

- Verify that all deviation from the procedure have been documented in the procedure and initialed by the FPA Field Supervisor. Design changes require either an approved Request for Deviation, Minor Procedure Change or formal revision of procedure.

- Lead Technician should use a log book to pass useful information amongst Station technicians or when significant changes or events occur in Station activities.  Log book records shall be dated and initialed.

## 6.3	MC fit-up pre-check and surface insulation

Verify that mating MC's of a MCHP will come together without interferences by pre-fitting mating coils.  This will include the Type-C coil with its interfacing Period Type-C coil. The full assembly layout of the mating MC's can be found in Table 2  Figure below and Error: Reference source not found next page.  Some of this effort may be done before the half period assembly activity begins.

Lead Technician See Appendix A – Document Sign-off Record

| Period | Left Side | Right Side |
| --- | --- | --- |
| 1 | C1 / B1 / A1 | A2 / B2 / C2 |
| 2 | C3 / B3 / A3 | A4 / B4 / C4 |
| 3 | C6 / B5 / A5 | A6 / B6 /C5 |

Table 2  Figure Modular Coil Half Period (MCHP) Assembly Makeup

1st Period

2nd Period

3rd Period

C2

C1

B1

A1

A2

B2

C3

B3

A3

B4

A4

C4

C6

B5

A5

A6

B6

C5

Y

X

X

Y

Z

CS0

MCHP – Right Side

Figure 1  MC Arrangement for The Full Machine Assembly

## 6.4 	Racking of the Modular Coils

The following steps are provided to rack the modular coils:

6.4.1 	Set up a wedge fixture, with the top surface approximately level, with the appropriate top plate for the type of coil to be measured. Support the narrow edge at its corners and approximately midway along its length. The top plate shall have precisely drilled holes for monuments at its corners, or pucks to receive the 1.5” diameter reflecting ball shall be glued to the corners.

6.4.2 	Place the wedge jacks, roughly under each conical seat located on the inside casting surface.

6.4.3	Place the laser tracker in a position relative to the wedge, and at a height, where it will be able to measure at least 75% of the conical seats on the coil, and three of the corner monuments on the wedge. Note: this position, for each type of coil, is to be determined during pre-measurement of the first coil of each type.

6.4.4 	Measure a plane [“measure plane” in Verisurf©] by measuring three arbitrary points on the top surface of the fixture. One point should be near each corner at the thick end of the wedge, and the third point should be approximately midway along the narrow edge. This plane will be referred to as plane “G”.

6.4.5	Measure the four corner monuments on the wedge, and a set of five or more global monuments attached to the building. These will be the global monuments used for subsequent global alignments. The set of monuments must be approved by the Dimensional Control Coordinator.

Dimensional Control Coordinator Appendix A – Document Sign-off Record

    - Using the laser tracker and the “Build to Surface” feature of Verisurf©, set the jacks to a constant height relative to plane “G”.

Lead Technician See Appendix A – Document Sign-off Record

6.4.7	Lower the coil onto the jacks. For type “B” and type “C” coils datum “E” shall face down. For type “A” coils, datum “D” shall face down. SeeError: Reference source not found below for datum reference

Type-A

Type-B

Type-C

Side-A (datum D)

Side-B (datum E)

Side-B (datum E)

Side-A (datum D)

Type-A

Type-B

Type-C

Side-A (datum D)

Side-B (datum E)

Side-B (datum E)

Side-A (datum D)

Figure 2   Datum's

6.4.8	 Re-check the measurements of global monuments on the fixture. If they have moved more than .002”, re-measure the full set of global monuments.

6.4.9	Measure the locations of all of the conical seats that are accessible, in sequence from lowest to highest number.

6.4.10	In Microsoft Excel, open the racking spreadsheet for the particular coil that has been prepared by Dimensional Control. In Verisurf©, select only the level in which plane “G” has been defined, do a point report on the three points, and transfer the results to the spreadsheet in the cells assigned to those points. This enables the spreadsheet to compute the unit normal vector and the scalar that define the plane in 3dimensional Cartesian space.

6.4.11	In Verisurf©, select only the level on which the conical seats are defined. Do a point report, transfer the results to the racking spreadsheet in the cells that are assigned to the conical seats. The “nominal”, or as-wound, positions of the conical seats, will have already been entered into the spreadsheet by Dimensional Control. The coordinates of each conical seat are pasted into sheet 2 of the spreadsheet, in the assigned location, to calculate the offsets of the conical seats from plane “G”. These offsets are entered in the assigned cells on sheet 1, and after this has been done for each conical seat, the spreadsheet will display the amount that each conical seat must be raised in order to twist the coil as close as possible to its as-wound condition.

6.4.12		Clamp a dial indicator to the fixture surface near each jack location so that it reads the vertical motion of the flange closest to the fixture surface. Take care that each indicator reads of an adequately smooth surface. Check each indicator to verify its proper operation.

6.4.13	Watching the dial indicators, jack at each location by the amount specified on the racking spreadsheet. Jack alternately at points roughly across the diameter, rather than working around circumferentially.

6.4.14	Save the racking spreadsheet as a new copy.

6.4.15	 Repeat steps 6.4.9 through 6.4.14. When the racking spreadsheet indicates that the required jacking at each location is 0.002” or less, the coil has been adjusted to the best of our ability. It is now permissible to do an alignment to conical seats.

6.4.16	Align to the set of conical seats that are accessible. The acceptance criterion is .005” rms deviation. If this is not met, consult the Dimensional Control office before proceeding further.

6.4.17	After alignment and resolution of any nonconformance’s, the alignment report is saved, and the alignment is accepted.

6.4.18	Measure the global monuments. Note that, because of the presence of the coil, one or two of the monuments on the fixture will no longer be accessible. This set of global monuments will be used for subsequent alignments of the laser tracker. All alignments to the global monuments will include the full set of building monuments, and at least two of the monuments on the fixture. The acceptance criterion for global alignments is .002” rms deviation. A failure to meet this criterion must be resolved by the Dimensional Control office.

Dimensional Control Coordinator Appendix A – Document Sign-off Record

6.5 	Pre-Measurement of Modular Coils

The following steps are provided to pre-measure the modular coils:

    - Check the location of two monuments on the fixture. If they are less than .003” from their original position, proceed to 6.5.2. If they are more than .003” from their original position, it may indicate that the laser has been bumped, or the fixture moved slightly. Re-align to the global monuments. If the acceptance criterion is not met, it may mean that the fixture and the building have moved relative to each other. Do not accept the alignment, but re-align to the conical seats. If this alignment is not acceptable, contact the Dimensional Control Office and work out a resolution to the problem before proceeding.

Lead Technician See Appendix A – Document Sign-off Record

6.5.2	Scan the top flange of the coil. This information will be used in the pre-calculation of shim thicknesses.

6.5.3	Measure the positions of all of the tooling balls accessible to the laser. Accuracy criteria are laid out in Section 2 of the  Station 2 Dimensonal Control Plan (NCSX-PLAN-FPA2DC)

6.5.4	Move the laser tracker to a new vantage point from which the remaining monuments on the part are visible. [note – a third and fourth position may be required]

6.5.5	Align to the global monuments, using the full set of building monuments and at least two monuments on the fixture. If the alignment does not meet the acceptance criterion, consult Dimensional Control before proceeding.

6.5.6	Measure the positions of all of the tooling balls accessible to the laser. Accuracy criteria are laid out in Section 2.1 of the Station 2 Dimensonal Control Plan (NCSX-PLAN-FPA2DC).

6.5.7	Repeat steps 6.5.4 through  until all of the monuments have been measured.

6.5.8	Save the data file and back it up. At this point, the pre-measurement of the modular coil is complete. The external tooling balls are now related to the position of the coil current center in the as-found condition of the coil. The external tooling balls, with the appropriate rigid body realignments as needed, will be the reference points for positioning and tracking the modular coil during subsequent assembly steps. The conical seats that interfere with coil-to-coil fit-up can be removed at this point, but should not be removed unless it is necessary. This will ensure that we retain redundant dimensional information as far as possible into the assembly sequence. It is anticipated that, prior to full period assembly, all remaining conical seats will be removed.

Lead Technician See Appendix A – Document Sign-off Record

# 7. Pre-installation Station 2 Setup

7.1.1	Back office calculations have predetermined shim thicknesses base on the scanned flanges. Using the back office data acquire the proper A/B shims.

7.1.2	Compress alumina coated shims for thickness measurements and sort by resulting measurements to determine the shim set that will be installed on the MCHP. Care must be taken when handling alumina shims to mitigate any possible surface contamination conditions.

# 8. A-B Modular Coil Assembly

    - Follow the steps defined in Section 6.4 of this document for racking coils, lower the Type-A modular coil onto the jacks, “A” flange (datum "D") down and rack the "A" coil into its proper shape. See Error: Reference source not found. The acceptance criterion is .003" RMS deviation in alignment to the set of tooling balls.  With a successful alignment a set of global fiducial monuments will have been established. Subsequent alignments of the laser tracker will be to the global fiducial monuments, with the criterion of .002” RMS deviation.

Lead Technician See Appendix A – Document Sign-off Record

Figure 3  Type “A” to Type “B” Setup

8.1.2	Using the Type-A (B-flange) inboard shim template mark the nose shim locations and puck locations.  Remove the template. A simple template of similar device to be developed to represent puck area for proper measurement of puck thickness.

8.1.3	Place an initial set of alumina shims (4-8) on the Type-A coil in designated locations for the initial alignment of the mating coil. Obtain the shim thicknesses from the NCSX back office.

8.1.4	Place unfilled shim bags in the wing areas

8.1.5	Lower the mating “B” coil into position. As shown below in figure 4

Figure 4  Mating “B” Coil into Position

8.1.6	Perform an alignment to the “B” coil tooling balls to verify that it has not changed shape. Do not accept the alignment if the alignment fails to meet the .003”RMS criterion;, add additional shims to the initial set, or adjust shim thicknesses as necessary, until the “B” coil meets the alignment criterion.

8.1.7	Install the jack screws and dial indicators for horizontal positioning

8.1.8 	Using three selected monuments on the “B” coil, position the coil within ±.002" normal to the mating flanges and within ±.060" horizontally

8.1.9	Install the remaining alumina coated shims; install studs and supernuts, proceed with a “hand wiggle test” (rotate on bolt) on all shims to make sure that they are tight.  Replace any loose shims with the proper thickness shim.

8.1.10	Torque supernuts to 50% of their final specified torque per attached table of super nut torque.  Use stud tension meter to verify a few (4) tension values.  Full tension is 72,000 lbs.

    - After tightening, measure the position of all monuments as per section 6.5, following steps 6.5.3 through 6.5.7.All monuments shall be within .007" (true distance) of their desired position. Adjust shims until this criterion is met.

Lead Technician See Appendix A – Document Sign-off Record

8.1.12 	Measure the shim puck height (at a number of points around the puck surface) at each of the nose shim puck locations.  Use the data to define each puck height.

8.1.13		Unfasten bolts and raise the "B" coil in height to remove the puck locating rings and install all nose shims with the properly sized pucks.  Use temporary shims to support the Type-B flex shims.

8.1.14	 “Lightly” tack weld the nose flexes shims to the perspective "A" and "B" coils

.  Unfasten all bolts and remove the "B" coil and place it on a separate fixture, with the Type-B coil side "A" flange (datum "D") facing up.

8.1.15	Recheck the part alignment of the "A" coil to make sure it is still within alignment. Verify that it still meets the .003” RMS criterion. Do not accept alignment. If the .003” criterion is not met, re-rack the “A” coil.

Lead Technician See Appendix A – Document Sign-off Record

8.1.16	 Weld all Type-A flex shims to the plasma side, following the weld sequence plan

8.1.17	After welding the "A" coil nose shims recheck alignment to determine if the part still meets the metrology acceptance criterion. The acceptance criterion is .003" RMS deviation in alignment to the set of tooling balls.

8.1.18	Time needs to be allocated for a back office assessment of the part after welding. If Control Plan acceptance criterion is not met project input is needed to determine how to proceed.

8.1.19	On the separate fixture measure the "B" fiducials to establish a reference coordinate system prior to welding the "B" coil nose shims.

8.1.20	With the successful "A" coil weld operation, weld all Type-B (A-flange) flex shims to the plasma side, following the weld sequence plan.

8.1.21	After welding the "B" coil nose shims recheck the part to determine if it still meets the metrology acceptance criterion. Align to measurements of 8.1.20. Acceptance criterion is RMS .le. .004". Project input is required in the event of failure.

8.1.22	Time needs to be allocated for a back office assessment of the part after welding. If Control Plan acceptance criterion is not met project input is needed to determine how to proceed.

8.1.23 	Remove alumina shims as necessary except for the (4-8) initial locating shims on the Type-A coil in designated locations for the initial alignment of the mating coil.

8.1.4	Place unfilled shim bags in the wing areas

8.1.24	Lower the mating “B” coil into position

8.1.25	Perform an alignment to the “B” coil tooling balls to verify that it has not changed shape. Do not accept the alignment if the alignment fails to meet the .003”RMS criterion, add additional shims to the initial set, or adjust shim thicknesses as necessary, until the “B” coil meets the alignment criterion.

Lead Technician See Appendix A – Document Sign-off Record

Quality Control See Appendix A – Document Sign-off Record

8.1.26	Using three selected monuments on the “B” coil, position the coil accurately in the x, y, and z directions. An accuracy of ±.002” or better in each direction is expected and required for this step.

8.1.27	Raise the "B" coil slightly and install the remaining alumina coated shims; install Fuji paper on all outboard shims, install studs, supernuts, and make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight.  If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted.

8.1.28	Torque to 50% of final value.

8.1.29	After tightening, measure the position of all monuments following steps 6.5.3 through 6.5.7.All monuments should be within .007" (true distance) of their desired position.

8.1.30	Unfasten the bolts, lift the “B” coil enough to remove the Fuji paper, and examine the load sharing. At the same time, the “back office” will analyze the measurements of the monument positions. A revised set of shim thicknesses, to provide adequate loads.

8.1.31	If a revised set of shims is required, install the new shims and Fuji paper. Lower and reposition the “B” coil. Repeat steps 8.1.29 thru 8.1.31.

8.1.32	With a successful Fuji load pattern, unfasten the bolts, lift the “B” coil enough to remove the Fuji paper and initial shims.  Install an equivalent set of alumina coated shims without Fuji paper, install studs, supernuts, and torque to 50% of final value.  Recheck alignment. Send the Fuji paper test shims out to be cleaned.

8.1.33	If the above step does not fall within .007" or less then loosen all studs, adjust shims locally. Re-torque all studs to 50%.All monuments shall be within .007" (true distance) of their desired position. Adjust shims until this criterion is met.

8.1.34	Remove supernuts one at a time or as many in an area that can be removed without chance of coil shift. Using the eccentric gage slid onto the stud define the hole eccentricity.  Select bushings and machine to match required eccentricity.  Install bushings. Replace nuts and tighten back to 50% and measure the position of all monuments following steps 6.5.3 through 6.5.7.This operation can be done concurrently at different locations if in so doing the part does not move.

8.1.35	After super bolt tightening, measure the position of all monuments following steps 6.5.3 through 6.5.7.All monuments shall be within .007" (true distance) of their desired position.

8.1.36	Tighten all bolts to their final torque.

8.1.37	After tightening hardware, measure the position of all monuments following steps 6.5.3 through 6.5.7.All monuments shall be within .009" (true distance) of their desired position.

8.1.38	Weld the A / B nose region solenoid side following the weld procedure.

8.1.39	Measure the positions of all monuments per the process defined in Section 6, steps 6.5.3 through 6.5.7.All monuments shall be within .012" (true distance) of their desired position.

8.1.40Review the above results with Back Office. Adjust wing supports if needed to meet alignment requirements .

Lead Technician See Appendix A – Document Sign-off Record

Dimensional Control Supervisor Appendix A – Document Sign-off Record

8.1.41	Identify, if possible, a set of monuments that have moved less than .005” from their original positions. The alignment that will be necessary for mating to the “C” coil will use monuments from among this set.

8.1.42	Fill all lose bushings with Stycast 2850FT

8.1.43	Scan the "B" flange (datum “E”) of the “B” coil, for the purpose of defining the shim thickness for the mating to the “C” coil.  Save the measurement file and back it up.

8.1.44Using the "B" flange (datum "E") measurement of the Type-B coil and the earlier "A" flange (datum "E") measurement of the Type-C coil, define all B/C flange shim thickness. This is a back office calculation where shim thickness is predetermined based on the scanned flange surface data.

Dimensional Control Supervisor Appendix A – Document Sign-off Record

- 9. (A-B) to C Modular Coil Assembly

9.1.1	Bolt the "A" coil to its fixture and lift the (A-B) coil, along with the fixture, onto another wedge with its top surface tilted at 20 degrees from horizontal.  Bolt the fixtures together.

9.1.2	Select a subset of monuments identified in step 8.1.42 that will be used for the initial alignment in this next phase of half period assembly.

9.1.3	Align to the set of monuments selected in 9.1.2. The acceptance criterion is .005" RMS deviation in alignment to the set of tooling balls.

    - Establish a set of global monuments, on the fixture and on the building. Subsequent alignments to these monuments must meet the .002"RMS criterion.

Lead Technician See Appendix A – Document Sign-off Record

Quality Control See Appendix A – Document Sign-off Record

9.1.5	Using the Type-B (B-flange) inboard shim template mark the nose shim locations and puck locations.  Remove the template. Use a thin equivalent washer of the puck diameter (or some other method) to provide a positional "feel" to allow measuring puck height in the A -B installed position.

9.1.6	Place an initial set of alumina shims (4-8) on the Type-B coil in designated locations for the initial alignment of the mating coil. Obtain the shim thicknesses from the NCSX back office.

9.1.7	Place unfilled shim bags in the wing areas

9.1.8	Lower the mating “C” coil into position.

9.1.9	Perform an alignment to the “C” coil tooling balls to verify that it has not changed shape. Do not accept the alignment. If the alignment fails to meet the .003”RMS criterion, add additional shims to the initial set, or adjust shim thicknesses as necessary, until the “C” coil meets the alignment criterion.

9.1.10	Install the jack screws and dial indicators for horizontal positioning.

    - Using three selected monuments on the “C” coil, position the coil within ±.002" normal to the plane of the mating flanges and within ±.060" in the plane of the mating flanges.

Lead Technician See Appendix A – Document Sign-off Record

Quality Control See Appendix A – Document Sign-off Record

9.1.12	Install the remaining alumina coated shims; install studs and supernuts, proceed with a “hand wiggle test” (rotate on bolt) on all shims to make sure that they are tight.  Replace any loose shims with the proper thickness shim.

9.1.13	Torque supernuts to 50% of there final specified torque.

    - After tightening, measure the position of all monument following steps 6.5.3 through 6.5.7. All monuments shall be within .015" (true distance) of their desired position. The component of the deviations of monuments on the “C” coil that is normal to the flange faces shall be less than .010”.  Adjust shims until this criterion is met.

Lead Technician See Appendix A – Document Sign-off Record

Quality Control See Appendix A – Document Sign-off Record

9.1.15	Measure the shim puck height (at a number of points around the puck surface) at each of the nose shim puck locations.  Use the data to define each puck height.

9.1.16	Unfasten bolts and raise the "C" coil in height to remove the puck locating rings and install all nose shims with the properly sized pucks.  Use temporary shims to support the Type-C flex shims.

9.1.17	“Lightly” tack weld the nose flexes shims to the respective "B" and "C" coils.

9.1.18	Unfasten all bolts and remove the "C" coil and place it on a separate fixture, with the Type-C coil side "A" flange (datum "D") facing up.

    - Recheck the part alignment of the "A / B" coil to make sure it is still within alignment and then weld all Type-B flex shims to the plasma side, following the weld sequence plan. RMS deviation .005" or less is the acceptance criterion. Consult Dimensional Control if this criterion is not met.

Dimensional Control Supervisor Appendix A – Document Sign-off Record

    - After welding the "B" coil nose shims recheck alignment to determine if the part still meets the metrology acceptance criterion. RMS deviation .005" or less is the acceptance criterion. Consult Dimensional Control if this criterion is not met.

Dimensional Control Supervisor Appendix A – Document Sign-off Record

9.1.21	Time needs to be allocated for a back office assessment of the part after welding. If Control Plan acceptance criterion is not met project input is needed to determine how to proceed.

9.1.22	On the separate fixture measure the "C" fiducials to establish a reference coordinate system prior to welding the "C" coil nose shims.

9.1.23	With the successful "A / B" coil weld operation, weld all Type-C (A-flange) flex shims to the plasma side, following the weld sequence plan.

9.1.24	After welding the "C" coil nose shims recheck the part to determine if it still meets the metrology acceptance criterion. RMS deviation .004" or less is the acceptance criterion. Consult Dimensional Control if this criterion is not met.

    - Time needs to be allocated for a back office assessment of the part after welding. If Control Plan acceptance criterion is not met project input is needed to determine how to proceed.

Dimensional Control Supervisor Appendix A – Document Sign-off Record

9.1.26	Remove alumina shims as necessary except for the (4-8) initial locating shims on the Type-B coil in designated locations for the initial alignment of the mating coil.

9.1.27	Lower the mating “C” coil into position.

    - Perform an alignment to the “C” coil tooling balls to verify that it has not changed shape. Do not accept the alignment. If the alignment fails to meet the .003”RMS criterion, add additional shims to the initial set, or adjust shim thicknesses as necessary, until the “C” coil meets the alignment criterion.

Lead Technician See Appendix A – Document Sign-off Record

Quality Control See Appendix A – Document Sign-off Record

    - Using three selected monuments on the “C” coil, position the coil accurately in the x, y, and z directions. An accuracy of .002” or better is expected and required for this step.

Lead Technician See Appendix A – Document Sign-off Record

9.1.30	Raise the "C" coil slightly and install the remaining alumina coated shims; install Fuji paper on all outboard shims, install studs, supernuts, and torque to 50% of final value.

9.1.31 	Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight.  If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted.  Tighten bolt and recheck.

9.1.32	After tightening, measure the position of all monuments following steps 6.5.3 through 6.5.7.All monuments shall be within .015" (true distance) of their desired position.

9.1.33	Unfasten the bolts, lift the “C” coil enough to remove the Fuji paper, and examine the load sharing. At the same time, the “back office” will analyze the measurements of the monument positions. A revised set of shim thicknesses, to provide adequate load sharing and dimensional accuracy, will be generated if required.

9.1.34	If a revised set of shims is required, install the new shims and Fuji paper. Lower and reposition the “C” coil. Repeat steps 9.1.31 thru 9.1.33.

9.1.35      With a successful Fuji load pattern, unfasten the bolts, lift the “C” coil enough to remove the Fuji paper and initial shims.  Install an equivalent set of alumina coated shims without Fuji paper, install studs, supernuts, and torque to 50% of final value.  Recheck alignment. Send the Fuji paper test shims out to be cleaned.

    - If the above step does not fall within .015" or less then loosen all studs, adjust shims locally. Re-torque all studs to 50%.Repeat until the desired tolerance is met.

Lead Technician See Appendix A – Document Sign-off Record

Quality Control See Appendix A – Document Sign-off Record

9.1.37	One hole at a time, remove the supernut.  Using the eccentric gage slid onto the stud define the hole eccentricity.  Select bushing and machine to match required eccentricity.  Install bushing. Replace nut and tighten back to 50% and recheck alignment. This operation can be done concurrently at different locations if in so doing the part does not move.

    - After super bolt tightening (50 % value), measure the position following steps 6.5.3 through 6.5.7.All monuments shall be within .015" (true distance) of their desired position.

Lead Technician See Appendix A – Document Sign-off Record

Quality Control See Appendix A – Document Sign-off Record

9.1.39	Tighten all bolts to their final torque.

9.1.40	After tightening hardware, measure the position of all monuments following steps 6.5.3 through 6.5.7.All monuments shall be within .017" (true distance) of their desired position.

9.1.41	Weld the B / C nose region solenoid side following the weld procedure.

    - Measure the positions of all monuments per the process defined in the Section 6, steps 6.5.3 through 6.5.7.All monuments shall be within .020" (true distance) of their desired position.

Lead Technician See Appendix A – Document Sign-off Record

Quality Control See Appendix A – Document Sign-off Record

    - Back office of above results and adjust wing supports if needed to meet alignment requirements

Dimensional Control Supervisor Appendix A – Document Sign-off Record

    - Fill all lose bushings with Stycast 2850FT

Lead Technician See Appendix A – Document Sign-off Record

# 10. Inflate all Wing Shim Bags

Lead Technician See Appendix A – Document Sign-off Record

# 11. Complete Local Service and Interface Details

    - Inject sealant compound to fill in all shim spaces in order to prevent VV/MC insulation from falling out.

Lead Technician See Appendix A – Document Sign-off Record

# 12. Final Measurements/Transfer Completed MCHP to Holding Area

12.1.1	Using tension tester measure bolt length on all tension fasteners and record the results. Bolts have been supplied measured from vendor for initial reference.

12.1.2 	Megger test of individual coils A,B and C.

12.1.3	Mark part for identification Part identification should indicate the period and subparts (ex. MCHP - Left Side C1/B1/A!)

12.1.4	Install base supports. See Figure 5.

12.1.5	Remove from stand and measure weight of completed assembly

12.1.6.	Move to holding area.

12.1.7	Remove upper wedge to original floor position, reset and grout for subsequent processes

Lead Technician See Appendix A – Document Sign-off Record

Precision Leveler

Precision Leveler support structure

Precision Leveler support mounted at three locations at the base of the MCHP.

Figure 5  MCHP  base supports

# 13. “A-A” Shear Plate Weldment

Note: this procedure can be done in either Station 2 or Station 3

13.1.1	Lift and orient the MCHP, position the “A” coil with the “A-A” flange up in a flat position for welding.

    - Weld “A-A” shear plates in the nose area as per approved drawings and weld procedures.

Field Supervisor See Appendix A – Document Sign-off Record

# Appendix A. Document Sign Off

## 1.3	 Vacuum Vessel Segment Identification

Verified by: _________________________ Date: __________________

Lead Technician

## 4.1	 Pre Job Briefing

Pre Job Briefing Complete:

VV Field Supervisor	Date

Quality Control	Date

## 6.3	MCFfit-up Pre-check and Surface Insulation

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 6.4.6	Plane “G” Verification

Verified by: _________________________ Date: __________________

Lead Technician

## 6.4.17	Alignment Acceptance

Verified by: _________________________ Date: __________________

Dimensional Control Supervisor

## 6.5.1	Pre Measurement of Modular Coils

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 6.5.8		Data Saved

Verified by: _________________________ Date: __________________

Lead Technician

## 8.1.1		Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 8.1.11	Shim Adjustment Criterion Met

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 8.1.15	Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

## 8.1.26	Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 8.1.41 	Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 8.1.45	Back Office Verification

Verified by: _________________________ Date: __________________

Dimensional Control Supervisor

## 9.1.4	Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 9.1.11	Coil Position

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

9.1.14  Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 9.1.19	Alignment Acceptance

Verified by: _________________________ Date: __________________

Dimensional Control Supervisor

## 9.1.20	Alignment Acceptance

Verified by: _________________________ Date: __________________

Dimensional Control Supervisor

## 9.1.25	Dimensional Control Acceptance

Verified by: _________________________ Date: __________________

Dimensional Control Supervisor

## 9.1.28	Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

## 9.1.29	Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 9.1.36	Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 9.1.38	Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 9.1.42	Alignment Acceptance

Verified by: _________________________ Date: __________________

Lead Technician

Verified by: _________________________ Date: __________________

Quality Control

## 9.1.43	Alignment Acceptance

Verified by: _________________________ Date: __________________

Dimensional Control Supervisor

## 9.1.44 	Stycast Application

Verified by: _________________________ Date: __________________

Lead Technician

## 10.0	Inflate all Wing Shim Bags

Verified by: _________________________ Date: __________________

Lead Technician

## 11.1.1	Complete Local Service and Interface Details

Verified by: _________________________ Date: __________________

Lead Technician

## 12.1.6	Final Measurements and Move to Holding Area

Verified by: _________________________ Date: __________________

Lead Technician and Field Supervisor

## 13.1.2	“A-A” Shear Plate Weldment

Verified by: _________________________ Date: __________________

Field Supervisor