# NCSX

# Field Period Assembly (FPA) Manufacturing/Assembly, Inspection, Test and Quality Assurance Plan

NCSX-MIT/QA-185-01-00

February 17, 2006

Author: ________________________________________________________________

Mike Viola - Field Period Assembly (FPA) Facility Manager

Reviewed by:

Jim Chrzanowski					     Judy Malsbury

NCSX Manufacturing Facility Manager				NCSX QA Representative

Jerry Levine					     	   Brent Stratton

PPPL Safety Representative				           Dimensional Control Coordinator

Steve Raftopoulos					      John Edwards

Lead Metrology Engineer				           FPA Field Supervisor

Tom Brown					     	Brad Nelson

WBS 186 Manager				           Stellarator Core Design RLM

_________________________________________

Wayne Reiersen

NCSX Engineering Manager

Approved By: ___________________________________________________________

Larry Dudek

RLM for the NCSX Manufacturing Facility

Controlled Document

THIS IS AN UNCONTROLLED DOCUMENT ONCE PRINTED.

Check the NCSX Engineering Web prior to use to assure that this document is current.

Record of Revisions

| Revision | Date | Description of Change |
| --- | --- | --- |
| 0-dD | 1/16/2006 | Complete re-write and reformatting. |

Table of Contents

1	Introduction and Scope	1

1.1	Introduction	1

1.2	Scope	1

2	Applicable Documents	1

2.1	Governing Documents	1

2.2	Training Requirements	2

3	Field Period Assembly Processes	2

3.1	Overall Field Period Assembly Process Outline	2

3.2	Field Period Assembly  Stations and Procedures	4

3.2.1	Station 1 – Vacuum Vessel Preparation	4

3.2.1.1	Station 1 Assembly Activities	4

3.2.1.2	Station 1 Tooling and Fixtures	5

3.2.2	Station 2 – Modular Coil Half-Period Assembly	5

3.2.3	Station 3 – Modular Coil Installation	5

3.2.4	Station 4 – Final Field Period Assembly	5

3.2.5	Station 5 – TF Half-period Assembly	5

4	Documentation Requirements	6

4.1	Document Control	6

4.2	Field Assembly Station Field Packages	6

4.3	Assembly/Injstallation Procedure Sign-Off’s	6

4.3.1	Procedure Completion	6

4.3.2	Authorized Signoff’s for Manufacturing Completions	6

4.4	Final Document Storage	7

5	Quality Assurance/Quality Control Requirements	7

5.1	Inspection/Surveillance and Audit	7

5.2	Inspection and Test by Field Crews and Engineering	7

5.3	Equipment/Material Identification and Status	7

5.4	Non-conformance & Corrective Actions	8

5.5	Release for Station Transfer	8

5.6	Process History	8

5.6.1	Material Certifications	8

5.6.2	Inspection/ Test Documents	8

5.6.3	Inspection Reports	8

5.6.4	Test Reports	8

6	Specification Verification Activities Check list	1

List of Figures

Figure 4-1 Field Period Assembly Process Outline	3

Figure 4-2 FPA Area Layout (Need new layout of just FPA stations)	4

Figure 4-3 Vacuum Vessel Support	5

# Introduction and Scope

## Introduction

The National Compact Stellarator Experiment (NCSX) will be assembled and built at Princeton Plasma Physics Laboratory.  The stellarator core will be preassembled into three 120° field period assemblies in the TFTR Test Cell.

The TFTR Test Cell is approximately 114 ft wide by 150 ft. long. The Coil Manufacturing Facility will occupy the east side of the building.  The Field Period Assembly will be located in the north and west side of the building. The building crane will be shared.

## Scope

Two plans have been prepared which cover the Field Period Assembly (FPA) activities.  These are the NCSX Manufacturing Operations Plan (NCSX-PLAN-MFOP) and this document, the NCSX Field Period Assembly Manufacturing, Inspection, Test, and Quality Assurance Plan (NCSX-PLAN-MIT/QA-185).

The Manufacturing Facility Operations Plan describes how the activities within the NCSX Manufacturing Facility will meet PPPL Integrated Safety Management (ISM) requirements specified in laboratory policies, programs, and procedures.  It also provides an overview of the general processes that occur in the facility, including general facility operating guidelines, safety controls, and reviews.

This document specifically addresses FPA activities, providing:

- A description of the field period assembly sequence including a process outline;

- A description of each station including tooling and fixtures; and

- A listing of governing specifications, assembly drawings, models, data files, and procedures for each station.

# Applicable Documents

## Governing Documents

Technical requirements are found in the specifications and drawings.  Section 4 of the specifications defines the means by which the requirements called out in the specification will be verified. Top-level assembly drawings provide the specific technical details of the manufacturing/assembly process and point to lower level detailed drawings.

This plan is organized by station (Section 3.2) and each specific station section that follows will provide the details of the specific governing documents.

Work Planning Form #1224 (Field period Assembly) has been prepared and approved. It provides specific planning guidance (requirements, scope, job hazard analysis requirements, ES&H considerations, and procedural and testing and other requirements as necessary) for all field period assembly activities.

In the event of abnormal conditions in the NCSX Manufacturing Facility, procedure “D-NCSX-OP-EO-41” identifies what actions should be taken. Abnormal conditions are identified as conditions which, if not corrected, could result in injury to personnel or damage to equipment.  All employees working in the coil manufacturing facility will be required to read the emergency response procedure.

## Training Requirements

A NCSX Field Period Assembly training matrix has been developed, approved, and posted on the NCSX Engineering Web site.  This matrix specifically identifies the training required by FPA position to specifically identify the training required.

# Field Period Assembly Processes

## Overall Field Period Assembly Process Outline

This section outlines the processes that are to be performed and procedures required to complete field period assembly.  The next section will describe the specific modular coil manufacturing sequence plans and procedures.

Figure 3-1 provides an outline of the overall field period assembly process and Figure 3-2 provides a layout of the Field Period Assembly layout within the NCSX Manufacturing Facility.

Material Receipt

Material Receipt

  - VVSA receipt & inspection

  - Cooling Tubes receipt & inspection

  - Misc. hardware inspection guidelines

Procedure No.

D-NCSX- FPA -QA1

- VVSA Preparation

  - Locate diagnostic loops

  - Install templates

  - Install Diag Loops

  - Locate cooling tubes

  - Install tube clamp studs

  - Perform measurements

Station No. V1

VVSA loops and tubes

Procedure No.

D-NCSX- FPA -001

Station No. V2

MC Assembly

- MC Assembly

  - Align and assembly 3 MC sets

Procedure No.

D-NCSX- FPA -002

- Install MC Assembly and port extension

  - Align and Install VVSA

  - Install first 3 MC sets

  - Install Second 3 MC sets

  - Align and bolt together

  - Align and Weld Port extension

Station No. V3

Install MC  and port extension

Procedure No.

D-NCSX- FPA -003

Station No. V4 Install TF and Trim Coils

- Assemble and Install TF Coils and Trim Coils

  - Assemble two 3 TF coil sets

  - Install Field Period

  - Install one 3 coil set onto TF fixture

  - Roll Coils on

  - Install second 3 coil set onto TF fixture

  - Roll Coils on

  - Install Trim Coils

Procedure No.

D-NCSX- FPA -004

Station No. V5

Final Prep for transport

- Final Prep for Transport

  - Perform Final Measurements

  - Install transportation supports

  - Load on truck

Procedure No.

D-NCSX- FPA -005

Send to NCSX Test Cell

Figure 3-1 Field Period Assembly Process Outline

Figure 3-2 FPA Area Layout

## Field Period Assembly Stations and Procedures

### Station 1 – Vacuum Vessel Preparation

#### Station 1 Assembly Activities

The Field Period Assembly will begin with the VVSA receipt Inspection, followed by the diagnostic loop and cooling tube installation. The Diagnostic loops will be installed using small tabs spot welded to the vessel surface and then the cooling tubes will be installed with studs welded to the surface and clamps applied.  The Assembly Sequence Plan (NCSX-PLAN-SEQ-FPA1), Station 1 Dimensional Control Plan (NCSX-PLAN–PA1DC), and top-level assembly drawing (SE185-???) provides guidance from the designer and dimensional control coordinator on how the components being handled in Station 1 were designed to be assembled and what dimensional control checks are needed.

The Field Period Assembly Manager will utilize these plans and the top-level assembly drawing as a basis for developing the FPA Station 1 Detailed Installation/Assembly Procedure (D-NCSX-FPA-001). This detailed procedure and any related detailed drawings shall govern each step in the assembly sequence for Station 1.

Confirmation of specification verification activities are shown in Appendix A to this MIT/QA Plan

#### Station 1 Tooling and Fixtures

This station is comprised of two trunions (See Figure 3-3) that will support the VVSA in a rotisserie style. This station will be built by the PPPL Tech Shop using drawing XXXX.

Figure 3-3 Vacuum Vessel Support

### Station 2 – Modular Coil Half-Period Assembly

This station is comprised of a tilting platform that will allow the modular coils to be aligned and bolted together. Details TBD.

### Station 3 – Modular Coil Installation

This station is comprised of a support that will hold the vacuum vessel vertical and allow the modular coils to be rotated (screwed) onto each end of the VVSA, one at a time.  Then the ports will be aligned and welded on. From this point forward, the Assembly will be called the Field Period Assembly.  Details TBD.

### Station 4 – Final Field Period Assembly

This station is comprised of a support for the Field Period Assembly and a large column that will be used to support the TF Coils and rotate them onto the Field Period.  Details TBD.

### Station 5 – TF Half-period Assembly

This station is space set aside for minor intermediate operations or storage both between stations and in preparation for transportation to the NCSX Test Cell. Details TBD.

# Documentation Requirements

## Document Control

All NCSX associated documents providing instruction for assembling the field period assembly (e.g. plans and procedures) will be maintained under NCSX Project document control.

## Field Assembly Station Field Packages

Each field period assembly station shall have a “Station Field Package” that shall be maintained by the field period assembly team.  This package shall include all process procedures, inspection reports, photographs, test results, and measurements used to document completion of major activities associated with the activities in each station to assemble the field period assembly. It shall also include ECNs, non–conformance reports (NCR), or other exceptions to or changes in requirements.  All documents shall be complete, legible and validated by responsible personnel.

## Assembly/Injstallation Procedure Sign-Off’s

Assembly/Installation procedures will be used as a signoff/approval document noting that critical manufacturing steps have been completed.  Authorized personnel associated with the manufacturing, inspection and test processes will perform the signoff’s. In addition, it will provide witness points as well as reference for test results, and measurements.

### Procedure Completion

The Lead Technician or Field Supervisor will document all critical completions on the procedure.  This will be completed using the signer’s initials or full signature.

The procedures will be filled out in a timely fashion once a particular activity has been completed.

### Authorized Signoff’s for Manufacturing Completions

The manufacturing procedures will identify what level of signoff is required for a particular step.  The following disciplines are the authorized signatures for the in-process procedures.

- Station Lead Technicians

- Field Supervisors

- Quality Control Representative

- Manufacturing Facility Manager

## Final Document Storage

All documents (hard copy) associated with the manufacturing will be stored in the PPPL Operations center, electronic documents will be stored on the NCSX Web site for the lifetime of the NCSX MIE Project, after which the files will be turned over to the Operations Center.

# Quality Assurance/Quality Control Requirements

## Inspection/Surveillance and Audit

Authorized representatives of the NCSX project will perform inspection and surveillances all during the manufacturing of modular coils. These representatives will include the Field Supervisors; lead technicians as well as the Quality Control (QC) representatives.

All measurements and tests will be performed by the field crews and engineering and do not require, unless outlined in the procedures, the presence of a QC representative.

Independent Audits may be performed by the Quality Assurance Division to ensure that approved manufacturing processes and quality of product is being observed.

## Inspection and Test by Field Crews and Engineering

Inspections, measurements, and tests shall be performed by field crews and engineering unless otherwise required by the procedure.  Where required by procedure, a QC representative shall be present during inspections, measurements, or tests.

Inspections and tests requirements shall be defined in written/approved procedures, referencing criteria for acceptance or testing.  Section 6 calls out verification tests and inspections identified in specifications.  Inspections, measurements, and tests shall be accomplished using properly calibrated measuring in accordance with PPPL procedure ENG-002, “Control of Measurement Test Equipment & Calibration.”

Adequate records to reproduce the inspection shall be maintained and available for NCSX Project reviews.

## Equipment/Material Identification and Status

Material and equipment identification shall be maintained throughout the program and be traceable to the records.  Status of acceptability shall be readily discernible through the use of tags, stamps, serial numbers or other positive means.

## Non-conformance & Corrective Actions

Nonconforming items shall be positively identified, and, where possible, segregated to prevent use.  The Modular Coil Manufacturing Team shall document each non-conformance in accordance with PPPL procedure QA-005 “Control of Non-conformances”.

## Release for Station Transfer

Prior to releasing a modular coil from one station to the next it is required that the all-responsible individuals sign the release indicating that all processes at that station have been satisfactorily completed.  The release (on the procedure) will include signatures from the Station Lead Technician, Field Supervisor and the QC representative.

## Process History

The Field Period Assembly team shall provide a Process History for the modular coils that includes a compilation of documents, detailing the objective evidence of the acceptability of the work performed.  Process History for each coil records shall be stored in the Operations Center after fabrication is completed. The Process History shall include as a minimum, but not be limited to the following:

### Material Certifications

The Field Period Assembly Team shall compile inspection reports, test data, and/or certifications from vendors, showing relevant chemical, mechanical and electrical properties of materials used, where applicable, as detailed in applicable procedures, as well as documents showing adherence to in-process requirements.  Material certifications from sub-tier suppliers shall also be submitted. {Certifications for the insulation, epoxy, conductor as well as chill plates and lead materials are required as a minimum}

### Inspection/ Test Documents

Original or copies of filled in and completed process planning and control documents (procedures, etc.), which verify controlled execution of the required work.  Each coil will have its own set of process planning and control documents.

### Inspection Reports

Copies of the original reports from all required inspections and examinations, that are properly validated by authorized personnel.

### Test Reports

Copies of the original test data sheets or reports of all required tests, both in-process and acceptance, that are properly validated by authorized personnel.

# Specification Verification Activities Check list

Figure 6-4 provides a pointer to where in detailed procedures the confirmation of specification verification activities has been accomplished.

| Specification | Verification Activity | FPA Procedure | FPA Procedure Section |
| --- | --- | --- | --- |
| NCSX-CSPEC-XXX-01 (XYZ Component) | 4.x.x - Weight – verification that the weight of the assembled components is in conformance the requirements of the specification. | D-NCSX-FPA-001 | Section y.y.y |
|  |  | D-NCSX-FPA-002 |  |
|  |  | D-NCSX-FPA-003 |  |
|  |  | D-NCSX-FPA-004 |  |
|  |  | D-NCSX-FPA-005 |  |

Figure 6-4 Confirmation of Verification Activity Check List

NOTE:  THIS IS ONLY INTENDED AS A FORMAT SAMPLE – WE WILL HAVE TO CHECK THE GRD, BSPECs, AND CSPECs TO DETERMINE WHAT ARE THE REQUIREMENTS.