NCSX

Modular Coil

Manufacturing, Inspection, Test and

Quality Assurance Plan

NCSX-MIT/QA-142-01-00

April 27, 2004

Author: _______________________________________  	Date: __________________

James H. Chrzanowski- Modular Coil Facility Manager

Reviewed By: _________________________________	Date: __________________

Judy Malsbury- NCSX QA Representative

Reviewed By: _________________________________	Date: __________________

Jerry Levine- PPPL Safety Representative

Reviewed By: _________________________________	Date: __________________

Dave Williamson- WBS Manager for Modular Coils

(WBS14)

Reviewed By: _________________________________	Date: __________________

Brad Nelson-Project Engineer for Stellerator Systems

(WBS 1) Manager

Approved By: _________________________________	Date: __________________

Larry Dudek- RLM for Modular Coil Mfg.Facility

Controlled Document

THIS IS AN UNCONTROLLED DOCUMENT ONCE PRINTED.

Check the NCSX Engineering Web prior to use to assure that this document is current.

RECORD OF CHANGE

| Revision | Date | Description of Change |
| --- | --- | --- |
| 00 |  | Initial release |

TABLE OF CONTENTS

1	Introduction and Scope	1

1.1	Introduction	1

1.2	Scope	1

2	Applicable Documents	1

2.1	Laboratory Procedures	1

2.2	NCSX Project Documents for Modular Coils	2

2.3	Modular Coil Manufacturing Procedures	2

2.4	Modular Coil Manufacturing Travelers	2

2.5	Drawings:	2

2.6	Permits	3

3	Safety Requirements:	4

3.1	Integrated Safety Management:	4

3.2	Job Hazard Analysis:	4

3.3	Personal Protective Equipment:	4

3.4	Radiation Controlled Area:	4

3.5	Food and Beverage	4

4	Training Requirements	4

4.1	General Training Requirements	4

4.2	Specialized Training Requirements	5

4.3	Training Matrix	5

5	General Notes for Modular Coil Fabrication:	6

5.1	General Operating Plan:	6

5.2	Cleanliness:	6

5.3	Housekeeping:	6

5.4	Markers and Pencils:	6

5.5	Chips and Filings:	6

5.6	Critical Lifts:	6

6	Materials and Parts	7

7	Fabrication Process	7

8	Documentation Requirements:	9

8.1	Document Control:	9

8.2	Field Package:	9

8.3	Traveler:	9

8.4	Final Document Storage:	10

9	Quality Assurance/Quality Control Requirements	10

9.1	Mission Statement: -Modular Coil QA/QC Plan	10

9.2	Inspection/Surveillance and Audit:	10

9.3	Inspection and Test Procedures:	10

9.4	Document Traceability and Records:	10

9.5	Equipment/Material Identification and Status	11

9.6	Nonconformance’s & Corrective Actions:	11

9.7	Calibration of Test and Measuring Equipment:	11

9.8	Release for Station Transfer:	11

9.9	Process History:	11

# Introduction and Scope

## Introduction

The National Compact Stellerator Experiment (NCSX) Modular coils will be manufactured at Princeton Plasma Physics Laboratory for the NCSX Project.  The Modular Coil Set consists of three field periods with 6 coils per period for a total of 18 coils.  Due to symmetry, only three different coil shapes are required to make up the complete coil set.  Each modular coil is constructed by winding pre-insulated rectangular compacted copper cable onto a stainless steel cast winding form. Each coil consists of two, 4-in-hand pancake windings.  Once wound, the entire coil will be vacuum-pressure impregnated (VPI) with epoxy.

## Scope

This document addresses the manufacturing, inspection, test and Quality Assurance (QA) plan to complete and deliver the modular coils to the NCSX Project.  This document includes the following Sections:

2	Applicable Documents

3   	Safety Requirements

5	General notes for fabrication of Modular Coils.

6	Materials and Parts

7	Fabrication Process

8	Documentation Requirements

9	Quality Assurance/Quality Control Requirements

### This document along with the “Winding Facility Operations Plan” [NCSX-PLAN-MCWFOP-00] will govern the processes by which the modular coils will be fabricated.

### This document meets the requirements of the NCSX Quality Assurance Plan [NCSX-PLAN-QAP].

# Applicable Documents

Identified below are the primary laboratory and project documents that that will be needed to complete the production of the Modular coils.

## Laboratory Procedures

| Procedure Number (Latest Version) | Title |
| --- | --- |
| ESH-004 | Job Hazard Analysis |
| ES&H 5008 | PPPL Environmental, Safety and Health Manual |
| ESH-008 | Access to Radiological Areas (RCA’s) |
| ENG-014 | Hydrostatic and Pneumatic Testing |
| ENG-021 | Hoisting & Rigging Procedure |
| EM-002 | General Welding & Brazing Requirements |

## NCSX Project Documents for Modular Coils

| Document No. | Title |
| --- | --- |
| NCSX-CSPEC-142-03 | Modular Coil Assembly Specification |
| NCSX-CSPEC-141-02 | Modular Coil Castings Specification |
| NCSX-CSPEC-142-04 | Modular Coil Conductor Specification |
| NEPA No. 1283 | Modular Coil Development and Production |
| NCSX-PLAN-MFCP-00 | Modular Coil Manufacturing Facility Operations Plan |
| WP-1138 | Manufacturing of Production Coils |
| WP-1188 | Mod coil Winding R&D (Twisted Racetrack coil) |

## Modular Coil Manufacturing Procedures

| Document No. | Title |
| --- | --- |
| NCSX-PROC-MCF-001 | Mod Coil Fabrication-Material Receipt |
| NCSX-PROC-MCF-002 | Mod Coil Fab-Station No. 1 Activities |
| NCSX-PROC-MCF-003 | Mod Coil Fab-Station No. 2 & 3 Activities |
| NCSX-PROC-MCF-004 | Mod Coil Fab-Station No. 4 Activities |
| NCSX-PROC-MCF-005 | Mod Coil Fab-Station No. 5 Activities |
| D-NCSX-OP-G-159 | Coil Test Facility Operation |
| D-L-NCSX-983 | Lifting Modular Coil Castings |
| D-L-NCSX-984 | Lifting Mod Coil Casting & Windings |

## Modular Coil Manufacturing Travelers

### NCSX-TRAV-MCF-001….	Mod Coil Fabrication Traveler

## Drawings:

| Drawing No. | Drawing Description |
| --- | --- |
| SE1405-252 | 40-turn clamp assembly |
| TBD |  |
| TBD |  |

## Permits

### D-site work permits:

Required whenever work is being performed at D-site.  It identifies the type of work and procedures being used.

### Confined space permits:

Required whenever a person is entering a confined space.  It identifies any restrictions, requirements and personnel who are authorized for entry. The PPPL Industrial Hygienist (IH) representative issues the permit.  [Requires a “safety watch”]  (Example: Autoclave entrances when the dome is in position)

### Flame/Fire Permit:

Required whenever open flame activities such as welding, soldering, grinding, etc. are being performed.  The permit is issued by PPPL’s Emergency Service Unit (ESU) and requires a fire watch.

# Safety Requirements:

## Integrated Safety Management:

All work will be performed in accordance with PPPL safety policies ES&H 5008 and “Integrated Safety Management” (ISM) policy.

## Job Hazard Analysis:

JHA’s will be generated for each workstation, identifying existing or potential workplace hazards and to evaluate the risk of worker injury or illness associated with job tasks. (Reference document ESH-004 “Job Hazard Analysis”)  The IH representative will review the JHA’s for accuracy as well as completeness.  It will be reviewed with all activity participants at the Pre-Job briefings.

## Personal Protective Equipment:

The PPPL Industrial Hygiene and Construction Safety representatives will work together with the Modular Coil Facility Manager to identify the necessary and correct personal protective equipment (PPE’s) needed to ensure a healthy and safe work environment for the work force.

## Radiation Controlled Area:

The modular coil manufacturing facility is located in a Radiation Controlled Area (RCA). As a result, all personnel entering or working in the area must be radiation qualified, or be escorted by a qualified escort.

## Food and Beverage

No food, gum, or beverage will be allowed in the MC manufacturing facility.

# Training Requirements

Training of personnel working on the modular coil fabrication is key to successfully completing the manufacturing of the modular coils.  There are two categories of training requirements, general and specialized.

## General Training Requirements

General training includes all laboratory-training requirements that are required to enter or work in the Modular Coil Winding Facility.  Examples of this training includes:

-	   General Employee Training [GET]

- Integrated Safety Management [ISM]

- Radiation Safety Training

## Specialized Training Requirements

Specialized training includes specific training or certification required to complete tasks during the fabrication of the modular coils.  Examples include:

- Weld or braze certifications

- Confined space

- Winding Facility Operations Plan [WFOP]

## Training Matrix

The training matrix below identifies the type of training required for individuals working on the modular coil fabrication.

Training Matrix

|  | Station 1 Casting Prep crew | Station 2 & 3 Winding crews | Station 4 Mold Prep crew | Station 5 VPI crew | Station 6 MC Test Facility crew | Riggers & Crane Operators | Field Supervisors | QC Represent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Confined Space |  |  | X | X | X |  | X | X |
| General Employee (GET) | X | X | X | X | X | X | X | X |
| Radiation Safety | X | X | X | X | X | X | X | X |
| Hazard Communications | X | X | X | X | X |  | X | X |
| Hazard Awareness (JHA) | X | X | X | X | X | X | X | X |
| Winding Facility Operations Plan | X | X | X | X | X |  | X | X |
| Lockout/Tagout | X | X | X | X | X |  | X | X |
| Basic Electrical | X | X | X | X | X |  | X | X |
| Ladder Safety | X | X | X | X |  |  | X | X |
| Fall Protection |  |  | X | X |  | X |  |  |
| Cryogenics Safety |  |  |  |  | X |  |  |  |
| Coil Lead Brazing |  | X |  |  |  |  |  |  |
| Stud Welding | X |  |  |  |  |  |  |  |
| Compressed Gas Safety |  |  | X | X |  |  |  |  |
| Rigging &/or crane operator training |  |  |  |  |  | X |  |  |
| Mechanical Arm training- Romer (operators only) |  |  |  |  |  |  |  |  |

# General Notes for Modular Coil Fabrication:

## General Operating Plan:

Document “NCSX-PLAN-MCWFOP-01-00” describes the general operating plan that will be used for the coil manufacturing facility.

## Cleanliness:

Clean, lint-free cotton or latex gloves will be worn at all times during the handling of modular coil conductor, insulation or any cleaned component that will become a part of the finished modular coil.

Coil parts that are inadvertently handled with bare hands or otherwise soiled must be replaced or cleaned using acetone.

All coils, conductors or parts will be covered at all times when not in use.  Windings will also be covered during work stoppage.

## Housekeeping:

Good Housekeeping is an essential element to the success of the manufacturing of the modular coils.  It is required that all stations be maintained in as clean a state as is reasonable for the specific activities being performed.

## Markers and Pencils:

The use of lead pencils or non-approved markers is prohibited in the fabrication stations. “Sharpie” permanent markers are the only markers that may be used without prior approval by the Field Supervisor.

## Chips and Filings:

Extreme care must be taken when using files, grinders, etc. that could generate metal chips or filings.  Surrounding areas must be protected from these activities.

## Critical Lifts:

All lifting of modular coil castings and/or completed coils will be considered a “Critical” lift that requires the presence of a lift engineer.  Note: The lift engineer may later identify the lift as repetitive, in which case his presence would not be required.

# Materials and Parts

| General Description | Material | Reference Document/Product No. |
| --- | --- | --- |
| Conductor | CDA 102 compacted copper rope | NCSX-CSPEC-142-04 |
| Turn Insulation- glass tape | S-2 Dry glass | NCSX-CSPEC-142-03 |
| Ground insulation-glass tape | S-2 Dry glass | NCSX-CSPEC-142-03 |
| Ground insulation - Kapton- 5mil | Type HN | NCSX-CSPEC-142-03 |
| Ground insulation - Kapton- 2mil | Type HN | NCSX-CSPEC-142-03 |
| Solvent | Chlor-Free Degreaser | CRC Product No. 03185 [MSDS #05032] |
| Solvent | Acetone | MSDS# 00561 |
| Fillers | G-10 | NCSX-CSPEC-142-03 |
| Chill Plates | Copper | NCSX-CSPEC-142-03 |
| Coil Leads | TBD | NCSX-CSPEC-142-03 |
| 3/8-16 x 1.5 inch long studs for coil clamp to casting stud | 316 Stainless steel | Commercial |
| Coil clamps | Stainless steel- 316L | Drawing SE1405-252 |
| Mold release | Release agent dry lubricant | “Miller-Stephenson” -PTFE MS122DF |
| Vacuum Pressure Impregnation Epoxy System | Resin/ Hardener/Accelerator | CTD-101K (Composite Tech Dev. Corp.) 3-part system |
| Epoxy system for shell mold | Resin/hardener | CTD-540 [2-part air cure system] |
| Bag mold material | Self-fusing Tape | Product no.7643A24 2 in. wide gray silicone tape |
| Bag mold shell material | Nomex Felt | Stk. No. NX 08-6 Nomex fabric 1/8 in. thick x 6 in. |

# Fabrication Process

This section of the MIT/QA plan outlines the processes that are to be performed and procedures required to complete the fabrication of the Modular coils.  Procedures for performing the activities are covered by the Modular Coil Fabrication procedures (MCFP).  Each station will have a separate MCFP detailing the manufacturing processes; use of travelers; inspection points and test plan for that station.

Station No.6

Coil Testing

Station No.4

Molding/VPI Preparation

Material Receipt

Station No.2

Winding Station A

Station No.3

Winding Station B

Station No.5

VPI/Autoclave Station

Station No.1

Casting Preparation

- Material Receipt

  - Conductor receipt & inspection

  - Casting receipt & inspection

  - General product inspection guidelines

Procedure No.        NCSX-PROC-MCF-001

Winding Facility Activities

- Casting Preparation

  - Mount casting to support ring

  - Measure/inspect casting surfaces

  - Install coil clamp studs

  - Clean & mold release winding surfaces

  - Install inner chill plates & measure

  - Install Diagnostics & measure

Procedure No.        NCSX-PROC-MCF-002

- Winding Operations

  - Install inner ground wrap insulation

  - Position leads for side “A” winding

  - Wind side “A” of modular coil

  - Measure turns as wound

  - Complete leads for side “A” winding

  - Coil Measurements/electrical tests

  - Reposition coil in turning fixture

  - Position leads for side “B” winding

  - Wind side “B” of coil

  - Measure turns as wound

  - Complete leads for side “B” winding

  - Complete ground wrap sides A & B

Procedure No.        NCSX-PROC-MCF-003

- Molding & VPI Preparation

  - Install outer Diagnostics & measure

  - Install Outer Chill plates

  - Install bag mold

  - Vacuum leak check bag mold

  - Install coil molding clamps

Procedure No.        NCSX-PROC-MCF-004

- VPI/Autoclave Activities

  - Install coil in autoclave and prep for VPI

  - Vacuum impregnate coil

  - Cleanup and install final coil clamps

  - Transport coil to test facility

Procedure No.        NCSX-PROC-MCF-005

- Coil Testing Activities

  - Cold test the modular coil

  - Store tested MC

Procedure No.               D-NCSX-OP-G-159

Basement Activities

Figure 1- Modular Coil Fabrication Plan Outline

# Documentation Requirements:

## Document Control:

All NCSX associated documents providing instruction for manufacturing the modular coils will be maintained under NCSX Project document control.

## Field Package:

Each coil will have a “Field Package” that will include all coil related documentation associated with the manufacturing of modular coils.  Documentation in this package will include Travelers, inspection & test reports, data sheets, photographs, etc.

## Traveler:

A “Traveler” will be used to document the completion of the various manufacturing phases of the Modular Coil from station to station.   The traveler will be used in conjunction with the manufacturing procedures as a signoff/approval form noting that critical manufacturing steps have been completed.  Authorized personnel associated with the manufacturing, inspection and test processes will perform the signoff’s. In addition, it will provide witness points as well as reference for test results, and measurements.

### Traveler Completion:

The Lead Technician or Field Supervisor will document all critical completions on the traveler.  This will be completed using the signer’s initials or pre-approved stamps identifying the signer.

The “Travelers” will be filled out in a timely fashion once a particular activity has been completed.

### Authorized Signoff’s for Manufacturing Completions:

The manufacturing procedures will identify what level of signoff is required for a particular step.  The following disciplines are the authorized signatures for the in-process Travelers.

-Station Lead Technicians

-Field Supervisors

-Quality Control Representative

-Manufacturing Facility Manager

## Final Document Storage:

All documents (hard copy) associated with the manufacturing will be stored in the PPPL Operations center for the lifetime of the NCSX Project.

# Quality Assurance/Quality Control Requirements

## Mission Statement: -Modular Coil QA/QC Plan

To observe and obtain any required information as may be necessary to assure that the manufacturing of the Modular Coils is being performed in accordance with the Manufacturing Facility Operations plan, Modular Coil Specifications, the NCSX Modular Coil Manufacturing Procedures and other applicable documents. [See section 2 for document numbers]

## Inspection/Surveillance and Audit:

Authorized representatives of the NCSX project will perform inspection and surveillances all during the manufacturing of modular coils. These representatives will include the Field Supervisors; lead technicians as well as the Quality Control (QC) representatives.

All measurements and tests will be performed by the field crews and engineering and do not require, unless outlined in the procedures, the presence of a QC representative.

Independent Audits may be performed by the Quality Assurance Division to ensure that approved manufacturing processes and quality of product is being observed.

## Inspection and Test Procedures:

Inspections and tests shall be performed in accordance with written/approved procedures referencing criteria for acceptance or rejection.  Adequate records shall be maintained and available for NCSX Project reviews.

## Document Traceability and Records:

The Modular Coil manufacturing team shall maintain a system of documentation whereby objective evidence of required operations, inspections, examinations, and tests is systematically compiled, indexed and stored.  Such objective evidence will include “travelers”; and material test, certification, inspection, examination, test and discrepancy reports; which shall be complete and legible and validated by responsible personnel and shall be traceable to subject items.

## Equipment/Material Identification and Status

Material and equipment identification shall be maintained throughout the program and be traceable to the records.  Status of acceptability shall be readily discernible through the use of tags, stamps, serial numbers or other positive means.

## Nonconformance’s & Corrective Actions:

Nonconforming items shall be positively identified, and, where possible, segregated to prevent use.  The Modular Coil Manufacturing Team shall document each non-conformance in accordance with PPPL procedure QA-005 “Control of Nonconformance’s”.

## Calibration of Test and Measuring Equipment:

Inspections and tests shall be performed using properly calibrated measuring and test equipment in accordance with PPPL procedure ENG-002  “Control of Measurement Test Equipment & Calibration”.

## Release for Station Transfer:

Prior to releasing a modular coil from one station to the next it is required that the all-responsible individuals sign the release indicating that all processes at that station have been satisfactorily completed.  The release (on the Traveler) will include signatures from the Station Lead Technician, Field Supervisor and the QC representative.

## Process History:

The Modular Coil Manufacturing team shall provide a Process History for the modular coils that includes a compilation of documents, detailing the objective evidence of the acceptability of the work performed.  The Process History shall include as a minimum, but not be limited to the following:

### Material Certifications:

The Modular Coil Manufacturing Team shall compile inspection reports, test data, and/or certifications from vendors, showing relevant chemical, mechanical and electrical properties of materials used, where applicable, as well as documents showing adherence to in-process requirements.  Material certifications from sub-tier suppliers shall also be submitted. {Certifications for the insulation, epoxy, conductor as well as chill plates and lead materials are required as a minimum}

### Inspection/ Test Documents:

Original or copies of filled in and completed process planning and control documents (travelers, etc.), which verify controlled execution of the required work.  Each modular coil will have its own set of process planning and control documents.

### Inspection Reports:

Copies of the original reports of all required inspections and examinations, properly validated by authorized personnel.

### Test Reports:

Copies of the original test data sheets or reports  of all required tests, both in-process and acceptance, properly validated by authorized personnel.