# NCSX

# Field Period Assembly (FPA) Manufacturing/Assembly, Inspection, Test and Quality Assurance Plan

NCSX-MIT/QA-185-01-00-dA

November 28, 2005

Author: ________________________________________________________________

Mike Viola - Field Period Assembly (FPA) Facility Manager

Reviewed By: ___________________________________________________________

Judy Malsbury - NCSX QA Representative

Reviewed By: ___________________________________________________________

Jerry Levine - PPPL Safety Representative

Reviewed By: ___________________________________________________________

Brent Stratton – Dimensional Control Coordinator

Reviewed By: ___________________________________________________________

Steve Raftopoulos – Lead Metrology Engineer

Reviewed By: ___________________________________________________________

John Edwards – FPA Field Supervisor

Reviewed By: ___________________________________________________________

Tom Brown - WBS Manager for FPA Tooling and Constructability (WBS 186)

Reviewed By: ___________________________________________________________

Brad Nelson -RLM for Stellarator Core Systems Design and Procurement

Approved By: ___________________________________________________________

Larry Dudek- RLM for NCSX Manufacturing Facility

Controlled Document

THIS IS AN UNCONTROLLED DOCUMENT ONCE PRINTED.

Check the NCSX Engineering Web prior to use to assure that this document is current.

Record of Revisions

| Revision | Date | Description of Change |
| --- | --- | --- |
| 0 |  | Initial release |

Table of Contents

1	Introduction and Scope	1

1.1	Introduction	1

1.2	Scope	1

2	Applicable Documents	1

3	Assembly Sequence – TOM BROWN	1

4	Assembly Stations	3

4.1	Station 1 – Vacuum Vessel Preparation (VVSA receipt Inspection, diagnostic loop and cooling tube installation)	3

4.2	Station 2 – Modular Coil Half-period Assembly	4

4.3	Station 3 – Modular Coil Installation	4

4.4	Station 4 – Final Field Period Assembly	5

4.5	Station 5 – TF Half-period Assembly	5

5	Safety and Training	5

6	Meetings and Communication	5

7	Process Documentation	5

# Introduction and Scope

## Introduction

The National Compact Stellarator Experiment (NCSX) will be assembled and built at Princeton Plasma Physics Laboratory.  The stellarator core will be preassembled into three 120° field period assemblies in the TFTR Test Cell.

The TFTR Test Cell is approximately 114 ft wide by 150 ft. long. The Coil Manufacturing Facility will occupy the east side of the building.  The Field Period Assembly will be located in the north and west side of the building. The building crane will be shared.

## Scope

Two plans have been prepared which cover the Field Period Assembly (FPA) activities.  These are the NCSX Manufacturing Operations Plan (NCSX-PLAN-MFOP) and this document, the NCSX Field Period Assembly Manufacturing, Inspection, Test, and Quality Assurance Plan (NCSX-MITQA-185).  The first document covers the entire Manufacturing Facility and discusses general facility operating guidelines; safety controls and reviews; permitting; and compliance with PPPL policies and procedures.

This document specifically addresses FPA activities, providing

- A description of the field period assembly sequence including a process outline

- A description of each station including tooling and fixtures

- A listing of governing specifications, assembly drawings, models, data files, and procedures for each station

- A process outline of the FPA Facility SAME AS FIRST ITEM

- A discussion of roles and responsibilities  IN MFOP

- A discussion of how the FPA Facility will be run including safety and training; meetings and communication; and process documentation. IN MFOP

# Applicable Documents

| Document Number | Title |
| --- | --- |
| ESH-004 | Job Hazard Analysis |
| ES&H 5008 | PPPL Environmental, Safety and Health Manual |
| NCSX-PLAN-MFOP-01 | NCSX Manufacturing Facility Operations Plan |
| NCSX-CSPEC-121-02 | VVSA Product Specification |
| WP-1224 | Work Planning Form for Field Period Assembly |
| ESH-008 | Access to Radiological Areas (RCA’s) |
| NEPA 1261 | FPA and Modular/TF Coil Development and Production? |
| D-NCSX-OP-EO-41 | NCSX Coil Manufacturing Facility Emergency Response |
| NCSX-? | NCSX FPA Metrology Plan |

# Assembly Sequence – TOM BROWN

SEE BELOW –

This is where Tom Brown’s input is translated into a top-level discussion of the assembly sequence and where the assembly stations and facility layout are introduced.  Let’s start with Station 1.

Material Receipt

  - VVSA receipt & inspection

  - Cooling Tubes receipt & inspection

  - Misc. hardware inspection guidelines

Procedure No.

NCSX-PROC- FPA -QA

Material Receipt

- VVSA Preparation

  - Locate diagnostic loops

  - Install templates

  - Install Diag Loops

  - Locate cooling tubes

  - Install tube clamp studs

  - Perform measurements

# Station No. V1

VVSA loops and tubes

Procedure No.

NCSX-PROC- FPA -001

Procedure No.

NCSX-PROC- FPA -002

- MC Assembly

  - Align and assembly 3 MC sets

# Station No. V2

MC Assembly

- Install MC Assembly and port extension

  - Align and Install VVSA

  - Install first 3 MC sets

  - Install Second 3 MC sets

  - Align and bolt together

  - Align and Weld Port extension

Procedure No.

NCSX-PROC- FPA -003

# Station No. V3

Install MC and port extension

- Assemble and Install TF Coils and Trim Coils

  - Assemble two 3 TF coil sets

  - Install Field Period

  - Install one 3 coil set onto TF fixture

  - Roll Coils on

  - Install second 3 coil set onto TF fixture

  - Roll Coils on

  - Install Trim Coils

Procedure No.

NCSX-PROC- FPA -004

# Station No. V4 Install TF and Trim Coils

- Final Prep for Transport

  - Perform Final Measurements

  - Install transportation supports

  - Load on truck

Station No. V5

Final Prep for transport

Procedure No.

NCSX-PROC- FPA -005

Send to NCSX Test Cell

Figure 1 - Field Period Assembly Process Outline

The overall layout of the FPA is found in figure 2.

Exit

Station #6

TF Coil Casting Assy

Station #1a

MC Prep

Station #1b

MC Prep

Station #3

Mfg TF Coils

Station #2

MC Mfg.

Station #4

MC Mfg.

Stat. #5

VPI

Station V1 VVSA then

Station V3 MC Install

Station V4 TF Install

Station V5 Storage

Station V2 MC Assy.

Crane limit 110T hook

Crane limit 25T hook

Crane limit

Crane limit 25T hook

Figure 3 FPA Layout (Need new layout of just FPA stations)

# Assembly Stations

NCSX-? provides the overall fpa Dimensional Control and Metrology Plan.

## Station 1 – Vacuum Vessel Preparation (VVSA receipt Inspection, diagnostic loop and cooling tube installation)

The Field Period Assembly will begin with the VVSA receipt Inspection, followed by the diagnostic loop and cooling tube installation. The Diagnostic loops will be installed using small tabs spot welded to the vessel surface and then the cooling tubes will be installed with studs welded to the surface and clamps applied.  NCSX-PROC- FPA -001 will govern the assembly sequence for station 1.

### Station 1 Tooling and Fixtures

This station is comprised of two trunions that will support the VVSA in a rotisserie style. This station will be built by the PPPL Tech Shop using drawing

Figure 3 Vacuum Vessel Support

### Station 1 Specifications, Assembly Drawings, Models, and Data Files – TOM BROWN?

| Document Number | Title |
| --- | --- |
|  | FPA Station 1 Specification |
|  | FPA Station 1 Assembly Drawing (top level) |
|  | FPA Station 1 Model |
|  | FPA Station 1 Supporting data files |

There will be at least one specification for each station.  The specification will identify performance requirements that will be verified by inspections and tests performed during or upon completion of the work at each station.  These inspections and tests need to be incorporated in the assembly procedures.  The spec will also identify an assembly drawing that will define the product upon completion of the work at each station.  Technical definition of the product may be supplemented by models and data files.  THIS SECTION SHOULD LIST RELEVANT SPECIFICATIONS, ASSEMBLY DRAWINGS, MODELS, AND DATA FILES.

## Station 2 – Modular Coil Half-period Assembly

This station is comprised of a tilting platform that will allow the modular coils to be aligned and bolted together.  NCSX-PROC- FPA -002 will govern the assembly sequence for station 2.

## Station 3 – Modular Coil Installation

This station is comprised of a support that will hold the vacuum vessel vertical and allow the modular coils to be rotated (screwed) onto each end of the VVSA, one at a time.  Then the ports will be aligned and welded on. From this point forward, the Assembly will be called the Field Period Assembly.  NCSX-PROC- FPA -003 will govern the assembly sequence for station 3.

## Station 4 – Final Field Period Assembly

This station is comprised of a support for the Field Period Assembly and a large column that will be used to support the TF Coils and rotate them onto the Field Period Assembly.  NCSX-PROC- FPA -004 will govern the assembly sequence for station 4.

## Station 5 – TF Half-period Assembly

This station is space set aside for minor intermediate operations or storage both between stations and in preparation for transportation to the NCSX Test Cell.  NCSX-PROC- FPA -005 will govern the assembly sequence for station 5.

# Safety and Training

Safety and training will be implemented per NCSX-PLAN-MFOP-01 section 9.

|  | Station V1 VVSA Prep | Station V2 MC Assy | Station V3 MC Install | Station V4 TF and Trim Coils Install | Station V5 Final Prep | Riggers & Crane Operators | Field Supervisors | QC Represent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Confined Space |  |  | X | X | X |  | X | X |
| General Employee (GET) | X | X | X | X | X | X | X | X |
| Radiation Safety | X | X | X | X | X | X | X | X |
| Hazard Communications | X | X | X | X | X |  | X | X |
| Hazard Awareness (JHA) | X | X | X | X | X | X | X | X |
| Mfg Facility Operations Plan | X | X | X | X | X |  | X | X |
| Lockout/Tagout | X | X | X | X | X |  | X | X |
| Basic Electrical | X | X | X | X | X |  | X | X |
| Ladder Safety | X | X | X | X |  |  | X | X |
| Fall Protection |  |  | X | X |  | X |  |  |
| Stud Welding | X |  |  |  |  |  |  |  |
| Rigging &/or crane operator training |  |  |  |  |  | X |  |  |
| Mechanical Arm training- Romer (operators only) | X | X |  |  |  |  |  |  |
| Fire Extinguisher | X | X | X | X |  |  | X |  |
| Emergency Response Procedure | X | X | X | X | X | X | X | X |

Table 1 - Field Period Assembly Training Matrix

# Meetings and Communication

Meetings and the flow of communications will be per NCSX-PLAN-MFOP-01 Section 10.

# Process Documentation

Process documentation (e.g. travelers, NCRs, etc.) will be developed, maintained and archived per NCSX- PLAN-MFOP-01 Section 11.

WAYNE – Are Sections 6 and 7 needed, they just point back to the MFOP