# NCSX

# Field Period Assembly (FPA) Manufacturing/Assembly, Inspection, Test and Quality Assurance Plan

NCSX-MIT/QA-185-01-00

February 28, 2006

Author: ________________________________________________________________

Mike Viola - Field Period Assembly (FPA) Facility Manager

Reviewed by:

Jim Chrzanowski					     Judy Malsbury

NCSX Manufacturing Facility Manager				NCSX QA Representative

Jerry Levine					     	   Brent Stratton

PPPL Safety Representative				           Dimensional Control Coordinator

Steve Raftopoulos					      John Edwards

Lead Metrology Engineer				           FPA Field Supervisor

Tom Brown					     	Brad Nelson

WBS 186 Manager				           Stellarator Core Design RLM

_________________________________________

Wayne Reiersen

NCSX Engineering Manager

Approved By: ___________________________________________________________

Larry Dudek

RLM for the NCSX Manufacturing Facility

Controlled Document

THIS IS AN UNCONTROLLED DOCUMENT ONCE PRINTED.

- Check the NCSX Engineering Web prior to use to assure thatFinal Prep for Transport

  - Perform Final Measurements

  - Install transportation supports

  - Load on truck

  - Locate cooling tubes

  - Install tube clamp studs

  - Perform measurements

  - nsion

document is current.

Record of Revisions

| Revision | Date | Description of Change |
| --- | --- | --- |
| 0-dD | 1/16/2006 | Complete re-write and reformatting. |
| 0-dE | 2/28/2006 | More Formatting and editorial comments |
| 0-dF | 2/28/2006 | Comment incorporation and alignment with existing MC MIT/QA again |

Table of Contents

1	Introduction and Scope	1

1.1	Introduction	1

1.2	Scope	1

2	Applicable Documents	1

2.1	Governing Documents	2

2.2	Training Requirements	Error! Bookmark not defined.

3	Field Period Assembly Processes	3

3.1	Overall Field Period Assembly Process Outline	3

3.2	Field Period Assembly  Stations and Procedures	5

3.2.1	Station 1 – Vacuum Vessel Preparation	5

3.2.1.1	Station 1 Assembly Activities	5

3.2.1.2	Station 1 Tooling and Fixtures	6

3.2.2	Station 2 – Modular Coil Half-Period Assembly	6

3.2.3	Station 3 – Modular Coil Installation	6

3.2.4	Station 4 – Final Field Period Assembly	6

3.2.5	Station 5 – TF Half-period Assembly	7

4	Documentation Requirements	7

4.1	Document Control	7

4.2	Field Assembly Station Field Packages	7

4.3	Assembly/Injstallation Procedure Sign-Off’s	7

4.3.1	Procedure Completion	7

4.3.2	Authorized Signoff’s for Manufacturing Completions	7

4.4	Final Document Storage	8

5	Quality Assurance/Quality Control Requirements	Error! Bookmark not defined.

5.1	Inspection/Surveillance and Audit	Error! Bookmark not defined.

5.2	Inspection and Test by Field Crews and Engineering	Error! Bookmark not defined.

5.3	Equipment/Material Identification and Status	Error! Bookmark not defined.

5.4	Non-conformance & Corrective Actions	Error! Bookmark not defined.

5.5	Release for Station Transfer	Error! Bookmark not defined.

5.6	Process History	Error! Bookmark not defined.

5.6.1	Material Certifications	Error! Bookmark not defined.

5.6.2	Inspection/ Test Documents	Error! Bookmark not defined.

5.6.3	Inspection Reports	Error! Bookmark not defined.

5.6.4	Test Reports	Error! Bookmark not defined.

6	Specification Verification Activities Check list	8

List of Figures

Figure 4-1 Field Period Assembly Process Outline	4

Figure 4-2 FPA Area Layout (Need new layout of just FPA stations)	5

Figure 4-3 Vacuum Vessel Support	6

# Introduction and Scope

## Introduction

### The National Compact Stellarator Experiment (NCSX) will be assembled and built at Princeton Plasma Physics Laboratory.  The stellarator core will be preassembled into three 120° field period assemblies in the TFTR Test Cell.  There will be five (5) stations to accomplish this task.  Once completed, the Field Period Assemblies (FPA) will be moved into the NCSX test cell.

## Scope

### This document addresses the manufacturing, inspection, test and Quality Assurance (QA) plan to complete and deliver three (3) Field Period Assemblies for the NCSX Project to the NCSX test cell.

# Applicable Documents

### Three plans have been prepared which cover the Field Period Assembly (FPA) activities.  These are the NCSX Manufacturing Operations Plan (NCSX-PLAN-MFOP-01), the Field Period Assembly Sequence Plan (NCSX-PLAN-SEQ-FPA1) and this document, the NCSX Field Period Assembly Manufacturing, Inspection, Test, and Quality Assurance Plan (NCSX-PLAN-MIT/QA-185-01).

### The Manufacturing Facility Operations Plan describes how the activities within the NCSX Manufacturing Facility will meet PPPL Integrated Safety Management (ISM) requirements specified in laboratory policies, programs, and procedures.  It also provides an overview of the general processes that occur in the facility, including general facility operating guidelines, safety controls, and reviews.

### The Field Period Sequence Plan provides guidance to convey the designer’s intentions as to how the Field Period Assembly is to be performed.  Field period procedures will be developed from the sequence plan, in combination with this MIT/QA plan, which explains how to perform the tasks at each of the 5 assembly stations.

### This document specifically addresses FPA activities, providing:

- A description of the field period assembly sequence including a process outline;

- A description of each station including tooling and fixtures; and

- A listing of governing specifications, assembly drawings, models, data files, and procedures for each station.

### Identified below are the primary documents that that will be needed to complete the FPA.

## NCSX Project Documents for FPA

| Document No. | Title |
| --- | --- |
| NCSX-CSPEC-141-03 | Modular Coil Winding Form Specification |
| NEPA No. 1224 | Modular Coil Development and Production |
| NCSX-PLAN-MFOP-01 | NCSX Manufacturing Facility Operations Plan |
| WP-1138 | Manufacturing of Production Coils |
| D-NCSX-OP-EO-41 | NCSX Coil Manufacturing Facility Emergency Response |
| NCSX-PLAN-MCWDC-00 | Modular Coil Dimensional Control Plan |

## Field Period Assembly Manufacturing Procedures

| Document No. | Title |
| --- | --- |
| D-NCSX- FPA -QA1 |  |
| D-NCSX- FPA -001 | Mod Coil Fab- Casting Preparation Activities |
| D-NCSX- FPA -002 | Mod Coil Fab- Winding/Molding Activities |
| D-NCSX- FPA -003 | Mod Coil Fab- VPI Activities |
| D-NCSX- FPA -004 | Mod Coil Fab- Post VPI Activities |
| D-NCSX- FPA -005 | Dimensional Control & Metrology for Modular Coils |

## Drawings

### Drawings for each field period assembly and station will be provided by the NCSX project.  Only signed and “Approved For Fabrication” stamped drawings may be used.  A complete list of field period drawings is listed in the filed period assembly specification.

# Training Requirements

### Training of personnel working on the FPA is critical to successfully completing the assembly of the FPA.  There are two categories of training requirements, general and specialized.

## General Training Requirements

### General training includes all laboratory-training requirements that are required to enter or work in the Manufacturing Facility.  Examples of this training include:

- General Employee Training [GET]

- Integrated Safety Management [ISM]

- Radiation Safety Training

## Specialized Training Requirements

### Specialized training includes specific training or certification required to complete tasks during the assembly of the FPA.  Examples include:

- Weld or braze certifications

- Confined space

- NCSX Manufacturing Facility Operations Plan [MFOP]

## Training Matrix

### An NCSX Manufacturing training matrix exists for the FPA stations which is posted on the NCSX Web site.

# Field Period Assembly Processes

## Overall Field Period Assembly Process Outline

### This section outlines the processes that are to be performed and procedures required to complete field period assembly.  Figure 4-1 provides a pictorial of the general layout with the NCSX manufacturing facility.  The FPA activities will take place along the North wall and in the South West corner.  The Modular Coil activities take place along the East wall and on the center 102 foot elevation.

Figure 4-1  FPA Area Layout

### 2 provides an outline of the overall field period assembly process and provides a layout of the Field Period Assembly layout within the NCSX Manufacturing Facility.

Send to NCSX Test Cell

Assemble and Install TF Coils and Trim Coils

Assemble two 3 TF coil sets

Install Field Period

Install one 3 coil set onto TF fixture

Roll Coils on

Install second 3 coil set onto TF fixture

Roll Coils on

Install Trim Coils

Material Receipt

VVSA receipt & inspection

Cooling Tubes receipt & inspection

Misc. hardware inspection guidelines

MC Assembly

Mechanically Align and assemble 3 MC set

Magnetically align two 3 coil sets

Final Prep for Transport

Perform Final Measurements

Install transportation supports

Load on truck

VVSA Preparation

Locate diagnostic loops

Install templates

Install Diag Loops

Locate cooling tubes

Install tube clamp studs

Perform measurements

Install MC Assembly and port extension

Align and Install VVSA

Install first 3 MC sets

Install Second 3 MC sets

Align and bolt together

Align and Weld Port extension

Procedure No.

D-NCSX- FPA -004

Procedure No.

D-NCSX- FPA -003

Procedure No.

D-NCSX- FPA -005

Procedure No.

D-NCSX- FPA -001

Procedure No.

D-NCSX- FPA -002

Procedure No.

D-NCSX- FPA -QA1

Station No. V4 Install TF and Trim Coils

Material Receipt

Station No. V2

MC Assembly

Station No. V3

Install MC and port extension

Station No. V5

Final Prep for transport

Station No. V1

VVSA loops and tubes

Figure 4-2 Field Period Assembly Process Outline

## Field Period Assembly Stations and Procedures

### Each Field Period procedure will be generated from an approved sequence plan generated to

### Station 1 – Vacuum Vessel Preparation

#### Station 1 Assembly Activities

The Field Period Assembly will begin with the VVSA receipt Inspection, followed by the diagnostic loop and cooling tube installation. The Diagnostic loops will be installed using small tabs spot welded to the vessel surface and then the cooling tubes will be installed with studs welded to the surface and clamps applied.  The Assembly Sequence Plan (NCSX-PLAN-SEQ-FPA1), Station 1 Dimensional Control Plan (NCSX-PLAN–PA1DC), and top-level assembly drawing (SE185-???) provides guidance from the designer and dimensional control coordinator on how the components being handled in Station 1 were designed to be assembled and what dimensional control checks are needed.

The Field Period Assembly Manager will utilize these plans and the top-level assembly drawing as a basis for developing the FPA Station 1 Detailed Installation/Assembly Procedure (D-NCSX-FPA-001). This detailed procedure and any related detailed drawings shall govern each step in the assembly sequence for Station 1.

Confirmation of specification verification activities are shown in Appendix A to this MIT/QA Plan

#### Station 1 Tooling and Fixtures

This station is comprised of two trunions (See ) that will support the VVSA in a rotisserie style. This station will be built by the PPPL Tech Shop using drawing SE184-001.

Figure 4-1 Vacuum Vessel Support

### Station 2 – Modular Coil Half-Period Assembly

This station is comprised of a tilting platform that will allow the modular coils to be aligned and bolted together. Details TBD.

### Station 3 – Modular Coil Installation

This station is comprised of a support that will hold the vacuum vessel vertical and allow the modular coils to be rotated (screwed) onto each end of the VVSA, one at a time.  Then the ports will be aligned and welded on. From this point forward, the Assembly will be called the Field Period Assembly.  Details TBD.

### Station 4 – Final Field Period Assembly

This station is comprised of a support for the Field Period Assembly and a large column that will be used to support the TF Coils and rotate them onto the Field Period.  Details TBD.

### Station 5 – TF Half-period Assembly

This station is space set aside for minor intermediate operations or storage both between stations and in preparation for transportation to the NCSX Test Cell. Details TBD.

# Documentation Requirements

## Document Control

All NCSX associated documents providing instruction for assembling the field period assembly (e.g. plans and procedures) will be maintained under NCSX Project document control.

## Field Assembly Station Field Packages

Each field period assembly station shall have a “Station Field Package” that shall be maintained by the field period assembly team.  This package shall include all process procedures, inspection reports, photographs, test results, and measurements used to document completion of major activities associated with the activities in each station to assemble the field period assembly. It shall also include ECNs, non–conformance reports (NCR), or other exceptions to or changes in requirements.  All documents shall be complete, legible and validated by responsible personnel.

## Assembly/Installation Procedure Sign-Off’s

Assembly/Installation procedures will be used as a signoff/approval document noting that critical manufacturing steps have been completed.  Authorized personnel associated with the manufacturing, inspection and test processes will perform the signoff’s. In addition, it will provide witness points as well as reference for test results, and measurements.

### Procedure Completion

The Lead Technician or Field Supervisor will document all critical completions on the procedure.  This will be completed using the signer’s initials or full signature.

The procedures will be filled out in a timely fashion once a particular activity has been completed.

### Authorized Signoff’s for Manufacturing Completions

The manufacturing procedures will identify what level of signoff is required for a particular step.  The following disciplines are the authorized signatures for the in-process procedures.

- Station Lead Technicians

- Field Supervisors

- Quality Control Representative

- Manufacturing Facility Manager

## Final Document Storage

All documents (hard copy) associated with the manufacturing will be stored in the PPPL Operations center, electronic documents will be stored on the NCSX Web site for the lifetime of the NCSX MIE Project, after which the files will be turned over to the Operations Center.

# Quality Assurance/Quality Control Requirements

## Inspection/Surveillance and Audit:

Field Supervisors; lead technicians and Quality Control (QC) representatives will perform FPA inspection and surveillances as required by FPA procedures.

Independent Audits may be performed by the Quality Assurance Division to ensure that approved manufacturing processes and quality of product is being observed.

## Inspection and Test Procedures:

Inspections, measurements, and tests will be performed by the field crews and engineering. Where required by procedure, a QC representative shall be present during inspections, measurements, or tests.

Inspections and tests shall be performed:

- 	In accordance with written/approved procedures referencing criteria for acceptance or rejection.

-  	Using properly calibrated measuring and test equipment in accordance with PPPL procedure ENG-002 “Control of Measurement Test Equipment & Calibration”.

Adequate records to reproduce the inspection shall be maintained and available for NCSX Project reviews.

## Equipment/Material Identification and Status

Material and equipment identification shall be maintained throughout the program and be traceable to the records.  Status of acceptability shall be readily discernible through the use of tags, stamps, travelers, serial numbers or other positive means.

## Non-conformance & Corrective Actions:

Nonconforming items shall be positively identified, and, where possible, segregated to prevent use.  The Modular Coil Manufacturing Team shall document each non-conformance in accordance with PPPL procedure QA-005 “Control of Non-conformances”.

## Release for Station Transfer:

Prior to releasing a VVSA or FPA from one station to the next, the Station Lead Technician, Field Supervisor, FPA Manager and the QC representative will review and approve the release indicating that all processes at that station have been satisfactorily completed. The Lead Tech and Field Supervisor are signing that the procedural aspects of the assembly stage are completed.  The FPA Manager is signing that the Documentation package is complete and ready for verification.  The QA representative is signing that he has reviewed the documentation package, verified that it is complete and verified that it meets all specification requirements and tests.

## Process History:

The FPA team shall provide a Process History for the VVSA or FPA that includes a compilation of documents, detailing the objective evidence of the acceptability of the work performed.  Process History shall be stored in the Operations Center after assembly is completed. The Process History shall include as a minimum, but not be limited to the following:

### Material Certifications:

The FPA Team shall compile inspection reports, test data, and/or certifications from vendors, showing relevant chemical, mechanical and electrical properties of materials used, where applicable, as detailed in applicable procedures, as well as documents showing adherence to in-process requirements.  Material certifications from sub-tier suppliers shall also be submitted.

### Inspection/ Test Documents:

Original or copies of filled in and completed process planning and control documents (procedures, etc.), which verify controlled execution of the required work.  Each FPA will have its own set of process planning and control documents.

### Inspection Reports:

Copies of the original reports from all required inspections and examinations, that are properly validated by authorized personnel.

### Test Reports:

Copies of the original test data sheets or reports of all required tests, both in-process and acceptance, that are properly validated by authorized personnel.

# Specification Verification Activities Check list

Figure 7-2 provides a pointer to where in detailed procedures the confirmation of specification verification activities has been accomplished.

| Specification | Verification Activity | FPA Procedure | FPA Procedure Section |
| --- | --- | --- | --- |
| NCSX-CSPEC-XXX-01 (XYZ Component) | 4.x.x - Weight – verification that the weight of the assembled components is in conformance the requirements of the specification. | D-NCSX-FPA-001 | Section y.y.y |
|  |  | D-NCSX-FPA-002 |  |
|  |  | D-NCSX-FPA-003 |  |
|  |  | D-NCSX-FPA-004 |  |
|  |  | D-NCSX-FPA-005 |  |

Figure 7-2 Confirmation of Verification Activity Check List

NOTE:  THIS IS ONLY INTENDED AS A FORMAT SAMPLE – WE WILL HAVE TO CHECK THE GRD, BSPECs, AND CSPECs TO DETERMINE WHAT ARE THE REQUIREMENTS.