## Sheet1
| Field Period Assembly Steps | Days
Stage 1 (VV Prep) Not a critical path task |  | 39
1 | Receive VV, inspect and test
2 | Mount to installation fixture and align temporary support base.
3 | Mount magnetic diagnostic sensors to surface.
4 | Install cooling/heating lines to vacuum vessel surface
5 | Install insulation to vacuum vessel
Stage 2 - R (MC Half Period Assembly - Right side) |  | 26
1 | Mount mating Type C in holding fixture; take metrology measurements to define part orientation; mark and store for next period | 2
2 | Mount another Type C assembly in holding fixture, take metrology measurements to define part orientation and make C to C tooling ball adjustments | 2
3 | Mount Type C in half period assembly fixture; tilt fixture to accept Type B | 1
4 | Mount Type B in holding fixture; take metrology measurements to define part orientation; make B to C tooling ball adjustments | 2
5 | Mount Type B in half period assembly fixture; tilt fixture to accept Type A | 0.5
6 | Take C to B gap measurements; fabricate shims | 5
7 | Separate C and B as required to install shims; bolt together; perform metrology position check | 2
8 | Mount Type A in holding fixture; take metrology measurements to define part orientation; make A to B tooling ball adjustments | 2
9 | Mount Type A in half period assembly fixture; | 0.5
10 | Take B to A gap measurements; fabricate shims | 5
11 | Separate B and A as required to install shims; bolt together; perform metrology position check | 2
12 | Mount mating Type A in holding fixture; take metrology measurements to define part orientation; make A to A tooling ball adjustments; mark and store for next period | 2
Stage 2 - L (MC Half Period Assembly - Left side) |  | 24
1 | Mount mating Type C in holding fixture; take metrology measurements to define part orientation; mark and store for next period | 2
2 | Mount another Type C assembly in holding fixture, take metrology measurements to define part orientation and make C to C tooling ball adjustments | 2
3 | Mount Type C in half period assembly fixture; tilt fixture to accept Type B | 1
4 | Mount Type B in a holding fixture; take metrology measurements to define part orientation; make B to C tooling ball adjustments | 2
5 | Mount Type B in half period assembly fixture; tilt fixture to accept Type A | 0.5
6 | Take C to B gap measurements; fabricate shims | 5
7 | Separate C and B as required to install shims; bolt together; perform metrology position check | 2
8 | Mount Type A in holding fixture; take metrology measurements to define part orientation; make A to B tooling ball adjustments | 2
9 | Mount Type A in half period assembly fixture; | 0.5
10 | Take B to A gap measurements; fabricate shims | 5
11 | Separate B and A as required to install shims; bolt together; perform metrology position check | 2
12 | Not needed for left side half period
Stage 3 (MC installation) |  | 20
1 | Mount VV to MC turning fixture assembly | 1
2 | Rotate right MC to stand-off position | 1
3 | Check position, transfer load to gantry crane and recheck position | 2
4 | Move MC turning fixture to left side and mount left side MC | 1
5 | Rotate left MC to stand-off position and check position | 2
6 | Move left and right MC to final position and take gap measurements for shim fabrication | 5
7 | Back off left and right MC’s slightly to install shims. | 2
8 | Move MC’s to final position with shims in place; perform metrology position check | 2
9 | Bolt left and right MC’s at interface; perform metrology position check | 2
10 | Assemble VV support hardware to MC structure and attach VV to MC’s | 2
Stage 4 (Final FP Assembly) |  | 60
1 | Mount MC/VV assembly to support frame at final assembly station | 1
2 | Position and weld all ports to VV except for the two large horizontal diagnostic ports | 10
3 | Assemble right TF Coil Assembly | 1
4 | Assemble left TF Coil Assembly | 1
5 | Attach TF coils to MC's | 2
6 | Position and weld two large horizontal diagnostic ports to VV | 5
7 | Bakeout VV to 150 deg C and leak check | 26
8 | Assemble external trim coils to TF Coil | 5
9 | Using metrology measurements adjust final support base interfaces | 2
10 | Prepare Field Period for shipment | 2
11 | Ship Field Period | 1
12 | Field Period ready for installation | 4
- place Field Period on device core radial support system (1 day)
- perform metrology measurements to assure final alignment (3 days)
| Total Elapse Time | 169