## Sheet1
Optimize and document the process for aligning the coils (especially the modular coils) (1901)
| Task | status | next | Est. to complete
|  |  |  | Who | Hours | $ labor | $ matl. | Start Date | duration | Finish Date
1 | Where is winding center for as-built coil? | Wrote code to implement SVD method for determining winding center based on grid of field measurements. Results so far good to within 80 % of initial error. | improve on results via iteration on solution | Strickler | 0 | 0
1a | - Accuracy of determination vs accuracy of absolute field measurement | initial results not impacted if error is within .001 (.1% accuracy) |  |  |  | 0
1b | - Accuracy of determination vs accuracy of field measurement location | function of field gradient, closer points must be more accurate | put random error in grid point locations and re-run problem | Strickler | 0 | 0
1c | - effect of 3 axis (Hall probe) vs Bmod (NMR probe) | Both capabilities in code, NMR is quicker |  |  |  | 0
1e | Replace coil winding center representation with 3D coil model |  |  |  | 80
1f | transform field measurements (hall probe) into coil coordinate system |  |  |  | 40
1d | - document code and procedure | draft report written | add procedure for coil measurement and recommend no. of points in grid, grid spacing relative to coil, accuracy of field measurement, and accuracy of field measurement location | Strickler | 16 | 2800
2 | Where do we put the coils once they are built? |  |  | Strickler | 40 | 7000
2a | stellarator symmetric coils | optimization installed in Stellopt to provide best rotation and translation of coil to reduce island sizes, using "residue" method |  |  |  | 0
2b | non-stellarator symmetric coils | Under development outside STELLOPT | 1. method for finding island location and size in 2D must be adapted for non-symmetric case (try grid method first) | Strickler / Hirshman |  | 0
|  |  | 2. incorporate in Stellopt(?) |  |  | 0
2c | Additional tasks |  | 1. must include coil currents as variables in vacuum optimization (need to include separate coil current distributions for low and high beta in Stellopt) |  |  | 0
|  |  | 2. establish effect of vacuum optimization of coil geometry on high beta physics |  |  | 0
2d | - document code and procedure | status report written in May, updated in Sept. | Add procedure for using codes and example problems to document/benchmark code | Strickler | 40 | 7000
4 | Prepare test setup
| Procure Hall probe | Tentative selection of GMW 3M 12-4-3-.2T and associated aluminum holder, waiting on cost estimate |  | Nelson | 8 | 1400 | 10000
4a | Borrow Romer arm from PPPL | Romer arm ordered? |  | Raftopolous | 8 | 1400 | 200
4b | Integrate Hall probe / Romer arm
| mechanical integration / drawings | not started | get Romer end effector drawings and design adaptor piece | Cole | 40 | 7000
|  |  | fabricate adaptor piece | vendor |  |  | 2500
|  |  | mount adaptor piece | Fehling | 8 | 1400
| electrical integration / data acquisition | not started | get Hall probe and Romer arm interface information and design software/hardware to synchronize and acquire data | Fehling | 40 | 7000 | 3000
5 | Test racetrack coil | not started | 1. Establish method to energize coil at low current (~0.5 ka/turn) | Gettlefinger | 8 | 1400
|  | not started | 2. Establish metrology targets at 10 slices through coil | Raftopolous | 40 | 7000
|  | not started | 3. Write safety plan / procedure for coil test | Gettelfinger | 16 | 2800
|  | not started | 4. Set up coil and make field measurements | Raftopolous | 40 | 7000
| Predict current center from magnetic meas. | not started | 1.Model theoretical UT coil, with leads | Strickler | 40 | 7000
|  | not started | 2.Run BFIT code | Strickler | 16 | 2800
| Dissect coil and determine physical current center | not started | Cut coil at metrology targets and determine coil center at these locations | PPPL shop | 40 | 4000
| Compare predicted winding geometry to measured winding geometry | not started | Reassess technique, propose additional work, if required | Strickler | 8 | 800
|  |  |  | TOTALS | 528 | 67800 | 15700

## Sheet1 (2)
Optimize and document the process for aligning the coils (especially the modular coils) (1901)
| Task | status | next | Est. to complete | [9 empty] | ORNL | PPPL
|  |  |  | Who | Hours to go | $ labor | $ matl. | $total | Start Date | duration | Finish Date
1 | Where is winding center for as-built coil? | complete |  | Strickler | 0 | 0 | 0 | 0
1a | - Accuracy of determination vs accuracy of absolute field measurement | complete |  |  |  | 0 | 0 | 0
1b | - Accuracy of determination vs accuracy of field measurement location | complete |  | Strickler | 0 | 0 | 0 | 0
1c | - effect of 3 axis (Hall probe) vs Bmod (NMR probe) | complete |  |  |  | 0 | 0 | 0
1e | Replace coil winding center representation with 3D coil model | Use of MAGFOR planned |  |  | 80 | 14000 | 0 | 14000
1f | transform field measurements (hall probe) into coil coordinate system | not started |  |  | 80 | 14000 | 0 | 14000
1d | - document code and procedure | draft report written | add procedure for coil measurement and recommend no. of points in grid, grid spacing relative to coil, accuracy of field measurement, and accuracy of field measurement location | Strickler | 40 | 7000 | 0 | 7000 |  |  |  | 35000 | 35000 | 35000
2 | Where do we put the coils once they are built? |  |  |  |  | 0 |  | 0
2a | stellarator symmetric coils | optimization installed in Stellopt to provide best rotation and translation of coil to reduce island sizes, using "residue" method |  |  | 0 | 0 |  | 0
2b | non-stellarator symmetric coils | Under development outside STELLOPT | 1. method for finding island location and size in 2D must be adapted for non-symmetric case (try grid method first) | Strickler / Hirshman | 80 | 14000 |  | 14000
|  |  | 2. incorporate in Stellopt(?) |  | 80 | 14000 |  | 14000
2c | Additional tasks |  | 1. must include coil currents as variables in vacuum optimization (need to include separate coil current distributions for low and high beta in Stellopt) |  | 80 | 14000 |  | 14000
|  |  | 2. establish effect of vacuum optimization of coil geometry on high beta physics |  | 80 | 14000 |  | 14000
2d | - document code and procedure | status report written in May, updated in Sept. | Add procedure for using codes and example problems to document/benchmark code | Strickler | 40 | 7000 |  | 7000 |  |  |  | 63000
3 | Review progress |  |  | Strickler | 8 | 1400 |  | 1400
1400
4 | Prepare test setup
| Procure Hall probe | Tentative selection of GMW 3M 12-4-3-.2T and associated aluminum holder |  | Nelson | 8 | 1400 | 10000 | 11400 | [5 empty] | 11400
4a | Borrow Romer arm from PPPL |  |  | Raftopolous | 8 | 1400 | 200 | 1600 | [6 empty] | 1600
4b | Integrate Hall probe / Romer arm
| mechanical integration / drawings | not started | get Romer end effector drawings and design adaptor piece | Cole | 40 | 7000 |  | 7000 | [5 empty] | 7000
|  |  | fabricate adaptor piece | vendor |  |  | 2500 | 2500 | [5 empty] | 2500
|  |  | mount adaptor piece | Fehling | 8 | 1400 |  | 1400 | [5 empty] | 1400
| electrical integration / data acquisition | not started | get Hall probe and Romer arm interface information and design software/hardware to synchronize and acquire data | Fehling | 40 | 7000 | 3000 | 10000 |  |  |  | 33900 | 33900 | 10000
5 | Test racetrack coil | not started | Establish method to energize coil at low current (~0.5 ka/turn) | Gettlefinger | 16 | 2800 |  | 2800 | [6 empty] | 2800
|  | not started | Write safety plan / procedure for coil test | Gettelfinger | 16 | 2800 |  | 2800 | [6 empty] | 2800
|  |  | Hook up power supply | PPPL Tech | 16 | 1600 | 1000 | 2600 | [6 empty] | 2600
|  | not started | Set up coil and make field measurements | Raftopolous | 40 | 7000 |  | 7000 |  |  |  | 15200 | 15200 |  | 7000
6 | Predict current center from magnetic meas. | not started | Model theoretical TRC coil, with leads | Strickler | 40 | 7000 |  | 7000
|  | not started | Run BFIT code | Strickler | 16 | 2800 |  | 2800 |  |  |  | 9800 | 9800 | 9800
7 | Establish actual coil current center | not started | Establish metrology targets at 10 slices through coil | Raftopolous | 40 | 7000 | 500 | 7500
|  | not started | Cut coil at metrology targets and determine coil center at these locations | PPPL shop | 40 | 4000 |  | 4000 |  |  |  | 11500
8 | Compare predicted winding geometry to measured winding geometry | not started | Compare data, reassess technique, propose additional work, if required | Strickler | 24 | 4200 |  | 4200 |  |  |  | 4200 | 4200 | 4200
subtotal
|  |  |  | TOTALS | 920 | 156800 | 17200 | 174000 |  |  |  |  | 98100 | 81300 | 16800
3000iSC
12 foot arm, 6 foot radius
have the arm
have the software
need the computer