Proposed VVSA Design Change  Replace spool piece and flanges on the ends of the VV sectors with 5 discrete plates per period to bridge the gap between VV sectors.  The plates would be fabricated from the cutoffs from panels pressed at MTM and formed in situ to the tolerances required for welding through the use of “C” clamps.

ORNL posed questions below on the proposed design that should be addressed by the proponents.

- Are backing rings installed at the weld locations, both poloidal and toroidal?

- Is gas fed into the backing rings from inside or are there separate tubes on the outside?

- Is the thermal insulation stuffed into place and attached to the mod coils?

- Do we eliminate the cooling/heating tubes in this region?

- Are all the plates tacked into position prior to final welding, or are they fully welded one at a time?

- Are the weld preps ground out in place?

- Is the vessel positioned slightly outboard of its nominal position so weld shrinkage carries into its final position?

- Is the radial port eliminated, attached to one of the in-situ plates or is there a hole in the in-situ plate?

- We are spending a lot of money to get a vessel that is supposed to be within 3/16 inch of its theoretical shape.  Are we willing to let it go wherever it wants to go during in-situ forming and welding?  If it is ok for the vessel field periods to move around, then this method should work.  It is not clear how we control where the vessel goes when we are using clamps and jacks to push everything around.  We still need clearance so the coils can cool down and the vessel can heat up and the insulation is still viable.  Preserving the tight clearance for NB injection is also a concern.

Summary

There are really two issues that need to be the addressed.  The first is a potential showstopper.  Proponents of changing the VVSA design argue that forming the plates in situ through the use of “C” clamps connected to the VV segments is no problem.  Skeptics are worried that this cannot be done without moving or deforming the VV segments.  (Moving or deforming the VV segments in the process is not acceptable.)  The skeptics point out that these segments are only hung by a couple of rods which cannot resist anything but vertical loads.  It seems that the burden of proof lies with the proponents that the in situ forming can be done without moving or deforming the VV segments.

If we get by this potential showstopper, then the second issue is whether the anticipated reduction in technical risk and cost and schedule benefits warrant making the change.  There are compelling arguments that the cost to manufacture the VVSA should go down but there is also the real possibility (and cost risk) that the contract price could go up significantly.  Costs for project activities should go down a bit.  Cost increases associated with implementing the change should be more than offset by eliminating the design and fabrication costs for the spool handling fixture and for installing the spool pieces on the fixture and testing the movement during final assembly.  No compelling schedule advantages were identified.  In fact, there might be a schedule disadvantage forming the plates in situ during final assembly versus installing a pre-fit spool piece.

No unmanaged technical risks have been identified for the baseline design.  The proposed design does have the potential showstopper of moving/distorting the vessel segments during the clamping/forming process.

Discussion of potential impacts of adopting proposed design change

Advantages of the proposed change are shown in blue, disadvantages in red.  Neutral and uncertain impacts are shown in black.

Technical impacts

- It is not clear to all that forming the plates in situ can be accomplished using “C” clamps without moving or deforming the VV segments.  This is a potential showstopper.  If the plates do not fit, any clamping will move the vessel field periods as rigid bodies long before it bends the 3/8 inch Inconel plates.

- The design basis for the proposed design not as substantial.  There is a risk of introducing new technical issues.  We need to draw the new design so we understand what it is.

- Reduced risk of not being able to assemble the modular coils over the VV during field period assembly should parts come in out of spec because of the lower profile without the flanges.  (This is only true if the vessel is nominal and not at the extremes of its envelope.  Note that the flanges are machined to a true position shape, not a shape relative to the vessel shell.  The vessel shell can be at the edge of the flange.)

- Less distortion is expected when making the final closure welds because the welds are smaller.

Cost impacts

- Adopting a new design costs money to change the baseline documentation, process a contract change, and for the supplier to adopt the change.

  - The cost impacts within the project should be modest.  Brown estimated 80 hours ($10K) to change the models and drawings, but it could be a lot higher.  ORNL reported that it took 140 hours just to make a STEP file. Administrative activities would largely be performed by folks who are LOE so it is not clear there would be a visible cost impact here.  However, just considering the change is proving to be a distraction for key personnel.

  - The incremental cost to the VVSA contract is TBD (and that is a big TBD).  It would be a project-directed change and an opportunity for MTM to “get well”.  It would cost them money administratively to implement the change.  However, MTM appears very supportive of this change per Viola.  It should make their job simpler and more profitable.  Although it is unlikely that the contract cost would go down, MTM might be less likely to send us a bill for costs incurred as a result of the misinformation they received from us regarding how much the VV shape changed from the PVVS.  Then again, they might indeed choose this opportunity to “get well” and cover past and future oversights and misjudgments.

- Additional analysis will need to be done to underpin the design modifications.  The scope and cost impact of these additional analyses are expected to be modest, but still TBD.

- The proposed design eliminates costs not already incurred to design and fabricate the fixture for handling the spool piece during final assembly, perhaps saving up to $80K but there may be a similar cost for a fixture to position the 3 field periods semi-rigidly so the splice plates can be welded in.

- No significant cost impact expected during field period assembly.

- Eliminating the need to install the spool pieces and test movement could save perhaps $40 K.

- No significant cost impact anticipated due to field welding during final assembly.  There are more linear feet of weld but the welding should go much faster according to Dudek.

Schedule impacts

- Impact on VVSA delivery schedule TBD.  Delays associated with developing and implementing the proposed design change should tend to be offset by faster production time (due to eliminating the spool piece).

- The time required for installation and trial runs using spool piece fixture is not on the critical path so it is only money that would be saved here.

- The spool piece is measured and machined during field period assembly and should not be on the critical path (except perhaps for the last one).  Custom fitting 15 splice plates would seem to be a longer process than clamping a prefit assembly in place.  Maybe the splice plates can be pre-fit somehow.

Reiersen 1/21/05