## Milestones
Milestones | Old Finish | New Finish | Sep | Oct | Nov |  | Dec | Jan | Feb | Mar | Apr | May | June
Reference coil set established for conceptual design | 2001-10-31 | 2001-12-13
Scopes of work and engineering budgets finalized for FY02. Work plans in place through CDR. | 2001-11-08 | 2001-12-19
Start manufacturing studies of modular coils and vacuum vessel | 2001-11-15 |  |  |  |  | Y
General (WBS Level 1) requirements finalized for conceptual design | 2001-11-21
Power supply and cooling requirements established for reference scenario | 2001-12-05
Port geometries and port allocations defined | 2001-12-12 | 2002-01-24
Divertor heat loads defined | 2001-12-12
Power supply and cooling requirements established for trim coils | 2001-12-21
NEPA planning form submitted to NEPA Compliance Mgr (Levine) | 2001-12-21
Technical data required to develop conceptual design in place | 2001-12-21
Complete manufacturing studies of modular coils and vacuum vessel | 2002-01-31
NEPA CX package submitted to DOE | 2002-01-31
All project plans completed | 2002-02-15
Complete all technical work for CDR. Start CDR preparations. | 2002-02-15
Cost and schedule estimates finalized | 2002-03-01
Draft CDR documentation completed | 2002-03-15
CDR documentation issued | 2002-03-22
Draft presentations complete | 2002-03-29
Initial dry runs complete | 2002-04-05
Ready for NCSX CDR | 2002-04-12
DOE CX determination complete | 2002-04-12
Formulas:
Old Finish = [Old Finish, row below]-14
New Finish = C5+([Old Finish]-B5)

## Project
Area | Task Descriptions | Start | Duration (weeks) | Finish | Neilson (Mgmt) | Zarnstorff (Physics) | Reiersen (Engr) | Brown (Design Integration) | Levine (ES&H) | Malsbury (QA) | Sutton (Procurement) | Brooks (EM analysis) | Nelson (WBS 1) | Kugel (WBS 2) | Johnson (WBS 3) | Ramakrishnan (WBS 4) | Oliaro (WBS 5) | Dudek (WBS 62-64) | Chrzanowski (WBS 61,7,9) | Deliverable or Comments
Project Engineering
| Develop new reference design | 2001-09-26 |  | 2001-10-31
| Update TF and PF designs, use as background coils in modular coil studies with 18 modular coils | 2001-09-26 | - | 2001-09-26 | [8 empty] | L | [6 empty] | Provide coil set definitions
| Develop improved modular coil options using CoilOpt and coupled CoilOpt-StellOpt, confirm engineering feasibility | 2001-09-26 | 5 | 2001-10-31 |  | L | [6 empty] | S | [6 empty] | Buildable modular coil design that provide adequate physics properties (Strickler, LPK, MZ))
| Finalize requirements, define scopes of work for CDR, and develop/coordinate work plans | 2001-07-24 |  | 2001-11-21
| General requirements review | 2001-07-24 | - | 2001-07-24 |  | S | L | [12 empty] | Done at July project meeting
| Modular coils | 2001-08-28 | - | 2001-08-28 |  | S | L | [12 empty] | Done at August project meeting
| Kick-off meeting | 2001-10-05 | - | 2001-10-05
| TF, PF, VV, PFCs | 2001-10-09 | - | 2001-10-09 |  | S | L | [5 empty] | S | [6 empty] | Weekly requirements review
| Auxiliary systems (WBS 2) | 2001-10-11 | - | 2001-10-11 |  | S | L | [6 empty] | S | [5 empty] | Weekly requirements review
| NCSX Project Meeting | 2001-10-16 |  | 2001-10-16
| General requirements review | 2001-10-17 |  | 2001-10-17 | [15 empty] | GHN, MZ, and WR to collect and disposition comments
| Diagnostics (WBS 3) | 2001-10-18 | - | 2001-10-18 |  | S | L | [7 empty] | S |  |  |  |  | Weekly requirements review
| Electrical Power (WBS 4) | 2001-10-23 | - | 2001-10-23 |  | S | L | [8 empty] | S |  |  |  | Weekly requirements review
| Central I&C (WBS 5) | 2001-10-25 | - | 2001-10-25 |  | S | L | [9 empty] | S |  |  | Weekly requirements review
| Site and Facilities (WBS 6) | 2001-10-30 | - | 2001-10-30 |  | S | L | [10 empty] | S | S | Weekly requirements review
| Machine Assembly (WBS 7), Prep for Ops (WBS 9) | 2001-11-01 | - | 2001-11-01 |  | S | L | [11 empty] | S | Weekly requirements review
| APS Meeting | 2001-10-29 |  | 2001-11-02
| Finalize scopes of work and engineering budgets for FY02. Work plans defined through CDR. | 2001-11-08 | - | 2001-11-08
| PAC Meeting | 2001-11-14 |  | 2001-11-15
| Finalize general requirements for conceptual design | 2001-10-17 | 5 | 2001-11-21
| Procurement activities for mfg studies | 2001-08-22 |  | 2001-11-15
| Conduct information meeting | 2001-08-22 | - | 2001-08-22
| Send out RFPs | 2001-09-28 | - | 2001-09-28
| Potential suppliers prepare responses | 2001-09-28 | 2.8571 | 2001-10-18
| Formally establish evaluation board(s) | 2001-10-01 | 2.4286 | 2001-10-18
| Select vendors for manufacturing studies | 2001-10-18 | 2 | 2001-11-01 |  |  | L | [5 empty] | S
| Put contracts in place | 2001-11-01 | 2 | 2001-11-15 |  |  | L | [5 empty] | S
| Develop technical data for CDR | 2001-10-31 | 7.2857 | 2001-12-21
| Develop power supply and cooling requirements for the reference scenarios | 2001-10-31 |  | 2001-12-05
| Develop static equilibria for breakpoints in reference equilibria for reference coil design | 2001-10-31 | 2 | 2001-11-14 |  | L | [13 empty] | Coil currents at breakpoints for reference scenarios (Pomphrey)
| Address volt-seconds constraints, optimize number of turns and volt-second bias for engineering, finalize current waveforms for reference scenarios | 2001-11-14 | 2 | 2001-11-28 |  | S | L | [12 empty] | Updated coil specifications and current waveforms (support from Pomphrey)
| Develop power supply and cooling requirements for reference scenarios | 2001-11-28 | 1 | 2001-12-05 |  |  | L | [8 empty] | S |  |  |  | Technical data posted on Web
| Develop power supply and cooling requirements for inboard trim coil | 2001-12-07 | 2 | 2001-12-21
| Hudsonize modular coil geometry for clean surfaces | 2001-10-31 | 13.2857 | 2002-02-15 |  | L | [13 empty] | Revised coil geometry. Document in update/addendum to PVR documentation.
| Develop static equilibria for extrema in flexibility space | 2001-12-05 | 8.2857 | 2002-02-15
| Develop engineering constraints for exploring flexibility space (e.g., maximum coil currents, first wall contour) | 2001-12-05 | 2 | 2001-12-19 |  |  | S | [5 empty] | L | [6 empty] | Engineering constraints based on mechanical and thermal limitations in coils and structures
| Develop static equilibria for extrema in flexibility space | 2001-12-19 | 6.2857 | 2002-02-15 |  | L | [13 empty] | Document in update/addendum to PVR documentation
| Develop Systems Engineering Plan and related procedures | 2001-11-01 |  | 2002-02-01
| Define evolution of controlled baselines | 2001-11-01 | 3 | 2001-11-22
| Define change control procedures | 2001-11-22 | 4.1429 | 2001-12-21
| Develop Systems Engineering Plan | 2001-12-21 | 6 | 2002-02-01
Physics
| Update PVR documentation | 2001-10-01 |  | 2002-03-15
Project Control
Develop Project Execution Plan (PEP)
| Develop initial draft of PEP | 2001-10-01 | 15.5714 | 2002-02-01
| Incorporate changes derived from SEP | 2002-02-01 | 2 | 2002-02-15
| Develop Project Acquisition Plan | 2001-10-01 | 17.5714 | 2002-02-15
ES&H
| Develop NEPA Planning Form and supporting information, submit to NEPA Compliance Mgr (Levine) | 2001-10-01 | 11.5714 | 2001-12-21 |  |  | L
| Develop NEPA CX Package, submit to DOE for determination | 2001-12-21 | 5.8571 | 2002-01-31 |  |  |  |  | L
| NEPA CX determination complete (DOE) | 2002-01-31 | 10.1429 | 2002-04-12
Quality Assurance
| Develop Quality Assurance Plan (QAP) | 2001-10-01 | 17.5714 | 2002-02-15
| Develop implementation plan covering applicable DOE and PPPL policies and procedures | 2001-10-01 |  | 2002-02-15
Formulas:
Start = MIN([Start, row below]:C6)
Start = [Finish, row above]
Finish = MAX([Finish, row below]:E6)
Finish = [Start]

## EMAnalysis
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Brooks | Jun | Deliverable or Comments
Support development of reference coil design. Explore surface smoothing, coil smoothing and manual separation, etc. | 2001-10-08 | 3.2857 | 2001-10-31
Prepare response to PVR recommendations for Nov 14 PAC meeting | 2001-10-08 | 4.5714 | 2001-11-09 |  |  | PVR recommendations include [1] III-1 re finite coil build [2] III-2 re effects of construction errors [3] III-3 re construction errors that break 3-fold symmetry. The perturbed coil geometry should be made available to Physics for assessment of physics properties. Need a report prepared in advance of the November 14 PAC meeting on accomplishments to date and plans to address remaining issues.
Conduct field error studies | 2001-10-01 |  | 2002-02-15
Calculate stray fields from stellarator coils in the region of the ion source and bending magnets | 2001-10-01 | 2 | 2001-10-15 |  |  | Analysis report (Jun). Support from Kugel to help model beamline.
Investigate field errors and plasma performance impacts from known sources | 2001-10-15 | 15.5714 | 2002-02-15 |  |  | This task needs to be expanded under the EM work plan. Known sources include the iron shielding and bending magnets in thebeamlines, the Eath's magnetic field, building steel, and magnetic material in the stellarator core and ancillary equipment
Develop disruption loads | 2001-10-01 | 11.5714 | 2001-12-21 |  |  | This task needs to be expanded under the EM work plan. Requires that SPARK modifications to accommodate stellarator symmetry be implemnted soon.
Assess plausibility of tolerance requirements
Input received on preliminary tolerance requirements from WBS 1 | 2001-10-03 | - | 2001-10-03
Assess island sizes induced by allowable coil perturbations. Update tolerance requirements. Provide plausibility argument that tolerance requirements are OK. | 2001-10-03 | 15.1429 | 2002-01-31 |  |  | This task needs to be expanded under the EM work plan.
Develop current and voltage requirements for inboard trim coils | 2001-10-01 |  | 2001-12-07
Identify/develop healed reference equilibrium for use in trim coil design | 2001-10-01 | 2 | 2001-10-15
Assess impact on healed reference equilibrium of energizing the inboard and outboard trim coils (individually and tegether). Establish current and voltage requirements. | 2001-10-15 | 7.5714 | 2001-12-07 |  |  | Support from Hudson and PIES group required. Use existing geometry of outboard trim coils in performance assessment
Formulas:
Finish = MAX([Finish, row below]:D10)
Finish = [Start]+[Duration (weeks)]*7
Start = MIN([Start, row below]:B10)
Start = [Finish, row above]

## WBS1(Coils)
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Nelson | Cole | Williamson | Fogarty | Goranson | Jones | Fan | Dahlgren | Reiersen | Heitzenroeder | Chrzanowski | Brown | Subcontract | Deliverable or Comments
Develop conceptual design of modular and TF/PF coils | 2001-10-31 | 13.2857 | 2002-02-15 | [13 empty] | This task needs to be expanded under WBS 1 work plans. Final deliverable is design description for modular, TF/PF, and trim coils; cryostat; and structure.
Develop conceptual design of inboard trim coils | 2001-12-07 |  | 2002-02-15
Input received on current and voltage requirements from EM analysis | 2001-12-07 | - | 2001-12-07
Develop conceptual design of inboard trim coils, including structural and thermal (cooldown) analyses | 2001-12-07 | 8 | 2002-02-15 | [13 empty] | This task needs to be expanded under WBS 1 work plans. Include in design description.
Finalize design criteria for coils | 2001-09-26 | 18.2857 | 2002-02-15 | [13 empty] | This task needs to be expanded in the WBS 1 work plan which includes supporting R&D. The deliverable is an NCSX design criteria document. Include limits on bend radius in conductor, allowable adiabatic temperature rise, and stress limits for copper-glass-epoxy composite winding pack
Assess what tolerances are reasonably achievable based on existing stellarator database. Establish preliminary tolerance requirements. | 2001-09-26 | 1 | 2001-10-03 | [13 empty] | Proposal for interim tolerance requirements based on what appears reasonably achievable based on existing stellarators. Provides basis for plausibility study by EM analysis group and conceptual design
Finalize tolerance requirements based on completion of plausibility study and cost sensitivity study | 2002-01-31 | 2.1429 | 2002-02-15 | [13 empty] | Updated design criteria
Finalize all design criteria | 2001-10-01 | 17.5714 | 2002-02-15 | [13 empty] | This task needs to be expanded in the WBS 1 work plan which includes supporting R&D. The deliverable is an NCSX design criteria document. Include limits on bend radius in conductor, allowable adiabatic temperature rise, and stress limits for copper-glass-epoxy composite winding pack
Conduct mfg studies of the modular coils | 2001-11-21 | 8.1429 | 2002-01-31
Contracts for mfg studies put in place | 2001-11-15 | - | 2001-11-15
Conduct mfg studies | 2001-11-15 | 9 | 2002-01-31
Update Pro/E model and product specification, make available to suppliers | 2001-10-31 | 3 | 2001-11-21
Prepare for CDR | 2002-02-15 | 8 | 2002-04-12
Formulas:
Start = MIN([Start, row below]:B8)
Start = [Finish, row above]
Finish = MAX([Finish, row below]:D8)
Finish = [Start]

## WBS 1 Design
| WBS 1 Workplan |  | Draft |  | 2001-12-14 16:38
Design Tasks
This workplan is intended to summarizedesign tasks required for the Conceptual Design Review
1 | Stellarator Core | [6 empty] | Estimated manweeks by performer
| WBS | Task Area | Subtask | Task Description | Deliverable(s) | start | finish | Cole | Fogarty | Goranson | Jones | Nelson | Williamson | Subcontract | Brooks | Brown | Chrzanowski | Dahlgren | Fan | Heitzenroeder | Reiersen | PPPL Designer | Subtotal / task
| 110 | Plasma Facing Components
| 111 | First Wall | a | Define geometry, ie stayout zone, convert to fourier representation | Design memo and coordinate geometry
|  |  | b | Divide FW into tile shapes | Pro-E model
| 112 | Divertor | a | Define geometry, including pumping zone, slot, baffles | Design memo and coordinate geometry
|  |  | b | Define divertor baffle tiles, add pumping slot | Pro-E model
| 113 | NBI armor |  | Define geometry for ultimate and day-1 operation | Pro-E model
| 114 | Support ribs | a | Define ribs: Confirm number and spacing of ribs, attachment scheme to VV, cooling line integration | Pro-E models and 2-D sketches
| 115 | Limiters | a | Confirm inboard limiters are just FW tiles between divertors, create day-1 geometry | Design memo and coordinate geometry
| 116 | PFC Cooling lines | a | Define cooling line routing | Pro-E model
|  |  | b | Define feedthroughs for cooling lines | memo and Pro-E model
| 117 | PFC Local I&C | a | Define number and type of T/C, strain gages, etc. required for PFC instr. | Design memo and sketches of locations
| 120 | Vacuum Vessel
| 121 | Vessel shell | a | Define geometry, convert to fourier representation, create Pro-E surface | Pro-E surface
|  |  | b | Divide vessel into half periods and spacer parts | Pro-E model
|  |  | c | Define assembly flanges, seals, bolt spacing | design memo and Pro-E model
|  |  | d | incorporate input from manufacturing studies | Pro-E model
| 122 | VV Ports & Extensions | a | Develop layout of port locations, sizes, and extensions | Pro-E model
|  |  | b | Provide port reinforcement scheme | Pro-E model
|  |  | c | Select basic seal types | design memo (table)
|  |  | d | incorporate input from manufacturing studies | Pro-E model
| 123 | Thermal insulation | a | Confirm choice of microtherm, solomide foam | design memo
| 124 | VV Heating and Cooling tracing | a | Confirm spacing of cooling lines, manifolding | design memo
|  |  | b | Develop method for heating port extensions | design memo
|  |  | c | incorporate input from manufacturing studies | Pro-E model
| 125 | VV Local I&C | a | Define number and type of T/C, strain gages, etc. required for VV instrumentation
| 130 | TF Coils (background coils)
| 131 | TF Winding Pack | a | Confirm geometry of TF coil set | Pro-E model
|  |  | b | Develop winding pack definition (turns, spacing, cooling, etc.) | Pro-E model
| 132 | TF Cases | a | Provide design of any integrated TF support system | Pro-E model
| 133 | TF Assembly |  | included in assy sequence, tasks 711a,b
| 134 | TF Power and Cooling Interfaces (leads) | a | Provide lead and cooling line routing concept | Pro-E model
|  |  | b | Provide vapor cooled lead concept | design memo
| 140 | PF Coils (VF, EQ. OH)
| 141 | PF - OH Solenoid | a | Confirm PF coil geometry | design memo and 2-D sketch
|  |  | b | Develop winding pack definition (turns, spacing, cooling, etc.) | Pro-E model
| 142 | PF - Ring Magnets | a | Develop winding pack definition (turns, spacing, cooling, etc.) | Pro-E model
| 143 | PF power and cooling interfaces (leads) | a | Provide lead and cooling line routing concept
|  |  | b | Provide vapor cooled lead concept (related to task 134b)
| 150 | Cryostat
| 151 | Cryostat Shell and Structure | a | Confirm design concept for cryostat | memo
|  |  | b | Re-do geometry of cryostat | Pro-E model
| 152 | Cryostat Thermal Insulation | a | same as 151a
| 153 | VV / cryostat boots | a | confirm boot design, clearances for ports | memo, 2-D sketch
|  |  | b | provide typical penetration model | Pro-E model
| 154 | Temp control / heaters | a | Determine number and location of heaters, blowers, etc. | memo
| 155 | Local I&C | a | Define number and type of T/C, strain gages, etc. required for VV instrumentation | memo and sketch of locations
| 160 | Machine Support Structure
| 161 | Base assembly (includes gravity supports to floor) | a | Confirm base assembly system still works, modify as required to compensate for elimination of radial plates | Pro-E model
| 162 | TF coil support structure | a | Provide new support scheme in lieu of radial plate structure | Pro-E model
| 163 | PF coil supports | a | Provide new support scheme in lieu of radial plate structure | Pro-E model
| 164 | Modular coil interface structure | a | Provide new support scheme in lieu of radial plate structure | Pro-E model
| 164 | Vacuum Vessel supports | a | Provide vacuum vessel support and adjustment system | Pro-E model
| 170 | Modular Coils
| 171 | windings and coil assembly | a | Develop new modular coil geometry, including twist, bend radius mods., etc. | Pro-E model and geometry files
|  |  | b | Provide new coil pack dimensions, including cable dimensions, insulation thickness, ground wrap, and chill plate arrangement and overall stackup tolerances. Determine system for accommodation of keystoning | 2-D sketch, memo
|  |  | c | Develop details of crossover and lead region for typical coil pack | Pro-E model
|  |  | d | Provide winding clamp concept and approximate clamp distribution around machine | Pro-E model
|  |  | e | Provide local manifolding for typical coil pack, but not for each type of six types unless time permits | Pro-E model
|  |  | f | modify design as required to integrate suggestions from manufacturing studies | design memo and Pro-E model
| 172 | winding form / structure | a | Provide new shell surfaces, inside and outside, convert to fourier representation | Design memo and coordinate geometry
|  |  | b | Re-do Pro-E model based on fourier representation | Pro-E model
|  |  | c | Provide coil form machining details | Pro-E model
|  |  | d | Develop bolting interface, including electrical insulation scheme | design memo and Pro-E model
|  |  | e | modify design as required to integrate suggestions from manufacturing studies | design memo and Pro-E model
| 173 | leads | a | Provide lead and local buswork routing concept | Pro-E model
Provide vapor cooled lead concept (related to task 134b)
| 174 | cooling system inside cryostat | a | Provide coolant manifold routing
| 175 | local I&C | a | Define number and type of T/C, strain gages, voltage taps, etc. required for modular coil instr.
| 180 | Trim Coils
| 181 | coil assemblies | a | Develop Pro-E model of coil shape | Pro-E model
|  |  |  | Develop winding pack details, including number and size of turns, insulation type and thickness, etc. | Pro-E model
|  |  | b | Develop coil form/can concept and support scheme to vessel wall | Pro-E model
| 182 | leads and cooling | a | Provide lead concept inside vessel | Pro-E model
|  |  | b | Provide lead routing outside vessel to boundary of cryostat | Pro-E model
| 183 | local I&C | c | Define number and type of T/C, strain gages, voltage taps, etc. required for trim coil instr. | memo and sketch of location
7 | Machine Assembly
| 711 | New Machine Core Assembly | a | Develop core assembly sequence, confirm components can be assembled

## WBS 1 Analysis
| WBS 1 Workplan |  | Draft |  | 2001-12-14 16:38
Analysis Tasks
This workplan is intended to summarize analysis tasks required for the Conceptual Design Review
1 | Stellarator Core | [6 empty] | Estimated manweeks by performer
| WBS | Task Area | Subtask | Task Description | Deliverable(s) | start | finish | Cole | Fogarty | Goranson | Jones | Nelson | Williamson | Subcontract | Brooks | Brown | Chrzanowski | Dahlgren | Fan | Heitzenroeder | Reiersen | PPPL Designer | Subtotal / task
| 110 | Plasma Facing Components
| 111 | First Wall | a | Est. temperature rise in FW panels for various heat loads | Thermal analysis memo
|  |  | b | Est. heat leak from first wall panels to vessel during bakeout | Thermal analysis memo
| 112 | Divertor | a | Est pumping speed of slot | pumping memo
| 113 | NBI armor |  | re-confirm nbi armor temp rise | memo
| 114 | Support ribs | a | est. heat leak from ribs to VV during bakeout | memo
| 115 | Limiters
| 116 | PFC Cooling lines | a | est. pressure drop, flow rate for PFC rib cooling/bakeout lines | memo
| 117 | PFC Local I&C
| 120 | Vacuum Vessel
| 121 | Vessel shell | a | Perform EM analysis for typical disruption scenario and define vessel loading | EM analysis
|  |  | b | Create global FEA model of vessel, port reinforcement and extensions | FEA model
|  |  | c | Apply vacuum, seismic, disruption loads in static linear analysis | memo with stress/defl analysis results
|  |  | d | Provide time constant estimation for shell, and mutual inductance to coils and plasma | memo
| 122 | VV Ports & Extensions | a | create local model of port reinforcement to determine simplifications for global model | FEA model
| 123 | Thermal insulation | a | Estimate heat leak from vessel to coils | memo
| 124 | VV Heating and Cooling tracing | a | Estimate temperature distr. In VV forgiven spacing of cooling lines | memo
|  |  | b | Est. temp in port extensions for given cooling line / heater spacing | memo
|  |  | c | est. pressure drop, flow rate for VV cooling/bakeout lines | memo
| 125 | VV Local I&C
| 130 | TF Coils (background coils)
| 131 | TF Winding Pack | a | Calculate em loads for TF coils (single em analysis task under modular coils)
|  |  | b | est. inductance of TF coils and mutuals to other coils (part of global em analysis under modular coils)
|  |  | c | Determine fault conditions for TF coil set | memo
|  |  | d | Calculate stresses, deflections in winding for various loading conditions | memo
|  |  | e | est. temp rise in coils for various oper. scenarios | memo
| 132 | TF Cases | a | Calculate stresses / deflections in case | memo
| 133 | TF Assembly
| 134 | TF Power and Cooling Interfaces (leads) | a | est. voltage drop, temp rise in leads | memo
|  |  | b | est. cooling required for vapor cooled leads | memo
|  |  | c | est pressure drop, flow rate for TF coil cooling system inside cryostat | memo
| 140 | PF Coils (VF, EQ. OH)
| 141 | PF - OH Solenoid | a | Calculate em loads for PF coils (single em analysis task under modular coils)
|  |  | b | est. inductance of PF coils and mutuals to other coils (part of global em analysis under modular coils)
|  |  | c | Determine fault conditions for PF coil set | memo
|  |  | d | Calculate stresses, deflections in winding for various loading conditions | memo
|  |  | e | est. temp rise in coils for various oper. scenarios | memo
| 142 | PF - Ring Magnets |  | (included in tasks 141 a-e)
| 143 | PF power and cooling interfaces (leads) | a | est. voltage drop, temp rise in leads | memo
|  |  | b | est. cooling required for vapor cooled leads | memo
|  |  | c | est pressure drop, flow rate for PF coil cooling system inside cryostat | memo
| 150 | Cryostat
| 151 | Cryostat Shell and Structure | a | est. heat leak through cryostat | memo
|  |  | b | est. stresses in cryostat structure from gravity, pressure loads | memo
| 152 | Cryostat Thermal Insulation | a | same as 151a
| 153 | VV / cryostat boots | a | same as 151a
| 154 | Temp control / heaters
| 155 | Local I&C
| 160 | Machine Support Structure
| 161 | Base assembly (includes gravity supports to floor) | a | Est. stresses/deflections in base assembly | memo
| 162 | TF coil support structure | a | Est. stresses/deflections in TF support system | memo
| 163 | PF coil supports | a | Est. stresses/deflections in PF support brackets | memo
| 164 | Modular coil interface structure | a | Est. stresses/deflections in modular coil interface structure | memo
| 164 | Vacuum Vessel supports | a | Est. stresses/deflections in VV supports | memo
| 170 | Modular Coils
| 171 | windings and coil assembly | a | Provide EM analysis of all coils, including fields, forces, inductance matrix, etc. | memo and data files
|  |  | b | Provide fault condition matrix for all coils | memo
|  |  | c | provide field error calculations due to leads and crossovers | memo
|  |  | d | Provide thermal / cooldown analysis of modular coil windings | memo
|  |  | e | Provide thermal stress analysis of windings for various operating conditions and various support conditions | memo
| 172 | winding form / structure | a | Provide stress / deflection analysis for integrated coil / shell structure for various em and thermal loading conditions | memo
|  |  | b | Provide time constant estimation for shell, and mutual inductance to coils and plasma | memo
| 173 | leads | a | est. voltage drop, temp rise in leads | memo
|  |  | b | est. cooling required for vapor cooled leads | memo
| 174 | cooling system inside cryostat | a | est pressure drop, flow rate for modular coil cooling system inside cryostat | memo
|  |  |  | Est. pressure rise for two phase flow in fault condition | memo
| 175 | local I&C
| 180 | Trim Coils
| 181 | coil assemblies | a | Calculate em loads for trim coils (single em analysis task under modular coils)
|  |  | b | est. inductance of trim coils and mutuals to other coils (part of global em analysis under modular coils)
|  |  | c | Determine fault conditions for trim coil set | memo
|  |  | d | Calculate stresses, deflections in winding for various loading conditions | memo
|  |  | e | est. temp rise in coils for various oper. scenarios | memo
| 182 | leads and cooling | a | est. voltage drop, temp rise in leads | memo
| 183 | local I&C
7 | Machine Assembly
| 711 | New Machine Core Assembly | a | Calculate weights and envelope dimensions of all components and subassemblies | weights and envelope dimensions on all drawings
|  |  | b | Perform geometry check at room temperature and operating temperatures, include tolerance stackup if possible | memo

## WBS 1 R&D
| WBS 1 Workplan |  | Draft |  | 2001-12-14 16:38
R&D Tasks
This workplan is intended to summarize R&D tasks planned for completion prior to the Conceptual Design Review
1 | Stellarator Core | [6 empty] | Estimated manweeks by performer
| WBS | Task Area | Subtask | Task Description | Deliverable(s) | start | finish | Cole | Fogarty | Goranson | Jones | Nelson | Williamson | Subcontract | Brooks | Brown | Chrzanowski | Dahlgren | Fan | Heitzenroeder | Reiersen | PPPL Designer | Subtotal / task
| 110 | Plasma Facing Components
| 111 | First Wall |  | none planned at this time
| 112 | Divertor
| 113 | NBI armor
| 114 | Support ribs
| 115 | Limiters
| 116 | PFC Cooling lines
| 117 | PFC Local I&C
| 120 | Vacuum Vessel
| 121 | Vessel shell | a | provide stereolithography model of vessel and major port extensions | stereolithography model
| 122 | VV Ports & Extensions
| 123 | Thermal insulation
| 124 | VV Heating and Cooling tracing
| 125 | VV Local I&C
| 130 | TF Coils (background coils)
| 131 | TF Winding Pack | a | provide stereolithography model of 6 TF coils and assoc. structure | stereolithography model
| 132 | TF Cases
| 133 | TF Assembly
| 134 | TF Power and Cooling Interfaces (leads)
| 140 | PF Coils (VF, EQ. OH)
| 141 | PF - OH Solenoid | a | provide stereolithography model of 6 PF coils and assoc. structure | stereolithography model
| 142 | PF - Ring Magnets |  | included in 141a, above
| 143 | PF power and cooling interfaces (leads)
| 150 | Cryostat
| 151 | Cryostat Shell and Structure
| 152 | Cryostat Thermal Insulation
| 153 | VV / cryostat boots | a | obtain boot sample | sample
| 154 | Temp control / heaters
| 155 | Local I&C
| 160 | Machine Support Structure
| 161 | Base assembly (includes gravity supports to floor)
| 162 | TF coil support structure
| 163 | PF coil supports
| 164 | Modular coil interface structure
| 164 | Vacuum Vessel supports
| 170 | Modular Coils
| 171 | windings and coil assembly | a | provide stereolithography model of 6 PF coils and assoc. structure | stereolithography model
|  |  | b | perform vacuum impregnation tests on conductor bundles and test for wicking, insulation integrity, cure time etc. | epoxy/insulation system parameters
|  |  | c | perform mechanical tests of cured "logs" of bundled conductor to determine mechanical properties of winding pack
|  |  | d | perform winding and vpi tests for various various coil bends and twists, and check for keystoning in coil pack
|  |  | e | Incorporate chill plate in one or more "logs" for cooldown tests and perform cooldown tests
| 172 | winding form / structure
| 173 | leads
| 174 | cooling system inside cryostat
| 175 | local I&C
| 180 | Trim Coils
| 181 | coil assemblies
| 182 | leads and cooling
| 183 | local I&C
7 | Machine Assembly
| 711 | New Machine Core Assembly | a | Manipulate vessel and coil models to determine feasibility of assembly | sigh of relief

## WBS 1 Cost & sched
| WBS 1 Workplan |  | Draft |  | 2001-12-14 16:38
Cost and Schedule estimates
This workplan is intended to summarize who will provide what cost and schedule input for WBS 1 for the Conceptual Design Review
1 | Stellarator Core | [6 empty] | Estimated manweeks by performer
| WBS | Task Area | Subtask | Task Description | Deliverable(s) | start | finish | Cole | Fogarty | Goranson | Jones | Nelson | Williamson | Subcontract | Brooks | Brown | Chrzanowski | Dahlgren | Fan | Heitzenroeder | Reiersen | PPPL Designer | Subtotal / task
| 110 | Plasma Facing Components
| 111 | First Wall | a | Define cost for Plasma Facing Components required for day one operation and provide associated listing of cost elements, description of what is costed, and contingency justification. | Cost and contingency sheets
|  |  | b | Define procurement strategy and schedule for Plasma Facing Components | procurement strategy and schedule
| 112 | Divertor
| 113 | NBI armor
| 114 | Support ribs
| 115 | Limiters
| 116 | PFC Cooling lines
| 117 | PFC Local I&C
| 120 | Vacuum Vessel
| 121 | Vessel shell | a | Define cost for Vacuum Vessel required for day one operation and provide associated listing of cost elements, description of what is costed, and contingency justification. | Cost and contingency sheets
|  |  | b | Define procurement strategy and schedule for Vacuum Vessel | procurement strategy and schedule
| 122 | VV Ports & Extensions
| 123 | Thermal insulation
| 124 | VV Heating and Cooling tracing
| 125 | VV Local I&C
| 130 | TF Coils (background coils)
| 131 | TF Winding Pack | a | Define cost for TF Coils (background coils) required for day one operation and provide associated listing of cost elements, description of what is costed, and contingency justification. | Cost and contingency sheets
|  |  | b | Define procurement strategy and schedule for TF Coils (background coils) | procurement strategy and schedule
| 132 | TF Cases
| 133 | TF Assembly
| 134 | TF Power and Cooling Interfaces (leads)
| 140 | PF Coils (VF, EQ. OH)
| 141 | PF - OH Solenoid | a | Define cost for PF Coils (VF, EQ. OH) required for day one operation and provide associated listing of cost elements, description of what is costed, and contingency justification. | Cost and contingency sheets
| 142 | PF - Ring Magnets | b | Define procurement strategy and schedule for PF Coils (VF, EQ. OH) | procurement strategy and schedule
| 143 | PF power and cooling interfaces (leads)
| 150 | Cryostat
| 151 | Cryostat Shell and Structure | a | Define cost for Cryostat required for day one operation and provide associated listing of cost elements, description of what is costed, and contingency justification. | Cost and contingency sheets
|  |  | b | Define procurement strategy and schedule for Cryostat | procurement strategy and schedule
| 152 | Cryostat Thermal Insulation
| 153 | VV / cryostat boots
| 154 | Temp control / heaters
| 155 | Local I&C
| 160 | Machine Support Structure
| 161 | Base assembly (includes gravity supports to floor) | a | Define cost for Machine Support Structure required for day one operation and provide associated listing of cost elements, description of what is costed, and contingency justification. | Cost and contingency sheets
|  |  | b | Define procurement strategy and schedule for Machine Support Structure | procurement strategy and schedule
| 162 | TF coil support structure
| 163 | PF coil supports
| 164 | Modular coil interface structure
| 164 | Vacuum Vessel supports
| 170 | Modular Coils
| 171 | windings and coil assembly | a | Define cost for Modular Coils required for day one operation and provide associated listing of cost elements, description of what is costed, and contingency justification. | Cost and contingency sheets
|  |  | b | Define procurement strategy and schedule for Modular Coils | procurement strategy and schedule
| 172 | winding form / structure
| 173 | leads
| 174 | cooling system inside cryostat
| 175 | local I&C
| 180 | Trim Coils
| 181 | coil assemblies | a | Define cost for Trim Coils required for day one operation and provide associated listing of cost elements, description of what is costed, and contingency justification. | Cost and contingency sheets
|  |  | b | Define procurement strategy and schedule for Trim Coils | procurement strategy and schedule
| 182 | leads and cooling
| 183 | local I&C
7 | Machine Assembly
| 711 | New Machine Core Assembly | a | Define cost for machine assembly and provide associated listing of cost elements, description of what is costed, and contingency justification | Cost and contingency sheets
|  |  | b | Define schedule for machine assembly | schedule

## Sheet3
NCSX Engineering for CDR |  | DRAFT |  |  |  | 2001-12-14 16:38
| Key: High importance / leverage items = !!! | critical path xxx |  |  |  | physics | [5 empty] | engr. | [6 empty] | combined task
Near term tasks |  | eng alloc (hrs) | physics input reqd by: | Aug |  | Sept |  | Oct |  | Nov |  | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul
Improve modular coil geometry
| Eliminate sharp bends | 20 | 2001-09-01 |  |  |  | xx | xx | xx | xx | xx
| Optimize twist | 40 | 2001-10-01 | [8 empty] | xx | xx
| reduce current density | 20 | 2001-10-01
| improve manufacturability in general | 40
Improve structural design
| Simplify concept | 120
| Reduce cost | 80
Develop more fabrication details (e.g. castings, windings, “canning”)
| Involve industry and universities to a larger extent | 80
(UT, H1, HSX., Auburn, MAST)
| Perform manufacturing studies | 80
| limited R&D, prototypes (welded can) !!! | 80
Perform tradeoff of OH system !!!
| Air core solenoid vs iron core | 16 | 2001-06-15 | xx | xx | xx
| return coil geometry | 16
| Optimize VF coil number, shape, location | 24 | 2001-10-01 | [6 empty] | xx | xx
| Understand consequences of changing VV spool pieces from aluminum to stainless | 40
| Finalize design requirements !!! | 40 | 2001-10-15 | [10 empty] | xx
| SUBTOTAL, last 5 mo of FY 2001 | 696
CDR specific tasks:
Engineering Design: models/drawings/schematics
| Modular coils, including leads, cooling manifolds, vacuum can, clamps, etc. | 240 | [12 empty] | xx | xx
| TF coils, including no. of coils!!!, supports | 80
| centerstack assembly, with solenoid, can, etc. | 120
| PF coils, including supports | 60
| support structure | 120 | [14 empty] | xx | xx | xx
| bell jar vacuum vessel, ports, heaters, thermal blanket | 80
| vacuum pumping system, leak detection, etc. | 40
| gas fueling system description | 8 | 2001-01-30
| buswork for all coils | 40
| cooling distribution manifolds for all coils, gas compressor, heat exchangers, etc. | 40
| Day-1 diagnostics | 8 | 2001-01-30
| Power supply configuration !!! | 40
| I&C, DAS system description | 8 | 2001-01-30
Engineering Analysis: Fields/Forces/stresses/thermal
| magnetic field/forces (including fault conditions) | 40
| inductance calc., circuit calculations | 20
| support structure/coil form stress analysis | 80 | [17 empty] | xx | xx
| Modular coil winding stresses | 40
| TF, PF winding stresses | 40
| Modular coil thermal / cooling analysis | 40
| TF, PF thermal analysis | 40
| vacuum pumping analysis | 40
| ·Develop “bottoms up” schedule estimate | 80
| ·Refine cost estimates | 120 | [19 empty] | xx | xx
| Prepare conceptual design report | 80 | [21 empty] | xx | xx
| Prepare CDR documentation | 80 | [23 empty] | xx | CDR
| SUBTOTAL, all hours | 2280
| contingency (20%) | 456
| total allocated hours | 2736
| approximate cost ($k) | 370
| SUBTOTAL, First half FY 2002 only | 1504
| contingency (20%) | 300.8
| total allocated hours | 1804.8
| approximate cost ($k) | 250

## WBS1(VV)
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Nelson | Cole | Williamson | Fogarty | Goranson | Jones | Fan | Dahlgren | Reiersen | Heitzenroeder | Chrzanowski | Brown | Subcontract | PPPL Designer | Deliverable or Comments
Develop expanded VV geometry consistent with inbd RF/divertor/tangential NBI constraints and modular coil locations in current "best" 18-coil designs | 2001-09-26 | 2 | 2001-10-10 | [14 empty] | Pro/E model of VV surface
Define first wall contour based on building off vacuum vessel, allowing space for a pumped divertor and inbd RF launcher | 2001-10-10 | 3 | 2001-10-31 | [14 empty] | Pro/E model of first wall contour
Perform field line following studies based on preliminary first wall contour. Identify modifications required to keep heat flux channeled into divertor region. Modify first wall as required. Specify divertor heat loads (?). | 2001-10-31 | 6 | 2001-12-12 | [14 empty] | Updated Pro/E model of first wall contour. Analysis report and heat load specification (Mioduszewski).
Develop port geometries consistent with diagnostic viewing and other requirements, define port allocations. | 2001-10-31 | 6 | 2001-12-12 | [14 empty] | Updated Pro/E model, port allocations defined
Conduct study of in-vessel maintainability | 2001-12-12 | 7.2857 | 2002-02-15 | [14 empty] | Study documented in design description for WBS 11-12
Complete conceptual design of VV and PFCs | 2001-12-12 | 7.2857 | 2002-02-15 | [14 empty] | This task needs to be expanded under WBS 1 work plans. Final deliverable is design description for modular and VV and PFCs. Initial configuration and upgrade paths should be shown. Include design concept for RF launcher to show that it can be plausibly accommodated. Show integration of inbd trim coils with VV/PFCs.
Conduct mfg studies of the modular coils | 2001-11-21 | 8.1429 | 2002-01-31
Contracts for mfg studies put in place | 2001-11-15 | - | 2001-11-15
Conduct mfg studies | 2001-11-15 | 9 | 2002-01-31
Update Pro/E model and product specification, make available to suppliers | 2001-10-31 | 3 | 2001-11-21
Prepare for CDR | 2002-02-15 | 8 | 2002-04-12
Formulas:
Finish = [Start]+7*[Duration (weeks)]
Finish = [Start]+[Duration (weeks)]*7
Start = [Finish, row above]

## WBS2
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Kugel | Deliverable or Comments
Coordination meeting on requirements and scope of work for CDR | 2001-10-11 |  | 2001-10-11
Input received on stray fields in vicinity of neutral beamline | 2001-10-15 | - | 2001-10-15 |  | Provided by Brooks
Develop conceptual design for WBS 2 systems | 2001-11-08 | 12.1429 | 2002-02-15 |  | Expand tasks
Prepare for CDR | 2002-02-15 | 8 | 2002-04-12 |  | Expand tasks
Formulas:
Finish = [Start]

## WBS3
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Johnson | Deliverable or Comments
Coordination meeting on requirements and scope of work for CDR | 2001-10-18 |  | 2001-10-18
Support development of port geometry and allocations | 2001-10-31 | 6 | 2001-12-12
Complete conceptual design of diagnostics | 2001-12-12 | 7.2857 | 2002-02-15 |  | Expand tasks
Prepare for CDR | 2002-02-15 | 8 | 2002-04-12 |  | Expand tasks
Formulas:
Start = [Finish, row above]
Finish = [Start]

## WBS4
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Ramakrishnan | Deliverable or Comments
Coordination meeting on requirements and scope of work for CDR | 2001-10-23 |  | 2001-10-23
Develop conceptual design of electrical power systems | 2001-11-08 | 12.1429 | 2002-02-15 |  | Expand tasks
Prepare for CDR | 2002-02-15 | 8 | 2002-04-12 |  | Expand tasks
Formulas:
Finish = [Start]

## WBS5
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Oliaro | Deliverable or Comments
Coordination meeting on requirements and scope of work for CDR | 2001-10-25 |  | 2001-10-25
Develop conceptual design of Central I&C | 2001-11-08 | 12.1429 | 2002-02-15 |  | Expand tasks
Prepare for CDR | 2002-02-15 | 8 | 2002-04-12 |  | Expand tasks
Formulas:
Finish = [Start]

## WBS6
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Dudek | Chrzanowski | Deliverable or Comments
Coordination meeting on requirements and scope of work for CDR | 2001-10-30 |  | 2001-10-30
Develop conceptual design of Site and Facility systems | 2001-11-08 | 12.1429 | 2002-02-15 |  |  | Expand tasks
Prepare for CDR | 2002-02-15 | 8 | 2002-04-12 |  |  | Expand tasks
Formulas:
Finish = [Start]

## WBS7
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Chrzanowski | Deliverable or Comments
Coordination meeting on requirements and scope of work for CDR | 2001-11-01 |  | 2001-11-01
Develop conceptual design of Machine Assembly | 2001-11-08 | 12.1429 | 2002-02-15 |  | Expand tasks
Prepare for CDR | 2002-02-15 | 8 | 2002-04-12 |  | Expand tasks
Formulas:
Finish = [Start]

## WBS9
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Chrzanowski | Deliverable or Comments
Coordination meeting on requirements and scope of work for CDR | 2001-11-01 |  | 2001-11-01
Develop conceptual design of Prep for Ops | 2001-11-08 | 12.1429 | 2002-02-15 |  | Expand tasks
Prepare for CDR | 2002-02-15 | 8 | 2002-04-12 |  | Expand tasks
Formulas:
Finish = [Start]

## ProjEngr
Participants (man-weeks per task shown)
Task Descriptions | Start | Duration (weeks) | Finish | Reiersen | Deliverable or Comments
This is where a general description of the task goes. Tasks should be organized sequentially. (Use General worksheet as guide.) | 2001-10-10 | 20 | 2002-02-27 | 12 | The deliverable marking completion of the task and clarifying remarks should go in this column.
Project engineering tasks
Develop procurement plan
Develop and implement change control procedure for conceptual design
NEPA documentation
Project execution plan
Formulas:
Finish = [Start]+[Duration (weeks)]*7

## CalendarDates
HolidayBreak | 2001-12-21
StartNewYear | 2002-01-01