## PrintThis
| WBS managers | PPPL Engineering and Scientific Staff (person-weeks)
| WBS | Chrzanowski | Dudek | Johnson | Kugel | Oliaro | Ramakrishnan | Reiersen | Blanchard | Brooks | Brown | Dahlgren | Designers (mechanical) | Designers (electrical) | Fan | Klink/Gettelfinger | Heitzenroeder | Jun | Majeski | Neumeyer | Other | PPPL total
1 | Stellarator core systems | 2 | [8 empty] | 8 | 8 | 4 |  | 20 |  | 2 |  |  |  |  | 44
21 | Fueling |  |  |  | 1 | [16 empty] | 1
22 | Vacuum pumping |  |  |  | 1 |  |  |  | 2 | [12 empty] | 3
23 | Wall conditioning |  |  |  | 1 | [16 empty] | 1
24 | RF heating |  |  |  | 1 | [13 empty] | 3 |  | 1 | 5
25 | Neutral beams |  |  |  | 4 | [7 empty] | 2 | [7 empty] | 2 | 8
3 | Diagnostics |  |  | 9 | [17 empty] | 9
4 | Electrical Power | [5 empty] | 6 | [6 empty] | 4 | [6 empty] | 2 | 12
5 | Central I&C |  |  |  |  | 2.5 | [15 empty] | 2.5
61 | Facility mods and test cell prep | 2 | [10 empty] | 2 | [8 empty] | 4
62 | Heating and cooling |  | 2 | [9 empty] | 1 | [8 empty] | 3
63 | LN2 systems |  | 1 | [9 empty] | 1 |  |  | 3 | [5 empty] | 5
64 | Utility systems |  | 1 | [18 empty] | 1
7 | Machine assembly | 4 | [10 empty] | 4 | [7 empty] | 1 | 9
82 | Project engineering | [6 empty] | 33 |  | 33 | 4 | [5 empty] | 10 | 8 |  |  |  | 88
9 | Prep for ops | 1 | [19 empty] | 1
| Unspecified | [20 empty] | 0
| FY02 Proposed Engineering Budget | 9 | 4 | 9 | 8 | 2.5 | 6 | 33 | 2 | 33 | 12 | 8 | 14 | 4 | 20 | 3 | 12 | 8 | 3 | 0 | 6 | 196.5
| FY02 Adv Projects Budget | 3.8835 | 4.315 | 8.63 | 6.4725 | 2.1575 | 4.315 | 38.835 |  | 38.835 | 8.63 | 8.63 | 9.3765 | 4 | 25.89 |  | 14.671 | 8.63 | 4.315 | 4.7465 |  | 196.3325
| FY01 Actuals | 2.3825 | 0.65 | 7.6375 | 7.07 | 1.5175 | 4.495 | 45.175 | 0 | 42.845 | 23.7 | 12.7825 | 1.5175 | 1.8 | 20.94 | 4.3325 | 16.195 | 11.375 | 6.5 | 5.9575 | 8.62 | 225.4925

## Summary
| WBS managers | PPPL Engineering and Scientific Staff (person-weeks) | [20 empty] | ORNL Engineering (person-weeks)
| WBS | Chrzanowski | Dudek | Johnson | Kugel | Oliaro | Ramakrishnan | Reiersen | Blanchard | Brooks | Brown | Dahlgren | Designers (mechanical) | Designers (electrical) | Fan | Klink/Gettelfinger | Heitzenroeder | Jun | Majeski | Neumeyer | Other | PPPL total | Nelson | Cole | Fogarty | Goranson | Jones | Williamson | ORNL total
1 | Stellarator core systems | 2 | [8 empty] | 8 | 8 | 4 |  | 20 |  | 2 |  |  |  |  | 44 | 21.575 | 34.52 | 10.7875 | 16.8285 | 22.438 | 34.52 | 140.669
21 | Fueling |  |  |  | 1 | [16 empty] | 1 | [6 empty] | 0
22 | Vacuum pumping |  |  |  | 1 |  |  |  | 2 | [12 empty] | 3 | [6 empty] | 0
23 | Wall conditioning |  |  |  | 1 | [16 empty] | 1 | [6 empty] | 0
24 | RF heating |  |  |  | 1 | [13 empty] | 3 |  | 1 | 5 | [6 empty] | 0
25 | Neutral beams |  |  |  | 4 | [7 empty] | 2 | [7 empty] | 2 | 8 | [6 empty] | 0
3 | Diagnostics |  |  | 9 | [17 empty] | 9 | [6 empty] | 0
4 | Electrical Power | [5 empty] | 6 | [6 empty] | 4 | [6 empty] | 2 | 12 | [6 empty] | 0
5 | Central I&C |  |  |  |  | 2.5 | [15 empty] | 2.5 | [6 empty] | 0
61 | Facility mods and test cell prep | 2 | [10 empty] | 2 | [8 empty] | 4 | [6 empty] | 0
62 | Heating and cooling |  | 2 | [9 empty] | 1 | [8 empty] | 3 | [6 empty] | 0
63 | LN2 systems |  | 1 | [9 empty] | 1 |  |  | 3 | [5 empty] | 5 | [6 empty] | 0
64 | Utility systems |  | 1 | [18 empty] | 1 | [6 empty] | 0
7 | Machine assembly | 4 | [10 empty] | 4 | [7 empty] | 1 | 9 | [6 empty] | 0
82 | Project engineering | [6 empty] | 33 |  | 33 | 4 | [5 empty] | 10 | 8 |  |  |  | 88 | [6 empty] | 0
9 | Prep for ops | 1 | [19 empty] | 1 | [6 empty] | 0
| Unspecified | [20 empty] | 0 | [6 empty] | 0
| FY02 Proposed Engineering Budget | 9 | 4 | 9 | 8 | 2.5 | 6 | 33 | 2 | 33 | 12 | 8 | 14 | 4 | 20 | 3 | 12 | 8 | 3 | 0 | 6 | 196.5 | 21.575 | 34.52 | 10.7875 | 16.8285 | 22.438 | 34.52 | 140.669
| FY02 Adv Projects Budget | 3.8835 | 4.315 | 8.63 | 6.4725 | 2.1575 | 4.315 | 38.835 |  | 38.835 | 8.63 | 8.63 | 9.3765 | 4 | 25.89 |  | 14.671 | 8.63 | 4.315 | 4.7465 |  | 196.3325 | 100.1% |  |  |  |  | Grand total | 337.169 | person-weeks
| FY01 Actuals | 2.3825 | 0.65 | 7.6375 | 7.07 | 1.5175 | 4.495 | 45.175 | 0 | 42.845 | 23.7 | 12.7825 | 1.5175 | 1.8 | 20.94 | 4.3325 | 16.195 | 11.375 | 6.5 | 5.9575 | 8.62 | 225.4925 | 87.14%
[29 empty] | 7.8139 | FTE
[21 empty] | FY02 FTE | 4.5539
1726 | Hours per year (hpy) | [19 empty] | PPPL Engineering and Scientific Staff | 1083823.8702
43.15 | Weeks per year (wpy) | [19 empty] | Georgiyevsky | 30000
238000 | Avg rate (dpy) | [19 empty] | Industrial contracts for manufacturing studies | 125000
1238823.8702