# Annex I

NCSX WBS Dictionary

| WBS Element: 1 | WBS Level: 2 |
| --- | --- |
| WBS Title: | Stellarator Core Systems |
| Description: | This summary-level WBS element consists of all the systems within the cryostat boundary and their associated support structures. Stellarator Core Systems include the Plasma Facing Components (WBS 11), the Vacuum Vessel and In-Vessel Structures (WBS 12), the TF Magnets and Structures (WBS 13), the PF Magnets and Structures (WBS 14), the Cryostat (WBS 15), the Machine Support Structure (WBS 16), the Modular Coils (WBS 17), and the Trim Coils (WBS 18). Included in these elements are all the engineering and physics design efforts starting with the preliminary design phase (Title I) and ending at first plasma, all the necessary Research and Development (R&D) and prototyping to support the design effort, and all component fabrication activities. Once stellarator core components and assemblies have been delivered and accepted at PPPL, subsequent (on-site) assembly, installation, and testing is covered under WBS 7 (Machine Assembly) and WBS 9 (Preparations for Operation). Stellarator core assembly, installation, and integrated systems testing are covered in WBS 7 (Machine Assembly) and WBS 9 (Preparations for Operations). |

| WBS Element: 11 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Plasma Facing Component Systems |
| Description: | This WBS element consists of all the in-vessel systems required to absorb the heat and particle fluxes from the plasma and to effect divertor operation for neutral recycling and density control. This WBS element also includes all the in-vessel systems that serve to protect the vacuum vessel and in-vessel components from energetic particles and heat fluxes from the plasma. Sub-elements within WBS 11 include the: First Wall Panels (WBS 111); Support Ribs (WBS 112); PFC Heating and Cooling Distribution System (WBS 113) Divertor Plenum Baffles (WBS 114) Divertor Plenum Pumping System (WBS 115) PFC Local I&C (WBS 116) Included in these elements are all the engineering and physics design efforts starting with the preliminary design phase (Title I) and ending at first plasma, all the necessary Research and Development (R&D) and prototyping to support the design effort, and all PFC component fabrication. Once PFC components and assemblies have been delivered and accepted at PPPL, subsequent (on-site) assembly, installation, and testing is covered under WBS 7 (Machine Assembly) and WBS 9 (Preparations for Operation). |
| WBS Element: 111 | WBS Level: 4 |
| WBS Title: | First Wall Panels |
| Description: | The first wall panels absorb the particle and heat fluxes from the plasma; effect divertor operation for neutral recycling and plasma density control; and protect the Vacuum Vessel (WBS 12) and in-vessel hardware form energetic particles and radiation heat fluxes. The first wall panels consist of contoured panels. The extent of coverage of the first wall with these formed panels will be determined by the performance requirements for initial operation. The first wall panels are mounted on the Support Ribs (WBS 112). The first wall panels are heated and cooled through thermal contact with the Support Ribs (WVS 112). The first wall panels feature a slot to permit passage of neutral particles to the divertor plenum, which is formed by the Divertor Plenum Baffles (WBS 114), Support Ribs (WBS 112), Vacuum Vessel (WBS 12), and first wall panels. Temperature sensors (and any other sensors and local instrumentation) for the first wall panels, if required, would be included under PFC Local I&C (WBS 116). This WBS element consists of the design (Title 1, Title 2, and Title 3); R&D and prototyping (if required); and fabrication of the first wall panels. On-site assembly, installation, and testing are included under Machine Assembly (WBS 7) and Preparation for Operations (WBS 9). |
| WBS Element: 112 | WBS Level: 4 |
| WBS Title: | Support Ribs |
| Description: | The support ribs provide structural support for the First Wall Panels (WBS 111). They also serve as the means by which the first wall panels are heated and cooled (by conduction). In locations where the support ribs see the plasma directly, i.e. are not protected by the first wall panels, protective features may be required. If so, these protective features (local low-Z tiles or coated metal clips) are part of WBS 112. The support ribs are supported by the vacuum vessel (WBS 12). Gas heating and cooling for the support ribs is provided by the PFC Heating and Cooling Distribution System (WBS 113). Temperature sensors (and any other sensors and local instrumentation) for the support ribs, if required, would be included under PFC Local I&C (WBS 116). This WBS element consists of the design (Title 1, Title 2, and Title 3); R&D and prototyping (if required); and fabrication of the support ribs. On-site assembly, installation, and testing are included under Machine Assembly (WBS 7) and Preparation for Operations (WBS 9). |
| WBS Element: 113 | WBS Level: 4 |
| WBS Title: | PFC Heating and Cooling Distribution System |
| Description: | The PFC heating and cooling distribution system connects the support ribs (WBS 112) with the vacuum vessel and PFC heating and cooling System (WBS 625). Local I&C, if required, would be included under PFC Local I&C (WBS 116). This WBS element consists of the design (Title 1, Title 2, and Title 3); R&D and prototyping (if required); and fabrication of the PFC heating and cooling distribution system. On-site assembly, installation, and testing are included under Machine Assembly (WBS 7) and Preparation for Operations (WBS 9). |
| WBS Element: 114 | WBS Level: 4 |
| WBS Title: | Divertor Plenum Baffles |
| Description: | The divertor plenum baffles block the flow of neutral particles from the divertor plenum back to the plasma. This is accomplished by providing a low conductance seal between the Vacuum Vessel (WBS 12), First Wall Panels (WBS 111), and Support Ribs (WBS 112). Local I&C, if required, would be included under PFC Local I&C (WBS 116). This WBS element consists of the design (Title 1, Title 2, and Title 3); R&D and prototyping (if required); and fabrication of the divertor plenum baffles. On-site assembly, installation, and testing are included under Machine Assembly (WBS 7) and Preparation for Operations (WBS 9). |
| WBS Element: 115 | WBS Level: 4 |
| WBS Title: | Divertor Plenum Pumping System |
| Description: | The divertor plenum shall be designed to be pumped with a local cryopump (as a future upgrade). This WBS element consists of the design effort to assure that a local cryopump can be accommodated as a future upgrade and includes defining space envelopes within the divertor plenum and support features for a local cryopump. No R&D and prototyping; fabrication; and assembly, installation, and testing is required for WBS 115. |
| WBS Element: 116 | WBS Level: 4 |
| WBS Title: | PFC Local I&C |
| Description: | This WBS element provides the local I&C required by other WBS elements included under Plasma facing Components Systems (WBS 11). Local I&C requirements will be determined in the design of these other WBS elements. Temperature sensing for the Support Ribs (WBS 112) and First Wall Panels (WBS 111) will be among the Local I&C requirements. This WBS element consists of the design (Title 1, Title 2, and Title 3); R&D and prototyping (if required); and fabrication of the divertor plenum baffles. On-site assembly, installation, and testing are included under Machine Assembly (WBS 7) and Preparation for Operations (WBS 9). |

| WBS Element: 12 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Vacuum Vessel Systems |
| Description: | This WBS element consists of all the following: Vacuum Vessel Shell (WBS 121); Vacuum Vessel Ports and Extensions (WBS 122); Vacuum Vessel/PFC Interfaces (WBS 123); Thermal Insulation (WBS 124); Vacuum Vessel Heating and Cooling Systems (WBS 125); Vacuum Vessel Supports (WBS 126); and Vacuum Vessel Local I&C and Sensors (WBS 127). The vacuum vessel provides a vacuum boundary around the plasma chamber suitable for high vacuum conditions; structural support for all internal hardware, including the PFC Support Ribs (WBS 112); and access for Auxiliary Systems (WBS 2) and Diagnostics (WBS 3). Included in these elements are all the engineering and physics design efforts starting with the preliminary design phase (Title I) and ending at first plasma, all the necessary Research and Development (R&D) and prototyping to support the design effort, and all vacuum vessel component fabrication activities. Once Vacuum Vessel (WBS 12) components and assemblies have been delivered and accepted at PPPL, subsequent (on-site) assembly, installation, and testing is covered under WBS 7 (Machine Assembly) and WBS 9 (Preparations for Operation). |
| WBS Element: 121 | WBS Level: 4 |
| WBS Title: | Vacuum Vessel Shell |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3) and fabricate a vacuum vessel for the NCSX device, including contracts. The vacuum vessel is a complex, three period structure with a geometry that repeats every 120 degrees toroidally. The geometry is also mirrored every 60 degrees so that the top and bottom sections of the first (0 to 60 degree) segment can be flipped over and serve as the corresponding sections of the adjacent (60 to 120 degree) segment. The VV is a single walled shell and is fabricated of approximately 3/8 of an inch Inconel 625. The vessel will be fabricated in three subassemblies that are bolted together, complete with modular coils and ports. It provides the vacuum boundary around the plasma chamber suitable for high vacuum conditions; structural support for all internal hardware; vacuum vessel armor; cooling for the VV and internal elements; access and support for vacuum pumping, plasma heating and diagnostics. Included in this WBS element are sufficient R&D funds to provide for a full scale partial (1/2 field period) vessel, typical port extensions, cooling lines and other features. |

| WBS Element: 122 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Vacuum Vessel Ports and Extensions |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3) and fabricate the vacuum vessel ports and extensions for the NCSX vacuum vessel, including contracts. The vessel port extensions are needed to transfer the vacuum interface flanges on the ports to an accessible location outside the modular coil structure. Each extension includes the flanges, extension tube with weld prep, and seal/bolting hardware. Several sizes of radial and vertical ports are used to best utilize the limited access between modular coils. The port extensions must be welded onto the three liner sub-assemblies after installation of the modular coils and prior to final assembly. Port stubs are provided on the vessel to permit the modular coils to slip on first, followed by automatic welding of the port extensions from the outside, that is, by a pipe welder inserted down into the port extensions. However, the port extension welding is not included in this WBS element, but is covered in WBS 7. Any necessary R&D is included in WBS 121 above. |
| WBS Element: 123 | WBS Level: 4 |
| WBS Title: | Thermal Insulation |
| Description: | The vessel will be baked to 150ºC and operate at 20ºC. The vessel is insulated on its exterior surface to provide thermal isolation from the modular coils, which operate at cryogenic temperature. The insulation consists of a layer of high temperature (eg, microtherm) bat and a layer of polyimide foam (e.g, solomide). In conceptual design, the insulation thickness will be increased where space allows, substantially reducing the conductive heat loss. This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3) and fabricate the thermal insulation blanket material. At this time no R&D is anticipated for this WBS element. |
| WBS Element: 124 | WBS Level: 4 |
| WBS Title: | Vacuum Vessel Heating and Cooling Systems |
| Description: | The vessel will be baked to 150ºC and operated at 20ºC. The vessel is maintained at temperature by helium gas circulated through tracing lines attached to the vessel exterior. The coolant tracing is installed on the outside surface on approximately 20 cm centers. To minimize distortion of the vessel, these lines are probably not skip welded or brazed, but are attached by clips and compression gaskets, bolted to the vessel, every15 cm along the tubing. Until a more definitive design is developed as part of the conceptual design process, skip welding of the lines has been assumed. This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the tracing lines and mounting hardware. Any necessary R&D is included in WBS 121 above. |
| WBS Element: 125 | WBS Level: 4 |
| WBS Title: | Vacuum Vessel Local I&C |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3) and fabricate the baseline complement of RTDs and/or thermocouples for measuring temperature of the shell, select port flanges, and PFC support points.. This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the local I&C hardware and mounting components. At this time no R&D is anticipated for this WBS element. |

| WBS Element: 1.3 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Toroidal Field Magnets and Structures |
| Description: | This WBS element consists of the following: TF Winding Pack (WBS 1.3.1); TF Cases (WBS 1.3.2); TF Magnet Assembly (WBS 1.3.3); and TF Power & Cooling Interfaces (WBS 1.3.4). Included in these elements are all the engineering and physics design efforts starting with the preliminary design phase (Title I) and ending at first plasma, all TF magnet component fabrication and assembly activities, and all system level commissioning and testing. At this time no R&D is anticipated for this WBS element. TF magnets and structure assembly and installation within the Test Cell and integrated systems testing of the TF magnet systems are covered in WBS Element 7 (Machine Assembly) and WBS 9 (Preparations for Operations).. |
| WBS Element: 1.3.1 | WBS Level: 4 |
| WBS Title: | TF Winding Pack |
| Description: | This WBS element consists of the manufacturing design and fabrication of the TF conductor, and the assembly of the TF winding packs. A set of toroidal field coils is included to provide flexibility in the magnetic configuration. There are 21 identical, equally spaced coils providing a 1/R field at the plasma. The TF coils are mounted on flat, radial plates that get bolted between adjacent modular coil winding forms. Each coil consists of a pair of windings, one on either side of radial support plates. The windings are split about the plate for structural, magnetic and geometric symmetry, for improved accuracy, and for ease of mounting. The coils are wound from hollow copper conductor and vacuum impregnated with epoxy. They operate at the same temperature as the modular coil set, nominally 85K (cooled by 80 K helium) and are connected in series. The leads consist of coaxial conductor to minimize field errors. At this time no R&D is anticipated for this WBS element. |
| WBS Element: 1.3.2 | WBS Level: 4 |
| WBS Title: | TF Magnet Cases (Clamps) |
| Description: | This WBS element consists of the manufacturing design and fabrication of the TF magnet cases and support structures integral with the case assembly. Clamps are needed to attach the TF coils to the flat, radial plates that get bolted between adjacent modular coil winding forms. The initial configuration assumes 12 clamps for each winding pack, however, this design will evolve as the conceptual design process proceeds.. |
| WBS Element: 1.3.3 | WBS Level: 4 |
| WBS Title: | TF Magnet Assembly |
| Description: | This WBS element includes the engineering and installation of the clamps that attach the TF coil windings to the radial support plates. |
| WBS Element: 1.3.4 | WBS Level: 4 |
| WBS Title: | TF Power and Cooling Interface |
| Description: | This WBS element consists of the manufacturing design and fabrication of the bus, manifolds, and cooling pipes within the cryostat boundary up to and including interface elements for connections to power and cooling supply at the cryostat boundary. The TF coils operate at the same temperature as the modular coil set, nominally 85K (cooled by 80 K helium) and are connected in series. The leads consist of coaxial conductor to minimize field errors. |

| WBS Element: 1.4 | WBS Level: 3 |
| --- | --- |
| WBS Title: | PF Magnets and Structure |
| Description: | The poloidal field (PF) magnets produce the poloidal magnetic field within the FIRE device. This WBS element consists of the following: OH Solenoid and PF Integration (WS 1.4.1) PF Ring Coils (WBS 1.4.2); and PF Power and Cooling Interfaces (WBS 1.4.3) Included are the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the PF solenoid and ring coils. It also includes any PF magnets R&D, the PF conductor subcontracts, the PF magnet contracts, and the local I&C that is integral with the PF magnets. At this time no R&D is anticipated for this WBS element. PF magnets and structure assembly and installation within the Test Cell and integrated systems testing of the PF magnet systems are covered in WBS Element 7 (Machine Assembly) and WBS 9 (Preparations for Operations). |
| WBS Element: 1.4.1 | WBS Level: 4 |
| WBS Title: | OH Solenoid and PF Integration |
| Description: | A set of poloidal field coils is provided for inductive current drive and plasma shape and position control. The coil set consists of two inner solenoid pairs (PF-1 and PF-2), a mid coil pair (PF-3) and an outer coil pair (PF-4). Coil pairs are symmetric about the horizontal midplane. The coils are of conventional construction, wound from hollow copper conductor and vacuum impregnated with epoxy. The PF coils operate at the same temperature as the modular and TF coil sets, nominally 85K (cooled by 80 K helium). This WBS element consists of the manufacturing design and fabrication of the PF solenoid conductor. |
| WBS Element: 1.4.2 | WBS Level: 4 |
| WBS Title: | PF Ring Coil |
| Description: | This WBS element covers design and fabrication of the the larger ring coils, including a mid coil pair (PF 3) and an outer coil pair (PF 4). Coil pairs are symmetric about the horizontal midplane. The coils are of conventional construction, wound from hollow copper conductor and vacuum impregnated with epoxy. The PF coils operate at the same temperature as the modular and TF coil sets, nominally 85K (cooled by 80 K helium). The coils are supported via adjustable clamps to the radial support plates. The coils are designed to be self-supporting for radial loads. Vertical loads will be transmitted through the adjustable clamps to the radial support plates. |
| WBS Element: 1.4.3 | WBS Level: 4 |
| WBS Title: | PF Magnets Power and Cooling Interfaces |
| Description: | This WBS element consists of the manufacturing design and fabrication of the bus, manifolds, and cooling pipes within the cryostat boundary up to and including interface elements for connections to power and cooling supply at the cryostat boundary. This element covers leads and cooling interfaces for all the PF coils. The leads consist of coaxial conductor to minimize field errors. Upper and lower PF coils in a given pair are connected in series. Thus, there are four independent electrical circuits. The PF coils operate at the same temperature as the modular and TF coil sets, nominally 85K (cooled by 80 K helium). |

| WBS Element: 1.5 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Cryostat |
| Description: | This WBS element consists of all the following: Cryostat Shell and Structure (WBS 1.5.1); Cryostat Thermal Insulation (WBS 1.5.2); Vacuum Vessel/Cryostat Boots (WBS 1.5.3); Cryostat Temperature Control/Heaters (WBS 1.5.4); and Cryostat Local I&C (WBS 1.5.5) The cryostat encloses the NCSX device to provide a suitable thermal environment for the magnets. This WBS element includes the cryostat shell & structure, the wall insulation for the cryostat shell & structure, attachments for the structural support of internal components, and the required electrical, cooling and mechanical penetrations. Provisions shall be established to maintain thermal and electrical isolation, a slight positive pressure within the cryostat, local I&C, and appropriate interface control with the other WBS elements. Included in these elements are the necessary engineering and physics design efforts starting with the preliminary design phase (Title I) and ending at first plasma, all cryostat component fabrication and assembly activities, and all system level commissioning and testing. At this time, no R&D is anticipated for this WBS element. Cryostat assembly and installation within the Test Cell and integrated systems testing of the cryostat systems are covered in WBS Element 7 (Machine Assembly) and WBS 9 (Preparations for Operations). |
| WBS Element: 1.5.1 | WBS Level: 4 |
| WBS Title: | Cryostat Shell and Structure |
| Description: | A cryostat is provided for thermal isolation. The cryostat must also seal the coil space from the outside air to prevent condensation on the cold surfaces and to provide a means for circulating dry nitrogen inside the cryostat. The cryostat is approximately 250 inches in diameter and 140 inches tall. The baseline concept consists of a simple frame and panel design covered with urethane insulation. The frame consists of fiberglass channels mounted along the edges of each of the radial TF coil support plates, or on the bottom, suspended from the base frame. Fiberglass panels are attached to the frame to form a surface for the urethane. This WBS covers the frame and panels. This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), fabricate, and pre-assemble/disassemble the cryostat shell & structure before assembly on the tokamak structure. |
| WBS Element: 1.5.2 | WBS Level: 4 |
| WBS Title: | Cryostat Thermal Insulation |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3) and provide the cryostat thermal insulation that forms the thermal barrier between the magnets and the ambient temperature test cell. The insulation does not serve any radiation shielding or structural support functions. Urethane is sprayed on the cryostat panel assembly using a commercial process typically used for large stationary cryogenic tanks. The exterior surface of the urethane is then sprayed with a butyl rubber coating for an additional gas seal and to provide a durable surface. |
| WBS Element: 1.5.3 | WBS Level: 4 |
| WBS Title: | Vacuum Vessel/Cryostat Boots |
| Description: | The cryostat must seal the coil space from the outside air to prevent condensation on the cold surfaces and provide a means for circulating dry nitrogen inside the cryostat to cool down and maintain the temperature of the interior structures. A flexible silicone rubber boot is used to provide a seal between the cryostat and the penetration openings. These boots are commercially available. |

| WBS Element: 1.5.4 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Cryostat Temperature Control/Heating Systems |
| Description: | The urethane insulation is probably not sufficient to prevent condensation on the outside of the cryostat. For this reason, heaters will be used to control the outside surface temperature and prevent condensation. This estimate provides an allotment to purchase standard heaters and controls. This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3) and fabricate the cryostat temperature control/heating system components. |
| WBS Element: 1.5.5 | WBS Level: 4 |
| WBS Title: | Cryostat Local I&C and Sensors |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), fabricate, and install the cryostat local I&C systems and sensors. Approximately 30 thermocouples will be installed on the baseline device. |
| WBS Element: 1.6 | WBS Level: 3 |
| WBS Title: | Support Structures |
| Description: | This WBS element consists of all the following: Base Assembly and Gravity Supports (WBS 1.6.1); TF Coil Support Assembly (WBS 1.6.2); PF Coil Supports (WBS 1.6.3); Modular Coils Interfac Sttructure (WBS 1.6.4) and Vacuum Vessel Supports (WBS 1.6.5). The support structures provide the overall supporting mechanism for the tokamak components to the test cell floor. At this time, no R&D is anticipated for this WBS element. Assembly and installation of these support structures within the Test Cell is covered in WBS Element 7 (Machine Assembly).. |
| WBS Element: 1.6.1 | WBS Level: 4 |
| WBS Title: | Machine Base Assembly |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the machine base assembly. The machine base assembly consists of the base column assemblies, interconnecting beams and column base hardware. The base columns are tall enough to provide headroom under the machine and are mounted on rollers to provide a means of accommodating thermal movement. The columns will be covered with thermal insulation to provide a long conduction path for reducing heat leakage to the machine. The interconnecting beams provide support for rails that allow individual field periods to be retracted 18 inches radially to provide vertical clearance between the modular coils. |
| WBS Element: 1.6.2 | WBS Level: 4 |
| WBS Title: | TF Coil Support Structure |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the TF coil support structure. The radial support plates provide a set of interface planes for the modular coils as well as convenient support structure for accurately locating and mounting the TF and PF coils. Shims can be used if necessary between the support plates and the modular coil structure for minute adjustments in coil position and to avoid tolerance buildup of the whole assembly. |
| WBS Element: 1.6.3 | WBS Level: 4 |
| WBS Title: | PF Coil Supports |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the PF coil supports. Adjustable brackets will provide the interface between the radial support plates and the PF coils to accurately align the coils with respect to the modular coils and TF coils. Since large ring coils are often out-of-round, these brackets will also serve to bring the coils into an acceptably round shape. |

| WBS Element: 1.6.4 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Modular Coil Interface Structure |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of modular coil interface structure. Radial slide assemblies are installed on top of the support base to interface with the modular coil field period subassemblies and to provide a means of assembling the machine in three field periods. The slide assemblies also provide a set of horizontal interface planes for the radial support plates. Each of three assemblies includes a horizontal alignment plate, two radial slide assemblies, four interface brackets to the radial support plates, and assorted shims and hardware. |
| WBS Element: 1.6.5 | WBS Level: 4 |
| WBS Title: | Vaccum Vessel Supports |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the mechanical structure to support the vacuum vessel to the floor. The vacuum vessel.. The vacuum vessel supports consist of the vertical links, toroidal links, and backets to position the vessel and restrain if against gravity, seismic, and disruption loads. The links are connected to the outboard region of the vessel near the midplane ports and to the inner bore of the TF coil structure. The links must accommodate thermal movement during all phases of operation, including coil cooldown and vessel bakeout. |

| WBS Element: 1.7 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Modular Coils |
| Description: | This WBS element consists of all the following: Windings and Coil Assembly (WBS 1.7.1); Winding Form/Structure (WBS 1.7.2); Modular Coil Leads (WBS 1.7.3); Modular Coils Cooling System (WBS 1.7.4) and Modular Coil Local I&C (WBS 1.7.5) The modular coils provide a major plasma shaping function for the NCSX device. These coils are positioned outboard of the TF and PF coils. This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the modular coil components, including supporting R&D necessary for the design and fabrication of these components. Modular coil assembly and installation within the Test Cell and integrated systems testing of the cryostat systems are covered in WBS Element 7 (Machine Assembly) and WBS 9 (Preparations for Operations). |
| WBS Element: 1.7.1 | WBS Level: 4 |
| WBS Title: | Modular Coil Windings and Coil Assembly |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the modular coil windings and coil assembly. The modular coil set consists of three field periods with 6 coils per period, for a total of 18 coils. Due to symmetry, only three different coil shapes are needed to make up the complete coil set. The maximum toroidal field at 1.4 m produced by the modular coils with a flattop of 0.5s is 1.7 T. Within the modular coil envelope is a 16 mm thick web that supports two multi-turn winding packs. The design concept uses flexible, copper cable conductor that has been compacted into a rectangular cross-section and wrapped with kapton and glass tape insulation. The conductor is wound in a double pancake on each side of the structural web. When the first pancake has been wound, a chill plate is placed against the first pancake. The chill plates consist of a copper sandwich containing a serpentine cooling passage with inlet and outlet pipes for the gas cooling. Then the second pancake is wound. After winding is complete, the final geometry is verified and the assembly is vacuum pressure impregnated with epoxy to complete the insulation system. The epoxy fills the voids within the cable conductor so the winding pack becomes a monolithic copper-glass-epoxy composite. Auxiliary clamping brackets are then installed. This element includes the conductor, insulation, winding, epoxy impregnation, clamp brackets, inspection and electrical testing. |
| WBS Element: 1.7.2 | WBS Level: 4 |
| WBS Title: | Modular Coil Winding Form/Structure |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the modular coil winding form/structure. There are three different coil types and three different winding forms that are repeated for a total of 18 winding forms. Each winding form is fabricated as a casting. Due to the complexity of the shape, the pattern geometry is assumed to require at least two iterations by a pattern maker. After stress relieving the castings in a fixture, all structural interface features are machined. Instead of making the winding cavity undersized and contour machining it to the required size and accuracy, it is proposed to make the cavity oversized in most areas. A very accurate, multi-part set of patterns would be created using rapid prototyping techniques (such as stereolithography or laminated object modeling) and accurately positioned in the casting. The space between the winding pattern and the structure would be filled with an epoxy grout. The pattern would be removed leaving a very accurate, molded winding cavity. In some areas there may not be room for the epoxy grouting and in these areas the structural web would be locally machined to exact size. After the coils are wound , the winding forms are bolted together, along with the TF coil radial plates, to form a complete modular coil structure. No other integrating structure is needed. |
| WBS Element: 1.7.3 | WBS Level: 4 |
| WBS Title: | Modular Coil Leads |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the modular coil leads. The coils are connected electrically in 3 circuits in groups of 3 or 6, according to type. Each circuit is independently powered to provide maximum flexibility. A crossover between layers occurs at the outside of each coil and the leads extend from the plasma side of the winding pack in a coaxial arrangement to the interconnecting bus. |
| WBS Element: 1.7.4 | WBS Level: 4 |
| WBS Title: | Modular Coil Cooling System |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of modular coil cooling system inside the cryostat. The modular coil windings will be cooled with helium gas at 80K via chill plates integrated into the coil windings. . |
| WBS Element: 1.7.5 | WBS Level: 4 |
| WBS Title: | Modular Coil Local I&C |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the modular coil local I&C components. The modular coil set requires several types of sensors at each coil. The initial design assumes 2 strain gages, 4 RTDs, 2 voltage taps, and 1 flow sensor per coil. |
| WBS Element: 1.8 | WBS Level: 3 |
| WBS Title: | Trim Coils |
| Description: | This WBS element consists of all the following: Trim Coil Assemblies (WBS 1.8.1); Trim Coil Leads (WBS 1.8.2); Trim Coil Local I&C (WBS 1.8.3) The trim coils mitigate field errors in the NCSX device. These coils are positioned inboard of the vacuum vessel. This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the modular trim components, including supporting R&D necessary for the design and fabrication of these components. Trim coil assembly and installation within the Test Cell and integrated systems testing of the cryostat systems are covered in WBS Element 7 (Machine Assembly) and WBS 9 (Preparations for Operations). |
| WBS Element: 1.8.1 | WBS Level: 4 |
| WBS Title: | Trim Coil Assemblies |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the trim coil assemblies. Trim coils are provided to mitigate field errors, in particular the errors on m=5 and m=6 resonant surfaces. The coils are configured in a saddle geometry and are located inside the vacuum vessel on the inboard and outboard regions of the v=0 (bean-shaped) plasma cross-section. The coils should require no more than 10 kA-turns per coil. To provide this, five turns are envisaged in a 5 cm x 1 cm winding pack. Since the coils are located in the vacuum vessel, they must be vacuum tight (canned). High temperature electrical insulation will be required. The present concept for the coils is to provide a formed and embossed stainless steel panel into which the four saddle coils would be wound, with a second panel seam welded over the coils to provide the vacuum closure. Special tooling will be required to provide an accurate, contoured shape. The completed panels can be fully supported by the vacuum vessel on the inboard side, but must be cantilevered from the top and bottom on the outboard side. |

| WBS Element: 1.8.2 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Trim Coil Leads |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the trim coil leads. A set of coaxial leads will be provided from each trim coil panel assembly and will be routed to the outside through continuous conduit. The coils in each group will be connected in series and connected to power supplies in the ESAT building at C-site. The trim coils will be cooled with helium gas at the same temperature as the vacuum vessel. The gas feeds will be in the same conduit as the leads. This element includes the coaxial leads with high temperature insulation, conduit, vacuum feedthroughs, lead routing, inspection and electrical testing. |
| WBS Element: 1.8.3 | WBS Level: 4 |
| WBS Title: | Trim Coil Local I&C |
| Description: | This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the trim coil local I&C components. The trim coils will be fitted with voltage taps, temperature sensors and flow switches. This element includes an allotment for 1 set of sensors per coil. |

| WBS Element: 2 | WBS Level: 2 |
| --- | --- |
| WBS Title: | Auxiliary Systems |
| Description: | This summary-level WBS element consists of all the auxiliary systems required for the FIRE experimental program. Some of these systems are required for day one operation while others may be added as upgrades during the experimental program phase. The Auxiliary Systems include the Fueling Systems (WBS 2.1), the Vacuum Pumping Systems (WBS 2.2), the Wall Conditioning Systems (WBS 2.3), the RF Heating Systems (WBS 2.4), and the Neutral Beam Heating Systems (WBS 2.5). Included in these elements are the necessary Research and Development (R&D) to support the design effort, all the engineering and physics design efforts starting with the preliminary design phase (Title I) and ending at first plasma, all component fabrication and assembly activities, and all system level commissioning and testing. Auxiliary systems assembly and installation within the Test Cell and integrated systems testing of the entire NCSX device is covered in WBS Element 7 (Machine Assembly) and WBS 9 (Preparations for Operations). |
| WBS Element: 2.1 | WBS Level: 3 |
| WBS Title: | Fueling Systems |
| Description: | This WBS element consists all of the effort and systems to provide gas and pellet injection fueling systems for the NCSX device. The existing PBX-M legacy systems will be used for both systems. At this time no R&D is anticipated to be needed for these systems. |
| WBS Element: 2.1.1 | WBS Level: 4 |
| WBS Title: | Gas Fueling Systems |
| Description: | This WBS element consists of the effort to provide gas fueling systems. This WBS element consists of the repair and maintenance needed to bring the existing PBX-M legacy system to operational status. The legacy PBX-M Fuel Gas System includes the Hydrogen Gas Purification System. The PLC used for the vacuum pumping systems (WBS 2.2.1) will also be used for this system. |
| WBS Element: 2.12 | WBS Level: 4 |
| WBS Title: | Pellet Injection Fueling Systems |
| Description: | This WBS element consists of the effort to provide a pellet injection fueling system for use on NCSX. This WBS element consists of the repair and maintenance needed to bring the existing PBX-M legacy system to operational status. This is a stand alone system with its own PLC (either the existing PLC or a new one). This system has been in storage in the PBX-M Cryo-Shed. In addition, special guide tubes will be installed for vertical, inner wall, and outer wall injection. Guide Tube requirements will be reviewed after the completion of the vessel design to determine if any Guide tube related installations are required during the vessel assembly. |
| WBS Element: 2.2 | WBS Level: 3 |
| WBS Title: | Vacuum Pumping Systems |
| Description: | This WBS element only consists of the legacy torus pumping systems of the PBX-M device. The total effort will be to repair, maintain, and upgrade (as necessary) the existing systems. The legacy PBX-M Vacuum Vessel Pumping System consists of: Four (4) Leybold Heraeus TMP 1500 turbos= Four (4) Model 1398 belt driven backing pumps One (1) Kinney KT 500 belt driven roughing pump A new Residual Gas Analyzer (RGA) will be required. In addition, the legacy Pumping System controls will be replaced with a PLC based system. It is noted that routine scheduled maintenance has not been performed on these systems CY92-93 and therefore additional items may be identified as work proceeds. |

| WBS Element: 2.3 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Wall Conditioning Systems |
| Description: | This WBS element consists of the effort to provide wall conditioning and impurity control. Included are theHe Gas Bakeout and Cooling Systems (WBS 2.3.1), Glow Discharge Cleaning (WBS 2.3.2), Boranization Systems (WBS 2.3.3) and Lithiumization Systems (WBS 2.3.4). Boronization startup and testing. This WBS element consists of the design (conceptual, Title 1, Title 2, and Title 3) and fabrication of the wall conditioning systems with R&D as needed. It is anticipated that, at least for the baseline device, no R&D will be needed since maximum use of the legacy PBX-M systems is envisioned. |
| WBS Element: 2.3.1 | WBS Level: 4 |
| WBS Title: | He Gas Bakeout and Cooling Systems |
| Description: | The baseline device does not include He gas bakeout and cooling systems. If needed, these will be added as upgrades during the operational phase. |
| WBS Element: 2.3.2 | WBS Level: 4 |
| WBS Title: | Glow Discharge Cleaning System |
| Description: | This WBS element consists of the effort to provide a glow discharge cleaning (GDC) system for use on NCSX. The WBS element will consist of one fixed wall anode and one dual biased pre-ionization filament unit. These will be installed in each of the 3 NCSX Sectors. A positive bias will be applied between each filament and the vessel so electrons fill the vessel volume. The vessel will be filled with He or D2 to a pressure of 2-4 mT. A bias of about positive 500V will be applied between each anode (+) and the vessel walls (-). The pre-ionization electrons will facilitate the ignition of the GDC at the desired operating pressure and voltage. Initially, the GDC process will be controlled by manual operation of the Vacuum Pumping and Gas Injection Systems PLC (WBS 2.2). Eventually a permissive signal from the computer control system will allow automated HeGDC between plasma discharges. |
| WBS Element: 2.3.3 | WBS Level: 4 |
| WBS Title: | Boranization Systems |
| Description: | This WBS element consists of the effort to provide a boranization system for use on NCSX. Trimethylboron (TMB) Boronization uses the regular torus Gas Injection, GDC, and Vacuum Pumping Systems. A HeGDC is established and a mixture of 90% He and 10% TMB [B(CD3)3] is injected into the HeGDC. After about 3 hrs, 10 g of B/C are deposited on the walls of the vessel to provide a very effective impurity gettering layer about 70-100 monolayers thick. The work required to implement TMB boronization involves installing suitable pressure sensors and interlocking the TMB injection to the GDC current in the PLC. |
| WBS Element: 2.3.4 | WBS Level: 4 |
| WBS Title: | Lithiumization Systems |
| Description: | The baseline device does not include lithiumization systems. If needed, these will be added as upgrades during the operational phase. |
| WBS Element: 2.4 | WBS Level: 3 |
| WBS Title: | RF Heating Systems |
| Description: | The baseline device does not include RF heating systems. If needed, these will be added as upgrades during the operational phase. |

| WBS Element: 2.5 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Neutral Beam Injection Systems |
| Description: | NCSX will utilize the 2 of the 4 existing PBX-M neutral beams and components. The other two beams will be stored for later use. This summary WBS elements consists of the necessary effort to repair and maintain the existing systems and the effort to bring these systems to an operational status (WBS 2.5.1) and the relocation of 2 of the 4 beams. Since NCSX will use existing PBX-M legacy neutral beam systems, no R&D is anticipated. These WBS elements include the effort to reinstall and test the two beams to be utilized for the baseline device. |

| WBS Element: 2.5.1 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Neutral Beam System Startup and Integrated Subsystems Testing |
| Description: | This WBS element consists of the effort to repair and maintain the 2 PBX-M legacy systems (power, vacuum, cryogenic, water, air, instrumentation, PLC control, computer control, computer archiving, and diagnostic subsystems). These systems have not been maintained since the mid-1990’s, so additional scope may be identified as the work progresses. While not an issue for the baseline device, if 4 beams are eventually deployed, replacement of the Accel Power Rectifier and Modulator Systems will be needed. |
| WBS Element: 2.5.2 | WBS Level: 4 |
| WBS Title: | He Gas Bakeout and Cooling Systems |
| Description: | This WBS element consists of the effort to remove the existing 4 legacy PBX-M neutral beam systems and to relocate two (2) of those beams to more tangential injection angle. The above work requires removing a designated Beamline (weight =7.5 Tons) from the PBX-M Test Cell to a suitable storage location (e.g., D-Site NB Power Conversion Building) using the Perry Lift Rig. At this storage location, refurbishing work will be performed. The Beamline base-plates will be moved to the new location. The required Ion Source power junction box and cables located under the Platform will be refabricated for new base-plate location. All control and diagnostic cables will reinstalled. The air, water, cryo, and vacuum lines will be extended to the new location. The Beamline will then be lifted from its storage location, and placed on its base plate at the new location. |

| WBS Element: 3 | WBS Level: 2 |
| --- | --- |
| WBS Title: | Diagnostic Systems |
| Description: | This summary-level WBS element consists of plasma diagnostic subsystems and components to provide the capability to measure the performance of the NCSX device and then evaluate this performance against the physics and engineering objectives. Design of the diagnostic elements near the torus include considerations of space utilization, remote maintenance, neutron shielding, and allowable neutron lifetime dose levels. The suite of NCSX diagnostics are divided into 4 phases as follows: Startup Diagnostics (Phase I); Initial Experimental Program Diagnostics (Phase II); Second Experimental Program Diagnostics (Phase III); and Full Physics Program Diagnostics (Phase IV). Generally, the plasma diagnostics have been categorized as follows (where ‘X” indicates the phase): Magnetic Diagnostics (WBS 3.X.1); General Plasma Monitoring Diagnostics (WBS 3.X.2); Impurity Diagnostics (WBS 3.X.3); MHD Diagnostics (WBS 3.X.4); Profile Diagnostics (WBS 3.X1.5); Edge & Divertor Diagnostics (WBS 3.X.6); Turbulence Diagnostics (WBS 3.X.7); EB Mapping (WBS 3.X.8); and Diagnostic Integration (WBS 3.X.9). Only the start-up (Phase I) diagnostics will be considered as needed for first plasma. All other phases (even though the design may start during the construction project) will be considered upgrades and will be funded outside the NCSX construction project. Integrated systems testing of the entire NCSX device is covered in WBS Element 7 (Machine Assembly). |

| WBS Element: 3.1 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Start-up Diagnostic (Phase I) Systems |
| Description: | This WBS element includes the following diagnostic systems needed for first plasma: Magnetic Diagnostics (WBS 3.1.1); General Plasma Monitoring Diagnostics (WBS 3.12); Impurity Diagnostics (WBS 3.1.3); MHD Diagnostics (WBS 3.1.4); EB Mapping (WBS 3.1.8); and Diagnostic Integration (WBS 3.1.9). This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and assemble magnetic probes and associated electronics. |
| WBS Element: 3.1.1 | WBS Level: 4 |
| WBS Title: | Phase I Magnetic Diagnostics |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and install magnetic probes and associated electronics needed for plasma control. The magnetics sensors include a diamagnetic loop, flux loops, rogowski coils, and B-coils which will provide signals to measure the magnetic flux change in the many geometries necessary to determine the internal magnetic field geometry using an equilibrium reconstruction code. A typical magnetic channel consists of a high temperature sensor coil mounted between the carbon first wall and the vacuum vessel with high temperature leads to a vacuum feedthrough. The signal is transmitted via field cables to an integrator, and finally to a digitizer to provide flux vs time. Many of the signals will also be inputs to the plasma control computer, which will use them to control the coil currents, which determine the plasma size and shape as well as the toroidal plasma current. This task will cover the design and prototyping of the sensors, leads, and sensor mounting structures, the fabrication of the baseline compliment of these sensors, installation of the sensors, leads, vacuum feedthrus, and cabling to junction boxes outside the cryostat. It does not cover field cabling or data acquisition hardware, instrumentation racks or AC power. |

| WBS Element: 3.12 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Phase I General Plasma Monitoring Diagnostics |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and install general plasma monitoring diagnostics associated electronics. This will include a visible camera and an interferometer. One visible camera will be used initially to view all three periods of the plasma with identical ‘tangential views’. This will be a moderately fast framing camera with a frame rate of at least 250 Hz to permit viewing of the startup evolution. Because of plans for wall conditioning and bakeout, shutters will be needed to protect the viewing windows from coating. The light from the plasma will be coupled through viewing lenses into coherent fiber bundles. The camera will be located outside of the cryostat and will view the images through interference filters. The viewing lenses and fiber bundles may need cooling to protect them during bakeout. PCs with frame grabbers will be used to control the cameras, and to capture and store the data. This task covers the procurement of the camera, fiber bundles, associated optics, control PCs and DAQ boards. It also covers the design and fabrication of cooled reetrant window/shutter assemblies. A support structure for an optical table that will house the filter optics and cameras must also be designed and fabricated. The interferometer will be used to monitor the line density on a single line of sight through the core of the plasma during the initial plasma run. A low cost, uncompensated 1 mm microwave system is under consideration, with a chirped solid state source and mixer. The vacuum interface will consist of a quartz window with shutter. Optics will guide the beam through the window to a machined PFC surface on the vessel wall opposite the input port. This task consists of the design and fabrication of the vacuum window, the shutter, and PFC modifications to provide a reflecting surface. It covers the design and procurement of the microwave circuit and optics, and associated support structures and electronics. |

| WBS Element: 3.1.3 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Phase I Impurity Diagnostics |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and install impurity diagnostics associated electronics. This will include visible filterscopes, a visible survey spectometer, and vacuum UV spectrometer. It also includes assembly and testing in the laboratory is also included along with final assembly, system integration, calibration and alignment. on NCSX. At one location there will be a window with shutters and reentrant assemblies consisting of lenses imagining the plasmas onto an array of ~10 large (~1 mm) quartz fibers. The fibers from this window will be routed to a remote optical table, where 12 interference filter/detector assemblies will be used on selected views to monitor selected impurity lines and H (D) recycling lines with high time resolution. This task consists of determining the sightlines of the various views, design and fab of the reentrant window assembly and associated shutters, design and fab of the cooled, reentrant optical heads, design and fabrication of the filter and detector optics and supporting structures and electronics. A visible survey spectrometer capable of simultaneously monitoring several lines of sight will also be purchased. This instrument will view the plasma through a quartz or sapphire window for near UV measurements. In addition, it will simultaneously view several quartz fibers relaying light from sightlines at 3 other windows around NCSX. The task will consist of procurement of the spectrometer and the high dynamic range CCD detector and associated control computer and DAQ board. It will include the design and fabrication of a vacuum window and shutter. An optical system will be designed and built to image ~5 fibers onto the input slit of the spectrometer. A support structure will be built to house the spectrometer at a location where it can view through the window via a short fiber. Most of the line radiation is in the vacuum UV and a spectrometer/detector system capable of surveying this region of the spectrum will be purchased to provide measurements in this spectral range along a single sightline. This system will need a vacuum connection to NCSX, with an interface valve and a dedicated vacuum system. This task consists of determining the system sightline, the design and fab of the vacuum extension and dedicated pumping system, design and fab of a support structure for the vacuum system and spectrometer/detector. It covers the procurement of the UV survey spectrometer and intensifier, a high dynamic range CCD detector and associsated control computer. |

| WBS Element: 3.1.4 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Phase I MHD Diagnostics |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and install MHD diagnostics associated electronics. Included in this category are the soft X-ray diagnostics. Soft x-ray imaging arrays that spatially resolve x-ray emissivity along a fan array of sightlines with good time response is very useful to detect internal MHD activity, and can also provide information on radiated power and Zeff, if used with other baseline diagnostics. Ultimately a large set of such fan arrays will be needed for tomographic reconstruction of the dynamics of magnetic islands at several toroidal positions. For the first plasma run, one 3 -16 channel array will be installed. The proposed array will use compact, integrated, 16 channel linear AXUV diodes behind a pinhole. Metal foils of known thickness can be used to provide crude energy resolution. The high sensitivity and speed of these detectors make them ideally suited for fast MHD measurements in the temperature and density range expected for NCSX. It is proposed that these sensors be cooled to enhance sensitivity. This task consists of the design and fab of 1 reentrant pinhole x-ray camera assembly that will image the x-rays onto cooled sensor arrays that are in vacuum. Detectors, vacuum coaxial feedthrus, preamplifers, and amplifer/digitizers will be procured and integrated into the array. This task includes associated field cabling, lab testing of the array, and assembly and integration on NCSX. |
| WBS Element: 3.1.5 | WBS Level: 4 |
| WBS Title: | Phase I Profile Diagnostics |
| Description: | The baseline device does not include profile diagnostics. These will be added as upgrades during latter operational phases. |
| WBS Element: 3.1.6 | WBS Level: 4 |
| WBS Title: | Phase I Edge & Divertor Diagnostics |
| Description: | The baseline device does not include edge and divertor diagnostics. These will be added as upgrades during latter operational phases. |
| WBS Element: 3.1.7 | WBS Level: 4 |
| WBS Title: | Phase I Turbulence Diagnostics |
| Description: | The baseline device does not include turbulence diagnostics. These will be added as upgrades during latter operational phases. |
| WBS Element: 3.1.8 | WBS Level: 4 |
| WBS Title: | Phase I EB Mapping |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and install EB mapping components. The field mapping hardware consists of a probe drive with an electron gun at its tip, which can be accurately positioned along a line through the nominal cross-section. The axis of the gun also needs to be adjustable for alignment with the local field. During field mapping the electron beam from the gun will intercept a fluorescent screen as it repeatedly transits the device. The light from the strike points will be imaged by a high resolution CCD camera. Careful metrology will reference screen positions to machine coordinates. Strike points will be compared to expectations of a code, which will compute the beam trajectory for given coil currents. Magnetic island structures will be investigated near reference equilibrium conditions. The influence of trim coil currents will be assessed. |

| WBS Element: 3.1.9 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Phase I Diagnostic Integration |
| Description: | This WBS element consists of the physics support to provide diagnostic input through the detailed design phase of the machine. This continues through machine assembly phase and as the baseline diagnostics are being developed. This specific element only includes the effort needed to support the design, fabrication, installation, and testing of the Phase I diagnostics. |
| WBS Element: 3.2 | WBS Level: 3 |
| WBS Title: | Initial Experimental Program Diagnostics (Phase II) |
| Description: | This WBS element includes the following diagnostic systems needed for the first few years of the experimental program. Although the design and perhaps even early procurement efforts may occur during the NCSX construction project, the above early experimental phase diagnostics will be installed as upgrades to the Phase I suite of diagnostics and will be funded separately. |
| WBS Element: 3.3 | WBS Level: 3 |
| WBS Title: | Second Experimental Program Diagnostics (Phase III) Systems |
| Description: | This WBS element includes the following diagnostic systems needed for the second experimental program. Although the design and perhaps even early procurement efforts may occur during the NCSX construction project, the above early experimental phase diagnostics will be installed as upgrades to the Phase I suite of diagnostics and will be funded separately. |
| WBS Element: 3.4 | WBS Level: 3 |
| WBS Title: | Full Capability Diagnostic Program (Phase IV) |
| Description: | This WBS element includes the following diagnostic systems needed for the full capability experimental program. Although the design and perhaps even early procurement efforts may occur during the NCSX construction project, the above early experimental phase diagnostics will be installed as upgrades to the Phase I suite of diagnostics and will be funded separately. |

| WBS Element: 4 | WBS Level: 2 |
| --- | --- |
| WBS Title: | Power Systems |
| Description: | This summary-level WBS element consists of the power systems needed by the NCSX device and components such as the site and experimental magnet systems and the site systems. Since a major portion of existing site, TFTR, and PBX-M legacy power systems will be utilized, it is not anticipated that significant R&D will be needed. Included in these elements are the necessary the engineering and physics design efforts starting with the preliminary design phase (Title I) and ending at first plasma, all fabrication, assembly, and installation activities, and all system level commissioning and testing. This WBS includes bus up to the interface with subsystems at the cryostat boundary or at the Tokamak. Integrated systems testing of the entire NCSX device is covered in WBS Element 9 (Preparation for Operations). Power supplies for the Heating and Current Drive Systems are not included in this WBS element, but are covered in WBS 2. Included in this WBS are AC Power, AD/DC Convertors, DC Systems, Control and Protection Systems, and Power System Design and Integration. |
| WBS Element: 4.1 | WBS Level: 3 |
| WBS Title: | AC Power Systems |
| Description: | This WBS element consists of the following subsystems: Auxiliary AC Power Systems (WBS 4.1.1); and Experimental AC Power Systems (WBS 4.12). |
| WBS Element: 4.1.1 | WBS Level: 4 |
| WBS Title: | Auxiliary AC Power Systems |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3) and reconfigure existing auxiliary AC power systems. The existing AC power infrastructure at C-site will be reused to the maximum practical extent, except for that in the Test Cell which will be stripped. A new AC distribution system, up to and including power panels, is provided in the Test Cell. Activities associated with the reactivation of AC power systems at C-site are included. UPS systems are provided for the controllers of the cryogenic systems associated with NBI and the main NCSX magnets. Grounding in the NCSX test cell is provided. |
| WBS Element: 4.12 | WBS Level: 4 |
| WBS Title: | Experimental AC Power Systems |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), reconfigure existing experimental AC power systems. This WBS element covers the work associated with the use of the D-site Pulsed AC Power 13.8kV distribution systems for NCSX, including reactivation of feeders not in use since TFTR along with minor changes to the lockout and E-stop interlocks which must now interface with the NCSX interlock system. The D-site Pulsed AC Power System, including the MG sets, and 13.8kV SV1/SV2 buses will be shared by NCSX and NSTX. In addition, some of the SV1/SV2 switchgear, feeders, and transformers will be shared. Other SV1/SV2 switchgear, feeders, and transformers not presently in use by NSTX and not used since TFTR operations need to be reactivated. |

| WBS Element: 4.2 | WBS Level: 3 |
| --- | --- |
| WBS Title: | AC/DC Convertors |
| Description: | This WBS element consists of the following subsystems: C-Site AC/DC Convertors (WBS 4.2.1); and D-Site AC/DC Convertors (WBS 4.2.2). |
| WBS Element: 4.2.1 | WBS Level: 4 |
| WBS Title: | C-Site AC/DC Convertors |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), reconfigure existing experimental C-Site AC/DC power convertors. Existing Robicon rectifiers in the ESAT building at C-site will be used to power the NCSX trim coils. These are designated the T-1, -2, -3, -4 units which are rated 5kA/300V. They need to be reactivated and brought to an operating condition. This includes various preliminary tests such as hipot, controls check out, water system check out, trip settings, and dummy load test. Some modifications to the controls may be required to interface with the NCSX real time control system. |
| WBS Element: 4.2.2 | WBS Level: 4 |
| WBS Title: | D-Site AC/DC Convertors |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), reconfigure existing experimental D-Site AC/DC power convertors. Existing Transrex rectifiers in the FCPC building at D-site will be used to power the NCSX Modular, Poloidal Field, and Toroidal Field coils. For those systems which do not share the power supplies with NSTX (namely PF2, PF3, PF4, and TF) the associated rectifier units (10 power supplies, 20 power supply sections) need to be reactivated and brought to an operating condition. This includes various preliminary tests such as hipot, controls check out, water system check out, trip settings, and dummy load test. Some modifications to the controls may be required to interface with the NCSX real time control system. |
| WBS Element: 4.3 | WBS Level: 3 |
| WBS Title: | DC Systems |
| Description: | This WBS element consists of the following subsystems: C-Site DC Systems (WBS 4.3.1); D-to-C- Site DC Systems (WBS 4.3.2); and D-Site DC Systems (WBS 4.3.3). |
| WBS Element: 4.3.1 | WBS Level: 4 |
| WBS Title: | C-Site DC Systems |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), reconfigure existing experimental C-Site DC systems. For the main coils (Modular, PF, TF) the sixteen (16) 1000MCM power cables coming across from D-site will be received in the existing PLT OH/EF building, and spliced to eighteen (18) existing 1000MCM cables which connect to the Disconnect/Link area in the C-site MG basement. The existing switches and bus bar carry the current into the Test Cell. From the stubs penetrating the floor, eighteen (18) new 1000MCM cables will be connected to the coil circuit terminals. For the trim coils, eight (8) new 250MCM cables will be spliced to the existing cables coming from the ESAT Robicon rectifiers to make the connection to the four (4) trim coil circuits. |

| WBS Element: 4.3.2 | WBS Level: 4 |
| --- | --- |
| WBS Title: | D-to-C-Site DC Systems |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), fabricate, and install experimental D-Site D-to-C-Site DC Systems. A new cable run, approximately 600 feet long, will be installed from the East-West wing of the FCPC building at D-site, 2nd floor, to the C-site PLT OH/EF building. This will include sixteen (16) 1000MCM cables, a cable tray, and support system mounted approximately 20 feet above ground level. |
| WBS Element: 4.3.3 | WBS Level: 4 |
| WBS Title: | D-Site DC Systems |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), reconfigure existing experimental D-Site DC systems Reconfiguration of the outputs of the NCSX- dedicated Transrex power supplies (ten (10) power supply units) via new power cabling (1/c-1000MCM per pole) and six (6) new DC current limiting reactors. Modification of existing cabling and provision of a common tie points for the shared systems (NCSX Modular with NSTX TF, and NCSX PF1 with NSTX OH) via 1000 MCM cable. Dummy load testing of NSTX systems after reconnection. Provision of isolating switches provided for opening the circuit for troubleshooting purposes at the FCPC. |
| WBS Element: 4.4 | WBS Level: 3 |
| WBS Title: | Control and Protection Systems |
| Description: | This WBS element consists of the following subsystems: Electrical Interlocks (WBS 4.4.1); Kirk Key Interlocks (WBS 4.4.2) Real Time Control Systems (WBS 4.4.3) Instrumentation Systems (WBS 4.4.4) Coil Protection Systems (WBS 4.4.5); and Ground Fault Monitoring System (WBS 4.4.6). |
| WBS Element: 4.4.1 | WBS Level: 4 |
| WBS Title: | Electrical Interlock System |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), fabricate, and install an electrical interlock system for NCSX. An electrical interlock system is designed and installed which ensures the proper configuration of the power system in accordance with the commanded state from the NCSX control room and access control systems, and which provides coordinated fast fault response of the power supplies when faults are detected. The system is implemented by Programmable Logic Controllers (PLCs) at various C-site and D-site locations interconnected through a fiber optic network. The system must be compatible with both NCSX and NSTX operations, at least for the shared power supplies. |
| WBS Element: 4.4.2 | WBS Level: 4 |
| WBS Title: | Kirk Key Interlocks |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), procure, fabricate, and kirk key interlocks for NCSX. Mechanical kirk key interlocks are used throughout the D-site power supply system to ensure the proper sequence of manual switching operations and that equipment is in the safe state prior to accessing hazardous areas. This system must be modified to reflect the modified power supply configuration, and must include appropriate elements from the C-site elements of the power system. |

| WBS Element: 4.4.3 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Real Time Control Systems |
| Description: | This WBS element consists of the effort to develop the specification of the hardware requirements and software algorithms to be provided by WBS 5 (Cental I&C) for the real time digital feedback control of the power supply system, including the high speed digital input and output links. |
| WBS Element: 4.4.4 | WBS Level: 4 |
| WBS Title: | Instrumentation Systems |
| Description: | This WBS element consists of the effort to design and specify, procure, install, and implement current and voltage measurements for the Modular, PF, and TF magnets. Current measurements are made at D-site using one precision DC Current Transducer and one optically isolated shunt per circuit. Voltage measurements are at C-site using voltage transducers from line to ground, one from each pole of each circuit to ground. Also included are signal conditioners that receive the current measurements and buffer, filter, and fan out each signal to multiple destinations. |
| WBS Element: 4.4.5 | WBS Level: 4 |
| WBS Title: | Coil Protection Systems |
| Description: | This WBS element consists of the effort to design and specify, procure, program, and implement hardware and software as required to provide 1) digital coil protection system and 2) ground fault detection system for the Modular, PF, and TF coil systems. The digital coil protection system uses the coil current measurements as input and declares a fault if electrical, thermal, or mechanical limits are exceeded. The ground fault detection system declares a fault if excessive ground current flow is detected. |
| WBS Element: 4.4.6 | WBS Level: 4 |
| WBS Title: | Ground Fault Monitoring System |
| Description: | This WBS element consists of the effort to design and specify, procure, implement a ground fault monitoring system which serves to detect the integrity of machine grounds and generate alarms in case of spurious grounds. |
| WBS Element: 4.5 | WBS Level: 3 |
| WBS Title: | Power System Design and Integration |
| Description: | This WBS element consists of the following subsystems: System Design and Interfaces (WBS 4.51); Electrical Systems Support (WBS 4.5.2);and System Testing/PTPs (WBS 4.5.3). |
| WBS Element: 4.5.1 | WBS Level: 4 |
| WBS Title: | Electrical Interlock System |
| Description: | This WBS element consists of the electrical system engineering and design/drafting, which includes the design and analysis of the overall electrical system, its documentation, and the conduct of design reviews. |
| WBS Element: 4.5.2 | WBS Level: 4 |
| WBS Title: | Kirk Key Interlocks |
| Description: | This WBS element consists of the effort to ensure overall project coordination of electrical systems by providing electrical systems support to other systems, including diagnostics, which provides the engineering, design/drafting, and installation of diagnostic cabling (total 90 cables assumed). |

| WBS Element: 4.5.3 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Systems Testing (PTPs) |
| Description: | This WBS element consists of the effort to conduct all systems-related preoperational testing, including DC Circuit Hipots and Impedance Measurements, Electrical Interlock Testing, Overall integrated systems testing, including Kirk Key Interlock Testing, Instrumentation Test & Calibration, Real Time Control System Testing, Coil Protection System Testing, Ground Fault Monitor Testing, Coil Power Supply Dummy Load Testing, and Trim Coil Power Supply Dummy Load Testing. Support of Integrated System Testing is covered in WBS 9 (Preparations for Operation). |

| WBS Element: 5 | WBS Level: 2 |
| --- | --- |
| WBS Title: | Central I&C and Data Acquisition (CICADA) Systems |
| Description: | This summary-level WBS element consists of the central instrumentation and control (I&C) systems that provide the central supervisory control and data handling systems for FIRE. These systems interface with the subsystem local I&C systems and allow for control and monitoring of FIRE experiments from the control room (local or remote) and the analysis of the results. The central I&C systems covered under this WBS elements include TCP/IP Infrastructure Systems, Central Instrumentation and Control, Facility Timing and Synchronization, Real Time Power Supply Control, Data Acquisition & Facility Computing, Central Safety Interlock Systems, and Control Room Facility Design. Integrated systems testing of the entire NCS device is covered in WBS Element 9 (Preparations for Operations). |
| WBS Element: 5.1 | WBS Level: 3 |
| WBS Title: | TCP/IP Infrastructure Systems |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and assemble TCP/IP infrastructure system components and associated electronics Installation of the these components on the NCSX device is covered under WBS 9 (Preparations for Operations). The TCP/IP network infrastructure will provide the common backbone for all data acquisition, and I&C communications. The network will consist of three distinct networks: Physics, Engineering and Plant networks. All cable and switch infrastructure will minimally support 100Mbps Ethernet and all uplinks will be designed for 1Gigabit and possibly 10 Gigabit Ethernet. The Test Cell Ethernet infrastructure will be completely fiber optic. The cost basis will assume that current prices for 10 Mbps and 100Mbps Ethernet will correspond to 100Mbps and 1-10 Gbps Ethernet in 2005. The primary switch hubs will be deployed in five locations: D-Site FCPC (Power Conversion and Plasma Control); D-Site MG; C-Site S1 Area (RF); C-Site NCSX Control Room (Test Cell and NBI); and PPLCC A fiber optic infrastructure will be deployed to all primary and secondary hubs. Two fiber optic distribution panels will be located in the Test Cell on each side of the machine. A fiber optic infrastructure will also be deployed for facility timing and synchronization. 96 Diagnostic fiber optics for video cameras and other diagnostic requirements will be deployed between the control room and the test cell and 12 fiber optics between C-Site and D-Site will be deployed for real time plasma control communications. |

| WBS Element: 5.2 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Central Instrumentation and Control Systems |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and assemble central I&C system components and associated electronics. Installation of these components on the NCSX device is covered under WBS 9 (Preparations for Operations). The central process control system will provide the common user interface to all engineering subsystems and high-energy processes. It will provide the synchronization between two or more operating machines at PPPL using shared power conversion resources. It will support current and historical trending, alarm logging, mimic displays, machine state archival, and process control and monitoring functions for NCSX. It will be designed using the Experimental Physics and Industrial Control System (EPICS). The following subsystems will be supported with control and display pages: Fueling Systems; Cryogenic Systems; Vacuum Pumping Systems Water Systems; Thermocouples (NBI, Water, Coil, Vacuum Vessel); Magnet Power Systems; Motor Generators; RF Heating Systems (when added as future upgrades); Wall Conditioning Systems; and Neutral Beam Heating Systems. |
| WBS Element: 5.3 | WBS Level: 3 |
| WBS Title: | Facility Timing and Synchronization Systems |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and assemble facility timing and synchronization system components and associated electronics. Installation of the these components on the FIRE device is covered under WBS 9 (Preparation for Operations). A new timing and synchronization technology is required for NCSX. The CAMAC based TFTR Timing System was developed in the late 70’s. Typical resolution was 1ms for periods over 1 second. A requirement to use off-the-shelf or existing solutionsfor NCSX is highly desirable. A VME based system from BNL used on the Relativistic Heavy Ion Collider (RHIC) is being investigated. This system is being modified for use on the Spallation Neutron Source at ORNL and will provide the basis for the NCSX design. The systems will satisfy the following requirements: Timing stability and jitter under 5ns; Timing granularity of 60-100 ns; Overall accuracy +/- 0.5us with contention; 256 event triggers; and Single fiber optic broadcast transmission using self clocking encoding scheme. This activity will provide the engineering to convert the V102 timing modules to CPCI and PCI formats. Additional manpower to write software drivers will also be provided. |

| WBS Element: 5.4 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Real Time Power Supply Control Systems |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and assemble real time power supply control system components and associated electronics. Installation of the these components on the FIRE device is covered under WBS 9 (Preparation for Operations). The Real Time Power Supply Control System will calculate an Alpha control signal and transmit it to the power conversion firing generators in the FCPC area. A coil current digitizer will be provided and remote signals will be transmitted to it using existing fiber optic transceivers. The Real Time Power Supply Control System will not provide primary coil protection functions. This design will be based on the existing Power Supply Real Time Control System (PSRTC) software, however, will not include any Plasma Control functions. The system will be based on PC technology and will not use a high-speed parallel processing platform. The design will allow for the addition of a higher speed processor for future real time plasma control, including real time efit. |
| WBS Element: 5.5 | WBS Level: 3 |
| WBS Title: | Data Acquisition & Facility Computing Systems |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and assemble data acquisition and facility computing system components and associated electronics. The design will use the existing MIT developed MDSplus software for data acquisition, data archiving and display. Individual diagnostic local control and data acquisition will use standard PC architecture machines or Compact PCI chassis. 20 diagnostic operator interface units will be configured and deployed for day 1 operations. Approximately 10 PC’s/CPCI units with IO channels as specified by WBS 3(Diagnostic Systems) will be purchased and deployed for day 1 operations. Legacy CAMAC will not be used in the design of the NCSX DAS. An additional facility compute server/cluster, tape library expandable to 0.5PB-1.0PB, and disk storage area network (RAID 5) will be deployed for the data acquisition system. A standard Software Interface Specification to MDSplus will be designed for use at PPPL and for remote collaborators. The standard will be composed of a set of interfaces and applications, which when used, will insure a smooth integration of diagnostics into the DAS. A standard inter-processor messaging system to allow coordination of remote diagnostics and the central data acquisition system will be included in the Software Interface Specification.. |
| WBS Element: 5.6 | WBS Level: 3 |
| WBS Title: | Central Safety Interlock Systems |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3), procure and assemble data central safety interlock system components and associated electronics. The Central Safety Interlock System will provide system wide coordination of personnel and hardware interlocks. Its primary man machine interface will be EPICS. The Central Safety Interlock System will be a fail-safe, hybrid system. Mechanical components and hardwired devices will provide primary protective functions. Redundant PLC technology with redundant sensors will be used to achieve effective, safety system capabilities. Each NCSX high-energy subsystem will interface with the Central Safety Interlock System. A badge reader access control system will restrict access to the Test Cell for only authorized/trained personnel. Critical components will be powered by UPS and Standby power. |

| WBS Element: 5.7 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Control Room Facility |
| Description: | This WBS element consists of the effort necessary to design (conceptual, Title 1, Title 2, and Title 3) and installation of a new NCSX control room facility. The PLT and PBX control room area is approximately 2400 sq.ft. and will not large enough for both PPPL physicists and remote collaborators. The NSTX control room, not including the annex, is approximately 3200 sq.ft. The old DAS computer area will have to be used soon after day one if this area is used for the control room. This WBS element will be responsible for the design and installation of the following subsystems in a new control room: Installation of raised flooring; Installation of 25 dual workstation tables wired for network and power Installation of raised flooring; Installation of 6-12 equipment racks wired for network and power; Expandable closed circuit TV system with 3 PTZ cameras; A Test Cell PA system; Diagnostic machine microphones data included in MDSplus tree; and Dual screen “comfort” display system. |

| WBS Element: 6 | WBS Level: 2 |
| --- | --- |
| WBS Title: | Site and Facilities |
| Description: | This summary-level WBS element consists of the site and facilities needed to support the NCSX experimental program. The NCSX device will make maximum use of existing PPPL systems and facilities. This WBS element includes Facility Modifications and Test Cell Preparations, Heating and Cooling Systems, Liquid Nitrogen Storage and Supply Systems, and Utility Systems Maintenance and Refurbishment. Integrated systems testing of the entire NCSX device is covered in WBS Element 9 (Preparations for Operations). |
| WBS Element: 6.1 | WBS Level: 3 |
| WBS Title: | Facility Modifications and Test Cell Preparations |
| Description: | This WBS element includes site improvements and interfaces needed for the NCSX device and experimental program: Facility modifications outside the Test Cell (WBS 611); Test Cell cleanup (WBS 612); and Test Cell preparations (WBS 613). This WBS element consists of the effort necessary to modify and/or refurbish existing facilities to accommodate the NCSX device in the combined PLT/PBX-M Test Cell. |
| WBS Element: 6.1.1 | WBS Level: 4 |
| WBS Title: | Site and Facility Improvements |
| Description: | This WBS element includes the modification of facilities outside of the C-site Test Cell, which will be required for NCSX usage for either assembly or operation. The following work scope is anticipated: PLT/PBX Control Rooms - Safing and clearing the PLT/PBX Control Rooms including the adjacent computer room. Includes installation of new lighting, ceiling, electrical panels and walls. OH/EF building - Installation of a weatherproofed penetration through the wall of the OH/EF building for cable runs from D-site. The removal of equipment, cable trays, etc. will be covered by ERWM funds FCPC- second floor - Relocation of personnel from 2nd. Floor of FCPC including the removal of office walls, AC power etc. The Vacuum Prep lab will remain untouched. Installation of twenty (20) 6 inch diameter penetrations through the FCPC floor. Installation of weatherproofed penetration through the 2nd. Floor wall of FCPC for cables running from FCPC to the new Test Cell D-site Test Cell (TFTR) - Extend the Helium Gas Bakeout System line from the NSTX Test Cell to the vacant D-site Test Cell, to be used for baking out of vacuum vessel segments during assembly of field periods. |

| WBS Element: 6.12 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Test Cell Cleanup |
| Description: | This WBS element includes the activities associated with the cleanup of the C-site Test Cell for NCSX occupancy. Work to be complete includes: Electrical Safing of the NCSX Test Cell in anticipation of the bulk removal of the PBX device; Disconnection and removal of the hydraulic systems in anticipation of bulk removal of the PBX device; Removal of all lead (approx. 16,000 lbs.) from the PBX machine in anticipation of bulk removal of the PBX device; Bulk removal of the PBX device by outside salvage contractor. Oversight and planning will be provided by PPPL engineering; and Removal and storage of shield walls between the PLT and PBX Test Cells along with the walls around the delivery area. Removal of Neutral Beams are responsibility of WBS 25 and removal of reusable diagnostics is the responsibility of WBS 3. |
| WBS Element: 6.1.3 | WBS Level: 4 |
| WBS Title: | Seismic Modification to the Test Cell Walls |
| Description: | This WBS element includes the activities associated with modifications to Shield walls to be meet seismic requirements. The work scope includes: Reconfiguring and seismically supporting shield walls to meet seismic requirements; and Increasing the height of the shield walls on the east, west and south sides of the Test Cell to help reduce shine. |
| WBS Element: 6.2 | WBS Level: 3 |
| WBS Title: | Heating and Cooling Systems |
| Description: | This WBS element consists of the following subsystems: NB Water (WBS 621); Vacuum Water (WBS 622); Bakeout Water (WBS 623); Diagnostics Water (WBS 624); and Vacuum Vessel & PFC Bakeout Water (WBS 6.2.5). |
| WBS Element: 6.2.1 | WBS Level: 4 |
| WBS Title: | Neutral Beam Water Systems |
| Description: | The WBS element consists of the effort to provide a 375 gpm cooling water capability for the NCSX neutral beams for day one operations. This job includes the design for (4) Neutral Beams but the fabrication and installation of only 2 systems. Electrical connections to motorized valves will be covered by the Neutral Beam WBS (WBS 25). |
| WBS Element: 6.2.2 | WBS Level: 4 |
| WBS Title: | Vacuum Water Systems |
| Description: | The WBS element consists of the effort to provide a small < 10 gpm cooling water loop to reject heat produced by the vacuum vessel vacuum pumping system. Work includes design, fabrication and installation. The existing system will be reused were practical by replacing existing instrumentation and heat exchanger. A backflow preventer from the potable water system will also need to be installed. |
| WBS Element: 6.2.3 | WBS Level: 4 |
| WBS Title: | Bakeout Water Systems |
| Description: | The WBS element consists of the effort to provide the cooling water system for the helium bakeout skid to reject waster heat. The system load is expected to be 22 kw provided from the CS cooling water system at C-site. |

| WBS Element: 6.2.4 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Diagnostic Water Systems |
| Description: | The WBS element consists of the effort to provide a small 25 gpm manifold around the machine which supplies DI cooling water facility for the diagnostics systems. The work includes design, fabrication and installation. |
| WBS Element: 625 | WBS Level: 4 |
| WBS Title: | Vacuum Vessel & PFC Heating and Cooling Systems |
| Description: | The WBS element consists of the effort to provide a bakeout skid and associated gas manifold system to the stellerator. This work includes design, fabrication and installation of the skid and system. The skid mounted bakeout system will be procured as a custom manufactured item from an outside supplier. The bakeout system will provide a 350 C bakeout capability to the vacuum vessel and PFCs, 150 C cooling capability to the vacuum vessel liner and a standby heating capability to the vacuum vessel and PFCs. |
| WBS Element: 6.3 | WBS Level: 3 |
| WBS Title: | Liquid Nitrogen Storage & Supply Systems |
| Description: | This WBS element consists of the following subsystems: New LN2 System (WBS 631); Cryogenic Line Upgrade (WBS 6.3.2) and Helium Cooling & Circulation Systems (WBS 6.3.3). |
| WBS Element: 6.3.1 | WBS Level: 4 |
| WBS Title: | New Liquid LN2 System |
| Description: | The WBS element consists of the effort to design and install a system to supply up to 15,000 gallons per day liquid nitrogen to the NCSX cryostat and neutral beam line including 7100 gallons for cooldown. The basis for the design is an initial dissipative load of 33 MJ upgradeable to 76 MJ with 48 pulses per day. Based on pre-conceptual design effort, it is anticipated that the design will consist of one 15,000 gallon LN tank and associated control valves, a transfer line to the cryostat and means to control icing and safely exhaust the vaporized nitrogen to the atmosphere. If required, a second tank can be installed at a later date. |
| WBS Element: 6.3.2 | WBS Level: 4 |
| WBS Title: | Cryogenic Line Upgrade |
| Description: | The WBS element consists of the effort to upgrade existing neutral beam helium supply system. The baseline machine will not include this upgrade. When needed, four beam lines and a pellet injector uses up to 1100 gallons per week based on PBX historical usage. The upgrade will consist of inspection and repair of the existing He/LN supply line, adding line as required and installing new jumper lines to the neutral beams. |
| WBS Element: 6.3.3 | WBS Level: 4 |
| WBS Title: | Helium Cooling & Circulation |
| Description: | The WBS element consists of the effort to design and install a new helium cooling and circulation system. It has been determined that ~ 1016.4 g/s total He cooling flow is required to cool the coils (121 g/s per cooling passage x 840 passages (7.55 mm x 2 mm each)). This is preferred over direct nitrogen cooling to lower the coil temperatures as much as possible and due to uncertainties of the two-phase nature of LN2 cooling in such small passages. The closed loop He system will run at a pressure of approximately five atmospheres, with an estimated pressure drop of .05 atm through the passages. This closed loop cooling system will consist of a reciprocating or centrifugal helium compressor, SS piping/manifold and a stainless steel heat exchanger with a brazed aluminum core cooled by low pressure LN2. The compressor power is approximately 150 hp (6.7 MJ/min). For the 1.7T case, the total helium T is ~35 oK. This requires 250 gallons of LN2 per pulse at a nominal flow rate of 30 gpm. |

| WBS Element: 6.4 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Utility Systems Maintenance and Refurbishment |
| Description: | The WBS element only consists of the effort to provide the design, fabrication and installation of a manifold system around the NCSX for compressed air, gaseous nitrogen and vacuum venting. |

| WBS Element: 7 | WBS Level: 2 |
| --- | --- |
| WBS Title: | Machine Assembly |
| Description: | This summary-level WBS element consists of the necessary engineering and field craft labor to install the fusion core systems, provide special machine assembly tools and equipment as needed, in-vessel measurement systems, and remote maintenance systems. Based on Davis-Bacon determinations, this may be performed by either craft labor or national laboratory labor, depending on the degree of specialization required. This WBS element includes Assembly Planning and Oversight Operations, On-Site Pre-Assembly Operations, Assembly Operations in the Test Cell and Basement, and Measurement Systems. |
| WBS Element: 7.1 | WBS Level: 3 |
| WBS Title: | Assembly Planning and Oversight Operations |
| Description: | This WBS element consists of the following subsystems: Planning Activities (WBS 7.1.1); NCSX Platform Design and Fabrication (WBS 7.12); Tooling Design & Fabrication (WBS 7.1.3); and Oversight Activities During Construction (WBS 7.1.4). |
| WBS Element: 7.1.1 | WBS Level: 4 |
| WBS Title: | Planning Activities |
| Description: | This WBS element consists of the activities associated with planning the assembly of the NCSX device. Included is the development of a plan for assembly of machine components, providing integration between WBS elements involving assembly activities, and initiating and maintaining General Aarrangement drawings of the Test Cell (routing of cable trays, plumbing, electrical leads, etc. |
| WBS Element: 7.12 | WBS Level: 4 |
| WBS Title: | NCSX Platform Design and Fabrication |
| Description: | The WBS element consists of the activities associated with design and fabrication of the NCSX machine platform. This work scope encompasses is the design and fabrication of a platform around the NCSX device, including platform material procurements. |
| WBS Element: 7.1.3 | WBS Level: 4 |
| WBS Title: | Tooling Design & Fabrication |
| Description: | The WBS element consists of the activities associated with the design and fabrication of tooling required to assemble the NCSX device. The work scope includes the design and fabrication of special fixtures and tooling which will be required to assemble the NCSX machine components, general procurements of miscellaneous items required for assembly such as safety equipment, general tools, hardware and disposable items, specific procurement of welding supplies (Inconel wire) and equipment required to assemble the NCSX device. |
| WBS Element: 7.1.4 | WBS Level: 4 |
| WBS Title: | Oversight Activities During Construction |
| Description: | The WBS element consists of the activities associated managing the assembly of the individual field periods and the overall NCSX device. Specific work to be accomplished includes oversight and coordination of all assembly activities in the NCSX Test Cell and basement, including those activities between WBS packages and oversight and coordination of Pre-assembly activities, which will occur in the vacated TFTR Test Cell, and assembly of the (3) field periods. This WBS element also provides for a Construction Manager, plus engineering and supervisory support for assembly activities. Required, but not costed in this proposal (overhead) are a full time Construction Safety representative and coverage by both Industrial Hygiene and Quality Control personnel – this will be covered in WBS 83 (ES&H/QA). |

| WBS Element: 7.2 | WBS Level: 3 |
| --- | --- |
| WBS Title: | On-Site Pre-Assembly Operations |
| Description: | This WBS element consists of the following subsystems: Preparation of the Pre-Assembly Area (WBS 7.2.1); Receive, Inspect, and Test TF & Modular Coils (WBS 7.2.2); Assemble TF/Modular Coils (WBS 7.2.3); Receive, Inspect, & Test Vacuum Vessel (WBS 7.2.4); Assemble 1st Field Period (WBS 7.2.5); Assemble 2nd Field Period (WBS 7.2.6); and Assemble 3rd Field Period (WBS 7.2.7). |
| WBS Element: 7.2.1 | WBS Level: 4 |
| WBS Title: | Preparation of the Pre-Assembly Area |
| Description: | The WBS element consists of the activities associated with preparing the field period pre-assembly area for receipt of components. This includes preparing the area (TFTR Test Cell) to assemble field periods, installing assembly fixtures, and assembly tooling. |
| WBS Element: 7.2.2 | WBS Level: 4 |
| WBS Title: | Receive, Inspect, and Test TF & Modular Coils |
| Description: | The WBS element consists of the activities associated with the receipt of coil components from the fabrication vendors. This includes receiving and unloading of new coil systems at the D-site pre-assembly area and Mechanical inspections and electrical testing of delivered coil systems. |
| WBS Element: 7.2.3 | WBS Level: 4 |
| WBS Title: | Assemble TF/Modular Coils |
| Description: | The WBS element consists of the activities associated with the assembly of the TF/Modular coils to verify alignment and fit up. This includes assembly of the individual TF and Modular coil sections together for alignment and component fit up and disassembly of the coil components following alignment activities. |
| WBS Element: 7.2.4 | WBS Level: 4 |
| WBS Title: | Receive, Inspect, and Test Vacuum Vessel |
| Description: | The WBS element consists of the activities associated with receiving and inspecting the (3) sections of NCSX vacuum vessel. This includes delivery and receiving inspections of the three (3) sections(plus port extensions) and unloading of the vacuum vessel segments to the D-site pre-assembly area. |
| WBS Element: 7.2.5 | WBS Level: 4 |
| WBS Title: | Assemble 1st Field Period |
| Description: | The WBS element consists of the activities associated with assembling together the 1st. Field Period. The work scope includes: Assembly/alignment of the TF/Modular coils with 1/3 of the vacuum vessel; Positioning and welding (22) port extensions onto the VV segment; Positioning and welding the PFC support rings inside of the VV; Completing bakeout of the VV segment to 150 degrees C; Vacuum leak checking the vessel segment and port extensions; Partially installing internal diagnostics; Installing (4) sets of Trim coils; and Transporting the 1st. Field Period to the NCSX Test Cell. |

| WBS Element: 7.2.6 | WBS Level: 4 |
| --- | --- |
| WBS Title: | Assemble 2nd Field Period |
| Description: | The WBS element consists of the activities associated with assembling together the 2nd. Field Period. The work scope includes: Assembly/alignment of the TF/Modular coils with 1/3 of the vacuum vessel; Positioning and welding (22) port extensions onto the VV segment; Positioning and welding the PFC support rings inside of the VV; Completing bakeout of the VV segment to 150 degrees C; Vacuum leak checking the vessel segment and port extensions; Partially installing internal diagnostics; Installing (4) sets of Trim coils; and Transporting the 2nd. Field Period to the NCSX Test Cell. |
| WBS Element: 7.2.7 | WBS Level: 4 |
| WBS Title: | Assemble 3rd Field Period |
| Description: | The WBS element consists of the activities associated with assembling together the 3rd. Field Period. The work scope includes: Assembly/alignment of the TF/Modular coils with 1/3 of the vacuum vessel; Positioning and welding (22) port extensions onto the VV segment; Positioning and welding the PFC support rings inside of the VV; Completing bakeout of the VV segment to 150 degrees C; Vacuum leak checking the vessel segment and port extensions; Partially installing internal diagnostics; Installing (4) sets of Trim coils; and Transporting the 3rd. Field Period to the NCSX Test Cell. |
| WBS Element: 7.3 | WBS Level: 3 |
| WBS Title: | Test Cell & Basement Assembly Operations |
| Description: | The WBS element consists of the activities associated with the final assembly of the NCSX components in the Test Cell and Test Cell Basement. Work to be accomplished includes the following activities in order of work to be performed: Installing and leveling machine support columns; Installing the lower support ring plates w/fiberslip; Installing the lower Cryostat floor; Installing the lower PF-3 & 4 coils in preliminary positions; Installing the (3) field periods Installing the vacuum pump system.(Note: WBS 200 responsibility); Performing the Pumpdown and Vacuum Leak Test PTP; Installing PFC’s and internal diagnostics; Raising the lower PF-3 & 4 into a final position; Installing the upper PF-3 & 4 coils; Installing the PF-1 & PF-2 solenoid; Installing the bus connections to coil systems (WBS 400 responsibility); Connecting the Bakeout, Water and Cryogenic systems (WBS 600 responsibility); Installing external Cryostat walls and ceiling; Completing Bus connections (WBS 400 responsibility); Performing the Cryostat Systems Test PTP; and Installing the machine platform. |

| WBS Element: 7.4 | WBS Level: 3 |
| --- | --- |
| WBS Title: | In-Vessel Measurement Systems |
| Description: | This WBS element consists of all the following: Mechanical Position Measurement/Metrology Systems (WBS 7.4.1); and Laser Measurement Systems (WBS 7.4.2). The in-vessel measurement systems provide the magnetic and physical measurement systems for placing components in-vessel. Assembly within the tokamak is not part of this WBS element, rather it is part of the WBS Element 9 (Preparation for Operations).. |
| WBS Element: 7.4.1 | WBS Level: 4 |
| WBS Title: | Mechanical Measurement Systems |
| Description: | This WBS element consists of the effort to design (conceptual, Title 1, Title 2, and Title 3), procure/fabricate, install, and checkout the mechanical measurement systems. Mechanical Measurement systems which will be used during the Assembly of Field Periods and overall machine components. Systems will be used to align internal and external components. This work scope includes procurement of (2) measurement arms and the design of the necessary alignment equipment to work in conjunction with measurement arms. |
| WBS Element: 7.4.2 | WBS Level: 4 |
| WBS Title: | Laser Measurement Systems |
| Description: | This WBS element consists of the effort to design, procure/fabricate, install, and checkout equipment for the laser measurement systems. Laser Measurement systems which will be used during the assembly of field periods and overall machine components. Systems will be used to align internal and external components. This work scope includes procurement of Laser alignment equipment and the design of the necessary alignment equipment to be used in conjunction with Laser equipment. |

| WBS Element: 8 | WBS Level: 2 |
| --- | --- |
| WBS Title: | Project Oversight and Support |
| Description: | This summary-level WBS element consists of all the non-hardware-related activities necessary to develop requirements and manage the NCSX Project such as project management, systems engineering, environmental and safety/QA management, and, project physics. |
| WBS Element: 8.1 | WBS Level: 3 |
| WBS Title: | Project Management and Control |
| Description: | This WBS element includes the overall project direction, oversight, and administrative support, including budgeting, cost control, scheduling, and procurement activities. These are in direct support of the NCSX design and construction project (TEC). In addition, there are program activities supporting the Conceptual Design and those of a more general nature supporting development and planning of the experimental program and generic stellarator fusion studies that have been estimated, but are not part of the TEC. Some of these project management oversight and support functions are funded directly and some via the indirect costs pool in the G&A rate (e.g., the Procurement and Accounting Division’s activities). Specific categories of labor included in this are: Direct project management and oversight personnel (e.g., the NCSX Project Manager and his support staff and senior PPPL management personnel such as the Advanced Projects Department Head); Procurement support personnel in support of the procurement of goods and services necessary for the NCSX Project => these personnel are funded under the general indirect costs pool via the G&A rate rather than by direct project funds. Accounting support personnel in support of the tracking and accounting of project cost categories => these personnel are funded under the general indirect costs pool via the G&A rate rather than by direct project funds. In addition, PPPL collects direct allocations charged to the NCSX Project and Program. The direct allocation charges are to cover the allocated charges for the Computer Division's support and maintenance of the VAX, UNIX and CADD computer systems and desktop computer support here at PPPL. These costs are allocated across all the hardware-oriented WBS elements. |
| WBS Element: 8.2 | WBS Level: 3 |
| WBS Title: | Project Engineering |
| Description: | This WBS element includes all the overall engineering management and support of the design and construction process. Since these activities cut across all WBS elements, the effort is defined and collected here. It includes the following activities: Engineering requirements and interface definition; Overall project design integration; Configuration management and control; and Systems code studies. Specific categories of labor included in this are: Direct project engineering management and oversight personnel (e.g., the NCSX Deputy Project Manager for Engineering, the Project Engineering Manager, and his support staff); Personnel responsible for developing and maintaining the overall NCSX project design model; Personnel responsible for developing and administering the NCSX Configuration Management System; and Personnel responsible for performing specialized and global systems code studies to assess the feasibility of various design options |

| WBS Element: 8.3 | WBS Level: 3 |
| --- | --- |
| WBS Title: | Environmental and Safety/QA Management |
| Description: | This WBS element includes all the ES&H and Quality Assurance/Quality Control support of the design and construction process. Since these activities cut across all WBS elements, the effort is defined and collected here. It includes the following activities: Construction Safety; Electrical Safety; Radiation Safety; NEPA & Safety Assessment Review & Coordination; Industrial Hygiene & Safety; Quality Assurance; and Quality Control of the procurement and construction processes. Specific categories of labor included in this are: Environmental, safety, and health (ES&H) support personnel to provide general review and support of project activities from a ES&H perspective => these personnel are funded under the general indirect costs pool via the G&A rate rather than by direct project funds; Quality assurance and quality control support personnel to provide quality oversight and review of the NCSX Project activities => these personnel are funded under the general indirect costs pool via the G&A rate rather than by direct project funds |
| WBS Element: 8.4 | WBS Level: 3 |
| WBS Title: | Project Physics |
| Description: | This WBS element includes the project physics activities in direct support of the NCSX design and construction project (TEC). In addition, there are program activities supporting the Conceptual Design and those of a more general nature supporting development and planning of the experimental program and generic stellarator fusion studies that have been estimated, but are not part of the TEC. Since these activities cut across all WBS elements, the effort is defined and collected here. It includes the following activities: Physics requirements and interface definition; Physics models and codes to facilitate the physics design and analyses of options; and Physics analyses of options. Specific categories of labor included in this are: Direct physics management and oversight personnel (e.g., NCSX Physics Head and his support staff); Researchers directly involved in developing specific physics requirements and physics configurations and analyses that impact the physics performance and engineering design of NCSX. |

| WBS Element: 9 | WBS Level: 2 |
| --- | --- |
| WBS Title: | Preparations for Operations |
| Description: | This summary-level WBS element consists of all the necessary preparations for operations and the integrated systems testing needed to achieve first plasma and to carryout the initial experimental program. These costs will be incurred during the latter stages of the construction project and include the one-time costs related to testing, startup, operator training, and commissioning of the NCSX device for first plasma. Commissioning costs for the individual subsystems are included in the subsystem scope of work. Similarly pre-operational expenses to support the experimental program after first plasma are not included. Nor is an initial allowance for operational spares.. |
| WBS Element: 9.1 | WBS Level: 3 |
| WBS Title: | Pre-Operational Planning |
| Description: | In order to be prepared for operations, there is a necessary buildup and training of the operations team and the preparation of operating procedures. The work scope for this will be covered outside the construction project baseline. |
| WBS Element: 9.2 | WBS Level: 3 |
| WBS Title: | Pre-Operational and Integrated Systems Testing |
| Description: | The NCSX device will have to undergo a series of pre-operational and integrated systems test to demonstrate that it is ready for operation. This WBS element covers the planning, coordination, procedurization, and execution of the Integrated System Tests, which consist of 1) first energization of all of the magnet coil systems, and 2) first plasma. Costs for operating and staffing the facility for these tests is included. Prior Preoperational Tests are assumed covered by the individual WBS elements. |
| WBS Element: 9.3 | WBS Level: 3 |
| WBS Title: | Operational Spares |
| Description: | Limited operational spares may be needed to support first plasma, however these will be funded by funds outside the construction project. The baseline project does not include any allowance for these operational spares. |