Minutes of the NCSX-DOE IPT Meeting on December 17, 2002

On the teleconference:  Warren Marton (DOE-OFES), Greg Pitonak (DOE-PG),

Chuck Finfgeld (DOE-OFES), Jim Lyon (ORNL), Rich Hawryluk (PPPL), John

Schmidt (PPPL), Hutch Neilson (PPPL), Wayne Reiersen (PPPL), and Bob Simmons

(PPPL).

Topics of Discussion:

(1) Overall Project Status - Warren Marton, Greg Pitonak, and Hutch Neilson

(a) CR continues, although there are some expectations that Congress will

pass an omnibus funding bill early in 2003 (perhaps in February). The

current "baseline" is the $73.5M total cost/June 2007 schedule.  The

baseline will be updated for the PDR/EIR to incorporated the effects of the

Continuing Resolution, accounting changes (e.g., safeguards and security

costs at PPPL) and any technical changes resulting from design and R&D

activities.

(b) (b) A general discussion of how to react to the release of the CR

ensued.  Hutch noted that the Project is proceeding with the placement of

the two (VV and mod coil winding form) prototype contracts with award

expected in January - February time frame. These will be funded by OPEX

funds.  PPPL costing guidelines indicated that prototypes that have "no

value" relative to use as production units should be funded by OPEX funds

and not MIE funds.  It was previously thought that because this work was in

support of manufacturing development, it could be funded by MIE.

(c) We also discussed the options available for re-planning the work once

the CR is released. OFES feels that Advanced Conceptual Design activities

cannot extend beyond the CR.

(2) Project Status - Hutch Neilson and Wayne Reiersen

(a) Technical progress - Wayne indicated that the engineering team is

continuing to address configuration issues in the context of the CDR design.

Engineering is just starting to evaluate the impact of the new coil design

point (M50) and is revising its plans accordingly.

(b) The proposals for the modular coils winding form prototype have been

received - a total of 5 proposals received. It is anticipated that the

contract will be placed in late January or early February.  The vacuum

vessel proposals are due in early January.

(c) Hutch indicated that the impact of the CR on the ORNL planned staffing

buildup has been significant, although recent progress has been made in this

area.  The problem has been the funding allocation received from ORO has not

been as great as needed to support the ORNL staffing buildup.

(3) NCSX Review Discussions - Warren Marton, Hutch Neilson, and Greg Pitonak

(a) A general discussion of the various reviews indicated in the attached

table.  Actions were assigned as indicated on the table (e.g., who will run

the review, the approach needed, conflicts with other planned PPPL meetings,

etc.  The specific actions from this discussion are as follows:

i. Hutch will coordinate the scheduling of the NCSX PDR with other planned

PPPL meetings - tentatively the PDR is scheduled for late June.

ii. Warren will confirm the makeup of the PDR review committee.

(b) Greg stressed that the PDR presentations must address the

technical basis for the performance baseline (CD-2).  The Project agrees.

The NCSX PDR will be an overall DOE PDR for the entire project and an

internal detailed PDR for the modular coils and vacuum vessel.

The next IPT meeting will be Tuesday, January 21st, at 11:00 am.

If you have any corrections, please contact me.

Bob S.

| Milestone | PDR | EIR | CD-2 | FDRs | CD-3 |
| --- | --- | --- | --- | --- | --- |
| When | June 23(?), 2003 (GHN to coordinate with other meetings) | July, 2003 | August, 2003 (allows for EIR follow-ups and ESAAB members to review EIR report) | MC: Sep., 2003 VV: Dec., 2003 | January, 2004 |
| Who runs it | Project (W.M. to confirm) | DOE-OECM Liaison: SC-CMSD | SC-OFES | Project | SC-OFES |
| Review Team Members | Fusion engineers & DOE (+CMSD reps. for cost review?- W.M. to confirm) | Jupiter or LMI | ESAAB members | Fusion engineers | ESAAB members |
| Main Objective | Validate MC & VV design maturity sufficient to proceed with development of build-to specs. Review updated C&S estimate for entire project. | Validate that there is sufficient confidence in the estimates (i.e., sound technical basis and plans) and mgt. systems to establish performance baseline. | DOE Approval of the performance baseline. DOE approval to continue with FD and initiate critical fabrication activities. | Validate that technical specs and estimates are sufficient to issue for fabrication. | DOE approval to proceed with all fabrication activities. |
| Desired Output | Report that concludes: MC & VV design is sound, satisfies requirements. Plans are sound. Proceed with final design. CDR issues have been resolved as appropriate. C&S estimates for all systems have a sufficiently sound basis (well beyond conceptual design) for performance baseline. | Report that concludes: Estimates are sound, based on: Appropriate technical reviews conducted. Risks identified, mitigation plans incorporated. Execution plans sound. NEPA requirements satisfied. Ready for CD-2. | Approval of performance baseline. Approval to continue with FD and initiate critical fabrication activities. | Reports that conclude: VV & MC procurement packages (e.g., specs, MIT plans) are sound. In-house R&D plans, fabrication and assembly specs, and MIT plans are sound. Estimates are well bracketed, based on design and R&D input. Ready for CD-3. | Approval to fabricate modular coils and VV. |
| Required Input | Design package: Design documents for VV & MC. Interface documents demonstrating that VV & MC boundary conditions are established. Analyses demonstrating that design satisfies all requirements and boundary conditions. Risk assessment and mitigation plans. Plans and estimates to complete the design, fabrication, inspection, and testing. Manufacturability R&D input supporting the estimates. Resolution of CDR issues commensurate with design stage. Documentation of design, cost, & schedule for all systems. | PDR inputs & outputs, including: Design documents for VV, MC, and their interfaces. Risk assessment and mitigation plans. Technology development (R&D) results and procurement decisions. Report from the PDR. Resource-loaded schedule, with technical basis documentation: Updated system estimates. Risk-based contingency analysis. Documentation of readiness to proceed with other critical fabrication tasks, e.g. power cables, test cell mods. ISTP (how detailed?) Management plans: Final PEP. SEMP. Final EA/FONSI. | Positive report from the EIR / C&S Review. |  |  |