# NCSX VACUUM VESSEL	WBS 12		PLG 3/21/03

# WBS TASK

# Basic Scope

Provide a vacuum boundary around the plasma chamber to provide:

- High vacuum conditions

- Structural support for all internal hardware

- Access for Auxiliary Systems (WBS 2) and Diagnostics (WBS 3)

Sub-Elements: As defined in WBS Dictionary

- Vacuum Vessel Assembly (WBS 121)

Vacuum vessel shell, Ports and extensions, Blank port covers, PFC support rib interfaces, Vacuum vessel support interfaces, Cooling tubes.

- Vacuum Vessel Thermal Insulation (WBS 122);

- Vacuum Vessel Heating and Cooling Distribution Systems (WBS 123)

- Vacuum Vessel Supports (WBS 124); and

- Vacuum Vessel Local I&C (WBS 125).

# NCSX VACUUM VESSEL	WBS 12

WBS TASK	Contin.

# Requirements and Constraints

Requirements and constraints are clear

Geometry stay in zones defined

Modular coil geometry incorporated

Cooling and insulation zones reserved (vessel buildup)

Scope sheets written but not ICDs

# Interface Discussions

# Initial criteria defined for magnetic loop diagnostics (WBS 125)	Dave Johnson

# NCSX VACUUM VESSEL	WBS 12

## DESIGN STATUS

## Progress to Date

- New vessel contour still being refined

- Vendor selection for 20 degree sector complete

- Sloped joint (25 degrees) design workable

- Viable Technical Concepts are in place for all systems except:

Local I&C is in preliminary stages

PFC mounting is preliminary

## Feasibility Issues

Adequacy of space for possible Divertor (WBS 11) unclear

## Major changes since CDR

Plasma changed

Vessel geometry changed

Vessel contour constraints refined

Revealed vessel flange joint interference with Modular Coils

Would not slip over

Solution is to incline interface 20-30 degrees

# NCSX VACUUM VESSEL	WBS 12

### Cost Status

## Cost Impacts from Changes

PVVS vessel segment fab rose from 400K to 800K

## Update of Costs

Should be sufficient information to update costs in early May

# NCSX VACUUM VESSEL	WBS 12

#### RESOURCE ISSUES

Resources are earmarked.

## PDR Milestones (SEML deliverables)

CAD models		Jones, Fortier, Cole

###### Drawings			Jones, Fortier

Analyses			Dahlgren, Freudenberg

ICDs				PLG

Design to Specs	PLG

FMECAs			PLG

Build to Specs		PLG

## Cost Update Milestone	PLG

# NCSX VACUUM VESSEL	WBS 12

### GOALS

##### Next 4 weeks

## SEML Sheets

VV Design to Spec

ICDs