## Scope
NCSX Documentation Closeout Job 8221
Scope
WBS/Job/Title/Closeout Note Link |  | Job Manager | Status at Closeout | Scope (posted)
|  |  |  | Close-out Note | Project Files, memos,meeting notes,photos | Specs & SOW's | Design reviews,calcs,chits | Design Data (Dsn descriptions, BOM,FEA models,Mat'l properties,Released dwgs, studies,Models) | Fabr/Assy/Constr info (Plans, procedures,metrology, invemntory list,prototype info | Other (NCR's, Audit reports,test results)
WBS 12 - Vacuum Vessel
| 1201 - Vacuum Vessel Preliminary Design | Goranson | Completed (Oct 2003)
| 1202 - Vacuum Vessel R&D | Goranson | Completed (Sept 2005)
| 1203 - Vacuum Vessel Final Design | Goranson | Completed (Aug 2006)
| 1204 - Vacuum Vessel System Procurements (Non-VVSA) | Dudek | In Process at Time of Cancellation
| 1206 - Vacuum Vessel Field Weld Joint | Goranson | Completed (Sept 2005)
| 1250 - Vacuum Vessel Fabrication | Viola | Completed (Sept 2006)
| 1260 - Neutral Beam Transition Duct | Cole | In Process at Time of Cancellation
| 1270 - Heater Control System | Goranson | In Process at Time of Cancellation
WBS 13 - Conventional Coils
TF Coils
| 1301 - TF Coil Design | Kalish | Completed (April 2006)
| 1350 - TF Coil Fabrication Preparations | Chrzanowski | Cancelled when Decision Made for Industry to Fabricate (Mar 2006)
| 1351 - TF Coil Fabrication Supplies | Kalish | Completed (Oct 2006)
| 1361 - TF Coil Fabrication | Kalish | Will Complete as Part of Closeout
| 1302/1352 - PF Coil | Chrzanowski | Completed (May 2007)
| 1353 - CS Structures Design | Dahlgren | Cancelled when Decision Made to Use NSTX PF1a (Aug 2006)
| 1354 - Trim Coils | Kalish | In Process at Time of Cancellation
| 1355 - Conventional Coil I&C | Cole | In Process at Time of Cancellation
WBS 14 - Modular Coils
| 1401 - Modular Coil Preliminary Design | Williamson | Completed (Sept 2005)
| 1402 - Modular Coil Analyses | Williamson | Completed (Sept 2005)
| 1403 - Modular Coil Final Design | Williamson | Completed (April 2006)
| 1404 - MCWF R&D & First Production Casting | Chrzanowski | Completed (Sept 2005)
| 1405 - Modular Coil Winding R&D Preparations | Chrzanowski | Completed (Sept 2005)
| 1406 - Modular Coil Winding R&D | Chrzanowski | Completed (Mar 2006)
| 1407 - Modular Coil Winding Facility | Chrzanowski | Completed (Mar 2006)
| 1408 - Modular Coil Winding Facility | Chrzanowski | Will Complete as Part of Closeout
| 1409 - Coil Test Stand | Gettelfinger | Completed (July 2006)
| 1410 - Modular Coil Twisted Racetrack Fabrication | Chrzanowski | Completed (Mar 2006)
| 1411 - MCWF Fabrication | Heitzenroeder | Completed (June 2007)
| 1412 - Complete Winding Facilities | Chrzanowski | Completed (Mar 2006)
| 1413 - MCWF Fracture Analyses | Williamson | Completed (Mar 2006)
| 1414 - Coil Testing | Gettelfinger | Completed (July 2006)
| 1416 - Modular Coil Type A/B Design | Cole | In Process at Time of Cancellation
| 1419 - Winding Facilities Modifications | Chrzanowski | Completed (Jan 2007)
| 1421 - Modular Coil Interface Design @ ORNL | Cole | In Process at Time of Cancellation
| 1429 - Modular Coil Interface R&D @ PPPL | Dudek | In Process at Time of Cancellation
| 1431 - Modular Coil Interface Hardware | Dudek | In Process at Time of Cancellation
| 1451 - Modular Coil Winding Operations | Chrzanowski | Will Complete as Part of Closeout
| 1459 - Modular Coil Fabrication Punch List Items | Chrzanowski | In Process at Time of Cancellation
| 1460 - Modular Coil Third Winding Fixture | Chrzanowski | In Process at Time of Cancellation
WBS 15 Coil Support Structures |  | Dahlgren | Will Complete as Part of Closeout
WBS 16 - Coil Services
| 1601-161 - LN2 Distribution Systems | Goranson | In Process at Time of Cancellation
| 1601-162 - Coil Electrical Leads | Goranson | In Process at Time of Cancellation
| 1601-163 - Coil Protection System Interfaces | Harris | In Process at Time of Cancellation
WBS 17 - Cryostat & Base Support Structure
| 1701/1751 - Cryostat Design | Raftopoulos | In Process at Time of Cancellation
| 1702/1752 - Base Support Structure Design | Dahlgren | In Process at Time of Cancellation
WBS 18 - Field Period Assembly
| 1801 - FPA (ORNL) | Cole | Closed (Sept 2006)
| 1802 - FP Assembly Oversight & Support | Viola | In Process at Time of Cancellation
| 1803 - FP Assembly Tooling/Constructibiliuty | Brown | In Process at Time of Cancellation
| 1804 - Metrology Hardware | Raftopoulos | In Process at Time of Cancellation
| 1805 - FP Assembly Hardware & Fixture Procurements | Dudek | In Process at Time of Cancellation
| 1806 - FP Assembly Specs & Drawings | Cole | In Process at Time of Cancellation
| 1810 - FPA Operations - Stations 1, 2, 3 | Viola | In Process at Time of Cancellation
| 1815 - PPA Operations - Station 5 | Viola | In Process at Time of Cancellation
WBS 19 - Stellartor Core Management & Integration
| 1901 - 191 - Stellarator Core Management & Oversight | Cole | In Process at Time of Cancellation
| 1901 - 192 - Stellarator Core Integration & Analysis | Cole | In Process at Time of Cancellation
| 1901- 193 - Risk Mitigation Activities | Cole | In Process at Time of Cancellation
WBS 2 - Auxiliary/Anciliary Systems
| 2101 - Fueling Systems | Blanchard | In Process at Time of Cancellation
| 2201 - Torus Vacuum pumping Systems | Blanchard | In Process at Time of Cancellation
WBS 3 - Diagnostic Systems
| 3101 - Magnetic Diagnostic Systems | Stratton | In Process at Time of Cancellation
| 3601 - Edge & Divertor Diagnostics Systems | Stratton | In Process at Time of Cancellation
| 3801 - Electron Beam Mapping Systems | Stratton/Harris | In Process at Time of Cancellation
| 3901 - Diagnostic Systems Integration | Stratton | In Process at Time of Cancellation
WBS 4 - Electrical Power Systems |  | Ramakrishnan | In Process at Time of Cancellation
WBS 5 - Central Controls & Computing |  | Sichta | In Process at Time of Cancellation
WBS 6 - Facility Systems
| 6101 - Cooling Water Systems | Dudek | In Process at Time of Cancellation
| 6201 - Cryogenic Systems | Raftopoulos | In Process at Time of Cancellation
| 6301 - Utility Systems | Dudek | In Process at Time of Cancellation
| 6401 - Bakeout Systems | Kalish/Gororason | In Process at Time of Cancellation
WBS 7 - Test Cell Prep & Machine Assembly |  | Perry | In Process at Time of Cancellation
WBS 81 - Project Management & Integration
| 8101 - Project Management @ PPPL | Rej | In Process at Time of Cancellation
| 8102 - Project Management @ ORNL | Harris | In Process at Time of Cancellation
WBS 82 - Project Engineering
| 8202 - Engineering Mgmt & Systems Engineering | Heitzenroeder | In Process at Time of Cancellation
| 8203 - Design Integration | Brown | In Process at Time of Cancellation
| 8204 - Systems Analysis & Technical Assurance | Brooks | In Process at Time of Cancellation
| 8205 - Dimensional Control Coordination | Ellis | In Process at Time of Cancellation
| 8210 - Rebaselining Exercise | Strykowsky | In Process at Time of Cancellation
| 8215 - Plant Design | Perry | In Process at Time of Cancellation
| 8220 - Equipment Disposition/Facility Restorations | Perry | Will Complete as Part of Closeout
| 8221 - Documentation for Closeout | Heitzenroeder | Will Complete as Part of Closeout
| 8222 - Prepare Manuscripts for Peer Reviewed Papers | Neilson | Will Complete as Part of Closeout
WBS 84 - Project Physics
| 8401 - Project Physics @ PPPL | Zarnstorf | Closed (Sept 2006)
| 8402 - Project Physics @ ORNL | Lyon/Harris | Closed (Sept 2006)
WBS 85 - Integrated System Testing |  | Gentile | In Process at Time of Cancellation

## Time
NCSX Documentation Closeout Job 8221
Time Charges
|  |  | ACCOUNT |  | TOTAL | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | EAC
1 |  | ORNL | COLE | Planned | 79 |  | 20 | 19 | 19 | 21
2 |  |  |  | Actual | 0
3 |  | ORNL | FOGARTY | Planned | 79 |  | 20 | 19 | 19 | 21
4 |  |  |  | Actual | 0
5 |  | ORNL | FREUDENBERG | Planned | 280 |  | 86 | 82 | 80 | 32
6 |  |  |  | Actual | 0
7 |  | ORNL | GORANSON | Planned | 79 |  | 20 | 19 | 19 | 21
8 |  |  |  | Actual | 0
9 |  | ORNL | HARRIS | Planned | 20 |  | 5 | 5 | 5 | 5
10 |  |  |  | Actual | 0
11 |  | ORNL | MMORRIS | Planned | 20 |  | 5 | 5 | 5 | 5
12 |  |  |  | Actual | 0
13 |  | ORNL | MOON | Planned | 10 |  | 3 | 2 | 2 | 3
14 |  |  |  | Actual | 0
15 |  | ORNL | NELSON | Planned | 10 |  | 3 | 2 | 2 | 3
16 |  |  |  | Actual | 0
17 |  | ORNL | WILLIAMSON | Planned | 79 |  | 20 | 19 | 19 | 21
18 |  |  |  | Actual | 0
19 |  | PPPL | AVASARALA | Planned | 160 |  | 56 | 53 | 51
20 |  |  |  | Actual | 0
21 |  | PPPL | BLANCHARD | Planned | 41 |  | 10 | 10 | 10 | 11
22 |  |  |  | Actual | 2 |  | 2
23 |  | PPPL | BROOKS | Planned | 99 |  | 25 | 24 | 24 | 26
24 |  |  |  | Actual | 0
25 |  | PPPL | BROWN | Planned | 376 |  | 95 | 91 | 91 | 99
26 |  |  |  | Actual | 0
27 |  | PPPL | CARROL | Planned | 0
28 |  |  |  | Actual | 0
29 |  | PPPL | CHRZANOWSKI | Planned | 168 |  | 42 | 41 | 41 | 44
30 |  |  |  | Actual | 35 |  | 35
31 |  | PPPL | DAHLGREN | Planned | 560 |  | 157 | 150 | 147 | 106
32 |  |  |  | Actual | 0
33 |  | PPPL | DODSON | Planned | 41 |  | 10 | 10 | 10 | 11
34 |  |  |  | Actual | 0
35 |  | PPPL | DUDEK | Planned | 32 |  | 8 | 8 | 8 | 8
36 |  |  |  | Actual | 0
37 |  | PPPL | ELLIS | Planned | 41 |  | 10 | 10 | 10 | 11
38 |  |  |  | Actual | 0
39 |  | PPPL | FAN | Planned | 160 |  | 56 | 53 | 51
40 |  |  |  | Actual | 0
41 |  | PPPL | GENTILE | Planned | 20 |  | 5 | 5 | 5 | 5
42 |  |  |  | Actual | 0
43 |  | PPPL | HAMPTON | Planned | 100 |  | 35 | 33 | 32
44 |  |  |  | Actual | 0
45 |  | PPPL | HEITZENROED | Planned | 160 |  | 40 | 39 | 39 | 42
46 |  |  |  | Actual | 0
47 |  | PPPL | JUN | Planned | 99 |  | 25 | 24 | 24 | 26
48 |  |  |  | Actual | 0
49 |  | PPPL | KALISH | Planned | 57 |  | 14 | 14 | 14 | 15
50 |  |  |  | Actual | 8 | 4 | 4
51 |  | PPPL | LABIK | Planned | 41 |  | 10 | 10 | 10 | 11
52 |  |  |  | Actual | 0
53 |  | PPPL | LANGISH | Planned | 24 |  | 6 | 6 | 6 | 6
54 |  |  |  | Actual | 0
55 |  | PPPL | MORRIS | Planned | 336 |  | 85 | 81 | 81 | 89
56 |  |  |  | Actual | 0
57 |  | PPPL | PERRY | Planned | 16 |  | 4 | 4 | 4 | 4
58 |  |  |  | Actual | 0
59 |  | PPPL | PRINISKI | Planned | 16 |  | 4 | 4 | 4 | 4
60 |  |  |  | Actual | 0
61 |  | PPPL | RAFTOPOULOS | Planned | 220 |  | 56 | 53 | 53 | 58
62 |  |  |  | Actual | 17 | 17
63 |  | PPPL | RAKI | Planned | 16 |  | 4 | 4 | 4 | 4 | [5 empty] | 160
64 |  |  |  | Actual | 22 |  | 22
65 |  | PPPL | REIERSEN | Planned | 160 |  | 40 | 39 | 39 | 42
66 |  |  |  | Actual | 0
67 |  | PPPL | RUSHINSKI | Planned | 336 |  | 85 | 81 | 81 | 89
68 |  |  |  | Actual | 0
69 |  | PPPL | SICHTA | Planned | 79 |  | 20 | 19 | 19 | 21
70 |  |  |  | Actual | 0
71 |  | PPPL | SIMMONS | Planned | 762 | 75 | 119 | 114 | 113 | 100 | 45 | 43 | 53 | 50 | 50
72 |  |  |  | Actual | 226 | 61 | 165
73 |  | PPPL | SMITH | Planned | 16 |  | 4 | 4 | 4 | 4
74 |  |  |  | Actual | 0
75 |  | PPPL | STRATTON | Planned | 41 |  | 10 | 10 | 10 | 11
76 |  |  |  | Actual | 0
77 |  | PPPL | STRYKOWSKY | Planned | 160 |  | 40 | 39 | 39 | 42
78 |  |  |  | Actual | 0
79 |  | PPPL | SUCH | Planned | 200 |  | 24 | 23 | 23 | 25 | 20 | 19 | 23 | 22 | 21
80 |  |  |  | Actual | 0
81 |  | PPPL | TYRELL | Planned | 100 |  | 35 | 33 | 32
82 |  |  |  | Actual | 0
83 |  | PPPL | UPCAVAGE | Planned | 215 |  | 54 | 52 | 52 | 57
84 |  |  |  | Actual | 0
85 |  | PPPL | VIOLA | Planned | 158 |  | 40 | 38 | 38 | 42
86 |  |  |  | Actual | 0
87 |  | PPPL | ZHANG | Planned | 160 |  | 56 | 53 | 51
88 |  |  |  | Actual | 0
89 |  | PPPL | Designer unassigned - for as-builts | Planned | 1994 |  | 360 | 343 | 343 | 376 | 294 | 278
90 |  |  |  | Actual | 0
91
93 |  |  |  | TOTAL PLAN = | 7820 | 75 | 1826 | 1747 | 1733 | 1521 | 359 | 340 | 76 | 72 | 71
94 |  |  |  | TOTAL ACTUAL = | 310 | 82 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0